## Sheet1
Project Name: |  | 300 MW Solar PV Project at Ramagiri village, A.P
CA Date (BoS): |  | 2025-02-06
SCD: |  | 2026-02-05
% physical progress |  | 4%
% financial progress |  | 0.76% |  | Date: | 2025-07-07
S.No. | Issues | Present status | Concerned Dept | Target date/ Requirement date | Remarks
1 | PGCIL Agreement signing for ISTS bay execution | PGCIL has informed that the approval process is experiencing a delay due to the incorporation of minor changes. The revised e-office file is currently being circulated for further review and clearance | PS-Project Dept | This matter is immediate, as work at the ISTS bay can only commence after signing the agreement. Post-facto approval from the management may be obtained for the minor changes made, which needs to be discussed and agreed upon.
2 | Power Transformer Delivery | Revised drawing and MQP needs to be submitted by ARIPL. | PS-Project Dept | 09-07-2025 During the CPSU visit to Gujarat, Mr. Debajyoti will visit the transformer manufacturing facility to expedite the delivery process and collect the necessary documents.
3 | Design Basis report and Control room foundation drawings | M/s AmaraRaja needs to be submitted | PS-Eng Dept. | 2025-07-09 | Upon approval of Design basis, foundation drawing will be submitted.
4 | Tower and equipment of Switchyard drawings | Desgin basis for the same is submitted | PS-Eng Dept. | 2025-07-08 | Upon approval of Design basis, foundation drawing will be submitted.
5 | Pile marking coordinates drawing | Drawing submitted on 04-07-25 | PS-Eng Dept. | 2025-07-07
6 | Pile test report clearance and heigh of column post finalization | Drawing submitted on 05-07-25 | PS-Eng Dept. | 2025-07-07
7 | Contractual staff to Site | File Approved with HR Dept. | HR Dept. |  | One Civil and Electrical Eng. (Contractual)- To be deployed at site,