## Construction DASHBOARD
Daily Progress Report
Project Name | 300MW SECI Solar Project Ramagiri | [10 empty] | Week | Month
Project Capacity (in MWp) | 390 | [10 empty] | 2025-07-14 | 2025-07-01
Project Start Date | 2025-02-06 | [10 empty] | 2025-07-19 | 2025-07-31
Project Finish Date | 2026-02-05 | [8 empty] | Week Cycle | Month Cycle
Date | 2025-07-15 | [8 empty] | 2025-07-14 | 2025-07-01
[10 empty] | 2025-07-19 | 2025-07-31
Description | Scope | UoM | Completed | Balance | Weightage (in %) | Progress as per weightage (in %) | Actual Progress (in %) | Day- Actual | Today-Plan | Week- Actual | Month-Actual
Land Development
Bush removal | 1033 | Acre | 872 | 161 | 1% | 0.8441% | 84.41% | 0 | 5 | 0 | 0 | 2025-04-07 | 1
Land grading | 1033 | Acre | 872 | 161 | 1% | 0.8441% | 84.41% | 0 | 5 | 0 | 0
Site Initials | [11 empty] | 2025-04-08 | 1
Boundry Coordinate capturing | 1 | Lot | 1 | 0 | 0.6% | 0.6% | 100% | 0 |  | 0 | 0 | 2025-04-09 | 1
Topo Survey | 1 | Lot | 1 | 0 | 0.75% | 0.75% | 100% | 0 |  | 0 | 0 | 2025-04-10 | 1
Soil Investigation | 79 | Lot | 79 | 0 | 0.5% | 0.5% | 100% | 0 |  | 0 | 0 | 2025-04-11 | 2
ERT Test | 36 | Lot | 36 | 0 | 0.25% | 0.25% | 100% | 0 |  | 0 | 0 | 2025-04-12 | 2
Test Pile Casting | 240 | Lot | 240 | 0 | 0.2% | 0.2% | 100% | 0 |  | 0 | 0 | 2025-04-13 | 1
Pile Testing | 240 | Lot | 63 | 177 | 0.2% | 0.0525% | 26.25% | 0 | 4 | 0 | 0 | 2025-04-14 | 1
Civil | [11 empty] | 2025-04-15
Pile - Marking, Drilling & Casting |  | Nos. |  |  | 21% | [6 empty] | 2025-04-16
Equipments Foundation | 24 | Block |  |  | 5% | [6 empty] | 2025-04-17 | 4
Excavation For Trenches | 24 | Block |  |  | 5% | [6 empty] | 2025-04-18 | 4
MCR Civil Works | 1 | Lot |  |  | 6% | [6 empty] | 2025-04-19 | 4
Road Work |  | km |  |  | 2% | [6 empty] | 2025-04-20 | 4
Fencing | 21000 | km |  |  | 2% | [6 empty] | 2025-04-21 | 4
MMS | [11 empty] | 2025-04-22 | 6
Module Mounting Structures | 24 | Block |  |  | 8% | [6 empty] | 2025-04-23 | 6
PV Modules | 24 | Block |  |  | 6% | [6 empty] | 2025-04-24 | 6
DC | [11 empty] | 2025-04-25 | 6
Solar Cables (Interconnection after module installation) | 1360 | SCB |  |  | 2% | [6 empty] | 2025-04-26 | 4
SCB-MOUNTING | 1360 | SCB |  |  | 2% | [6 empty] | 2025-04-27
Array & Module Earthing | 1360 | SCB |  |  | 3%
SCB Installation | 1360 | SCB |  |  | 2.5%
DC Power Cables | 1360 | SCB |  |  | 4%
DC Power Cables Terminations | 1360 | SCB |  |  | 2%
DC Earthing | 1360 | SCB |  |  | 2%
AC
Equipment Installation | 24 | Block |  |  | 2%
Cable Tray Works | 24 | Block |  |  | 2%
HT&LT Cable Laying | 24 | Block |  |  | 4%
Communication Cable Laying & termination | 24 | Block |  |  | 1%
HT&LT Cable Termination | 24 | Block |  |  | 1%
Equipment Earthing | 24 | Block |  |  | 2%
Plant Earthing Completion | 24 | Block |  |  | 1%
External Works
Street Light Works | 1173 | nos. |  |  | 2%
External Earthing Completion | 24 | Block |  |  | 2%
Allied works
WMS | 1 | Lot |  |  | 0.5%
MCS | 1 | Lot |  |  | 1%
FAS Installation | 1 | Lot |  |  | 0.25%
Allied work completion | 1 | Lot |  |  | 0.25%
Commissioning & HOTO
Pre-Commissioning | 100 | % |  |  | 1%
Synchinization Approval | 100 | % |  |  | 1%
Commissioning | 100 | % |  |  | 1%
COD | 100 | % |  |  | 1%
[5 empty] | 100% | 4.041%
| Scope | 100%
| Actual | 4.041%
| Balance | 95.96%
Formulas:
Week = [Week, row above]+5
Month Cycle = [Month Cycle, row above]+30

## Sheet1 (hidden)
Date | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14
No. of JCBs | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 |  |  | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 6 | 6 | 4 | 4 | 6 | 6 | 6 | 5 | 4 | 3 | 5 | 5 | 5 | 4 | 6 |  | 135
Bush Cutting | 1.5 | 3.5 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 20 | 20 | 25 | 26 | 40 | 40 | 40 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5 | 10 | 10 | 5 | 7 | 5 |  |  | 317 | 2.3481
Land Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 12 | 13 | 10 | 12 | 11 | 20 | 14 | 16 | 16 | 10 | 10 | 5 | 7 | 5 |  |  | 87
Per Day Producticity | [38 empty] | 201 | 2.3103
Bush Cutting | 1.5 | 3.5 | 4 | 4 | 2 | 2 | 3 | 2 |  |  | 5 | 5 | 6.25 | 6.5 | 10 | 6.6667 | 6.6667 | 6.3333
Land Grading | [18 empty] | 1.6667 | 2.5 | 2.5 | 2.5 | 2 | 2.1667 | 2.5 | 3 | 1.8333 | 3.3333 | 2.3333 | 3.2 | 4 | 3.3333 | 2 | 1 | 1.4 | 1.25 | 0 | #DIV/0!
Manpower
Land Development | [25 empty] | 6 | 8 | 8 | 8 | 6 | 6 | 6 | 5 | 8 | 8 | 7 | 9
[28 empty] | Bushing |  | Balance | Remaining days | Per day requirement
[9 empty] | 250 | 47 | [17 empty] | 250 | 47 | 203 | 19 | 10.6842
Grading
[28 empty] | 250 | 121 | 129 | 19 | 6.7895

## Preliminary Activity
# | Contract Signing & Key Preliminary Activities | Planned | Actual/ Expected | Status
1 | Project Start Date | 2025-02-06 | 2025-02-06
2 | Contract Agreement Signing | 2025-02-10 | 2025-02-10 | Completed
3 | Kick Off meeting_SECI HO | 2025-02-10 | 2025-02-10 | Completed
4 | PBG Submission | 2025-03-05 | 2025-03-05 | Completed
5 | ABG Submission | 2025-03-14 | 2025-03-14 | Completed
6 | Boundary Coordinates Capturing | 2025-02-21 | 2025-02-21 | Completed
7 | Labor License related documents (Form 2, Form 5) | 2025-03-17 | 2025-03-17 | Completed
8 | Labor License | 2025-04-11 | 2025-04-02 | Completed
9 | Customer GST commercial registration & Address (Billing & Delivery) Details | 2025-04-07 | 2025-05-16 | Completed
10 | Topography Survey | 2025-03-14 | 2025-03-14 | Completed
11 | Soil Test (5m) | 2025-03-19 | 2025-03-19 | Completed
12 | Soil Test (10m) | 2025-04-15 | 2025-04-30 | Completed
13 | ERT Test | 2025-04-13 | 2025-04-10 | Completed
14 | Test Pile Casting | 2025-04-26 | 2025-06-07 | Completed
15 | Pull out test | 2025-05-24 | 2025-06-29 | Work in Progress
# | Site Establishment | Planned | Actual/ Expected | Status
1 | Area development | 2025-04-13 | 2025-04-05 | Completed
2 | Store Yard Fencing Work | 2025-06-25 | 2025-06-29 | Completed
3 | Delivery of office cabins/ Toilets/ Security cabins | 2025-05-06 | 2025-06-30 | Completed
4 | Construction Power arrangement | 2025-04-20 | 2025-04-20 | Completed
5 | Internet availability | 2025-04-20 | 2025-04-05 | Completed
6 | Placement of security personnel | 2025-04-15 | 2025-03-24 | Security personal deployed at Site
7 | Set up of Quality Lab | 2025-04-27 | 2025-07-06 | Completed
8 | Set up of safety induction room | 2025-04-27 | 2025-06-30 | Completed
9 | Set up of material storage | 2025-04-17 | 2025-06-30 | Work in Progress
# | Civil Activities | Planned | Actual/ Expected | Status
1 | Periphery Boundary Fencing |  | 2025-06-28 | Work in Progress

## Manpower (hidden)
Project Name : | 300MW SECI RAMAGIRI PROJECT
Project Size : | 300MW AC Capacity & 390 Mwp DC Capacity
Date of Report: | 2025-02-14
S No. | Contractor Name | Resources Category | Manpower Description | 2025-02-14 | Cum. Nos | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25
|  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  |  | Staff | 0 | 0
2 |  | Surveying | Suveryor | 0
3 |  |  | Suveryor | 0 | 0
4 |  | Surveying | Suveryor | 0 | 0
5 |  |  | Suveryor | 0 | 0
6 |  | Security | Security | 1 | 0
7 |  | Grading | Engineers / Supervisors | 0 | 0
8 |  |  | Workers - Skilled | 0 | 0
9 |  |  | Workers - Unskilled | 0 | 0
10 |  | Piling | Engineers / Supervisors | 0 | 0
11 |  |  | Workers - Skilled | 0 | 0
12 |  |  | Workers - Unskilled | 0 | 0
13 |  | Grading | Engineers / Supervisors | 0 | 0
14 |  |  | Workers - Skilled | 0 | 0
15 |  |  | Workers - Unskilled | 0 | 0
16 |  | Piling | Engineers / Supervisors | 0 | 0
17 |  |  | Workers - Skilled | 0 | 0
18 |  |  | Workers - Unskilled | 0 | 0
19 |  | Grading | Engineers / Supervisors | 0 | 0
20 |  |  | Workers - Skilled | 0 | 0
21 |  |  | Workers - Unskilled | 0 | 0
22 |  | Piling | Engineers / Supervisors | 0 | 0
23 |  |  | Workers - Skilled | 0 | 0
24 |  |  | Workers - Unskilled | 0 | 0
25 |  | Grading | Engineers / Supervisors | 0 | 0
26 |  |  | Workers - Skilled | 0 | 0
27 |  |  | Workers - Unskilled | 0 | 0
28 |  | Piling | Engineers / Supervisors | 0 | 0
29 |  |  | Workers - Skilled | 0 | 0
30 |  |  | Workers - Unskilled | 0 | 0
31 |  | Grading | Engineers / Supervisors | 0 | 0
32 |  |  | Workers - Skilled | 0 | 0
33 |  |  | Workers - Unskilled | 0 | 0
34 |  | Piling | Engineers / Supervisors | 0 | 0
35 |  |  | Workers - Skilled | 0 | 0
36 |  |  | Workers - Unskilled | 0 | 0
37 |  | Grading | Engineers / Supervisors | 0 | 0
38 |  |  | Workers - Skilled | 0 | 0
39 |  |  | Workers - Unskilled | 0 | 0
40 |  | Piling | Engineers / Supervisors | 0 | 0
41 |  |  | Workers - Skilled | 0 | 0
42 |  |  | Workers - Unskilled | 0 | 0
43 |  | ICR Works | ICR Engineers / Supervisors | 0 | 0
44 |  |  | ICR Workers - Skilled | 0 | 0
45 |  |  | ICR Workers - Unskilled | 0 | 0
46 |  | MCR Works | Engineers / Supervisors | 0 | 0
47 |  |  | Skilled worker | 0 | 0
48 |  |  | Unskilled worker | 0 | 0
49 |  | DC Works | Engineers / Supervisors | 0 | 0
50 |  |  | DC Technician | 0 | 0
51 |  |  | DC worker - skilled | 0 | 0
52 |  |  | DC worker - unskilled | 0 | 0
53 |  |  | Structure Team | 0 | 0
54 |  |  | safety engineer | 0 | 0
55 |  | DC Works | Engineers / Supervisors | 0 | 0
56 |  |  | DC Technician | 0 | 0
57 |  |  | DC worker - skilled | 0 | 0
58 |  |  | DC worker - unskilled | 0 | 0
59 |  |  | Structure Team | 0 | 0
60 |  |  | safety engineer | 0 | 0
61 |  |  | Engineers / Supervisors | 0 | 0
62 |  |  | DC Technician | 0 | 0
63 |  |  | DC worker - skilled | 0 | 0
64 |  |  | DC worker - unskilled | 0 | 0
65 |  |  | Structure Team | 0 | 0
66 |  |  | safety engineer | 0 | 0
67 |  |  | Engineers / Supervisors | 0 | 0
68 |  |  | DC Technician | 0 | 0
69 |  |  | DC worker - skilled | 0 | 0
70 |  |  | DC worker - unskilled | 0 | 0
71 |  |  | Structure Team | 0 | 0
72 |  |  | safety engineer | 0 | 0
73 |  |  | Engineers / Supervisors | 0 | 0
74 |  |  | DC Technician | 0 | 0
75 |  |  | DC worker - skilled | 0 | 0
76 |  |  | DC worker - unskilled | 0 | 0
77 |  |  | Structure Team | 0 | 0
78 |  |  | safety engineer | 0 | 0
79 |  |  | Engineers / Supervisors | 0 | 0
80 |  |  | DC Technician | 0 | 0
81 |  |  | DC worker - skilled | 0 | 0
82 |  |  | DC worker - unskilled | 0 | 0
83 |  |  | Structure Team | 0 | 0
84 |  |  | safety engineer | 0 | 0
85 |  |  | Engineers / Supervisors | 0 | 0
86 |  |  | DC Technician | 0 | 0
87 |  |  | DC worker - skilled | 0 | 0
88 |  |  | DC worker - unskilled | 0 | 0
89 |  |  | Structure Team | 0 | 0
90 |  |  | safety engineer | 0 | 0
91 |  |  | Engineers / Supervisors | 0 | 0
92 |  |  | DC Technician | 0 | 0
93 |  |  | DC worker - skilled | 0 | 0
94 |  |  | DC worker - unskilled | 0 | 0
95 |  |  | Structure Team | 0 | 0
96 |  |  | safety engineer | 0 | 0
97 |  |  | Engineers / Supervisors | 0 | 0
98 |  |  | DC Technician | 0 | 0
99 |  |  | DC worker - skilled | 0 | 0
100 |  |  | DC worker - unskilled | 0 | 0
101 |  |  | Structure Team | 0 | 0
102 |  |  | safety engineer | 0 | 0
103 |  |  | Engineers / Supervisors | 0 | 0
104 |  |  | DC Technician | 0 | 0
105 |  |  | DC worker - skilled | 0 | 0
106 |  |  | DC worker - unskilled | 0 | 0
107 |  |  | Structure Team | 0 | 0
108 |  |  | safety engineer | 0 | 0
109 |  |  | Engineers / Supervisors | 0 | 0
110 |  |  | DC Technician | 0 | 0
111 |  |  | DC worker - skilled | 0 | 0
112 |  |  | DC worker - unskilled | 0 | 0
113 |  |  | Structure Team | 0
114 |  |  | safety engineer | 0
115 |  |  | Engineers / Supervisors | 0
116 |  |  | DC Technician | 0
117 |  |  | DC worker - skilled | 0
118 |  |  | DC worker - unskilled | 0
119 |  |  | Structure Team | 0
120 |  |  | safety engineer | 0
121 |  |  | Engineers / Supervisors | 0 | 0
122 |  |  | Technician | 0 | 0
123 |  |  | worker - unskilled | 0 | 0
124 |  |  | safety engineer | 0 | 0
125 |  |  | Engineers / Supervisors | 0 | 0
126 |  |  | Technician | 0 | 0
127 |  |  | worker - unskilled | 0 | 0
128 |  |  | Engineers / Supervisors | 0 | 0
129 |  |  | Technician | 0 | 0
130 |  |  | worker - unskilled | 0 | 0
131 |  |  | Engineers / Supervisors | 0 | 0
132 |  |  | Technician | 0 | 0
133 |  |  | worker - unskilled | 0 | 0

## Machinery (hidden)
Project Name : | 300MW SECI RAMAGIRI PROJECT
Project Size : | 300MW AC Capacity & 390 Mwp DC Capacity
Date of Report: | 2025-02-15
S No. | Contractor Name | Resources Category | Resources Description | 2025-02-15 | Cum. Nos | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | PR Construction |  | JCB |  | 58 | [51 empty] | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 |  |  | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 4
2 |  |  | Tractor |  | 0
3 |  |  | Farana |  | 0
2 |  |  | Hire Vehicle | 0 | 0
3 | Boundary wall works |  | Manual Loading Transit mixer |  | 0
4 |  |  | Tractor mounted auger |  | 0
5 |  |  | Tractor with trolly |  | 0
6 |  |  | Water tanker |  | 0
7 |  |  | Pickup |  | 0
13 | Bush cleaning |  | JCB |  | 0
14 |  |  | Tractor with trolly |  | 0
18 | Internal Road works |  | JCB / Grader |  | 0
19 |  |  | Tractor Trolley |  | 0
20 |  |  | Roller |  | 0
21 |  |  | Dumper |  | 0
22 |  |  | Water tanker |  | 0
23 | Approach Road works |  | JCB / Grader |  | 0
24 |  |  | Tractor Trolley |  | 0
25 |  |  | Roller |  | 0
26 |  |  | DG |  | 0
27 |  |  | Water tanker |  | 0
33 | Piling |  | DTH |  | 0
34 |  |  | Tractor Augur |  | 0
35 |  |  | Water tanker |  | 0
36 |  |  | Tractor with trolly |  | 0
37 |  |  | JCB |  | 0
38 |  |  | DG |  | 0
77 | ICR Building |  | Total Station |  | 0
78 |  |  | Tractor with trolly |  | 0
79 |  |  | Water tanker |  | 0
80 |  |  | Tractor mounted auger |  | 0
68 | MCR CIVIL |  | Tractor mounted auger |  | 0
69 |  |  | Water tanker |  | 0
70 |  |  | Tractor with trolly |  | 0
71 |  |  | JCB |  | 0
72 |  |  | DG |  | 0
102 | DC Works |  | Tractor with trolly |  | 0
103 |  |  | Water tanker |  | 0
104 |  |  | DG |  | 0
105 |  |  | Camber |  | 0
106 |  |  | JCB |  | 0

## Ordering
# | Ordering | Make/ OEM | Planned | Actual/ Expected | Remarks
1 | Module Mounting Structure | Pennar | 2025-04-10 | 2025-04-12 | Completed
2 | Inverter Duty Transformer | T&R | 2025-04-10 | 2025-03-31 | Completed
3 | NIFPS |  | 2025-05-03 | 2025-06-30
4 | ICOG/RMU PANEL | Trisquare | 2025-04-21 | 2025-05-20 | Completed
5 | Main HT Switchgear Panel | Trisquare | 2025-04-21 | 2025-05-20 | Completed
6 | Auxiliary LT Panel |  | 2025-05-07 | 2025-06-27
7 | Auxiliary Transformer |  | 2025-05-07 | 2025-06-27
8 | Central Inverter(PCU) | Fimer | 2025-04-13 | 2025-03-31 | Completed
9 | String Combiner Box (SCB) | Trinity Touch | 2025-04-10 | 2025-06-30 | Completed
10 | DC string cable |  | 2025-05-06 | 2025-07-07
11 | DC power cable |  | 2025-04-21 | 2025-07-07
12 | LT AC power cable |  | 2025-04-21 | 2025-07-07
13 | HT AC power cable |  | 2025-05-06 | 2025-07-07
14 | LT power and control cables |  | 2025-05-06 | 2025-07-07
15 | Communication cables |  | 2025-05-06 | 2025-07-07
16 | SCADA system | Adaptive | 2025-04-21 | 2025-06-07 | Completed
17 | UPS and Battery System |  | 2025-05-06 | 2025-06-27
18 | SVG |  | 2025-05-07 | 2025-07-15
19 | Harmonic Filter and its Acessories |  | 2025-05-26 | 2025-07-15
20 | Other BOQ (Lighting, Gland, Lungs, HT termination KIT etc.) |  | 2025-07-01 | 2025-07-01

## MDL (2)
MDL SUMMARY - 300MW SECI PV | [10 empty] | Data Date | 2025-06-22 |  | 2025-07-15 | [5 empty] | 2025-07-15
Sl.No. | Discipline | Discipline | Document Title | Document Number | Approval Catogery | Planned Submission Date (EPCC) | Submitted/Expected Submission | Other drawing linked | Tentative approval date- linked docs. | Revision | Submission Date | Response date | CLIENT Comments / Approval(CAT-I,CAT-II CAT-III & CAT-IV) | No.of Days Reviwed by SECI | No.of Days Reviwed by ARIPL | Approved date | Submission/Review By | Approved Category | Status | Days taken for review/re-submission
1 | General | Survey & Studies | SoW & Method Statement for Topography and Contour Survey | SECI-RG300-PL-CIV-001 | Approval | 2025-02-10 | 2025-02-10 |  |  | R0 | 2025-02-10 | [5 empty] | Approved | CAT - III | Approved
[10 empty] | R1 | 2025-02-12 | 2025-02-12 |  | 0 | 2 | [5 empty] | Submitted - Under Review
[10 empty] | R2 | 2025-02-14 | 2025-02-17 |  | 3 | 2 | [5 empty] | Approved
[10 empty] | R3 | 2025-02-19 | [9 empty] | Re-Submission
2 | General | Survey & Studies | Topography and Contour Report | SECI-RG300-PL-CIV-002 | Information | 2025-03-24 | 2025-03-24 |  |  | R0 | 2025-03-24 | 2025-03-27 | CAT -IV R | 3 | 6 | 2025-04-08 | Approved | CAT -IV | Approved | 6 | Yet to be submitted
[10 empty] | R1 | 2025-04-02 | 2025-04-08 | CAT -IV | 6
3 | General | Survey & Studies | SoW & Method Statement for Geotechnical Investigation | SECI-RG300-PL-CIV-003 | Approval |  |  |  |  | R0 | [7 empty] | CAT - I | Approved
4 | General | Survey & Studies | Geotechnical Investigation Report (Soil Test, CBR, Chemical Analysis & Thermal Resistivity) | SECI-RG300-PL-CIV-004 | Information | 2025-04-21 | 2025-04-21 |  |  | R0 | 2025-04-21 | 2025-04-29 | CAT -IV R | 8 |  | 2025-04-29 | Approved | CAT -IV R | Approved
[10 empty] | R1 | 2025-06-19
5 | General | Survey & Studies | SoW & Method Statement for Hydrology Investigation | SECI-RG300-PL-CIV-005 | Information | 2025-06-06 | 2025-06-12 | [9 empty] | SECI |  | Submitted - Under Review
6 | General | Survey & Studies | Hydrology Investigation Report | SECI-RG300-PL-CIV-006 | Information | 2025-06-06 | 2025-06-07 |  |  | R0 | 2025-06-07 | 2025-06-20 | CAT -IV R |  |  |  | ARIPL | CAT -IV R | Approved | 38
7 | General | Survey & Studies | SoW & Method Statement for Soil resistivity test (ERT) | SECI-RG300-PL-CIV-007 | Approval | 2025-03-26 | 2025-03-26 |  |  | R0 | 2025-03-26 | 2025-04-04 | CAT - II | 9 | 0 |  | SECI | CAT - II | Approved | 102
[10 empty] | R1 | 2025-04-04 |  |  | 102
8 | General | Survey & Studies | Soil resistivity test report (ERT) | SECI-RG300-PL-CIV-008 | Information | 2025-04-24 | 2025-04-24 |  |  | R0 | 2025-04-25 |  |  | 81 |  |  | SECI |  | Submitted - Under Review | 81
9 | General | Survey & Studies | Water Test Report | SECI-RG300-PL-CIV-009 | Information |  |  |  |  | R0 | [6 empty] | Approved | CAT - I | Approved
10 | General | Survey & Studies | Concrete Mix Design Report | SECI-RG300-PL-CIV-010 | Information | 2025-04-25 | 2025-04-25 |  |  | R0 | 2025-04-25 | 2025-05-01 | CAT -IV R | 6 |  |  | ARIPL | CAT -IV R | Re-Submission | 75
11 | General | Survey & Studies | Pile Pull out and Lateral Test Layout & Procedure | SECI-RG300-PL-CIV-011 | Approval | 2025-04-22 | 2025-04-22 |  |  | R0 | 2025-04-22 | 2025-04-24 | CAT - III | 2 | 6 | 2025-05-16 | SECI | CAT - I | Approved | 7
[10 empty] | R1 | 2025-04-30 | 2025-05-01 | CAT - II | 1 | 8
[10 empty] | R2 | 2025-05-09 | 2025-05-16 | CAT - I | 7
12 | General | Survey & Studies | Pile Pull out and Lateral Test Report | SECI-RG300-PL-CIV-012 | Information | 2025-05-24 | 2025-07-05
13 | General | Survey & Studies | SoP for Site Cleaning & Grading | SECI-RG300-PL-CIV-013 | Information
14 | General | Survey & Studies | Design Basis Study Report for Civil & Structural | SECI-RG300-PL-CIV-014 | Approval
1 | Civil | Civil & Structural (MMS) | MMS - Structural Design Calculations & Staad report (2PX26) | SECI-RG300-PL-CIV-101 | Approval | 2025-03-11 | 2025-03-11 |  |  | R0 | 2025-03-11 | 2025-03-20 | CAT - III | 9 | 19 |  | Approved | CAT - I | Approved | 48
[10 empty] | R1 | 2025-04-08 | 2025-04-11 | CAT - II | 3 | 47
[10 empty] | R2 | 2025-05-28 | 2025-06-02 | CAT - I | 5
2 | Civil | Civil & Structural (MMS) | MMS - Structural Design Calculations & Staad report (2PX14 & 2PX28) | SECI-RG300-PL-CIV-102 | Approval | 2025-05-28 | 2025-06-03 |  |  | R0 | 2025-06-03 | 2025-06-10 | CAT - III | 42 |  |  | ARIPL | CAT - III | Re-Submission | 42
3 | Civil | Civil & Structural (MMS) | MMS - Pile Foundation Design Calculation | SECI-RG300-PL-CIV-103 | Approval | 2025-05-18 | 2025-06-05 |  |  | R0 | 2025-06-05 | 2025-06-20 | CAT - III | 40 |  |  | ARIPL | CAT - III | Re-Submission | 40
4 | Civil | Civil & Structural (MMS) | MMS - Structure GA drawings(2PX26) | SECI-RG300-PL-CIV-104 | Approval | 2025-04-04 | 2025-03-11 |  |  | R0 | 2025-03-11 | 2025-03-20 | CAT - II | 9 | 19 | 2025-06-17 | SECI | CAT - I | Approved | 1
[10 empty] | R1 | 2025-04-08 | 2025-04-11 | CAT - I | 3 | 25
[10 empty] | R2 | 2025-05-06 | 2025-05-07 | CAT - I | 1 | 21
[10 empty] | R3 | 2025-05-28 | 2025-05-30 | CAT - II | 2
[10 empty] | R4 | 2025-06-17 | 2025-06-17 | CAT - I | 0
5 | Civil | Civil & Structural (MMS) | MMS - Structure GA drawings(2PX14 & 2PX28) | SECI-RG300-PL-CIV-104A | Approval | 2025-06-03 | 2025-06-03 |  |  | R0 | 2025-06-03 | 2025-06-10 | CAT - III | 42 |  |  | ARIPL | CAT - III | Approved | 42
6 | Civil | Civil & Structural (MMS) | MMS - Structure GA drawings(2PX13) | SECI-RG300-PL-CIV-105 | Approval | 2025-04-04 | 2025-03-11 |  |  | R0 | 2025-03-11 | 2025-03-20 | CAT - III | 9 | 19 | 2025-04-11 | ARIPL | CAT - I | Approved
[10 empty] | R1 | 2025-04-08 | 2025-04-11 | CAT - I | 3
7 | Civil | Civil & Structural (MMS) | MMS - Structural Fabrication drawings(2PX28) | SECI-RG300-PL-CIV-106 | Information | 2025-04-22 | 2025-04-22 |  |  | R0 | 2025-04-22 | 2025-05-02 | CAT -IV | 10 | 3 | 2025-05-02 | SECI | CAT -IV | Approved
[10 empty] | R1 | 2025-05-05 | 2025-05-07 | CAT -IV | 2 | 41
[10 empty] | R2 | 2025-05-28 | 2025-05-30 | CAT -IV | 2
[10 empty] | R3 | 2025-06-17 | 2025-06-17 | CAT -IV
8 | Civil | Civil & Structural (MMS) | MMS - Structural Fabrication drawings(2PX14) & (2PX28) | SECI-RG300-PL-CIV-107 | Information | 2025-06-03 | 2025-06-03 |  |  | R0 | 2025-06-03 | 2025-06-10 | CAT -IV R | 42 |  |  | ARIPL | CAT -IV R | Approved
9 | Civil | Civil & Structural (MMS) | MMS - Pile marking co-ordinates Layout | SECI-RG300-PL-CIV-108 | Information | 2025-06-16 | 2025-06-28 |  |  |  |  | 2025-07-07 | [6 empty] | Approved
1 | Civil | Civil & Structural (MCR+AUX) | MCR - Architectural Drawings for Main Control Room (Plan, Section & Elevations and Finishing) | SECI-RG300-PL-CIV-201 | Approval | 2025-04-16 | 2025-04-16 |  |  | R0 | 2025-04-16 | 2025-05-07 | CAT - III | 21 | 41 |  | SECI | CAT - III | Submitted - Under Review
[10 empty] | R1 | 2025-05-14 | 2025-05-23
[10 empty] | R2 | 2025-06-08 | 2025-06-13
[10 empty] | R3 | 2025-06-17 | 2025-06-19 | CAT - II
2 | Civil | Civil & Structural (MCR+AUX) | MCR - Structural Calculations & Design Report for Building | SECI-RG300-PL-CIV-202 | Approval | 2025-07-30 | 2025-07-30 | MCR Architecture dwg.
3 | Civil | Civil & Structural (MCR+AUX) | MCR - Structural drawing of foundation, plinth beam & column | SECI-RG300-PL-CIV-203 | Approval | 2025-07-05 | 2025-07-05
4 | Civil | Civil & Structural (MCR+AUX) | MCR - Trench & Grade Slab Layout Drawings | SECI-RG300-PL-CIV-204 | Approval | 2025-06-30 | 2025-06-30
5 | Civil | Civil & Structural (MCR+AUX) | MCR - Structural drawing of Staircase, Roof Beams, Roof Slab & Lintel details | SECI-RG300-PL-CIV-205 | Approval | 2025-08-05 | 2025-08-05
6 | Civil | Civil & Structural (MCR+AUX) | MCR - Plumbing Drawings | SECI-RG300-PL-CIV-206 | Approval | 2025-09-05 | 2025-09-05
7 | Civil | Civil & Structural (MCR+AUX) | MCR - Septic Tank Drawings | SECI-RG300-PL-CIV-207 | Approval | 2025-09-08 | 2025-09-08
8 | Civil | Civil & Structural (MCR+AUX) | MCR - Aux Transformer Foundation Design Report | SECI-RG300-PL-CIV-208 | Approval | 2025-07-20 | 2025-07-20
9 | Civil | Civil & Structural (MCR+AUX) | MCR - Aux Transformer Foundation Drawings | SECI-RG300-PL-CIV-209 | Approval | 2025-07-30 | 2025-07-30
1 | Civil | Civil & Structural (Inverter Station) | Design document for Inverter Station | SECI-RG300-PL-CIV-301 | Approval | 2025-06-17 | 2025-06-28
2 | Civil | Civil & Structural (Inverter Station) | Inverter Platform - Architectural & Structural details ICOG) | SECI-RG300-PL-CIV-302 | Approval | 2025-06-17 | 2025-06-28
3 | Civil | Civil & Structural (Inverter Station) | Inverter Platform - Architectural & Structural details (RMU) | SECI-RG300-PL-CIV-303 | Approval | 2025-06-20 | 2025-06-28
4 | Civil | Civil & Structural (Inverter Station) | Inverter Duty Transformer Foundation design calculations | SECI-RG300-PL-CIV-304 | Approval | 2025-06-15 | 2025-06-28
5 | Civil | Civil & Structural (Inverter Station) | IDT Foundation GA and detail drawing | SECI-RG300-PL-CIV-305 | Approval | 2025-06-25 | 2025-06-28
6 | Civil | Civil & Structural (Inverter Station) | IDT - Burnt Oil Pit Design calculations & drawings. | SECI-RG300-PL-CIV-306 | Approval | 2025-07-02 | 2025-07-02
7 | Civil | Civil & Structural (Inverter Station) | ICR - NIFPS design calculations and detail drawing | SECI-RG300-PL-CIV-307 | Approval | 2025-06-28 | 2025-06-28
8 | Civil | Civil & Structural (Inverter Station) | ICR - Inverter to IDT Cable Support Strcuture GA Drawing | SECI-RG300-PL-CIV-308 | Approval | 2025-07-02 | 2025-07-14
9 | Civil | Civil & Structural (Inverter Station) | ICR - Yard Fencing & Gate Drawing | SECI-RG300-PL-CIV-309 | Approval | 2025-07-05 | 2025-07-05
1 | Civil | Civil & Structural (Infrastructure) | Layout - SCB Coordinates Layout | SECI-RG300-PL-CIV-401 | Information | 2025-06-20 | 2025-07-01
2 | Civil | Civil & Structural (Infrastructure) | Layout - ICR Coordinates Layout | SECI-RG300-PL-CIV-402 | Information | 2025-06-25 | 2025-07-01
3 | Civil | Civil & Structural (Infrastructure) | Layout - Boundary Fence Marking Layout | SECI-RG300-PL-CIV-403 | Information | 2025-03-22 | 2025-05-22 |  |  | R0 | 2025-05-22 | 2025-05-23 | CAT -IV R | 1 | 15 |  | ARIPL | CAT -IV R | Re-Submission | 53
[10 empty] | R1 | 2025-06-07 | 2025-06-18 | CAT -IV R | 38
4 | Civil | Civil & Structural (Infrastructure) | Boundary Chain Link Fence Drawing | SECI-RG300-PL-CIV-404 | Approval | 2025-03-03 | 2025-03-03 |  |  | R0 | 2025-03-03 | 2025-03-05 | CAT - III | 2 | 15 | 2025-05-23 | Approved | CAT - I | Approved | 1
[10 empty] | R1 | 2025-03-20 | 2025-03-22 | CAT - I | 2 | 61
[10 empty] | R2 | 2025-05-22 | 2025-05-23 | CAT - I | 1
5 | Civil | Civil & Structural (Infrastructure) | Plant Main Gate drawing | SECI-RG300-PL-CIV-405 | Approval | 2025-07-15 | 2025-07-15
6 | Civil | Civil & Structural (Infrastructure) | Road Calculations, Cross sections & Layout drawing | SECI-RG300-PL-CIV-406 | Approval | 2025-05-18 | 2025-07-10
7 | Civil | Civil & Structural (Infrastructure) | Watch Tower Design Calculations | SECI-RG300-PL-CIV-407 | Approval | 2025-07-20 | 2025-07-10
8 | Civil | Civil & Structural (Infrastructure) | Watch Tower Structural Drawing | SECI-RG300-PL-CIV-408 | Approval | 2025-07-25 | 2025-07-15
9 | Civil | Civil & Structural (Infrastructure) | Security Office - Design calculations | SECI-RG300-PL-CIV-409 | Approval | 2025-08-05 | 2025-07-15
10 | Civil | Civil & Structural (Infrastructure) | Security Office - Architectural & Structural drawings | SECI-RG300-PL-CIV-410 | Approval | 2025-08-08 | 2025-07-15
11 | Civil | Civil & Structural (Infrastructure) | Security Cabin - GA & Foundation drawing | SECI-RG300-PL-CIV-411 | Approval | 2025-08-12 | 2025-07-22
12 | Civil | Civil & Structural (Infrastructure) | Store Room - Design calculations | SECI-RG300-PL-CIV-412 | Approval | 2025-07-05 | 2025-07-22
13 | Civil | Civil & Structural (Infrastructure) | Store Room - Structural & Foundation Drawings | SECI-RG300-PL-CIV-413 | Approval | 2025-07-10 | 2025-07-26
14 | Civil | Civil & Structural (Infrastructure) | MCS - Underground water storage design calculation & Drawing | SECI-RG300-PL-CIV-414 | Approval | 2025-06-25 | 2025-08-01
15 | Civil | Civil & Structural (Infrastructure) | MCS - Tank, Piping Network Layout & Pump Sizing Calculations | SECI-RG300-PL-CIV-415 | Approval | 2025-06-30 | 2025-07-30
16 | Civil | Civil & Structural (Infrastructure) | Storm water Drainage - Design Calculations | SECI-RG300-PL-CIV-416 | Approval | 2025-07-05 | 2025-07-30
17 | Civil | Civil & Structural (Infrastructure) | Storm water Drainage - Drawing & cross sections | SECI-RG300-PL-CIV-417 | Approval | 2025-07-08 | 2025-08-01
18 | Civil | Civil & Structural (Infrastructure) | Bore well - Water Yield report & locations layout | SECI-RG300-PL-CIV-418 | Information | 2025-07-10 | 2025-07-10
19 | Civil | Civil & Structural (Infrastructure) | Bore well - Water test report | SECI-RG300-PL-CIV-419 | Information | 2025-07-15 | 2025-08-07
20 | Civil | Civil & Structural (Infrastructure) | Street Lighting Pole GA & Foundation Details | SECI-RG300-PL-CIV-420 | Approval | 2025-07-15 | 2025-08-07
21 | Civil | Civil & Structural (Infrastructure) | Street Lighting Pole Design Calculations | SECI-RG300-PL-CIV-421 | Information | 2025-07-20 | 2025-08-13
22 | Civil | Civil & Structural (Infrastructure) | Lightning Arrestor GA & Foundation Drawing | SECI-RG300-PL-CIV-422 | Approval | 2025-06-18 | 2025-08-13
23 | Civil | Civil & Structural (Infrastructure) | Lightning Arrestor Design Calculations | SECI-RG300-PL-CIV-423 | Information | 2025-06-25 | 2025-08-18
24 | Civil | Civil & Structural (Infrastructure) | Weather Monitoring System GA & Foundation Drawing | SECI-RG300-PL-CIV-424 | Approval | 2025-07-25 | 2025-08-18
25 | Civil | Civil & Structural (Infrastructure) | SCB - Support Structure GA Drawing | SECI-RG300-PL-CIV-425 | Approval | 2025-06-20 | 2025-08-18
26 | Civil | Civil & Structural (Infrastructure) | SCB - Support Structure Design Calculation | SECI-RG300-PL-CIV-426 | Information | 2025-06-25 | 2025-08-01
27 | Civil | Civil & Structural (Infrastructure) | Wet Cleaning System - GTP, Drawings, philosophy, calculation | SECI-RG300-PL-CIV-427 | Approval | 2025-06-28 | 2025-08-20
28 | Civil | Civil & Structural (Infrastructure) | SVG - Design calculations | SECI-RG300-PL-CIV-428 | Approval | 2025-07-20 | 2025-08-20
29 | Civil | Civil & Structural (Infrastructure) | SVG - Structural Drawings | SECI-RG300-PL-CIV-429 | Approval | 2025-07-25 | 2025-07-25
| Electrical | Electrical (SLD & Layouts) | AC SINGLE LINE DIAGRAM | SECI-RG300-PL-ELE-001 | Approval | 2025-03-03 | 2025-02-26 |  |  | R0 | 2025-02-26 | 2025-03-05 | CAT - III | 7 | 33 |  | Approved | CAT - I | Approved
3 | [9 empty] | R1 | 2025-04-07 | 2025-04-16 | CAT - III | 9 | 4
4 | [9 empty] | R2 | 2025-04-20 | 2025-04-23 | CAT - II | 3 | 1
[10 empty] | R3 | 2025-04-24 | 2025-06-12 | CAT - I | 82
5 | Electrical | Electrical (SLD & Layouts) | DC SINGLE LINE DIAGRAM | SECI-RG300-PL-ELE-002 | Approval | 2025-04-08 | 2025-04-25 |  |  | R0 | 2025-04-25 | 2025-05-13 | CAT - III | 18 | 3 |  | SECI | CAT - III | Re-Submission | 60
6 | [9 empty] | R1 | 2025-05-16 | 2025-06-19 |  | 60
7 | Electrical | Electrical (SLD & Layouts) | AUXILIARY SINGLE LINE DIAGRAM | SECI-RG300-PL-ELE-003 | Approval | 2025-04-15 | 2025-05-13 |  |  | R0 | 2025-05-13 | 2025-06-13 | CAT - III | 63 |  |  | ARIPL | CAT - III | Re-Submission | 63
8 | Electrical | Electrical (SLD & Layouts) | Layouts - Overall Array Layout | SECI-RG300-PL-ELE-004 | Approval | 2025-05-03 | 2025-04-11 |  | 2025-06-13 | R0 | 2025-04-11 | 2025-04-19 | CAT - III | 8 | 57 |  | ARIPL | CAT - II | Re-Submission | 26
9 | [9 empty] | R1 | 2025-05-16 | 2025-05-31 | CAT - III | 15
9 | [9 empty] | R2 | 2025-06-15 | 2025-06-19 | CAT - II
10 | Electrical | Electrical (SLD & Layouts) | Layouts -DC Cable routing layout & sections | SECI-RG300-PL-ELE-005 | Approval | 2025-06-27 | 2025-06-27 | Overall layout | 2025-06-13
11 | Electrical | Electrical (SLD & Layouts) | Layouts -AC Cable routing layout & sections | SECI-RG300-PL-ELE-006 | Approval | 2025-06-27 | 2025-06-27 | Overall layout | 2025-06-13
12 | Electrical | Electrical (SLD & Layouts) | Layouts - AC Earthing Layout | SECI-RG300-PL-ELE-007 | Approval | 2025-06-27 | 2025-06-27 | Overall layout | 2025-06-13
13 | Electrical | Electrical (SLD & Layouts) | Layouts -DC Earthing Layout | SECI-RG300-PL-ELE-008 | Approval | 2025-06-27 | 2025-06-27 | Overall layout | 2025-06-13
14 | Electrical | Electrical (SLD & Layouts) | Layouts - ICR Equipment Layout | SECI-RG300-PL-ELE-009 | Approval | 2025-04-21 | 2025-05-27 |  | 2025-05-27 | R0 | 2025-05-27 | 2025-06-04 | CAT - III | 8 | 41 |  | ARIPL | CAT - II | Re-Submission | 49
[10 empty] | R1 | 2025-06-13 | 2025-06-17 | CAT - III
[10 empty] | R2 | 2025-06-18 | 2025-06-20 | CAT - II
15 | Electrical | Electrical (SLD & Layouts) | Layouts - Plant Lightning Protection System Layout | SECI-RG300-PL-ELE-010 | Approval | 2025-05-23 | 2025-05-23 |  |  | R0 | 2025-05-23 |  |  | 53 |  |  | SECI |  | Submitted - Under Review | 53
16 | Electrical | Electrical (SLD & Layouts) | Layouts - Earthing & Lightning Protection Layout for ICR | SECI-RG300-PL-ELE-011 | Approval | 2025-06-18 | 2025-06-28 | ICR Equipment layout/ AC Earthing calculation | 2025-06-06
17 | Electrical | Electrical (SLD & Layouts) | Layouts - Plant Illuminatoin layout | SECI-RG300-PL-ELE-012 | Approval | 2025-06-18 | 2025-06-28 | ICR Equipment layout | 2025-06-06
18 | Electrical | Electrical (SLD & Layouts) | Layouts - Fire Fighting Layout for ICR & MCR | SECI-RG300-PL-ELE-013 | Approval | 2025-06-18 | 2025-06-28 | ICR Equipment layout | 2025-06-06
19 | Electrical | Electrical (SLD & Layouts) | Layouts - Equipment Layout for MCR | SECI-RG300-PL-ELE-014 | Approval | 2025-05-17 | 2025-06-28
20 | Electrical | Electrical (SLD & Layouts) | Layouts - Cable Trench Layout for MCR | SECI-RG300-PL-ELE-015 | Approval | 2025-06-13 | 2025-06-30
21 | Electrical | Electrical (SLD & Layouts) | SCADA - Weather Monitoring System (WMS) Mounting GA & Layout | SECI-RG300-PL-ELE-016 | Approval | 2025-06-27 | 2025-06-30 | GA GTP- SCADA | 2025-06-20
22 | Electrical | Electrical (SLD & Layouts) | SCADA - Communication Cable Routing Layout | SECI-RG300-PL-ELE-017 | Information | 2025-07-04 | 2025-07-04 | GA GTP- SCADA | 2025-06-20
23 | Electrical | Electrical (SLD & Layouts) | CCTV - Overall Plant CCTV Layout | SECI-RG300-PL-ELE-018 | Approval | 2025-07-15 | 2025-07-15 |  | 2025-06-27
24 | Electrical | Electrical (SLD & Layouts) | SCADA - System Architecture Schematics | SECI-RG300-PL-ELE-019 | Approval | 2025-06-30 | 2025-06-30 |  | 2025-06-30
25 | Electrical | Electrical (SLD & Layouts) | SVG - General Arragement Layout | SECI-RG300-PL-ELE-020 | Approval | 2025-07-12 | 2025-07-12 |  | 2025-07-12
1 | Electrical | Electrical (SLD & Layouts) | SVG Cable routing and trench details | SECI-RG300-PL-ELE-021 | Approval | 2025-07-14 | 2025-07-14 |  | 2025-07-14
2 | Electrical | Electrical (SLD & Layouts) | Harmonic filter GA layout | SECI-RG300-PL-ELE-022 | Approval | 2025-07-25 | 2025-07-25 |  | 2025-07-15
3 | Electrical | Electrical (SLD & Layouts) | Harmonic Cable routing and trench details | SECI-RG300-PL-ELE-023 | Approval | 2025-07-16 | 2025-07-16 |  | 2025-07-16
4 | Electrical | Electrical (SLD & Layouts) | Earthing Layout for SVG and Harmonic filter | SECI-RG300-PL-ELE-024 | Approval | 2025-07-22 | 2025-07-22 |  | 2025-07-22
| Electrical | Electrical (SLD & Layouts) | Illumination Layout for SVG and harmonic Filter | SECI-RG300-PL-ELE-025 | Approval | 2025-07-28 | 2025-07-28 |  | 2025-07-28
5 | Electrical | Electrical (Calculations) | Report - Energy Yield Assessment Report (PV Syst Report) | SECI-RG300-PL-ELE-101 | Approval | 2025-02-26 | 2025-02-26 |  |  | R0 | 2025-02-26 |  |  | 139 |  |  | SECI |  | Submitted - Under Review | 139
6 | Electrical | Electrical (Calculations) | Report - Shadow Analysis Report | SECI-RG300-PL-ELE-102 | Approval | 2025-08-08 | 2025-08-08 |  | 2025-08-08
7 | Electrical | Electrical (Calculations) | Grid Study Report in PSSE & PSCAD software | SECI-RG300-PL-ELE-103 | Approval | 2025-11-26 | 2025-11-26 |  | 2025-11-26
8 | Electrical | Electrical (Calculations) | Calc - DC Cable Sizing Calculations | SECI-RG300-PL-ELE-104 | Approval | 2025-04-07 | 2025-04-26 |  |  | R0 | 2025-04-26 | 2025-04-30 | CAT - III | 4 | 14 |  | SECI | CAT - I | Approved | 21
9 | [9 empty] | R1 | 2025-05-14 | 2025-06-04 | CAT - I | 21
10 | Electrical | Electrical (Calculations) | Calc - AC Cable Sizing Calculations | SECI-RG300-PL-ELE-105 | Approval | 2025-04-07 | 2025-05-14 |  |  | R0 | 2025-05-14 | 2025-06-01 | CAT - III | 18 | 12 |  | SECI | CAT - I | Approved | 62
[10 empty] | R1 | 2025-06-04 | 2025-06-12 | CAT - III
[10 empty] | R2 | 2025-06-13 | 2025-06-22 | CAT - I | 32
11 | Electrical | Electrical (Calculations) | Calc - DC Cable schedule and losses calculation | SECI-RG300-PL-ELE-106 | Approval | 2025-06-03 | 2025-06-29 |  | 2025-06-20
12 | Electrical | Electrical (Calculations) | Calc - AC Cable schedule and losses calculation | SECI-RG300-PL-ELE-107 | Approval | 2025-05-31 | 2025-06-29 |  | 2025-06-20
| Electrical | Electrical (Calculations) | Calc - Auxilary Cable Sizing & Schedules | SECI-RG300-PL-ELE-108 | Approval | 2025-06-23 | 2025-06-29 |  | 2025-06-23
13 | Electrical | Electrical (Calculations) | LT power & Control Cable Schedules and Termination details | SECI-RG300-PL-ELE-109 | Information | 2025-06-21 | 2025-06-29 |  | 2025-06-21
| Electrical | Electrical (Calculations) | Calc - DC Earthing Calculation | SECI-RG300-PL-ELE-110 | Approval | 2025-05-06 | 2025-05-15 |  |  | R0 | 2025-05-15 | 2025-06-05 | CAT - III | 61 |  | 2025-06-05 | SECI | CAT - II | Approved | 61
[10 empty] | R1 | 2025-06-05 | 2025-06-13 | CAT - II
[10 empty] | R2 | 2025-06-19 | 2025-06-22 | CAT - I
14 | Electrical | Electrical (Calculations) | Calc - AC Earthing Calculation | SECI-RG300-PL-ELE-111 | Approval | 2025-05-06 | 2025-05-14 |  |  | R0 | 2025-05-14 |  |  | 62 |  |  | SECI |  | Submitted - Under Review | 62
15 | Electrical | Electrical (Calculations) | Calc - Auxilary Transformer Sizing Calculation | SECI-RG300-PL-ELE-112 | Approval | 2025-04-08 | 2025-04-08 |  |  | R0 | 2025-04-08 | 2025-04-23 | CAT - III | 15 | 55 |  | SECI | CAT - I | Approved | 28
1 | [9 empty] | R1 | 2025-05-11 | 2025-06-01 | CAT - III | 21 | 16
1 | [9 empty] | R1 | 2025-06-17 | 2025-06-22 | CAT - I | 5 | 23
2 | Electrical | Electrical (Calculations) | Calc - UPS Sizing Calculation | SECI-RG300-PL-ELE-113 | Approval | 2025-04-08 | 2025-04-08 |  |  | R0 | 2025-04-08 | 2025-04-23 | CAT - III | 15 | 55 |  | SECI | CAT - I | Approved | 28
3 | [9 empty] | R1 | 2025-05-10 | 2025-06-01 | CAT - III | 22 | 16
3 | [9 empty] | R2 | 2025-06-17 | 2025-06-22 | CAT - I | 5
4 | Electrical | Electrical (Calculations) | SCADA - IO List for SCADA System | SECI-RG300-PL-ELE-114 | Information | 2025-05-30 | 2025-06-27 |  | 2025-05-30
5 | Electrical | Electrical (Calculations) | SCADA - Communication Cable Schedules & Termination | SECI-RG300-PL-ELE-115 | Information | 2025-07-07 | 2025-07-07 |  | 2025-07-07
6 | Vendor Documents | Electrical GTP and Type Test reports | Inverter Duty Transformer-GTP, GA & Type test reports | SECI-RG300-PL-ELE-201 | Approval | 2025-05-26 | 2025-05-27 |  |  | R0 | 2025-05-27 | 2025-06-16 | CAT - III | 49 |  |  | ARIPL | CAT - III | Re-Submission | 49
|  | Electrical GTP and Type Test reports | Inverter Duty Transformer-GTP, GA & Type test reports (T&R) | SECI-RG300-PL-ELE-201A | Approval | 2025-06-09 | 2025-06-05 |  |  | R0 | 2025-06-05 | [5 empty] | SECI |  | Submitted - Under Review
7 | Vendor Documents | Electrical GTP and Type Test reports | NIFPS-GTP, GA & Type test reports | SECI-RG300-PL-ELE-202 | Approval | 2025-06-08 | 2025-06-27 | Ordering
8 | Vendor Documents | Electrical GTP and Type Test reports | ICOG/RMU PANEL-GTP, GA & Type test reports | SECI-RG300-PL-ELE-203 | Approval | 2025-05-28 | 2025-06-09 | Ordering |  | R0 | 2025-06-09 | [5 empty] | SECI |  | Submitted - Under Review
9 | Vendor Documents | Electrical GTP and Type Test reports | Main HT Swtichgear Panel-GTP, GA & Type test reports | SECI-RG300-PL-ELE-204 | Approval | 2025-05-28 | 2025-06-09 | Ordering |  | R0 | 2025-06-09 | [5 empty] | SECI |  | Submitted - Under Review
10 | Vendor Documents | Electrical GTP and Type Test reports | Auxiliary LT Panel -GTP, GA & Type test reports | SECI-RG300-PL-ELE-205 | Approval | 2025-06-12 | 2025-06-30 | Ordering
11 | Vendor Documents | Electrical GTP and Type Test reports | Auxiliary Transformer-GTP, GA & Type test reports | SECI-RG300-PL-ELE-206 | Approval | 2025-06-06 | 2025-06-30 | Ordering
12 | Vendor Documents | Electrical GTP and Type Test reports | ESE Lightning Arrestor -GTP, GA & Type test reports | SECI-RG300-PL-ELE-207 | Approval | 2025-08-01 | 2025-08-01 | Ordering
13 | Vendor Documents | Electrical GTP and Type Test reports | Lighting Fixtures with calculations-GTP, GA & Type test reports | SECI-RG300-PL-ELE-208 | Approval | 2025-07-07 | 2025-07-07 | Ordering
14 | Vendor Documents | Electrical GTP and Type Test reports | String Combiner Box (SCB) -GTP, GA & Type test reports | SECI-RG300-PL-ELE-209 | Approval | 2025-05-11 | 2025-06-16 | Ordering | 2025-06-06
15 | Vendor Documents | Electrical GTP and Type Test reports | DC string cable -GTP, GA & Type test reports | SECI-RG300-PL-ELE-210 | Approval | 2025-07-27 | 2025-07-27 | Ordering
16 | Vendor Documents | Electrical GTP and Type Test reports | DC power cable -GTP, GA & Type test reports | SECI-RG300-PL-ELE-211 | Approval | 2025-07-05 | 2025-07-05 | Ordering
17 | Vendor Documents | Electrical GTP and Type Test reports | LT AC power cable -GTP, GA & Type test reports | SECI-RG300-PL-ELE-212 | Approval | 2025-07-02 | 2025-07-02 | Ordering
18 | Vendor Documents | Electrical GTP and Type Test reports | HT AC power cable -GTP, GA & Type test reports | SECI-RG300-PL-ELE-213 | Approval | 2025-06-14 | 2025-06-27 | Ordering
19 | Vendor Documents | Electrical GTP and Type Test reports | MC4 connectors -GTP, GA & Type test reports | SECI-RG300-PL-ELE-214 | Information | 2025-07-02 | 2025-07-02 | Ordering
20 | Vendor Documents | Electrical GTP and Type Test reports | LT power and control cables -GTP, GA & Type test reports | SECI-RG300-PL-ELE-215 | Information | 2025-07-09 | 2025-07-09 | Ordering
21 | Vendor Documents | Electrical GTP and Type Test reports | Communication cables -GTP, GA & Type test reports | SECI-RG300-PL-ELE-216 | Approval | 2025-08-25 | 2025-08-25 | Ordering
22 | Vendor Documents | Electrical GTP and Type Test reports | Earthing Strip & acessories -GTP, GA & Type test reports | SECI-RG300-PL-ELE-217 | Information | 2025-06-05 | 2025-06-28 | Ordering
23 | Vendor Documents | Electrical GTP and Type Test reports | Earth Pit -GTP, GA & Type test reports | SECI-RG300-PL-ELE-218 | Approval | 2025-07-20 | 2025-07-20 | Ordering
24 | Vendor Documents | Electrical GTP and Type Test reports | MV Cable Termination Kit & Jointing Kit -GTP, GA & Type test reports | SECI-RG300-PL-ELE-219 | Information | 2025-06-26 | 2025-06-26 | Ordering
25 | Vendor Documents | Electrical GTP and Type Test reports | Battery & Battery Charger-GTP, GA & Type test reports | SECI-RG300-PL-ELE-220 | Approval | 2025-07-02 | 2025-07-02 | Ordering
26 | Vendor Documents | Electrical GTP and Type Test reports | HDPE Conduit (DWC)-GTP, GA & Type test reports | SECI-RG300-PL-ELE-221 | Information | 2025-11-01 | 2025-11-01 | Ordering
27 | Vendor Documents | Electrical GTP and Type Test reports | UPS-GTP, GA & Type test reports | SECI-RG300-PL-ELE-222 | Approval | 2025-06-18 | 2025-06-30 | Ordering
28 | Vendor Documents | Electrical GTP and Type Test reports | Cable Trays & Accessories - Drawings | SECI-RG300-PL-ELE-223 | Information | 2025-07-15 | 2025-07-15 | Ordering
29 | Vendor Documents | Electrical GTP and Type Test reports | Lugs, Trefoils and Glands - Drawings, Details, Catalogue | SECI-RG300-PL-ELE-224 | Information | Done | Done | Ordering
30 | Vendor Documents | Electrical GTP and Type Test reports | Safety Items (Rubber Mat, Hand Gloves, First Aid Box, Safety chart, Fire fighting equipment, Danger Board ETC) - Datasheet, GA Drawing, TTR of Insulating Mats | SECI-RG300-PL-ELE-226 | Information | 2025-08-31 | 2025-08-31 | Ordering
31 | Vendor Documents | Electrical GTP and Type Test reports | SCADA Panel&PPC Schematics,GA and datasheets | SECI-RG300-PL-ELE-228 | Approval | 2025-06-26 | 2025-06-26 | Ordering
32 | Vendor Documents | Electrical GTP and Type Test reports | Weather Station - GTP & Drawings | SECI-RG300-PL-ELE-229 | Approval | 2025-06-06 | 2025-06-30 | Ordering
33 | Vendor Documents | Electrical GTP and Type Test reports | CCTV - GTP & Drawings | SECI-RG300-PL-ELE-230 | Approval | 2025-06-06 | 2025-06-30 | Ordering
1 | Vendor Documents | Electrical GTP and Type Test reports | Fire Alarm System & Equipments - GTP & Drawings | SECI-RG300-PL-ELE-231 | Approval | 2025-06-18 | 2025-06-30 | Ordering
2 | Vendor Documents | Electrical GTP and Type Test reports | SCADA SCREENS AND REPORT FORMAT | SECI-RG300-PL-ELE-232 | Approval | 2025-06-26 | 2025-06-30 | Ordering
3 | Vendor Documents | Electrical GTP and Type Test reports | SVG- -GTP, GA & Type test reports | SECI-RG300-PL-ELE-233 | Approval | 2025-07-10 | 2025-07-10 | Ordering
4 | Vendor Documents | Electrical GTP and Type Test reports | Harmonic Filter and its Acessires | SECI-RG300-PL-ELE-234 | Approval | 2025-07-30 | 2025-07-30 | Ordering
5 | Vendor Documents | Electrical GTP and Type Test reports | Central Inverter(PCU) -GTP, GA & Type test reports | SECI-RG300-PL-ELE-235 | Approval | 2025-05-20 | 2025-06-28 | Ordering |  | R0 | 2025-05-13 | 2025-06-04 | CAT - III | 22 | 41 |  | SECI | CAT - III | Submitted - Under Review | 63
[10 empty] | R1 | 2025-06-16
6 | Vendor Documents | MQP | Inverter Duty Transformer-MQP | SECI-RG300-PL-MQP-001 | Approval | 2025-06-18 | 2025-05-27 | Ordering |  | R0 | 2025-05-27 |  |  | 49 |  |  | SECI |  | Submitted - Under Review | 49
7 | Vendor Documents | MQP | NIFPS-MQP | SECI-RG300-PL-MQP-002 | Information | 2025-06-18 | 2025-06-27 | Ordering
8 | Vendor Documents | MQP | ICOG/RMU PANEL-MQP | SECI-RG300-PL-MQP-003 | Approval | 2025-06-25 | 2025-06-09 | Ordering |  | R0 | 2025-06-09 | 2025-06-20 | CAT - III |  |  |  | ARIPL | CAT - III | Re-Submission
9 | Vendor Documents | MQP | Main HT Swtichgear Panel-MQP | SECI-RG300-PL-MQP-004 | Approval | 2025-08-01 | 2025-06-09 | Ordering |  | R0 | 2025-06-09 | [5 empty] | SECI |  | Submitted - Under Review
10 | Vendor Documents | MQP | Auxiliary Panel -MQP | SECI-RG300-PL-MQP-005 | Approval | 2025-07-07 | 2025-07-07 | Ordering
11 | Vendor Documents | MQP | ESE Lightning Arrestor -MQP | SECI-RG300-PL-MQP-006 | Information | 2025-07-07 | 2025-07-07 | Ordering
12 | Vendor Documents | MQP | Lighting Fixtures --MQP | SECI-RG300-PL-MQP-007 | Information | 2025-07-27 | 2025-07-27 | Ordering
13 | Vendor Documents | MQP | String Combiner Box (SCB) -MQP | SECI-RG300-PL-MQP-008 | Approval | 2025-07-05 | 2025-07-05 | Ordering
14 | Vendor Documents | MQP | DC string cable -MQP | SECI-RG300-PL-MQP-009 | Approval | 2025-06-14 | 2025-06-27 | Ordering
15 | Vendor Documents | MQP | DC power cable -MQP | SECI-RG300-PL-MQP-010 | Approval | 2025-07-02 | 2025-07-02 | Ordering
16 | Vendor Documents | MQP | LT AC power cable -MQP | SECI-RG300-PL-MQP-011 | Approval | 2025-08-01 | 2025-08-01 | Ordering
17 | Vendor Documents | MQP | HT AC power cable -MQP | SECI-RG300-PL-MQP-012 | Approval | 2025-06-05 | 2025-06-27 | Ordering
18 | Vendor Documents | MQP | LT power and control cables -MQP | SECI-RG300-PL-MQP-013 | Information | 2025-07-20 | 2025-07-20 | Ordering
19 | Vendor Documents | MQP | Earthing Strip -MQP | SECI-RG300-PL-MQP-014 | Information | 2025-06-26 | 2025-06-26 | Ordering
20 | Vendor Documents | MQP | Earth Pit -MQP | SECI-RG300-PL-MQP-015 | Information | 2025-07-02 | 2025-07-02 | Ordering
21 | Vendor Documents | MQP | MV Cable Termination Kit & Jointing Kit -MQP | SECI-RG300-PL-MQP-016 | Information | 2025-06-18 | 2025-06-27 | Ordering
22 | Vendor Documents | MQP | Battery & Battery Charger-MQP | SECI-RG300-PL-MQP-017 | Approval | Done | Done | Ordering
23 | Vendor Documents | MQP | UPS-MQP | SECI-RG300-PL-MQP-018 | Approval | 2025-07-15 | 2025-07-15 | Ordering
24 | Vendor Documents | MQP | Cable Trays & Accessories - MQP | SECI-RG300-PL-MQP-019 | Information | 2025-06-18 | 2025-06-27 | Ordering
25 | Vendor Documents | MQP | Communication Cable-MQP | SECI-RG300-PL-MQP-020 | Approval | Done | Done | Ordering
26 | Vendor Documents | MQP | SCADA Panel&PPC MQP | SECI-RG300-PL-MQP-021 | Approval | 2025-07-30 | 2025-07-30 | Ordering
| Vendor Documents | MQP | Weather Station - MQP | SECI-RG300-PL-MQP-022 | Information | 2025-07-30 | 2025-07-30 | Ordering
27 | Vendor Documents | MQP | CCTV - MQP | SECI-RG300-PL-MQP-023 | Information | 2025-08-30 | 2025-08-30 | Ordering
28 | Vendor Documents | MQP | Fire Alarm System & Equipments - MQP | SECI-RG300-PL-MQP-024 | Information | 2025-08-30 | 2025-08-30 | Ordering
29 | Vendor Documents | MQP | SVG- -MQP | SECI-RG300-PL-MQP-025 | Approval | 2025-08-30 | 2025-08-30 | Ordering
| Vendor Documents | MQP | Central Inverter(PCU) -MQP | SECI-RG300-PL-MQP-026 | Approval | 2025-05-16 | 2025-05-16 | Ordering |  | R0 | 2025-05-16 | 2025-05-30 | CAT - III | 14 | 46 |  | ARIPL | CAT - III | Re-Submission | 46
R1
| Vendor Documents | MQP | Harmonic Filter - MQP | SECI-RG300-PL-MQP-027 | Approval | 2025-07-30 | 2025-07-30 | Ordering
| Vendor Documents | MQP | Auxiliary Transformer - MQP | SECI-RG300-PL-MQP-028 | Approval | 2025-06-18 | 2025-06-27 | Ordering
| Vendor Documents | MQP | Module Mounting Structure - MQP | SECI-RG300-PL-MQP-028 | Approval | 2025-05-26 | 2025-05-26 | Ordering |  | R0 | 2025-05-26 | 2025-06-02 | CAT - III | 7 | 8 |  | ARIPL | CAT - III | Approved | 33
[10 empty] | R1 | 2025-06-10 | 2025-06-12 | CAT - III | 2 | 33
Formulas:
Approved date = [Response date, row below]
Approved date = [Response date]
Submitted/Expected Submission = [Submission Date]
Submitted/Expected Submission = [Planned Submission Date (EPCC)]
Planned Submission Date (EPCC) = [2]Sheet4!E50

## Construction Status
| Date | 2025-07-15
Section | S.No | Site Activity | Planned Start | Planned Finish | No. of Days | Actual/ Expected Start | Actual/ Expected Finish | UoM | Qty | Start Date | Actual/ Expected Finish Date | No of Days | Avg/Day | Actual as on Date (%) | Comp. | Bal | Actual as on date | Till Last Month | time axis 2025-03-30 to 2025-08-06
 | time axis 2025-03-30 to 2025-08-06
L & G | 1 | Bush removal | 2025-04-03 | 2025-08-01 | 120 | 2025-04-07 | 2025-08-01 | Acre | 1033 | 2025-04-07 | 2025-05-19 | 43 | 24.0233 | 84.41% | 872 | 161 | 872 | 486 | 0 | 0 |  |  |  | 1.5 | 3.5 | 4 | 4 | 4 | 4 | 3 | 2 |  | 10 | 20 | 20 | 20 | 21 | 40 | 40 | 40 | 38 | [11 empty] | 5 | 10 | 10 | 10 | 5 | 7 | 5 | 0 | 0 | 7 | 0 | 17 | 19 | 24 | 9 | 12 | 0 | 16 | 0 | 0 | 0 | 0 | 6 | 16 | 15 | 18 | 14 | 16 | 15 | 14 | 18 | 14 | 15 | 10 | 11 | 16 | 13 | 15 | 17 | 5 | 14 | 16 | 13 | 13 | 11 | 7 | 5 | 5 | 5 | 5 | 5 | 7 | 10 | 7 | 6 | 5 | 7 | 12 | 9 | 8 | 7 | 7 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Land grading | 2025-04-03 | 2025-08-01 | 120 | 2025-04-07 | 2025-08-01 | Acre | 1033 | 2025-04-07 | 2025-05-19 | 43 | 24.0233 | 84.41% | 872 | 161 | 872 | 486 | [23 empty] | 10 | 10 | 10 | 10 | 12 | 13 | 10 | 12 | 11 | 20 | 14 | 16 | 10 | 6 | 10 | 5 | 7 | 5 | 7 | 7 | 7 | 12 | 17 | 19 | 24 | 9 | 12 | 18 | 16 | 15 | 23 | 22 | 20 | 18 | 16 | 15 | 18 | 14 | 16 | 15 | 14 | 18 | 14 | 15 | 10 | 11 | 16 | 13 | 15 | 17 | 5 | 14 | 16 | 13 | 13 | 11 | 7 | 5 | 5 | 5 | 5 | 5 | 7 | 10 | 7 | 6 | 5 | 7 | 12 | 9 | 8 | 7 | 7 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Site Initials | 3 | Boundry Coordinate capturing | 2025-02-12 | 2025-02-21 | 9 | 2025-02-12 | 2025-02-21 | Lot. | 1 | 2025-02-12 | 2025-02-22 | 11 | 0.090909 | 100% | 1 | 0 | 1 | 1 | bar: 2025-03-30
| 4 | Topo Survey | 2025-02-23 | 2025-03-14 | 19 | 2025-02-23 | 2025-03-14 | Lot. | 1 | 2025-02-15 | 2025-03-14 | 28 | 0.035714 | 100% | 1 | 0 | 1 | 1 | bar: 2025-03-30
| 5 | Soil Investigation | 2025-02-15 | 2025-04-15 | 59 | 2025-02-15 | 2025-04-29 | Nos. | 79 | 2025-02-23 | 2025-05-01 | 68 | 1.1618 | 100% | 79 | 0 | 79 | 79 | 2025-03-30: 52; 2025-04-03: 2; 2025-04-04: 2; 2025-04-05: 2; 2025-04-06: 2; 2025-04-07: 2; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1; 2025-04-11: 1; 2025-04-12: 1; 2025-04-13: 1; 2025-04-15: 1; 2025-04-16: 1; 2025-04-19: 1; 2025-04-20: 1; 2025-04-21: 1; 2025-04-22: 1; 2025-04-23: 1; 2025-04-26: 1; 2025-04-27: 1; 2025-04-28: 1; 2025-04-29: 1
| 6 | ERT Test | 2025-04-02 | 2025-04-13 | 11 | 2025-04-06 | 2025-04-10 | Lot. | 36 | 2025-04-06 | 2025-04-10 | 5 | 7.2 | 100% | 36 | 0 | 36 | 36 | 2025-03-30: 0; 2025-04-03: 0; 2025-04-06: 4; 2025-04-07: 8; 2025-04-08: 8; 2025-04-09: 10; 2025-04-10: 6
| 7 | Test Pile Casting | 2025-04-12 | 2025-04-26 | 14 | 2025-05-29 | 2025-06-03 | Lot. | 240 |  |  |  | - | 100% | 240 | 0 | 240 | 108 | 2025-03-30: 0; 2025-04-03: 0; 2025-05-29: 34; 2025-05-30: 38; 2025-05-31: 36; 2025-06-01: 40; 2025-06-05: 40; 2025-06-06: 32; 2025-06-07: 20
| 8 | Pile Testing | 2025-05-24 | 2025-05-30 | 7 | 2025-06-16 | 2025-08-15 | Lot. | 240 |  |  |  | - | 26.25% | 63 | 177 | 63 | 0 | 2025-03-30: 0; 2025-04-03: 0; 2025-06-20: 3; 2025-06-21: 4; 2025-06-22: 4; 2025-06-23: 4; 2025-06-24: 0; 2025-06-25: 6; 2025-06-26: 2; 2025-06-27: 2; 2025-06-28: 0; 2025-06-29: 7; 2025-06-30: 4; 2025-07-01: 4; 2025-07-02: 3; 2025-07-03: 6; 2025-07-04: 0; 2025-07-05: 3; 2025-07-06: 0; 2025-07-07: 1; 2025-07-08: 1; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 2; 2025-07-14: 7
Array Yard Civil Works | 9 | Pile Marking | 2025-06-16 | 2025-11-10 | 147 | 2025-06-30 | 2025-11-10 | Table | 13322 |  |  |  | - | 0% | 0 | 13322 | 77 | 0 | 2025-07-13: 30; 2025-07-14: 47
| 10 | Pile -Drilling | 2025-07-10 | 2025-11-15 | 128 | 2025-07-10 | 2025-11-15 | Table | 13322 |  |  |  | - | 0% | 0 | 13322 | 0 | 0
| 11 | Pile- Casting | 2025-07-20 | 2025-11-25 | 128 | 2025-07-20 | 2025-11-25 | Table | 13322 |  |  |  | - | 0% | 0 | 13322 | 0 | 0
| 12 | Pile-Capping | 2025-07-25 | 2025-12-04 | 132 | 2025-07-25 | 2025-12-04 | Table | 13322 |  |  |  | - | 0% | 0 | 13322 | 0 | 0
ICR Civil Works | 13 | ICR Marking & Excavation | 2025-06-13 | 2025-09-23 | 102 | 2025-06-13 | 2025-09-23 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 14 | ICR PCC | 2025-07-02 | 2025-09-29 | 89 | 2025-07-02 | 2025-09-29 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 15 | ICR Footing Casting | 2025-07-09 | 2025-10-06 | 89 | 2025-07-09 | 2025-10-06 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 16 | ICR Column Casting | 2025-07-24 | 2025-10-21 | 89 | 2025-07-24 | 2025-10-21 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 17 | ICR Beam Slab Casting | 2025-08-14 | 2025-11-11 | 89 | 2025-08-14 | 2025-11-11 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 18 | Transformer Marking & Excavation | 2025-06-30 | 2025-09-25 | 87 | 2025-06-30 | 2025-09-25 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 19 | Transformer PCC | 2025-07-02 | 2025-09-27 | 87 | 2025-07-02 | 2025-09-27 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 20 | Transformer Footing Casting | 2025-07-09 | 2025-10-04 | 87 | 2025-07-09 | 2025-10-04 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 21 | Transformer Pedestal Casting | 2025-07-16 | 2025-10-11 | 87 | 2025-07-16 | 2025-10-11 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 22 | Transformer Support Foundation | 2025-07-23 | 2025-10-18 | 87 | 2025-07-23 | 2025-10-18 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 23 | Transformer Grade Slab | 2025-08-07 | 2025-11-02 | 87 | 2025-08-07 | 2025-11-02 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 24 | Transformer Fencing | 2025-10-12 | 2025-11-11 | 30 | 2025-10-12 | 2025-11-11 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
Allied Civil Works | 49 | Road-Marking & Excavation | 2025-07-20 | 2025-10-15 | 87 | 2025-07-20 | 2025-10-15 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 50 | Road-GSB Filling | 2025-07-25 | 2025-10-20 | 87 | 2025-07-25 | 2025-10-20 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 51 | Road-WBM Layer-1 | 2025-11-05 | 2025-12-10 | 35 | 2025-11-05 | 2025-12-10 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 52 | Road-WBM Layer-2 | 2025-11-20 | 2025-12-18 | 28 | 2025-11-20 | 2025-12-18 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 53 | Periphary Road-Marking and Grading | 2025-11-10 | 2025-12-15 | 35 | 2025-11-10 | 2025-12-15 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 54 | Periphary Road-Compaction | 2025-12-05 | 2025-12-17 | 12 | 2025-12-05 | 2025-12-17 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 55 | Chain Link Fencing- Marking & Drilling | 2025-04-25 | 2025-06-15 | 51 | 2025-06-11 | 2025-08-01 | Mtrs | 21000 |  |  |  | - | 0% | 0 | 21000 | 0 | 0
| 56 | Chain Link Fencing-Pole Casting | 2025-04-26 | 2025-06-16 | 51 | 2025-06-12 | 2025-08-02 | Mtrs | 21000 |  |  |  | - | 0% | 0 | 21000 | 0 | 0
| 57 | Chain Link Fincing- Mesh Fixing | 2025-05-20 | 2025-06-20 | 31 | 2025-06-25 | 2025-08-05 | Mtrs | 21000 |  |  |  | - | 0% | 0 | 21000 | 0 | 0
| 58 | Chain Link Fencing-Barbed Wire Fixing | 2025-05-25 | 2025-06-24 | 30 | 2025-06-30 | 2025-08-08 | Mtrs | 21000 |  |  |  | - | 0% | 0 | 21000 | 0 | 0
| 59 | Drain Excavation | 2025-08-05 | 2025-10-20 | 76 | 2025-08-05 | 2025-10-20 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 60 | Drain Works | 2025-08-16 | 2025-10-28 | 73 | 2025-08-16 | 2025-10-28 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 61 | Drain Finishing | 2025-09-05 | 2025-11-15 | 71 | 2025-09-05 | 2025-11-15 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
DC System Works | 66 | Excavation For DC/Earthing Trenches | 2025-08-10 | 2025-12-15 | 127 | 2025-08-10 | 2025-12-15 | SCB | 1360 |  |  |  | - | 0% | 0 | 1360 | 0 | 0
| 67 | DC Cable Laying | 2025-08-18 | 2025-12-25 | 129 | 2025-08-18 | 2025-12-25 | SCB | 1360 |  |  |  | - | 0% | 0 | 1360 | 0 | 0
| 68 | Module Mounting Structures | 2025-07-11 | 2025-12-19 | 161 | 2025-07-11 | 2025-12-19 | SCB | 1360 |  |  |  | - | 0% | 0 | 1360 | 0 | 0
| 69 | PV Modules | 2025-08-19 | 2026-01-21 | 155 | 2025-08-19 | 2026-01-21 | SCB | 1360 |  |  |  | - | 0% | 0 | 1360 | 0 | 0
| 70 | PVM Cables (Interconnection after module installation) | 2025-10-03 | 2026-01-28 | 117 | 2025-10-03 | 2026-01-28 | SCB | 1360 |  |  |  | - | 0% | 0 | 1360 | 0 | 0
| 71 | Solar cable laying (6 Sq.mm/ 4 Sqmm) | 2025-09-28 | 2026-01-29 | 123 | 2025-09-28 | 2026-01-29 | SCB | 1360 |  |  |  | - | 0% | 0 | 1360 | 0 | 0
| 72 | SCB - Mounting Structure | 2025-07-18 | 2025-12-20 | 155 | 2025-07-18 | 2025-12-20 | SCB | 1360 |  |  |  | - | 0% | 0 | 1360 | 0 | 0
| 73 | Array yard Earthing | 2025-07-21 | 2025-12-05 | 137 | 2025-07-21 | 2025-12-05 | SCB | 1360 |  |  |  | - | 0% | 0 | 1360 | 0 | 0
| 74 | Earth pit installation | 2025-09-04 | 2025-12-10 | 97 | 2025-09-04 | 2025-12-10 | SCB | 1360 |  |  |  | - | 0% | 0 | 1360 | 0 | 0
| 75 | SCB Installation | 2025-08-20 | 2025-12-26 | 128 | 2025-08-20 | 2025-12-26 | SCB | 1360 |  |  |  | - | 0% | 0 | 1360 | 0 | 0
ICR Electrical Works | 76 | Inverter Erection | 2025-09-12 | 2025-11-21 | 70 | 2025-09-12 | 2025-11-21 | Nos | 74 |  |  |  | - | 0% | 0 | 74 | 0 | 0
| 77 | ICOG/RMU Panel Erection | 2025-09-12 | 2025-11-21 | 70 | 2025-09-12 | 2025-11-21 | Nos | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 78 | Inverter Duty Trafo. Erection | 2025-09-19 | 2025-12-03 | 75 | 2025-09-19 | 2025-12-03 | Nos | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 79 | Aux Trafo Erection | 2025-09-19 | 2025-10-29 | 40 | 2025-09-19 | 2025-10-29 | Nos | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 80 | UPS & Battery Bank Erection | 2025-09-13 | 2025-10-13 | 30 | 2025-09-13 | 2025-10-13 | Nos | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 82 | Scada panel's Erection | 2025-09-12 | 2025-10-12 | 30 | 2025-09-12 | 2025-10-12 | Nos | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 83 | Tray Works | 2025-10-10 | 2025-11-30 | 51 | 2025-10-10 | 2025-11-30 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 84 | AC Cable-Inv to Trafo. | 2025-10-15 | 2025-12-05 | 51 | 2025-10-15 | 2025-12-05 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 85 | Control & Aux Cable Laying | 2025-10-01 | 2025-11-18 | 48 | 2025-10-01 | 2025-11-18 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 86 | Equipment Earthing | 2025-10-05 | 2025-12-30 | 86 | 2025-10-05 | 2025-12-30 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 87 | Grid Earthing | 2025-10-10 | 2025-12-30 | 81 | 2025-10-10 | 2025-12-30 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 88 | Earth pit installation | 2025-11-25 | 2026-01-05 | 41 | 2025-11-25 | 2026-01-05 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
MCR Electrical Works | 89 | HT Panel installation | 2025-10-20 | 2025-11-15 | 26 | 2025-10-20 | 2025-11-15 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 90 | Aux. trf installation | 2025-09-19 | 2025-10-29 | 40 | 2025-09-19 | 2025-10-29 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 91 | DB's installation | 2025-10-05 | 2025-11-10 | 36 | 2025-10-05 | 2025-11-10 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 92 | UPS, Battery charger, battery bank installaiton | 2025-12-05 | 2026-01-05 | 31 | 2025-12-05 | 2026-01-05 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 93 | FFS installation | 2026-01-02 | 2026-01-20 | 18 | 2026-01-02 | 2026-01-20 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 94 | HT cable laying from MCR to Power Trafo | 2025-12-25 | 2026-01-02 | 8 | 2025-12-25 | 2026-01-02 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 95 | HT cable laying from HT panel to Aux. trf | 2025-12-20 | 2025-12-28 | 8 | 2025-12-20 | 2025-12-28 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 96 | Aux t/f to LT | 2025-12-28 | 2026-01-05 | 8 | 2025-12-28 | 2026-01-05 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 97 | SCADA installation | 2025-12-25 | 2026-01-05 | 11 | 2025-12-25 | 2026-01-05 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 98 | Grid earthing | 2026-01-07 | 2026-01-09 | 2 | 2026-01-07 | 2026-01-09 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 99 | Tray Works | 2025-11-05 | 2025-12-05 | 30 | 2025-11-05 | 2025-12-05 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 100 | Earth pit installation | 2025-12-25 | 2026-01-06 | 12 | 2025-12-25 | 2026-01-06 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 101 | Equipment earthing | 2025-12-26 | 2026-01-07 | 12 | 2025-12-26 | 2026-01-07 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
AC System | 102 | HT Trench Marking & Excavation | 2025-09-24 | 2025-10-20 | 26 | 2025-09-24 | 2025-10-20 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 103 | HT Cable Laying | 2025-09-29 | 2025-11-20 | 52 | 2025-09-29 | 2025-11-20 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 104 | HT Trench Backfilling & Rote Marking | 2025-10-01 | 2025-11-22 | 52 | 2025-10-01 | 2025-11-22 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
Array Area Terminations | 105 | Solar Cable Termination Table Side | 2025-08-20 | 2026-01-25 | 158 | 2025-08-20 | 2026-01-25 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 106 | Solar Cable Termination SCB Side | 2025-08-20 | 2026-01-25 | 158 | 2025-08-20 | 2026-01-25 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 107 | DC Power Cable Termination SCB Side | 2025-08-20 | 2026-01-25 | 158 | 2025-08-20 | 2026-01-25 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
ICR Areay Terminations | 108 | DC Power Cable Termination Inverter Side | 2025-10-20 | 2026-01-25 | 97 | 2025-10-20 | 2026-01-25 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 109 | AC cable Termination Inv Side | 2025-11-10 | 2025-12-20 | 40 | 2025-11-10 | 2025-12-20 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 110 | AC cable Termination Trafo Side | 2025-11-10 | 2025-12-20 | 40 | 2025-11-10 | 2025-12-20 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 111 | HT Cable Termination Trafo Side | 2025-11-10 | 2025-12-20 | 40 | 2025-11-10 | 2025-12-20 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 112 | HT Cable Termination ICOG/RMU | 2025-11-10 | 2025-12-20 | 40 | 2025-11-10 | 2025-12-20 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 113 | Control and comm. cable termination | 2025-11-10 | 2025-12-20 | 40 | 2025-11-10 | 2025-12-20 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 114 | LT Cables termination | 2025-11-10 | 2025-12-20 | 40 | 2025-11-10 | 2025-12-20 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
MCR Area Termination | 115 | HT Cable termiantion- MCR Panel | 2025-12-27 | 2026-01-04 | 8 | 2025-12-27 | 2026-01-04 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 116 | MCR to Power Trafo HT cable termination | 2025-12-27 | 2026-01-04 | 8 | 2025-12-27 | 2026-01-04 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 117 | Aux. t/f LT side cable termiantion | 2025-12-27 | 2026-01-04 | 8 | 2025-12-27 | 2026-01-04 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 118 | Control and comm. cable termination | 2025-09-19 | 2025-12-18 | 90 | 2025-09-19 | 2025-12-18 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
| 119 | LT Cables termination | 2025-09-19 | 2025-12-20 | 92 | 2025-09-19 | 2025-12-20 | Lot | 1 |  |  |  | - | 0% | 0 | 1 | 0 | 0
Scada Works | 120 | FO Cable Laying | 2025-10-10 | 2025-12-15 | 66 | 2025-10-10 | 2025-12-15 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 121 | FO Cable Splicing | 2025-12-01 | 2025-12-20 | 19 | 2025-12-01 | 2025-12-20 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 122 | FFS installation | 2025-11-01 | 2025-12-05 | 34 | 2025-11-01 | 2025-12-05 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
Testing and Commissioning | 123 | Pre-commissioning of inverters | 2025-11-25 | 2025-12-25 | 30 | 2025-11-25 | 2025-12-25 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 124 | HT panel @ blocks | 2025-11-23 | 2025-12-17 | 24 | 2025-11-23 | 2025-12-17 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 125 | Transformers & Aux T/F @ blocks | 2025-11-27 | 2025-12-16 | 19 | 2025-11-27 | 2025-12-16 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 127 | T/F to ICOG cables IR & Hi-pot test | 2025-11-17 | 2025-11-23 | 6 | 2025-11-17 | 2025-11-23 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 128 | ICOG to VCB cables IR & Hi-pot test | 2025-11-24 | 2025-11-28 | 4 | 2025-11-24 | 2025-11-28 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 129 | VCB to MCR cables IR & Hi-pot test | 2025-11-24 | 2025-12-01 | 7 | 2025-11-24 | 2025-12-01 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 130 | ERT | 2025-11-27 | 2025-12-26 | 29 | 2025-11-27 | 2025-12-26 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 131 | FFS functionality check | 2025-12-06 | 2026-01-06 | 31 | 2025-12-06 | 2026-01-06 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 132 | CCTV commissioning | 2025-12-15 | 2025-12-13 | -2 | 2025-12-15 | 2025-12-13 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 133 | WMS commissioning | 2025-12-25 | 2026-01-10 | 16 | 2025-12-25 | 2026-01-10 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
External Works | 134 | Street Light Poles | 2025-09-14 | 2025-11-05 | 52 | 2025-09-14 | 2025-11-05 | nos. | 1173 |  |  |  | - | 0% | 0 | 1173 | 0 | 0
| 135 | Light Fixtures | 2025-10-05 | 2025-11-13 | 39 | 2025-10-05 | 2025-11-13 | nos. | 1173 |  |  |  | - | 0% | 0 | 1173 | 0 | 0
| 136 | External LDB | 2025-11-15 | 2025-12-05 | 20 | 2025-11-15 | 2025-12-05 | nos. | 1173 |  |  |  | - | 0% | 0 | 1173 | 0 | 0
| 137 | LT Cables | 2025-11-18 | 2025-12-10 | 22 | 2025-11-18 | 2025-12-10 | nos. | 1173 |  |  |  | - | 0% | 0 | 1173 | 0 | 0
| 138 | LT Termination | 2025-11-25 | 2025-11-20 | -5 | 2025-11-25 | 2025-11-20 | nos. | 1173 |  |  |  | - | 0% | 0 | 1173 | 0 | 0
| 139 | External earthing work completion | 2025-07-21 | 2025-12-30 | 162 | 2025-07-21 | 2025-12-30 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
Allied Works | 140 | Weather Monitoring System | 2025-09-26 | 2025-10-11 | 15 | 2025-09-26 | 2025-10-11 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 141 | Module Cleaning System( after Module installation | 2025-09-29 | 2026-01-07 | 100 | 2025-09-29 | 2026-01-07 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
| 143 | Allied work completion | 2025-10-10 | 2026-01-20 | 102 | 2025-10-10 | 2026-01-20 | Block | 26 |  |  |  | - | 0% | 0 | 26 | 0 | 0
Commissioning & Handing Over | 144 | Pre-Commissioining (DC & AC) | 2025-11-05 | 2026-01-10 | 66 | 2025-11-05 | 2026-01-10 | % | 100 |  |  |  | - | 0% | 0 | 100 | 0 | 0
| 145 | CEA Approval | 2025-12-20 | 2026-01-18 | 29 | 2025-12-20 | 2026-01-18 | % | 100 |  |  |  | - | 0% | 0 | 100 | 0 | 0
| 146 | Synchronization Approval | 2025-12-21 | 2026-01-09 | 19 | 2025-12-21 | 2026-01-09 | % | 100 |  |  |  | - | 0% | 0 | 100 | 0 | 0
| 147 | Commissioning | 2026-01-10 | 2026-01-25 | 15 | 2026-01-10 | 2026-01-25 | % | 100 |  |  |  | - | 0% | 0 | 100 | 0 | 0
| 148 | COD | 2026-01-26 | 2026-02-05 | 10 | 2026-01-26 | 2026-02-05 | % | 100 |  |  |  | - | 0% | 0 | 100 | 0 | 0

## MDL (hidden)
MDL SUMMARY - 300MW SECI PV | [13 empty] | 2025-07-15 | [5 empty] | 2025-07-15
Sl.No. | Discipline | Discipline | Document Title | Document Number | Approval Catogery | Planned Submission Date (EPCC) | Submitted/Expected Submission | Other drawing linked | Tentative approval date- linked docs. | Revision | Submission Date | Response date | CLIENT Comments / Approval(CAT-I,CAT-II CAT-III & CAT-IV) | No.of Days Reviwed by SECI | No.of Days Reviwed by ARIPL | Approved date | Submission/Review By | Approved Category | Status | Days taken for review/re-submission
1 | General | Survey & Studies | SoW & Method Statement for Topography and Contour Survey | SECI-RG300-PL-CIV-001 | Approval | 2025-02-10 | 2025-02-10 |  |  | R0 | 2025-02-10 | [5 empty] | Approved | CAT - III | Approved
[10 empty] | R1 | 2025-02-12 | 2025-02-12 |  | 0 | 2 | [5 empty] | Submitted - Under Review
[10 empty] | R2 | 2025-02-14 | 2025-02-17 |  | 3 | 2 | [5 empty] | Approved
[10 empty] | R3 | 2025-02-19 | [9 empty] | Re-Submission
2 | General | Survey & Studies | Topography and Contour Report | SECI-RG300-PL-CIV-002 | Information | 2025-03-24 | 2025-03-24 |  |  | R0 | 2025-03-24 | 2025-03-27 | CAT -IV R | 3 | 6 | 2025-04-08 | Approved | CAT -IV | Approved | 6 | Yet to be submitted
[10 empty] | R1 | 2025-04-02 | 2025-04-08 | CAT -IV | 6
3 | General | Survey & Studies | SoW & Method Statement for Geotechnical Investigation | SECI-RG300-PL-CIV-003 | Approval |  |  |  |  | R0 | [7 empty] | CAT - I | Approved
4 | General | Survey & Studies | Geotechnical Investigation Report (Soil Test, CBR, Chemical Analysis & Thermal Resistivity) | SECI-RG300-PL-CIV-004 | Information | 2025-04-21 | 2025-04-21 |  |  | R0 | 2025-04-21 | 2025-04-29 | CAT -IV R | 8 |  | 2025-04-29 | Approved | CAT -IV R | Approved
5 | General | Survey & Studies | SoW & Method Statement for Hydrology Investigation | SECI-RG300-PL-CIV-005 | Information | 2025-06-06 | 2025-06-12 | [9 empty] | SECI |  | Submitted - Under Review
6 | General | Survey & Studies | Hydrology Investigation Report | SECI-RG300-PL-CIV-006 | Information | 2025-06-06 | 2025-06-12
7 | General | Survey & Studies | SoW & Method Statement for Soil resistivity test (ERT) | SECI-RG300-PL-CIV-007 | Approval | 2025-03-26 | 2025-03-26 |  |  | R0 | 2025-03-26 | 2025-04-04 | CAT - II | 9 | 0 |  | SECI | CAT - II | Submitted - Under Review | 102
[10 empty] | R1 | 2025-04-04 |  |  | 102
8 | General | Survey & Studies | Soil resistivity test report (ERT) | SECI-RG300-PL-CIV-008 | Information | 2025-04-24 | 2025-04-24 |  |  | R0 | 2025-04-25 |  |  | 81 |  |  | SECI |  | Submitted - Under Review | 81
9 | General | Survey & Studies | Water Test Report | SECI-RG300-PL-CIV-009 | Information |  |  |  |  | R0 | [6 empty] | Approved | CAT - I | Approved
10 | General | Survey & Studies | Concrete Mix Design Report | SECI-RG300-PL-CIV-010 | Information | 2025-04-25 | 2025-04-25 |  |  | R0 | 2025-04-25 | 2025-05-01 | CAT -IV R | 6 |  |  | ARIPL | CAT -IV R | Re-Submission | 75
11 | General | Survey & Studies | Pile Pull out and Lateral Test Layout & Procedure | SECI-RG300-PL-CIV-011 | Approval | 2025-04-22 | 2025-04-22 |  |  | R0 | 2025-04-22 | 2025-04-24 | CAT - III | 2 | 6 | 2025-05-16 | SECI | CAT - I | Approved | 7
[10 empty] | R1 | 2025-04-30 | 2025-05-01 | CAT - II | 1 | 8
[10 empty] | R2 | 2025-05-09 | 2025-05-16 | CAT - I | 7
12 | General | Survey & Studies | Pile Pull out and Lateral Test Report | SECI-RG300-PL-CIV-012 | Information | 2025-05-24 | 2025-07-05
13 | General | Survey & Studies | SoP for Site Cleaning & Grading | SECI-RG300-PL-CIV-013 | Information
14 | General | Survey & Studies | Design Basis Study Report for Civil & Structural | SECI-RG300-PL-CIV-014 | Approval
1 | Civil | Civil & Structural (MMS) | MMS - Structural Design Calculations & Staad report (2PX26) | SECI-RG300-PL-CIV-101 | Approval | 2025-03-11 | 2025-03-11 |  |  | R0 | 2025-03-11 | 2025-03-20 | CAT - III | 9 | 19 |  | Approved | CAT - I | Approved | 48
[10 empty] | R1 | 2025-04-08 | 2025-04-11 | CAT - II | 3 | 47
[10 empty] | R2 | 2025-05-28 | 2025-06-02 | CAT - I | 5
2 | Civil | Civil & Structural (MMS) | MMS - Structural Design Calculations & Staad report (2PX14 & 2PX28) | SECI-RG300-PL-CIV-102 | Approval | 2025-05-28 | 2025-06-03 |  |  | R0 | 2025-06-03 | 2025-06-10 | CAT - III | 42 |  |  | ARIPL | CAT - III | Re-Submission | 42
3 | Civil | Civil & Structural (MMS) | MMS - Pile Foundation Design Calculation | SECI-RG300-PL-CIV-103 | Approval | 2025-05-18 | 2025-05-09 |  |  | R0 | 2025-05-09 |  |  | 67 |  |  | SECI |  | Submitted - Under Review | 67
4 | Civil | Civil & Structural (MMS) | MMS - Structure GA drawings(2PX26) | SECI-RG300-PL-CIV-104 | Approval | 2025-04-04 | 2025-03-11 |  |  | R0 | 2025-03-11 | 2025-03-20 | CAT - II | 9 | 19 | 2025-05-07 | ARIPL | CAT - II | Re-Submission | 1
[10 empty] | R1 | 2025-04-08 | 2025-04-11 | CAT - I | 3 | 25
[10 empty] | R2 | 2025-05-06 | 2025-05-07 | CAT - I | 1 | 21
[10 empty] | R3 | 2025-05-28 | 2025-05-30 | CAT - II | 2
5 | Civil | Civil & Structural (MMS) | MMS - Structure GA drawings(2PX14 & 2PX28) | SECI-RG300-PL-CIV-104A | Approval | 2025-06-03 | 2025-06-03 |  |  | R0 | 2025-06-03 | 2025-06-10 | CAT - III | 42 |  |  | ARIPL | CAT - III | Re-Submission | 42
6 | Civil | Civil & Structural (MMS) | MMS - Structure GA drawings(2PX13) | SECI-RG300-PL-CIV-105 | Approval | 2025-04-04 | 2025-03-11 |  |  | R0 | 2025-03-11 | 2025-03-20 | CAT - III | 9 | 19 | 2025-04-11 | ARIPL | CAT - I | Re-Submission
[10 empty] | R1 | 2025-04-08 | 2025-04-11 | CAT - I | 3
7 | Civil | Civil & Structural (MMS) | MMS - Structural Fabrication drawings(2PX28) | SECI-RG300-PL-CIV-106 | Information | 2025-04-22 | 2025-04-22 |  |  | R0 | 2025-04-22 | 2025-05-02 | CAT -IV | 10 | 3 | 2025-05-02 | ARIPL | CAT -IV | Re-Submission | 46
[10 empty] | R1 | 2025-05-05 | 2025-05-07 | CAT -IV | 2 | 21
[10 empty] | R2 | 2025-05-28 | 2025-05-30 | CAT -IV | 2
8 | Civil | Civil & Structural (MMS) | MMS - Structural Fabrication drawings(2PX14) & (2PX28) | SECI-RG300-PL-CIV-107 | Information | 2025-06-03 | 2025-06-03 |  |  | R0 | 2025-06-03 | 2025-06-10 | CAT -IV R | 42 |  |  | ARIPL | CAT -IV R | Re-Submission
9 | Civil | Civil & Structural (MMS) | MMS - Pile marking co-ordinates Layout | SECI-RG300-PL-CIV-108 | Information | 2025-06-16 | 2025-06-15
1 | Civil | Civil & Structural (MCR+AUX) | MCR - Architectural Drawings for Main Control Room (Plan, Section & Elevations and Finishing) | SECI-RG300-PL-CIV-201 | Approval | 2025-04-16 | 2025-04-16 |  |  | R0 | 2025-04-16 | 2025-05-07 | CAT - III | 21 | 7 |  | SECI | CAT - III | Submitted - Under Review
[10 empty] | R1 | 2025-05-14 |  |  | 62
2 | Civil | Civil & Structural (MCR+AUX) | MCR - Structural Calculations & Design Report for Building | SECI-RG300-PL-CIV-202 | Approval | 2025-07-30 | 2025-07-30 | MCR Architecture dwg.
3 | Civil | Civil & Structural (MCR+AUX) | MCR - Structural drawing of foundation, plinth beam & column | SECI-RG300-PL-CIV-203 | Approval | 2025-07-05 | 2025-07-05
4 | Civil | Civil & Structural (MCR+AUX) | MCR - Trench & Grade Slab Layout Drawings | SECI-RG300-PL-CIV-204 | Approval | 2025-06-30 | 2025-06-30
5 | Civil | Civil & Structural (MCR+AUX) | MCR - Structural drawing of Staircase, Roof Beams, Roof Slab & Lintel details | SECI-RG300-PL-CIV-205 | Approval | 2025-08-05 | 2025-08-05
6 | Civil | Civil & Structural (MCR+AUX) | MCR - Plumbing Drawings | SECI-RG300-PL-CIV-206 | Approval | 2025-09-05 | 2025-09-05
7 | Civil | Civil & Structural (MCR+AUX) | MCR - Septic Tank Drawings | SECI-RG300-PL-CIV-207 | Approval | 2025-09-08 | 2025-09-08
8 | Civil | Civil & Structural (MCR+AUX) | MCR - Aux Transformer Foundation Design Report | SECI-RG300-PL-CIV-208 | Approval | 2025-07-20 | 2025-07-20
9 | Civil | Civil & Structural (MCR+AUX) | MCR - Aux Transformer Foundation Drawings | SECI-RG300-PL-CIV-209 | Approval | 2025-07-30 | 2025-07-30
1 | Civil | Civil & Structural (Inverter Station) | Design document for Inverter Station | SECI-RG300-PL-CIV-301 | Approval | 2025-06-10 | 2025-06-17
2 | Civil | Civil & Structural (Inverter Station) | Inverter Platform - Architectural & Structural details ICOG) | SECI-RG300-PL-CIV-302 | Approval | 2025-06-15 | 2025-06-17
3 | Civil | Civil & Structural (Inverter Station) | Inverter Platform - Architectural & Structural details (RMU) | SECI-RG300-PL-CIV-303 | Approval | 2025-06-20 | 2025-06-17
4 | Civil | Civil & Structural (Inverter Station) | Inverter Duty Transformer Foundation design calculations | SECI-RG300-PL-CIV-304 | Approval | 2025-06-15 | 2025-06-12
5 | Civil | Civil & Structural (Inverter Station) | IDT Foundation GA and detail drawing | SECI-RG300-PL-CIV-305 | Approval | 2025-06-25 | 2025-06-12
6 | Civil | Civil & Structural (Inverter Station) | IDT - Burnt Oil Pit Design calculations & drawings. | SECI-RG300-PL-CIV-306 | Approval | 2025-07-02 | 2025-06-14
7 | Civil | Civil & Structural (Inverter Station) | ICR - NIFPS design calculations and detail drawing | SECI-RG300-PL-CIV-307 | Approval | 2025-06-28 | 2025-06-14
8 | Civil | Civil & Structural (Inverter Station) | ICR - Inverter to IDT Cable Support Strcuture GA Drawing | SECI-RG300-PL-CIV-308 | Approval | 2025-07-02 | 2025-07-14
9 | Civil | Civil & Structural (Inverter Station) | ICR - Yard Fencing & Gate Drawing | SECI-RG300-PL-CIV-309 | Approval | 2025-07-05 | 2025-06-13
1 | Civil | Civil & Structural (Infrastructure) | Layout - SCB Coordinates Layout | SECI-RG300-PL-CIV-401 | Information | 2025-06-20 | 2025-07-01
2 | Civil | Civil & Structural (Infrastructure) | Layout - ICR Coordinates Layout | SECI-RG300-PL-CIV-402 | Information | 2025-06-25 | 2025-07-01
3 | Civil | Civil & Structural (Infrastructure) | Layout - Boundary Fence Marking Layout | SECI-RG300-PL-CIV-403 | Information | 2025-03-22 | 2025-05-22 |  |  | R0 | 2025-05-22 | 2025-05-23 | CAT -IV R | 1 | 15 |  | SECI | CAT -IV R | Submitted - Under Review | 53
[10 empty] | R1 | 2025-06-07 |  |  | 38
4 | Civil | Civil & Structural (Infrastructure) | Boundary Chain Link Fence Drawing | SECI-RG300-PL-CIV-404 | Approval | 2025-03-03 | 2025-03-03 |  |  | R0 | 2025-03-03 | 2025-03-05 | CAT - III | 2 | 15 | 2025-05-23 | Approved | CAT - I | Approved | 1
[10 empty] | R1 | 2025-03-20 | 2025-03-22 | CAT - I | 2 | 61
[10 empty] | R2 | 2025-05-22 | 2025-05-23 | CAT - I | 1
5 | Civil | Civil & Structural (Infrastructure) | Plant Main Gate drawing | SECI-RG300-PL-CIV-405 | Approval | 2025-07-15 | 2025-06-17
6 | Civil | Civil & Structural (Infrastructure) | Road Calculations, Cross sections & Layout drawing | SECI-RG300-PL-CIV-406 | Approval | 2025-05-18 | 2025-07-10
7 | Civil | Civil & Structural (Infrastructure) | Watch Tower Design Calculations | SECI-RG300-PL-CIV-407 | Approval | 2025-07-20 | 2025-07-10
8 | Civil | Civil & Structural (Infrastructure) | Watch Tower Structural Drawing | SECI-RG300-PL-CIV-408 | Approval | 2025-07-25 | 2025-07-15
9 | Civil | Civil & Structural (Infrastructure) | Security Office - Design calculations | SECI-RG300-PL-CIV-409 | Approval | 2025-08-05 | 2025-07-15
10 | Civil | Civil & Structural (Infrastructure) | Security Office - Architectural & Structural drawings | SECI-RG300-PL-CIV-410 | Approval | 2025-08-08 | 2025-07-15
11 | Civil | Civil & Structural (Infrastructure) | Security Cabin - GA & Foundation drawing | SECI-RG300-PL-CIV-411 | Approval | 2025-08-12 | 2025-07-22
12 | Civil | Civil & Structural (Infrastructure) | Store Room - Design calculations | SECI-RG300-PL-CIV-412 | Approval | 2025-07-05 | 2025-07-22
13 | Civil | Civil & Structural (Infrastructure) | Store Room - Structural & Foundation Drawings | SECI-RG300-PL-CIV-413 | Approval | 2025-07-10 | 2025-07-26
14 | Civil | Civil & Structural (Infrastructure) | MCS - Underground water storage design calculation & Drawing | SECI-RG300-PL-CIV-414 | Approval | 2025-06-25 | 2025-08-01
15 | Civil | Civil & Structural (Infrastructure) | MCS - Tank, Piping Network Layout & Pump Sizing Calculations | SECI-RG300-PL-CIV-415 | Approval | 2025-06-30 | 2025-07-30
16 | Civil | Civil & Structural (Infrastructure) | Storm water Drainage - Design Calculations | SECI-RG300-PL-CIV-416 | Approval | 2025-07-05 | 2025-07-30
17 | Civil | Civil & Structural (Infrastructure) | Storm water Drainage - Drawing & cross sections | SECI-RG300-PL-CIV-417 | Approval | 2025-07-08 | 2025-08-01
18 | Civil | Civil & Structural (Infrastructure) | Bore well - Water Yield report & locations layout | SECI-RG300-PL-CIV-418 | Information | 2025-07-10 | 2025-06-14
19 | Civil | Civil & Structural (Infrastructure) | Bore well - Water test report | SECI-RG300-PL-CIV-419 | Information | 2025-07-15 | 2025-08-07
20 | Civil | Civil & Structural (Infrastructure) | Street Lighting Pole GA & Foundation Details | SECI-RG300-PL-CIV-420 | Approval | 2025-07-15 | 2025-08-07
21 | Civil | Civil & Structural (Infrastructure) | Street Lighting Pole Design Calculations | SECI-RG300-PL-CIV-421 | Information | 2025-07-20 | 2025-08-13
22 | Civil | Civil & Structural (Infrastructure) | Lightning Arrestor GA & Foundation Drawing | SECI-RG300-PL-CIV-422 | Approval | 2025-06-18 | 2025-08-13
23 | Civil | Civil & Structural (Infrastructure) | Lightning Arrestor Design Calculations | SECI-RG300-PL-CIV-423 | Information | 2025-06-25 | 2025-08-18
24 | Civil | Civil & Structural (Infrastructure) | Weather Monitoring System GA & Foundation Drawing | SECI-RG300-PL-CIV-424 | Approval | 2025-07-25 | 2025-08-18
25 | Civil | Civil & Structural (Infrastructure) | SCB - Support Structure GA Drawing | SECI-RG300-PL-CIV-425 | Approval | 2025-06-20 | 2025-08-18
26 | Civil | Civil & Structural (Infrastructure) | SCB - Support Structure Design Calculation | SECI-RG300-PL-CIV-426 | Information | 2025-06-25 | 2025-08-01
27 | Civil | Civil & Structural (Infrastructure) | Wet Cleaning System - GTP, Drawings, philosophy, calculation | SECI-RG300-PL-CIV-427 | Approval | 2025-06-28 | 2025-08-20
28 | Civil | Civil & Structural (Infrastructure) | SVG - Design calculations | SECI-RG300-PL-CIV-428 | Approval | 2025-07-20 | 2025-08-20
29 | Civil | Civil & Structural (Infrastructure) | SVG - Structural Drawings | SECI-RG300-PL-CIV-429 | Approval | 2025-07-25 | 2025-07-25
| Electrical | Electrical (SLD & Layouts) | AC SINGLE LINE DIAGRAM | SECI-RG300-PL-ELE-001 | Approval | 2025-03-03 | 2025-02-26 |  |  | R0 | 2025-02-26 | 2025-03-05 | CAT - III | 7 | 33 |  | SECI | CAT - II | Approved
3 | [9 empty] | R1 | 2025-04-07 | 2025-04-16 | CAT - III | 9 | 4
4 | [9 empty] | R2 | 2025-04-20 | 2025-04-23 | CAT - II | 3 | 1
[10 empty] | R3 | 2025-04-24 |  |  | 82
5 | Electrical | Electrical (SLD & Layouts) | DC SINGLE LINE DIAGRAM | SECI-RG300-PL-ELE-002 | Approval | 2025-04-08 | 2025-04-25 |  |  | R0 | 2025-04-25 | 2025-05-13 | CAT - III | 18 | 3 |  | SECI | CAT - III | Submitted - Under Review | 60
6 | [9 empty] | R1 | 2025-05-16 |  |  | 60
7 | Electrical | Electrical (SLD & Layouts) | AUXILIARY SINGLE LINE DIAGRAM | SECI-RG300-PL-ELE-003 | Approval | 2025-04-15 | 2025-05-13 |  |  | R0 | 2025-05-13 |  |  | 63 |  |  | SECI |  | Submitted - Under Review | 63
8 | Electrical | Electrical (SLD & Layouts) | Layouts - Overall Array Layout | SECI-RG300-PL-ELE-004 | Approval | 2025-05-03 | 2025-04-11 |  | 2025-06-13 | R0 | 2025-04-11 | 2025-04-19 | CAT - III | 8 | 27 |  | ARIPL | CAT - III | Re-Submission | 45
9 | [9 empty] | R1 | 2025-05-16 | 2025-05-31 | CAT - III | 60
10 | Electrical | Electrical (SLD & Layouts) | Layouts -DC Cable routing layout & sections | SECI-RG300-PL-ELE-005 | Approval | 2025-06-27 | 2025-06-27 | Overall layout | 2025-06-13
11 | Electrical | Electrical (SLD & Layouts) | Layouts -AC Cable routing layout & sections | SECI-RG300-PL-ELE-006 | Approval | 2025-06-27 | 2025-06-27 | Overall layout | 2025-06-13
12 | Electrical | Electrical (SLD & Layouts) | Layouts - AC Earthing Layout | SECI-RG300-PL-ELE-007 | Approval | 2025-06-27 | 2025-06-27 | Overall layout | 2025-06-13
13 | Electrical | Electrical (SLD & Layouts) | Layouts -DC Earthing Layout | SECI-RG300-PL-ELE-008 | Approval | 2025-06-27 | 2025-06-27 | Overall layout | 2025-06-13
14 | Electrical | Electrical (SLD & Layouts) | Layouts - ICR Equipment Layout | SECI-RG300-PL-ELE-009 | Approval | 2025-04-21 | 2025-05-27 |  | 2025-05-27 | R0 | 2025-05-27 | 2025-06-04 | CAT - III | 8 | 41 |  | ARIPL | CAT - III | Re-Submission | 49
15 | Electrical | Electrical (SLD & Layouts) | Layouts - Plant Lightning Protection System Layout | SECI-RG300-PL-ELE-010 | Approval | 2025-05-23 | 2025-05-23 |  |  | R0 | 2025-05-23 |  |  | 53 |  |  | SECI |  | Submitted - Under Review | 53
16 | Electrical | Electrical (SLD & Layouts) | Layouts - Earthing & Lightning Protection Layout for ICR | SECI-RG300-PL-ELE-011 | Approval | 2025-06-18 | 2025-06-18 | ICR Equipment layout/ AC Earthing calculation | 2025-06-06
17 | Electrical | Electrical (SLD & Layouts) | Layouts - Plant Illuminatoin layout | SECI-RG300-PL-ELE-012 | Approval | 2025-06-18 | 2025-06-18 | ICR Equipment layout | 2025-06-06
18 | Electrical | Electrical (SLD & Layouts) | Layouts - Fire Fighting Layout for ICR & MCR | SECI-RG300-PL-ELE-013 | Approval | 2025-06-18 | 2025-06-18 | ICR Equipment layout | 2025-06-06
19 | Electrical | Electrical (SLD & Layouts) | Layouts - Equipment Layout for MCR | SECI-RG300-PL-ELE-014 | Approval | 2025-05-17 | 2025-06-17
20 | Electrical | Electrical (SLD & Layouts) | Layouts - Cable Trench Layout for MCR | SECI-RG300-PL-ELE-015 | Approval | 2025-06-13 | 2025-06-13
21 | Electrical | Electrical (SLD & Layouts) | SCADA - Weather Monitoring System (WMS) Mounting GA & Layout | SECI-RG300-PL-ELE-016 | Approval | 2025-06-27 | 2025-06-27 | GA GTP- SCADA | 2025-06-20
22 | Electrical | Electrical (SLD & Layouts) | SCADA - Communication Cable Routing Layout | SECI-RG300-PL-ELE-017 | Information | 2025-07-04 | 2025-07-04 | GA GTP- SCADA | 2025-06-20
23 | Electrical | Electrical (SLD & Layouts) | CCTV - Overall Plant CCTV Layout | SECI-RG300-PL-ELE-018 | Approval | 2025-07-15 | 2025-07-15 |  | 2025-06-27
24 | Electrical | Electrical (SLD & Layouts) | SCADA - System Architecture Schematics | SECI-RG300-PL-ELE-019 | Approval | 2025-06-30 | 2025-06-30 |  | 2025-06-30
25 | Electrical | Electrical (SLD & Layouts) | SVG - General Arragement Layout | SECI-RG300-PL-ELE-020 | Approval | 2025-07-12 | 2025-07-12 |  | 2025-07-12
1 | Electrical | Electrical (SLD & Layouts) | SVG Cable routing and trench details | SECI-RG300-PL-ELE-021 | Approval | 2025-07-14 | 2025-07-14 |  | 2025-07-14
2 | Electrical | Electrical (SLD & Layouts) | Harmonic filter GA layout | SECI-RG300-PL-ELE-022 | Approval | 2025-07-25 | 2025-07-25 |  | 2025-07-15
3 | Electrical | Electrical (SLD & Layouts) | Harmonic Cable routing and trench details | SECI-RG300-PL-ELE-023 | Approval | 2025-07-16 | 2025-07-16 |  | 2025-07-16
4 | Electrical | Electrical (SLD & Layouts) | Earthing Layout for SVG and Harmonic filter | SECI-RG300-PL-ELE-024 | Approval | 2025-07-22 | 2025-07-22 |  | 2025-07-22
| Electrical | Electrical (SLD & Layouts) | Illumination Layout for SVG and harmonic Filter | SECI-RG300-PL-ELE-025 | Approval | 2025-07-28 | 2025-07-28 |  | 2025-07-28
5 | Electrical | Electrical (Calculations) | Report - Energy Yield Assessment Report (PV Syst Report) | SECI-RG300-PL-ELE-101 | Approval | 2025-02-26 | 2025-02-26 |  |  | R0 | 2025-02-26 |  |  | 139 |  |  | SECI |  | Submitted - Under Review | 139
6 | Electrical | Electrical (Calculations) | Report - Shadow Analysis Report | SECI-RG300-PL-ELE-102 | Approval | 2025-08-08 | 2025-08-08 |  | 2025-08-08
7 | Electrical | Electrical (Calculations) | Grid Study Report in PSSE & PSCAD software | SECI-RG300-PL-ELE-103 | Approval | 2025-11-26 | 2025-11-26 |  | 2025-11-26
8 | Electrical | Electrical (Calculations) | Calc - DC Cable Sizing Calculations | SECI-RG300-PL-ELE-104 | Approval | 2025-04-07 | 2025-04-26 |  |  | R0 | 2025-04-26 | 2025-04-30 | CAT - III | 4 | 14 |  | SECI | CAT - I | Approved | 21
9 | [9 empty] | R1 | 2025-05-14 | 2025-06-04 | CAT - I | 21
10 | Electrical | Electrical (Calculations) | Calc - AC Cable Sizing Calculations | SECI-RG300-PL-ELE-105 | Approval | 2025-04-07 | 2025-05-14 |  |  | R0 | 2025-05-14 | 2025-06-01 | CAT - III | 18 | 3 |  | ARIPL | CAT - III | Re-Submission | 62
[10 empty] | R1 | 2025-06-04 |  |  | 41
11 | Electrical | Electrical (Calculations) | Calc - DC Cable schedule and losses calculation | SECI-RG300-PL-ELE-106 | Approval | 2025-06-03 | 2025-06-20 |  | 2025-06-20
12 | Electrical | Electrical (Calculations) | Calc - AC Cable schedule and losses calculation | SECI-RG300-PL-ELE-107 | Approval | 2025-05-31 | 2025-06-20 |  | 2025-06-20
| Electrical | Electrical (Calculations) | Calc - Auxilary Cable Sizing & Schedules | SECI-RG300-PL-ELE-108 | Approval | 2025-06-23 | 2025-06-23 |  | 2025-06-23
13 | Electrical | Electrical (Calculations) | LT power & Control Cable Schedules and Termination details | SECI-RG300-PL-ELE-109 | Information | 2025-06-21 | 2025-06-21 |  | 2025-06-21
| Electrical | Electrical (Calculations) | Calc - DC Earthing Calculation | SECI-RG300-PL-ELE-110 | Approval | 2025-05-06 | 2025-05-15 |  |  | R0 | 2025-05-15 | 2025-06-05 | CAT - III | 61 |  | 2025-06-05 | SECI | CAT - III | Submitted - Under Review | 61
[10 empty] | R1 | 2025-06-05
14 | Electrical | Electrical (Calculations) | Calc - AC Earthing Calculation | SECI-RG300-PL-ELE-111 | Approval | 2025-05-06 | 2025-05-14 |  |  | R0 | 2025-05-14 |  |  | 62 |  |  | SECI |  | Submitted - Under Review | 62
15 | Electrical | Electrical (Calculations) | Calc - Auxilary Transformer Sizing Calculation | SECI-RG300-PL-ELE-112 | Approval | 2025-04-08 | 2025-04-08 |  |  | R0 | 2025-04-08 | 2025-04-23 | CAT - III | 15 | 18 |  | ARIPL | CAT - III | Re-Submission | 65
1 | [9 empty] | R1 | 2025-05-11 | 2025-06-01 | CAT - III | 21 | 44
2 | Electrical | Electrical (Calculations) | Calc - UPS Sizing Calculation | SECI-RG300-PL-ELE-113 | Approval | 2025-04-08 | 2025-04-08 |  |  | R0 | 2025-04-08 | 2025-04-23 | CAT - III | 15 | 17 |  | ARIPL | CAT - III | Re-Submission | 66
3 | [9 empty] | R1 | 2025-05-10 | 2025-06-01 | CAT - III | 22 | 44
4 | Electrical | Electrical (Calculations) | SCADA - IO List for SCADA System | SECI-RG300-PL-ELE-114 | Information | 2025-05-30 | 2025-06-13 |  | 2025-05-30
5 | Electrical | Electrical (Calculations) | SCADA - Communication Cable Schedules & Termination | SECI-RG300-PL-ELE-115 | Information | 2025-07-07 | 2025-07-07 |  | 2025-07-07
6 | Vendor Documents | Electrical GTP and Type Test reports | Inverter Duty Transformer-GTP, GA & Type test reports | SECI-RG300-PL-ELE-201 | Approval | 2025-05-26 | 2025-05-27 |  |  | R0 | 2025-05-27 |  |  | 49 |  |  | SECI |  | Submitted - Under Review | 49
|  | Electrical GTP and Type Test reports | Inverter Duty Transformer-GTP, GA & Type test reports (T&R) | SECI-RG300-PL-ELE-201A | Approval | 2025-06-09 | 2025-06-05 |  |  | R0 | 2025-06-05
7 | Vendor Documents | Electrical GTP and Type Test reports | NIFPS-GTP, GA & Type test reports | SECI-RG300-PL-ELE-202 | Approval | 2025-06-08 | 2025-06-26 | Ordering
8 | Vendor Documents | Electrical GTP and Type Test reports | ICOG/RMU PANEL-GTP, GA & Type test reports | SECI-RG300-PL-ELE-203 | Approval | 2025-05-28 | 2025-06-09 | Ordering |  | R0 | 2025-06-09 | [5 empty] | SECI |  | Submitted - Under Review
9 | Vendor Documents | Electrical GTP and Type Test reports | Main HT Swtichgear Panel-GTP, GA & Type test reports | SECI-RG300-PL-ELE-204 | Approval | 2025-05-28 | 2025-06-09 | Ordering |  | R0 | 2025-06-09 | [5 empty] | SECI |  | Submitted - Under Review
10 | Vendor Documents | Electrical GTP and Type Test reports | Auxiliary LT Panel -GTP, GA & Type test reports | SECI-RG300-PL-ELE-205 | Approval | 2025-06-12 | 2025-06-18 | Ordering
11 | Vendor Documents | Electrical GTP and Type Test reports | Auxiliary Transformer-GTP, GA & Type test reports | SECI-RG300-PL-ELE-206 | Approval | 2025-06-06 | 2025-06-18 | Ordering
12 | Vendor Documents | Electrical GTP and Type Test reports | ESE Lightning Arrestor -GTP, GA & Type test reports | SECI-RG300-PL-ELE-207 | Approval | 2025-06-26 | 2025-06-26 | Ordering
13 | Vendor Documents | Electrical GTP and Type Test reports | Lighting Fixtures with calculations-GTP, GA & Type test reports | SECI-RG300-PL-ELE-208 | Approval | 2025-07-10 | 2025-07-10 | Ordering
14 | Vendor Documents | Electrical GTP and Type Test reports | String Combiner Box (SCB) -GTP, GA & Type test reports | SECI-RG300-PL-ELE-209 | Approval | 2025-05-11 | 2025-06-16 | Ordering | 2025-06-06
15 | Vendor Documents | Electrical GTP and Type Test reports | DC string cable -GTP, GA & Type test reports | SECI-RG300-PL-ELE-210 | Approval | 2025-06-18 | 2025-06-18 | Ordering
16 | Vendor Documents | Electrical GTP and Type Test reports | DC power cable -GTP, GA & Type test reports | SECI-RG300-PL-ELE-211 | Approval | 2025-06-18 | 2025-06-18 | Ordering
17 | Vendor Documents | Electrical GTP and Type Test reports | LT AC power cable -GTP, GA & Type test reports | SECI-RG300-PL-ELE-212 | Approval | 2025-06-18 | 2025-06-18 | Ordering
18 | Vendor Documents | Electrical GTP and Type Test reports | HT AC power cable -GTP, GA & Type test reports | SECI-RG300-PL-ELE-213 | Approval | 2025-06-25 | 2025-06-25 | Ordering
19 | Vendor Documents | Electrical GTP and Type Test reports | MC4 connectors -GTP, GA & Type test reports | SECI-RG300-PL-ELE-214 | Information | 2025-07-09 | 2025-07-09 | Ordering
20 | Vendor Documents | Electrical GTP and Type Test reports | LT power and control cables -GTP, GA & Type test reports | SECI-RG300-PL-ELE-215 | Information | 2025-08-01 | 2025-08-01 | Ordering
21 | Vendor Documents | Electrical GTP and Type Test reports | Communication cables -GTP, GA & Type test reports | SECI-RG300-PL-ELE-216 | Approval | 2025-08-01 | 2025-08-01 | Ordering
22 | Vendor Documents | Electrical GTP and Type Test reports | Earthing Strip & acessories -GTP, GA & Type test reports | SECI-RG300-PL-ELE-217 | Information | 2025-07-07 | 2025-07-07 | Ordering
23 | Vendor Documents | Electrical GTP and Type Test reports | Earth Pit -GTP, GA & Type test reports | SECI-RG300-PL-ELE-218 | Approval | 2025-07-07 | 2025-07-07 | Ordering
24 | Vendor Documents | Electrical GTP and Type Test reports | MV Cable Termination Kit & Jointing Kit -GTP, GA & Type test reports | SECI-RG300-PL-ELE-219 | Information | 2025-07-27 | 2025-07-27 | Ordering
25 | Vendor Documents | Electrical GTP and Type Test reports | Battery & Battery Charger-GTP, GA & Type test reports | SECI-RG300-PL-ELE-220 | Approval | 2025-07-05 | 2025-07-05 | Ordering
26 | Vendor Documents | Electrical GTP and Type Test reports | HDPE Conduit (DWC)-GTP, GA & Type test reports | SECI-RG300-PL-ELE-221 | Information | 2025-07-02 | 2025-07-02 | Ordering
27 | Vendor Documents | Electrical GTP and Type Test reports | UPS-GTP, GA & Type test reports | SECI-RG300-PL-ELE-222 | Approval | 2025-06-14 | 2025-06-14 | Ordering
28 | Vendor Documents | Electrical GTP and Type Test reports | Cable Trays & Accessories - Drawings | SECI-RG300-PL-ELE-223 | Information | 2025-07-02 | 2025-07-02 | Ordering
29 | Vendor Documents | Electrical GTP and Type Test reports | Lugs, Trefoils and Glands - Drawings, Details, Catalogue | SECI-RG300-PL-ELE-224 | Information | 2025-07-09 | 2025-07-09 | Ordering
30 | Vendor Documents | Electrical GTP and Type Test reports | Safety Items (Rubber Mat, Hand Gloves, First Aid Box, Safety chart, Fire fighting equipment, Danger Board ETC) - Datasheet, GA Drawing, TTR of Insulating Mats | SECI-RG300-PL-ELE-226 | Information | 2025-08-31 | 2025-08-31 | Ordering
31 | Vendor Documents | Electrical GTP and Type Test reports | SCADA Panel&PPC Schematics,GA and datasheets | SECI-RG300-PL-ELE-228 | Approval | 2025-06-05 | 2025-06-05 | Ordering
32 | Vendor Documents | Electrical GTP and Type Test reports | Weather Station - GTP & Drawings | SECI-RG300-PL-ELE-229 | Approval | 2025-07-20 | 2025-07-20 | Ordering
33 | Vendor Documents | Electrical GTP and Type Test reports | CCTV - GTP & Drawings | SECI-RG300-PL-ELE-230 | Approval | 2025-06-26 | 2025-06-26 | Ordering
1 | Vendor Documents | Electrical GTP and Type Test reports | Fire Alarm System & Equipments - GTP & Drawings | SECI-RG300-PL-ELE-231 | Approval | 2025-07-02 | 2025-07-02 | Ordering
2 | Vendor Documents | Electrical GTP and Type Test reports | SCADA SCREENS AND REPORT FORMAT | SECI-RG300-PL-ELE-232 | Approval | 2025-11-01 | 2025-11-01 | Ordering
3 | Vendor Documents | Electrical GTP and Type Test reports | SVG- -GTP, GA & Type test reports | SECI-RG300-PL-ELE-233 | Approval | 2025-06-18 | 2025-06-18 | Ordering
4 | Vendor Documents | Electrical GTP and Type Test reports | Harmonic Filter and its Acessires | SECI-RG300-PL-ELE-234 | Approval | 2025-07-30 | 2025-07-30 | Ordering
5 | Vendor Documents | Electrical GTP and Type Test reports | Central Inverter(PCU) -GTP, GA & Type test reports | SECI-RG300-PL-ELE-235 | Approval | 2025-05-20 | 2025-05-13 | Ordering |  | R0 | 2025-05-13 | 2025-06-04 | CAT - III | 22 | 41 |  | SECI | CAT - III | Submitted - Under Review | 63
6 | Vendor Documents | MQP | Inverter Duty Transformer-MQP | SECI-RG300-PL-MQP-001 | Approval | 2025-06-06 | 2025-05-27 | Ordering |  | R0 | 2025-05-27 |  |  | 49 |  |  | SECI |  | Submitted - Under Review | 49
7 | Vendor Documents | MQP | NIFPS-MQP | SECI-RG300-PL-MQP-002 | Information | 2025-06-26 | 2025-06-26 | Ordering
8 | Vendor Documents | MQP | ICOG/RMU PANEL-MQP | SECI-RG300-PL-MQP-003 | Approval | 2025-06-06 | 2025-06-09 | Ordering |  | R0 | 2025-06-09 | [5 empty] | SECI |  | Submitted - Under Review
9 | Vendor Documents | MQP | Main HT Swtichgear Panel-MQP | SECI-RG300-PL-MQP-004 | Approval | 2025-06-06 | 2025-06-09 | Ordering |  | R0 | 2025-06-09 | [5 empty] | SECI |  | Submitted - Under Review
10 | Vendor Documents | MQP | Auxiliary Panel -MQP | SECI-RG300-PL-MQP-005 | Approval | 2025-06-18 | 2025-06-18 | Ordering
11 | Vendor Documents | MQP | ESE Lightning Arrestor -MQP | SECI-RG300-PL-MQP-006 | Information | 2025-06-26 | 2025-06-26 | Ordering
12 | Vendor Documents | MQP | Lighting Fixtures --MQP | SECI-RG300-PL-MQP-007 | Information | 2025-07-10 | 2025-07-10 | Ordering
13 | Vendor Documents | MQP | String Combiner Box (SCB) -MQP | SECI-RG300-PL-MQP-008 | Approval | 2025-06-16 | 2025-06-16 | Ordering
14 | Vendor Documents | MQP | DC string cable -MQP | SECI-RG300-PL-MQP-009 | Approval | 2025-06-18 | 2025-06-18 | Ordering
15 | Vendor Documents | MQP | DC power cable -MQP | SECI-RG300-PL-MQP-010 | Approval | 2025-06-18 | 2025-06-18 | Ordering
16 | Vendor Documents | MQP | LT AC power cable -MQP | SECI-RG300-PL-MQP-011 | Approval | 2025-06-18 | 2025-06-18 | Ordering
17 | Vendor Documents | MQP | HT AC power cable -MQP | SECI-RG300-PL-MQP-012 | Approval | 2025-06-25 | 2025-06-25 | Ordering
18 | Vendor Documents | MQP | LT power and control cables -MQP | SECI-RG300-PL-MQP-013 | Information | 2025-08-01 | 2025-08-01 | Ordering
19 | Vendor Documents | MQP | Earthing Strip -MQP | SECI-RG300-PL-MQP-014 | Information | 2025-07-07 | 2025-07-07 | Ordering
20 | Vendor Documents | MQP | Earth Pit -MQP | SECI-RG300-PL-MQP-015 | Information | 2025-07-07 | 2025-07-07 | Ordering
21 | Vendor Documents | MQP | MV Cable Termination Kit & Jointing Kit -MQP | SECI-RG300-PL-MQP-016 | Information | 2025-07-27 | 2025-07-27 | Ordering
22 | Vendor Documents | MQP | Battery & Battery Charger-MQP | SECI-RG300-PL-MQP-017 | Approval | 2025-07-05 | 2025-07-05 | Ordering
23 | Vendor Documents | MQP | UPS-MQP | SECI-RG300-PL-MQP-018 | Approval | 2025-06-14 | 2025-06-14 | Ordering
24 | Vendor Documents | MQP | Cable Trays & Accessories - MQP | SECI-RG300-PL-MQP-019 | Information | 2025-07-02 | 2025-07-02 | Ordering
25 | Vendor Documents | MQP | Communication Cable-MQP | SECI-RG300-PL-MQP-020 | Approval | 2025-08-01 | 2025-08-01 | Ordering
26 | Vendor Documents | MQP | SCADA Panel&PPC MQP | SECI-RG300-PL-MQP-021 | Approval | 2025-06-05 | 2025-06-15 | Ordering
| Vendor Documents | MQP | Weather Station - MQP | SECI-RG300-PL-MQP-022 | Information | 2025-07-20 | 2025-07-20 | Ordering
27 | Vendor Documents | MQP | CCTV - MQP | SECI-RG300-PL-MQP-023 | Information | 2025-06-26 | 2025-06-26 | Ordering
28 | Vendor Documents | MQP | Fire Alarm System & Equipments - MQP | SECI-RG300-PL-MQP-024 | Information | 2025-07-02 | 2025-07-02 | Ordering
29 | Vendor Documents | MQP | SVG- -MQP | SECI-RG300-PL-MQP-025 | Approval | 2025-06-18 | 2025-06-18 | Ordering
| Vendor Documents | MQP | Central Inverter(PCU) -MQP | SECI-RG300-PL-MQP-026 | Approval | 2025-05-16 | 2025-05-16 | Ordering |  | R0 | 2025-05-16 | 2025-05-30 |  | 14 | 46 |  | ARIPL |  | Re-Submission | 46
R1
| Vendor Documents | MQP | Harmonic Filter - MQP | SECI-RG300-PL-MQP-027 | Approval | 2025-07-30 | 2025-07-30 | Ordering
| Vendor Documents | MQP | Auxiliary Transformer - MQP | SECI-RG300-PL-MQP-028 | Approval | 2025-06-18 | 2025-06-18 | Ordering
| Vendor Documents | MQP | Module Mounting Structure - MQP | SECI-RG300-PL-MQP-028 | Approval | 2025-05-26 | 2025-05-26 | Ordering |  | R0 | 2025-05-26 | 2025-06-02 |  | 7 | 43 |  | ARIPL |  | Re-Submission
R1
Formulas:
Approved date = [Response date, row below]
Approved date = [Response date]
Submitted/Expected Submission = [Submission Date]
Submitted/Expected Submission = [Planned Submission Date (EPCC)]
Planned Submission Date (EPCC) = [2]Sheet4!E41

## Engineering & Delivery (hidden)
# | Engineering-Key Equipment | Planned | Actual/ Expected | Status
1 | Module Mounting Structure | 2025-05-06 | 2025-05-06 | Drawing Submitted
2 | Inverter Duty Transformer | 2025-05-26 | 2025-05-30 | Drawing submitted
3 | NIFPS | 2025-06-08 | 2025-06-08
4 | ICOG/RMU PANEL | 2025-05-28 | 2025-06-09
5 | Main HT Switchgear Panel | 2025-05-28 | 2025-06-09
6 | Auxiliary LT Panel | 2025-06-12 | 2025-06-12
7 | Auxiliary Transformer | 2025-06-06 | 2025-06-10
8 | Central Inverter(PCU) | 2025-05-20 | 2025-05-13 | Drawing submitted
9 | String Combiner Box (SCB) | 2025-05-11 | 2025-07-07
10 | DC string cable | 2025-06-05 | 2025-06-10
11 | DC power cable | 2025-05-22 | 2025-07-14
12 | LT AC power cable | 2025-05-14 | 2025-07-14
13 | HT AC power cable | 2025-06-05 | 2025-06-12
14 | LT power and control cables | 2025-05-28 | 2025-07-14
15 | Communication cables | 2025-05-28 | 2025-07-14
16 | SCADA system | 2025-05-28 | 2025-06-14
17 | UPS and Battery System | 2025-06-05 | 2025-07-04
18 | SVG | 2025-06-12 | 2025-06-12
19 | Harmonic Filter and its Acessories | 2025-07-01 | 2025-07-01
20 | Other BOQ (Lighting, Gland, Lungs, HT termination KIT etc.) | 2025-08-31 | 2025-08-31
# | Engineering-General Drawing | Target | Actual/ Expected | Remarks
1 | Master Document List | 2025-02-13 | Submitted | Submitted
2 | Overall Plant Layout | 2025-05-03 | 2025-05-03 | R2 to be submitted
3 | MMS Structure foundation | 2025-06-15 | 2025-06-15 | Submitted, under SECI Review
4 | MMS Design and GA diagram | 04 Apr, 25 | Submitted | Approved
5 | Lighting Fixtures with calculations | 2025-06-04 | 2025-06-20
6 | ICR Equipment Layout | 2025-04-30 | 2025-05-27 | Submitted under SECI review
7 | MCR Equipment Layout | 2025-05-17 | 2025-05-17
8 | ICR Equipment Foundation Civil Drawing | 2025-05-30 | 2025-06-11
9 | MCR Equipment Foundation Civil Drawing | 2025-06-08 | 2025-06-08
10 | AC sizing calculation | 2025-04-25 | 2025-05-10 | R1 to be submitted
11 | DC sizing calculation | 2025-04-25 | 2025-04-26 | R1 submitted for review
12 | Earthing calculation | 2025-05-06 | 2025-05-18 | R0 submitted for review
13 | DC Cable schedule, laying and sectional drawings | 2025-06-03 | 2025-06-15
14 | AC Cable schedule, laying and sectional drawings | 2025-05-31 | 2025-06-15
15 | Control and Communication Cable schedule, | 2025-05-31 | 2025-06-20
16 | AC SLD | 2025-03-03 | Submitted | Approved under CAT 2, dwg submitted for CAT 1 approval, Revised to be submitted as per discussion
17 | DC SLD | 2025-04-15 |  | R0 Submitted, Under SECI Review since 25th Apr.
18 | AUX SLD | 2025-04-25 | 2025-05-10 | R0 submitted, under SECI Revew
19 | Fencing layout & Drawing | 2025-04-25 |  | Drawing approved, Layout Submitted, under SECI Review
20 | Road Calculations, Cross sections & Layout drawing | 2025-05-20 | 2025-06-06
19 | Calc - UPS Sizing Calculation |  |  | R2 to be submitted
20 | Calc - Auxiliary Transformer Sizing Calculation |  |  | R2 to be submitted
# | Manufacturing, FAT and Delivery at site- Key Equipment | Start | Finish | Remarks
1 | Module Mounting Structure | 2025-05-08 | 2025-10-26
2 | Inverter Duty Transformer | 2025-05-28 | 2025-11-25
3 | NIFPS | 2025-06-10 | 2025-11-08
4 | ICOG/RMU PANEL | 2025-05-30 | 2025-10-28
5 | Main HT Switchgear Panel | 2025-05-30 | 2025-10-28
6 | Auxiliary LT Panel | 2025-06-14 | 2025-10-13
7 | Auxiliary Transformer | 2025-06-08 | 2025-10-07
8 | Central Inverter(PCU) | 2025-05-22 | 2025-09-19
9 | String Combiner Box (SCB) | 2025-05-13 | 2025-09-10
10 | DC string cable | 2025-06-07 | 2025-10-06
11 | DC power cable | 2025-05-24 | 2025-09-21
12 | LT AC power cable | 2025-05-16 | 2025-09-13
13 | HT AC power cable | 2025-06-07 | 2025-10-06
14 | LT power and control cables | 2025-05-30 | 2025-09-27
15 | Communication cables | 2025-05-30 | 2025-09-27
16 | SCADA system | 2025-05-30 | 2025-09-27
17 | UPS and Battery System | 2025-06-07 | 2025-10-06
18 | SVG | 2025-06-14 | 2025-10-13
19 | Harmonic Filter and its Acessories | 2025-07-03 | 2025-12-01
20 | Other BOQ (Lighting, Gland, Lungs, HT termination KIT etc.) | 2025-09-02 | 2025-12-31
Formulas:
Actual/ Expected = [Planned]

## Hinderance Register (hidden)
WORK HINDERANCE REGISTER
S. No | Effected Date | Effect Impact | Description | Remarks | Progress affected in terms of days
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
Total Days | 0 |  |  |  | 0

## Construction Status (2) (hidden)
| Date | 2025-07-15 | [14 empty] | Till 30th Mar
Section | S.No | Site Activity | Planned Start | Planned Finish | Actual/Expected Start | Actual/Expected Finish | uom | Qty | Start Date | End Date | No of Days | Avg/Day | Actual as on Date (%) | Comp. | Bal | Actual as on date | time axis 2025-03-30 to 2025-05-17
 | time axis 2025-03-30 to 2025-05-17
L & G | 1 | Land Development | 2025-04-03 | 2025-08-01 | 2025-04-05 | 2025-08-01 | Acre | 1030 | 2025-04-05 | 2025-05-19 | 45 | 22.8889 | 24.85% | 256 | 774 | 256 | 2025-03-30: 0; 2025-04-03: 0; 2025-04-07: 1.5; 2025-04-08: 3.5; 2025-04-09: 4; 2025-04-10: 4; 2025-04-11: 4; 2025-04-12: 4; 2025-04-13: 3; 2025-04-14: 2; 2025-04-17: 20; 2025-04-18: 20; 2025-04-19: 20; 2025-04-20: 20; 2025-04-21: 40; 2025-04-22: 40; 2025-04-23: 30; 2025-04-24: 20; 2025-04-25: 10; 2025-04-26: 10
Site Initials | 2 | Boundry Coordinate capturing | 2025-02-12 | 2025-02-21 | 2025-02-12 | 2025-02-21 | Lot. | 1 |  |  |  | - | 100% | 1 | 0 | 1 | bar: 2025-03-30
| 3 | Topo Survey | 2025-02-23 | 2025-03-14 | 2025-02-23 | 2025-03-14 | Lot. | 1 |  |  |  | - | 100% | 1 | 0 | 1 | bar: 2025-03-30
| 4 | Soil Investigation | 2025-02-15 | 2025-04-15 | 2025-02-15 | 2025-04-28 | Nos. | 79 | 2025-02-23 |  |  | - | 94.94% | 75 | 4 | 75 | 2025-03-30: 52; 2025-04-03: 2; 2025-04-04: 2; 2025-04-05: 2; 2025-04-06: 2; 2025-04-07: 2; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1; 2025-04-11: 1; 2025-04-12: 1; 2025-04-13: 1; 2025-04-15: 1; 2025-04-16: 1; 2025-04-19: 1; 2025-04-20: 1; 2025-04-21: 1; 2025-04-22: 1; 2025-04-23: 1
| 5 | ERT Test | 2025-04-02 | 2025-04-13 | 2025-04-06 | 2025-04-27 | Lot. | 36 | 2025-02-23 | 2025-03-11 | 17 | 2.1176 | 100% | 36 | 0 | 36 | 2025-03-30: 0; 2025-04-03: 0; 2025-04-06: 4; 2025-04-07: 8; 2025-04-08: 8; 2025-04-09: 10; 2025-04-10: 6
| 6 | Test Pile Casting | 2025-04-12 | 2025-04-26 | 2025-04-12 | 2025-04-26 | Lot. | 236 |  |  |  | - | 0% | 0 | 236 | 0 | 2025-03-30: 0; 2025-04-03: 0
| 7 | Pull Out Test | 2025-04-15 | 2025-05-24 | 2025-04-15 | 2025-05-24 | Lot. | 236 |  |  |  | - | 0% | 0 | 236 | 0 | 2025-03-30: 0; 2025-04-03: 0
Array Yard Civil Works | 8 | Pile Marking |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 9 | Pile -Drilling |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 10 | Pile- Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 11 | Pile-Capping |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
ICR Civil Works | 12 | HT Panel Marking & Excavation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 13 | PCC |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 14 | Footing Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 15 | Pedestal Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 16 | Beam Slab Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 17 | ICR Marking & Excavation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 18 | ICR PCC |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 19 | ICR Footing Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 20 | ICR Column Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 21 | ICR Beam Slab Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 22 | PEB Structure Installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 23 | Transformer Marking & Excavation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 24 | Transformer PCC |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 25 | Transformer Footing Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 26 | Transformer Pedestal Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 27 | Transformer Support Foundation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 28 | Transformer Grade Slab |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 29 | Transformer Fencing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
MCR Civil Works | 30 | MCR Excavation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 31 | MCR Footing PCC |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 32 | MCR Footing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 33 | MCR Column upto Plinth Beam |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 34 | Plinth Beam |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 35 | Cable Trench |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 36 | Column 1st Lift |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 37 | Column 2nd Lift |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 38 | Lintel Beams |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 39 | Roof Beam |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 40 | Slab |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 41 | Brick Works |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 42 | Internal Plastering |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 43 | Outer Plastering |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 44 | Internal Paint Works |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 45 | Outer Painting Works |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 46 | MCR Miscillaneous Works |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 47 | MCR Finishing Works |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
Allied Civil Works | 48 | Asphalt Road-Marking & Excavation |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 49 | Asphalt Road-GSB Filling |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 50 | Asphalt Road-WBM Layer-1 |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 51 | Asphalt Road-WBM Layer-2 |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 52 | Ashpalt Laying |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 53 | Road-Marking & Excavation |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 54 | Road-GSB Filling |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 55 | Road-WBM Layer-1 |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 56 | Road-WBM Layer-2 |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 57 | Periphary Road-Marking and Grading |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 58 | Periphary Road-Compaction |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 59 | Precast Boundary-Marking & Drilling |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 60 | Precast Boundary-Pole Casting |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 61 | Precast Boundary- Panel Fixing |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 62 | Precast Cast Boundary -Arm Fixing & Barbed Wire Laying |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 63 | Chain Link Fencing- Marking & Drilling |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 64 | Chain Link Fencing-Pole Casting |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 65 | Chain Link Fincing |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 66 | Chain Link Fencing-Barbed Wire Ficing |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 67 | Drain Excavation |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 68 | Drain Works |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 69 | Drain Finishing |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
DC System Works | 70 | Excavation For DC/Earthing Trenches Module Mounting Structures |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 71 | DC Cable Laying |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 72 | Module Mounting Structures |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 73 | PV Modules |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 74 | PVM Cables (Interconnection after module installation) |  |  |  |  | Km |  |  |  |  | - | - | 0 | 0 | 0
| 75 | Solar cable laying (6 Sq.mm) |  |  |  |  | Km |  |  |  |  | - | - | 0 | 0 | 0
| 76 | SCB - Mounting Structure |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 77 | Array yard Earthing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 78 | Earth pit installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 79 | SCB Installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
ICR Electrical Works | 80 | Inverter Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 81 | ICOG/RMU Panel Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 82 | Inverter Duty Trafo. Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 83 | Aux Trafo Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 84 | UPS & Battery Bank Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 85 | UPS +LDB'S Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 86 | Scada panel's Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 87 | Tray Works |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 88 | AC Cable-Inv to Trafo. |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 89 | Control & Aux Cable Laying |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 90 | Equipment Earthing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 91 | Grid Earthing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 92 | Earth pit installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
MCR Electrical Works | 93 | HT Panel installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 94 | Aux. trf installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 95 | DB's installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 96 | UPS, Battery charger, battery bank installaiton |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 97 | FAS installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 98 | HT cable laying from MCR to Power Trafo |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 99 | HT cable laying from HT panel to Aux. trf |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 100 | Aux t/f to LT |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 101 | SCADA installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 102 | Grid earthing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 103 | Tray Works |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 104 | Earth pit installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 105 | Equipment earthing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
AC System | 106 | HT Trench Marking & Excavation |  |  |  |  | km |  |  |  |  | - | - | 0 | 0 | 0
| 107 | HT Cable Laying |  |  |  |  | km |  |  |  |  | - | - | 0 | 0 | 0
| 108 | HT Trench Backfilling & Rote Marking |  |  |  |  | km |  |  |  |  | - | - | 0 | 0 | 0
Array Area Terminations | 109 | Solar Cable Termination Table Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 110 | Solar Cable Termination SCB Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 111 | DC Power Cable Termination SCB Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
ICR Areay Terminations | 112 | DC Power Cable Termination Inverter Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 113 | AC cable Termination Inv Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 114 | AC cable Termination Trafo Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 115 | HT Cable Termination Trafo Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 116 | HT Cable Termination ICOG/RMU |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 117 | Control and comm. cable termination |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 118 | LT Cables termination |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
MCR Area Termination | 119 | HT Cable termiantion- MCR Panel |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 120 | MCR to Power Trafo HT cable termination |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 121 | Aux. t/f LT side cable termiantion |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 122 | Control and comm. cable termination |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 123 | LT Cables termination |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
Scada Works | 124 | FO Cable Laying |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 125 | FO Cable Splicing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 126 | FAS installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
Testing and Commissioning | 127 | Pre-commissioning of inverters |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 128 | HT panel @ blocks |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 129 | Transformers @ blocks |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 130 | Invertor, Aux T/F , ACCB, UPS |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 131 | T/F to ICOG cables IR & Hi-pot test |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 132 | ICOG to 3VCB cables IR & Hi-pot test |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 133 | 3VCB to MCR cables IR & Hi-pot test |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 134 | ERT |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 135 | FAS functionality check |  |  |  |  | % |  |  |  |  | - | - | 0 | 0 | 0
| 136 | CCTV commissioning |  |  |  |  | % |  |  |  |  | - | - | 0 | 0 | 0
| 137 | WMS commissioning |  |  |  |  | % |  |  |  |  | - | - | 0 | 0 | 0
External Works | 138 | Street Light Poles | [9 empty] | - | - | 0 | 0 | 0
| 139 | Light Fixtures | [9 empty] | - | - | 0 | 0 | 0
| 140 | External LDB | [9 empty] | - | - | 0 | 0 | 0
| 141 | LT Cables | [9 empty] | - | - | 0 | 0 | 0
| 142 | LT Termination | [9 empty] | - | - | 0 | 0 | 0
| 143 | External earthing work completion | [9 empty] | - | - | 0 | 0 | 0
Allied Works | 144 | Weather Monitoring System |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 145 | Module Cleaning System( after Module installation | [9 empty] | - | - | 0 | 0 | 0
| 146 | FDS | [9 empty] | - | - | 0 | 0 | 0
| 147 | Allied work completion | [9 empty] | - | - | 0 | 0 | 0
Commissioning & Handing Over | 148 | Pre-Commissioining (DC & AC) |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0
| 149 | CEIG Approval |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0
| 150 | Synchronization Approval |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0
| 151 | Commissioning |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0
| 152 | PR Acceptance |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0
| 153 | FAT & HO |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0