## Project Dashbord
Project Progress Report | [8 empty] | PROGRESS ON: 27-Jul-2025
Project Name : |  | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Taru, Leh, UT of Ladakh, India
Client : |  | Solar Energy Corporation of India Ltd
SPV : |  | Prozeal Green Energy Limited
Project Start Date |  | 2024-11-20
Project COD |  | 2027-11-05
Sr. No | Description | Scope | UOM | Completed | Balance | Actual Progress Front Wise (in %) | Scope Weightage % | Progress as per weightage (in %) | Overall Project Completion Status
1 | Plant Boundary Fencing | 5500 | RM | 4170.5 | 1329.5 | 75.8% | 1.2% | 0.9%
2 | MCR Civil Work | 1 | Lot | 0.13636 | 0.86364 | 13.6% | 9% | 1.2%
3 | MMS Pilling | 27000 | Nos | 0 | 27000 | 0% | 22.8% | 0%
4 | Switch Yard | 1 | Lot | 0 | 1 | 0% | 9% | 0%
5 | IDT - Solar | 4 | Lot | 3 | 1 | 75% | 1.2% | 0.9%
6 | IDT - BESS | 5 | Lot | 0 | 5 | 0% | 1.2% | 0%
7 | BESS-Civil | 1 | Lot | 0 | 1 | 0% | 3.6% | 0%
8 | LCR | 4 | Lot | 0 | 4 | 0% | 2.4% | 0%
9 | MMS Structure | 3934 | Table | 0 | 3934 | 0% | 7.2% | 0%
10 | Road | 3000 | Mtr. | 0 | 3000 | 0% | 1.2% | 0%
11 | Drain | 1000 | Mtr. | 0 | 1000 | 0% | 0.6% | 0%
12 | Misc Work | 1 | Lot | 0.2 | 0.8 | 20% | 0.6% | 0.1%
13 | AC-Electrical | 1 | Lot | 0 | 1 | 0% | 7.4% | 0%
14 | DC- Electrical | 1 | Lot | 0 | 1 | 0% | 7.4% | 0%
15 | Switchtard - Electrical | 1 | Lot | 0 | 1 | 0% | 7.4% | 0%
16 | MCR - Electrical | 1 | Lot | 0 | 1 | 0% | 3.7% | 0%
17 | Module Erection | 94416 | Nos | 0 | 94416 | 0% | 7.4% | 0%
18 | BESS - Electrical | 1 | Lot | 0 | 1 | 0% | 3.7% | 0%
19 | Transmission Line | 1 | Lot | 0 | 1 | 0% | 1% | 0%
20 | Project Charging & Commisioning | 1 | Lot | 0 | 1 | 0% | 2% | 0%
Overall Project Completion Status | [6 empty] | 100% | 3.1%

## MDL Status
Project Drawings Approval Report | [15 empty] | PROGRESS ON: 27-Jul-2025
Client Name | Solar Energy Corporation of India Ltd | [12 empty] | Total Documents | Submitted | Approved | Sub. Approved | Commented | Pending for Submission
EPC Contractor | Prozeal Green Energy Limited | [12 empty] | 100% | 37.63% | 9.14% | 0.5376% | 13.98% | 62.37%
Project Name | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Taru, Leh, UT of Ladakh, India | [12 empty] | 186 | 70 | 17 | 1 | 26 | 116
Project Capacity | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System | [12 empty] | Only apporval category
Particulars | Total Documents | [9 empty] | Remaining Documents | Total Received (%) | Engineering completion (%)
|  | VOID | UNDER EPC | UNDER OE | SUB. APPROVED | APPROVED | NOTED FOR INFORMATION | NOT APPROVED | PENDING | Total Sub
I. Review Engineering Electrical
A.Basic Engineering | 11 | 0 | 4 | 2 | 0 | 2 | 3 | 0 | 0 | 11 | 0 | 100% | 0%
B.Major Electrical Equipments (GTP, GA, Type Test Reports and QAP) | 4 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 1 | 3 | 25% | 0%
C.Cable sizing documents | 4 | 0 | 1 | 1 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 100% | 0%
D.Cable GTPs, Type Test Reports and QAP | 7 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 3 | 4 | 3 | 57.14% | 0%
E.Battery Energy Storage System (BESS) | 17 | 0 | 5 | 2 | 0 | 2 | 2 | 0 | 6 | 11 | 6 | 64.71% | 0%
F.Module Mounting structure | 11 | 0 | 6 | 1 | 0 | 0 | 1 | 0 | 3 | 8 | 3 | 72.73% | 0%
G.MCR Building | 11 | 0 | 0 | 5 | 0 | 1 | 0 | 0 | 5 | 6 | 5 | 54.55% | 0%
H.Open Plinth for LCR Equipment | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0% | 0%
I.BESS Foundation | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 2 | 5 | 28.57% | 0%
J.Equipment foundations | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0% | 0%
K.Layout, Ancillary Equipment GTP and DBR | 24 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 21 | 3 | 21 | 12.5% | 0%
M.Ancillary Systems | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0% | 0%
N.Cable Schedules | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 0% | 0%
O.System Drawings and Layouts | 14 | 0 | 4 | 2 | 0 | 1 | 0 | 0 | 7 | 7 | 7 | 50% | 0%
P.Equipment GTPs, Type test reports and Inspection Reports | 24 | 0 | 1 | 7 | 0 | 0 | 0 | 0 | 16 | 8 | 16 | 33.33% | 0%
Q.Equipment Foundation Drawings and Cable Schedules | 25 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 20 | 5 | 20 | 20% | 0%
Total documents | 186 | 0 | 26 | 26 | 1 | 11 | 6 | 0 | 116 | 70 | 116 | 37.63% | 0%
| 186 | 17 | 100% | 9.14%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sheet1 (hidden)
Sl. No. | Drawing/Document Title | Approval Category | Date Of Approval | Darwing Number | Approval Status | Proposed Submission Date
1 | Plant Boundary Fencing Layout and Details | CAT-I | 2025-02-27 | SECI-LEH25MW-DWG-CIV-10 | Approved |  | Approved
2 | Plant Main Gate - General Arrangement and Details | CAT-I | 2025-01-24 | SECI-LEH25MW-DWG-CIV-11 | Approved |  | Re-Submission
3 | DC cable (from SCB to PCU) | CAT-I | 2025-05-28 | SECI-LEH25MW-DBR-ELE-17 | Approved |  | PGEL
4 | LT cable (from PCU to IDT) | CAT-I | 2025-05-15 | SECI-LEH25MW-DBR-ELE-18 | Approved |  | SECI-Review
5 | 11kV LT Power Cable | CAT-I | 2025-07-24 | SECI-LEH25MW-DBR-ELE-19 | Approved |  | Yet To Submit
6 | LT cable (from PCU to IDT) | CAT-I | 2025-06-10 | SECI-LEH25MW-GTP-ELE-22 | Approved
7 | 11kV LT Power Cable | CAT-I | 2025-07-21 | SECI-LEH25MW-GTP-ELE-23 | Approved
8 | Battery Sizing Calculation | CAT-I | 2025-07-11 | SECI-LEH25MW-DBR-ELE-28 | Approved
9 | MCR - Architectural Details, Elevations, Sections and Finishing | CAT-I | 2025-07-03 | SECI-LEH25MW-DWG-CIV-51 | Approved
10 | AC Earthing Design and Calculation | CAT-I | 2025-05-27 | SECI-LEH25MW-DBR-ELE-80 | Approved
11 | 66kV HT Conductor Sizing Calculation | CAT-I | 2025-07-04 | SECI-LEH25MW-DBR-ELE-118 | Approved
12 | DC SLD | CAT-IV | 2025-04-21 | SECI-LEH25MW-DWG-ELE-4 | Approved
13 | AC SLD including BESS (upto 11 kV) | CAT-IV | 2025-04-21 | SECI-LEH25MW-DWG-ELE-5 | Approved
14 | Topographical Survey | CAT-IV | 2025-05-02 | SECI-LEH25MW-DWG-CIV-6 | Approved
15 | Auxiliary Power Consumption Calculation | CAT-IV | 2025-06-04 | SECI-LEH25MW-DBR-ELE-39 | Approved
16 | Heat Load Calculation of Container | CAT-IV | 2025-07-11 | SECI-LEH25MW-DBR-CIV-40 | Approved
17 | MMS Fabrication Drawing | CAT-IV | 2025-07-19 | SECI-LEH25MW-DWG-CIV-46 | Approved
18 | Solar cable (PV module to SCB) | CAT-II |  | SECI-LEH25MW-DBR-ELE-16 | Re-Submission
19 | Solar cable (PV module to SCB) | CAT-II |  | SECI-LEH25MW-GTP-ELE-20 | Re-Submission
20 | Module Mounting Structure DBR | CAT-II |  | SECI-LEH25MW-DBR-CIV-44 | Re-Submission
21 | MMS Drawing | CAT-II |  | SECI-LEH25MW-DWG-CIV-45 | Re-Submission
22 | MMS Foundation Drawing | CAT-II |  | SECI-LEH25MW-DWG-CIV-47 | Re-Submission
23 | Pile Test Location Drawing (if applicable) | CAT-II |  | SECI-LEH25MW-DWG-CIV-49 | Re-Submission
24 | DC Earthing Design and Calculation | CAT-II |  | SECI-LEH25MW-DBR-ELE-78 | Re-Submission
25 | Power Evacuation SLD (11/66kV Switchyard) | CAT-II |  | SECI-LEH25MW-DWG-ELE-119 | Re-Submission
26 | System Design Basis Report (including Energy Yield Simulation and shadow analysis report) | CAT-III |  | SECI-LEH25MW-DBR-ELE-3 | SECI-Review
27 | Overall Plant Layout covering Array layout, Buildings (MCR and LCR) marking, Road Layout, Lightning protection layout, WMS Location, etc. | CAT-III |  | SECI-LEH25MW-DWG-ELE-9 | SECI-Review
28 | BESS Fire Protection Systems | CAT-III |  | SECI-LEH25MW-DWG-ELE-38 | SECI-Review
29 | MCR Foundation and Super Structure - Design Basis Report | CAT-III |  | SECI-LEH25MW-DBR-CIV-52 | SECI-Review
30 | MCR - Foundation General Arrangement and Reinforcement Details | CAT-III |  | SECI-LEH25MW-DWG-CIV-53 | SECI-Review
31 | Power Conditioning Unit (Central) |  |  | SECI-LEH25MW-GTP-ELE-2 | PGEL
32 | Concrete Mix Design Report |  |  | SECI-LEH25MW-IR-CIV-7 | PGEL
33 | Design Basis Report for BESS with BESS PQR |  |  | SECI-LEH25MW-DBR-ELE-27 | PGEL
34 | Battery Management System (GTP and Drawings) |  |  | SECI-LEH25MW-GTP-ELE-31 | PGEL
35 | HVAC System (General Arrangement and Details) |  |  | SECI-LEH25MW-DWG-ELE-35 | PGEL
36 | BESS Auxiliary System SLD and DB Details |  |  | SECI-LEH25MW-GTP-ELE-36 | PGEL
37 | Module Mounting Structure DBR (Interior) |  |  | SECI-LEH25MW-DBR-CIV-44A | PGEL
38 | MMS Drawing (Interior) |  |  | SECI-LEH25MW-DWG-CIV-45A | PGEL
39 | Plant Auxilary Load Calculation with UPS sizing |  |  | SECI-LEH25MW-DBR-ELE-85 | PGEL
40 | Aux. Load Calculations and Aux. Transformer Sizing (Switchyard & BESS) |  |  | SECI-LEH25MW-DBR-ELE-122 | PGEL
41 | 66 kV Switchyard - Short Circuit Force & Cantilever Strength Calculation |  |  | SECI-LEH25MW-DBR-ELE-124 | PGEL
42 | Plant End Substation Earthing Design and Calculation |  |  | SECI-LEH25MW-DWG-ELE-126 | PGEL
43 | Power Transformer |  |  | SECI-LEH25MW-GTP-ELE-132 | PGEL
44 | Current Transformer (Metering and Protection) Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-164 | PGEL
45 | Voltage Transformer (Metering and Protection) Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-165 | PGEL
46 | Lightning Arrestor Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-166 | PGEL
47 | Grading and Levelling Plan |  |  | SECI-LEH25MW-DWG-CIV-8 | SECI-Review
48 | 11kV HT ICOG Panel |  |  | SECI-LEH25MW-GTP-ELE-14 | SECI-Review
49 | DC cable (from SCB to PCU) |  |  | SECI-LEH25MW-GTP-ELE-21 | SECI-Review
50 | Battery Bank (GTP, Drawings, Type Test Report and QAP) Along with Battery Container GA |  |  | SECI-LEH25MW-GTP-ELE-30 | SECI-Review
51 | Power Conditioning System (GTP, Drawings, Type Test Report and QAP) |  |  | SECI-LEH25MW-GTP-ELE-32 | SECI-Review
52 | MMS Foundation Marking Layout |  |  | SECI-LEH25MW-DWG-CIV-48 | SECI-Review
53 | MCR - Plinth Beam General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-54 | SECI-Review
54 | MCR - Lintel Beam General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-55 | SECI-Review
55 | MCR - Roof General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-56 | SECI-Review
56 | BESS Container Platform and Foundation - Design Basis Report |  |  | SECI-LEH25MW-DBR-CIV-68 | SECI-Review
57 | BESS Container Platform Superstructure and Foundation - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-69 | SECI-Review
58 | Plant End Switchyard Layout |  |  | SECI-LEH25MW-DWG-ELE-125 | SECI-Review
59 | Plant End Substation Earthing Layout |  |  | SECI-LEH25MW-DWG-ELE-127 | SECI-Review
60 | Lightning Arrestor - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-134 | SECI-Review
61 | Isolator - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-135 | SECI-Review
62 | BPI - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-136 | SECI-Review
63 | Circuit Breaker - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-137 | SECI-Review
64 | Current Transformer (Metering) - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-138 | SECI-Review
65 | Protection CT - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-145 | SECI-Review
66 | Protection PT/CVT - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-146 | SECI-Review
67 | Power Transformer Foundation and Burnt Oil Pit DBR |  |  | SECI-LEH25MW-DBR-CIV-156 | SECI-Review
68 | Power Transformer Foundation and Burnt Oil Pit - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-157 | SECI-Review

## Progress Abstract
Daily Progress Report | [9 empty] | Date:- | 2025-07-27
Project Name : |  | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Taru, Leh, UT of Ladakh, India
Client : |  | Solar Energy Corporation of India Ltd
SPV : |  | Prozeal Green Energy Limited | [11 empty] | 3905
Project Start Date |  | 2024-11-20
Project COD |  | 2027-11-05 | [9 empty] | 1080 | 831
Sr. No | Description | Work Status | UOM | Scope | Progress | Balance | %age | Status | Dashboard
CIVIL Package | [11 empty] | COMP
1 | Boundary Fencing | Boundary Demarcation and marking | Rm | 5500 | 5500 | 0 | 100% | COMP |  |  |  | WIP
|  | Plie Boring | Rm | 5500 | 4957.5 | 542.5 | 90.14% | WIP |  |  |  | Yet to Start
|  | Fence post Allignment and Concrete Pouring | Rm | 5500 | 4515 | 985 | 82.09% | WIP | [5 empty] | 0.34858 | 0.65142 | 30.75%
|  | Tension and Barbed wire installation | Rm | 5500 | 2720 | 2780 | 49.45% | WIP
|  | Mesh installation with connecting strip and tightening | Rm | 5500 | 3160 | 2340 | 57.45% | WIP
|  | Weightage Progress |  | 1 | 0.75827 | 0.24173 | 75.83%
2 | Main Gate | Foundation Excavation | Nos | 3 | 3 | 0 | 100% | COMP
|  | Foundation PCC | Nos | 3 | 3 | 0 | 100% | COMP
|  | Foundation RCC | Nos | 3 | 3 | 0 | 100% | COMP
|  | Columns | Nos | 3 | 3 | 0 | 100% | COMP
|  | Gate Febrication and Installation | Nos | 2 | 2 | 0 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 1 | 0 | 100%
3 | MCR | Excavation | No's | 33 | 33 | 0 | 100% | COMP
|  | Foundation PCC | No's | 33 | 33 | 0 | 100% | WIP
|  | Footing Foundation casting | No's | 33 | 17 | 16 | 51.52% | WIP
|  | Column upto Plinth Beam | No's | 33 | 0 | 33 | 0% | Yet to Start
|  | Plinth Beam Casting | Mtr | 322 | 0 | 322 | 0% | Yet to Start
|  | Column upto Lintel Beam | No's | 33 | 0 | 33 | 0% | Yet to Start
|  | Lintel and sunshade casting | Mtr | 132 | 0 | 132 | 0% | Yet to Start
|  | Column upto Roof Beam | No's | 33 | 0 | 33 | 0% | Yet to Start
|  | Roof Beam & Slab Casting | Ls | 1 | 0 | 1 | 0% | Yet to Start
|  | Cable Trench Raft Casting | Mtr | 50 | 0 | 50 | 0% | Yet to Start
|  | Cable Trench Wall casting | Mtr | 100 | 0 | 100 | 0% | Yet to Start
|  | Floor Slab Casting | Ls | 1 | 0 | 1 | 0% | Yet to Start
|  | Brick Masonry Work | Cu. Mtr | 310 | 0 | 310 | 0% | Yet to Start
|  | Wall & Celling Plaster | Sq. Mtr | 2380 | 0 | 2380 | 0% | Yet to Start
|  | Flooring | No's | 8 | 0 | 0 | 0% | Yet to Start
|  | Putty & Paint work | No's | 8 | 0 | 0 | 0% | Yet to Start
|  | Misc Work | LS | 1 | 0 | 0 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0.13636 | 0.86364 | 13.64%
4 | IDT- Solar | Excavation | No's | 4 | 3 | 1 | 75% | WIP
|  | Foundation PCC | No's | 4 | 3 | 1 | 75% | WIP
|  | Foundation Raft casting | No's | 4 | 3 | 1 | 75% | WIP
|  | Wall casting | No's | 8 | 6 | 2 | 75% | WIP
|  | Cashment Wall B/W | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Fencing - IDT | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0.54545 | 0.45455 | 54.55%
5 | LCR- Solar | Excavation | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Foundation PCC | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Foundation Raft casting | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Pedestal casting | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Slab Casting | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | B/W | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Canopy | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0 | 1 | 0%
6 |  | Pile marking | No's | 27000 | 1632 | 25368 | 6.044% | WIP
|  | Pile Boring | No's | 27000 | 0 | 27000 | 0% | Yet to Start
|  | Pile Casting | No's | 27000 | 0 | 27000 | 0% | Yet to Start
|  | Weightage Progress |  | 27000 | 544 | 26456 | 2.015%
7 | IDT- BESS | Excavation | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Foundation PCC | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Foundation Raft casting | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Wall casting | No's | 10 | 0 | 10 | 0% | Yet to Start
|  | Cashment Wall B/W | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Fencing - IDT | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0 | 1 | 0%
8 | BESS- Civil | Excavation of Container foundation | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | Container Foundation PCC | Nos | 80 | 0 | 80 | 0% | Yet to Start
|  | Container Foundation Concrete Pouring | Nos | 80 | 0 | 80 | 0% | Yet to Start
|  | Container Pedestal Concrete Pouring | Nos | 80 | 0 | 80 | 0% | Yet to Start
|  | Container Tie Beam & Slab Concrete Pouring | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | B/W of Container Plartform | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | Excavation of PCS foundation | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | PCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | Yet to Start
|  | RCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | Yet to Start
|  | RCC of PCS Pedestal | Nos | 40 | 0 | 40 | 0% | Yet to Start
|  | RCC of PCS Tie Beam | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | B/W of PCS Plartform | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | Weightage Progress | No's | 1 | 0 | 1 | 0%
ELECTRICAL Package
33 | Switchyard ELE | Structure Errection | Nos | 97 | 0 | 97 | 0%
34 |  | Equipment Errection | Nos | 97 | 0 | 97 | 0%
35 |  | Earthing Works | Mtr | 3252.375 | 0 | 3252.375 | 0%
36 |  | Cabling Works | LS | 1 | 0 | 1 | 0%
37 |  | Testing Works | LS | 1 | 0 | 1 | 0%
38 |  | Weightage Progress | LS | 689.675 | 0 | 689.675 | 0%
39 | DC Work | Trench Excavation | Mtr | 171000 | 950 | 170050 | 0.5556%
40 |  | 400sqmm Cable Laying(SCB) | No's | 1824 | 0 | 1824 | 0%
41 |  | Inv Installation | No's | 76 | 0 | 76 | 0%
42 |  | 400sqmm Cable Laying | Mtr | 638400 | 0 | 638400 | 0%
43 |  | SCB Stand Casting | No's | 3648 | 0 | 3648 | 0%
44 |  | SCB Installation | No's | 1824 | 0 | 1824 | 0%
45 |  | 6 Sq. mm Termination | No's | 1824 | 0 | 1824 | 0%
46 |  | Termination SCB End | No's | 1824 | 0 | 1824 | 0%
47 |  | Termination Inv End | No's | 1824 | 0 | 0 | 0%
48 |  | Earthing Conductor Laying | Mtr | 95000 | 0 | 95000 | 0%
49 |  | Earthpit Installation | No's | 912 | 0 | 912 | 0%
50 |  | String Cable Termination | No's | 1824 | 0 | 1824 | 0%
51 |  | LA Insatallation | No's | 190 | 0 | 190 | 0%
52 |  | LA Connection | No's | 190 | 0 | 190 | 0%
53 |  | MMS Installation | No's | 14592 | 0 | 14592 | 0%
54 |  | Module Installation | No's | 846336 | 0 | 846336 | 0%
55 |  | Weightage Progress | No's | 1 | 0.00034722 | 0.99965 | 0.03472%
56 | AC Work | AC Trench | Mtr | 26043.8846 | 0 | 26043.8846 | 0%
57 |  | 3CX240sqmm Cable Laying | Mtr | 18269.2308 | 0 | 18269.2308 | 0%
58 |  | 3CX400sqmm Cable Laying | Mtr | 58461.5385 | 0 | 58461.5385 | 0%
59 |  | 1CX400sqmm Cable Laying | LS | 38 | 0 | 38 | 0%
60 |  | OFC Cable Laying | LS | 38 | 0 | 38 | 0%
61 |  | Grid Earthing | mtr | 7600 | 0 | 7600 | 0%
62 |  | Tray support casting | No's | 38 | 0 | 38 | 0%
63 |  | Tray from INV to LV Side | No's | 38 | 0 | 38 | 0%
64 |  | Earthpit Installation | No's | 38 | 0 | 38 | 0%
65 |  | IDT Erection | No's | 38 | 0 | 38 | 0%
66 |  | ICOG Panel | No's | 38 | 0 | 38 | 0%
67 |  | LT Panel | No's | 38 | 0 | 38 | 0%
68 |  | UPS Panel | No's | 38 | 0 | 38 | 0%
69 |  | Aux Trafo | No's | 38 | 0 | 38 | 0%
70 |  | 1C*400Sqmm cable Termination | Sets | 38 | 0 | 38 | 0%
71 |  | Weightage Progress | No's | 1 | 0 | 1 | 0%
14%
MCR CIVIL Work
0%
Fencing Work
76%
100%
55%
0%
IDT- Solar Civil Work
IDT- BESS Civil Work
0%
0%
CIVIL PROGRESS%
2.015%
MMS PILLING

## Civil Progress
Civil Progress | [6 empty] | DAILY PROGRESS
Sr.no. | Description | UOM | Scope | Progress | Balance | % Progress | Cummulative | time axis 2025-05-05 to 2025-10-31
Boundary Fencing |  | Rm | 5500 | 4170.5 | 1329.5 | 75.83%
1 | Boundary Demarcation and marking | Rm | 5500 | 5500 | 0 | 100% | 5500 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 5250; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 125; 2025-07-03: 125
2 | Plie Boring | Rm | 5500 | 4957.5 | 542.5 | 90.14% | 4957.5 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 4957.5; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0
3 | Fence post Allignment and Concrete Pouring | Rm | 5500 | 4515 | 985 | 82.09% | 4515 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 1642.5; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 52; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 75.5; 2025-07-07: 0; 2025-07-08: 250; 2025-07-09: 250; 2025-07-10: 225; 2025-07-11: 272.5; 2025-07-12: 200; 2025-07-13: 250; 2025-07-14: 225; 2025-07-15: 175; 2025-07-16: 192.5; 2025-07-17: 0; 2025-07-18: 175; 2025-07-19: 187.5; 2025-07-20: 0; 2025-07-21: 155; 2025-07-22: 0; 2025-07-23: 187.5; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0
4 | Tension and Barbed wire installation | Rm | 5500 | 2720 | 2780 | 49.45% | 2720 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 1300; 2025-07-04: 180; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 290; 2025-07-12: 315; 2025-07-13: 315; 2025-07-14: 320; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0
5 | Mesh installation with connecting strip and tightening | Rm | 5500 | 3160 | 2340 | 57.45% | 3160 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 1300; 2025-07-04: 180; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 50; 2025-07-10: 60; 2025-07-11: 210; 2025-07-12: 180; 2025-07-13: 180; 2025-07-14: 220; 2025-07-15: 105; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 150; 2025-07-19: 165; 2025-07-20: 0; 2025-07-21: 180; 2025-07-22: 0; 2025-07-23: 180; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0
Main Gate |  | Nos | 2.8 | 2.8 | 0 | 100%
1 | Foundation Excavation | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 3
2 | Foundation PCC | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 3
3 | Foundation RCC | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 3
4 | Columns | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 1; 2025-07-12: 2
5 | Gate Febrication and Installation | Nos | 2 | 2 | 0 | 100% | 2 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 2
Street light Work |  | No's | 175 | 0 | 175 | 0%
1 | Pole Casting | No's | 175 | 0 | 175 | 0% | 0
2 | Light Erection | No's | 175 | 0 | 175 | 0% | 0
MCR | [5 empty] | 13.64%
1 | Excavation | No's | 33 | 33 | 0 | 100% | 33 | 2025-06-24: 33
2 | Foundation PCC | No's | 33 | 33 | 0 | 100% | 33 | 2025-06-24: 17; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 5; 2025-07-21: 11
3 | Foundation Reinforcement | No's | 33 | 17 | 16 | 51.52% | 17 | 2025-06-24: 17
4 | Foundation Shuttering | No's | 33 | 17 | 16 | 51.52% | 17 | 2025-06-24: 17
5 | Footing Foundation casting | No's | 33 | 17 | 16 | 51.52% | 17 | 2025-06-24: 17
6 | Back filling | No's | 33 | 0 | 33 | 0% | 0 | 2025-06-24: 0
7 | Column upto Plinth Beam | No's | 33 | 0 | 33 | 0% | 0 | 2025-06-24: 0
8 | Plinth Beam Reinforcement | Mtr | 322 | 0 | 322 | 0% | 0 | 2025-06-24: 0
9 | Plinth Beam shuttering | Mtr | 322 | 0 | 322 | 0% | 0 | 2025-06-24: 0
10 | Plinth Beam Casting | Mtr | 322 | 0 | 322 | 0% | 0 | 2025-06-24: 0
11 | Column upto Lintel Beam | No's | 33 | 0 | 33 | 0% | 0 | 2025-06-24: 0
12 | Lintel and sunshade reinforcement & shuttering | Mtr | 132 | 0 | 132 | 0% | 0 | 2025-06-24: 0
13 | Lintel and sunshade casting | Mtr | 132 | 0 | 132 | 0% | 0 | 2025-06-24: 0
14 | Cable Trench PCC Base | Mtr | 50 | 0 | 50 | 0% | 0 | 2025-06-24: 0
15 | Cable Trench Reinforcement & Shuttering | Mtr | 50 | 0 | 50 | 0% | 0 | 2025-06-24: 0
16 | Cable Trench Raft Casting | Mtr | 50 | 0 | 50 | 0% | 0 | 2025-06-24: 0
17 | Cable Trench Wall casting | Mtr | 100 | 0 | 100 | 0% | 0 | 2025-06-24: 0
18 | Column upto Roof Beam | No's | 33 | 0 | 33 | 0% | 0 | 2025-06-24: 0
19 | Roof Beam & Slab shuttering | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
20 | Roof Beam & Slab reinforcement | Ls | 1 | 0 |  |  | 0 | 2025-06-24: 0
21 | Roof Beam & Slab Casting | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
22 | Floor Slab Casting | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
23 | Brick Masonry Work | Cu. Mtr | 310 | 0 | 310 | 0% | 0 | 2025-06-24: 0
24 | Wall & Celling Plaster | Sq. Mtr | 2380 | 0 | 2380 | 0% | 0 | 2025-06-24: 0
25 | Flooring | No's | 8 | 0 | 0 | 0%
| Scada Room (10 x 7.8)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Conference Room (5.2 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Manager Room (2.5 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Store Room (2.51 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Battery Room (4.6 x 4.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| LT Panel Room (4.2 x 8.25)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Toilet (2.85 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Pantry Room (2.4 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
26 | Putty & Paint work | No's | 8 | 0 | 0 | 0%
| Scada Room (10 x 7.8)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Conference Room (5.2 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Manager Room (2.5 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Store Room (2.51 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Battery Room (4.6 x 4.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| LT Panel Room (4.2 x 8.25)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Toilet (2.85 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Pantry Room (2.4 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
27 | Misc Work | LS | 1 | 0 | 0 | 0%
| Drain | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Ramp | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Steps | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Septic Tank | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Soak Pit | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Plumbing Works | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Electrical works | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
IDT- Solar |  |  |  | 3 |  | 54.55%
1 | Excavation | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
2 | Foundation PCC | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
3 | Foundation Raft Reinforcement | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
4 | Foundation Raft Shuttering | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
5 | Foundation Raft casting | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
6 | Wall Reinforcement | No's | 8 | 6 | 2 | 75% | 6 | 2025-06-24: 6
7 | Wall Shuttering | No's | 8 | 6 | 2 | 75% | 6 | 2025-06-24: 6
8 | Wall casting | No's | 8 | 6 | 2 | 75% | 6 | 2025-06-24: 6
9 | Back filling | No's | 4 | 0 | 4 | 0% | 0 | 2025-06-24: 0
10 | Cashment Wall B/W | No's | 4 | 0 | 4 | 0% | 0 | 2025-06-24: 0
11 | Fencing - IDT | No's | 4 | 0 | 4 | 0% | 0 | 2025-06-24: 0
LCR- Solar | [5 empty] | 0%
1 | Excavation | No's | 32 | 0 | 32 | 0% | 0
2 | Foundation PCC | No's | 32 | 0 | 32 | 0% | 0
3 | Foundation Raft Reinforcement | No's | 32 | 0 | 32 | 0% | 0
4 | Foundation Raft Shuttering | No's | 32 | 0 | 32 | 0% | 0
5 | Foundation Raft casting | No's | 32 | 0 | 32 | 0% | 0
6 | Pedestal Reinforcement | No's | 32 | 0 | 32 | 0% | 0
7 | Pedestal Shuttering | No's | 32 | 0 | 32 | 0% | 0
8 | Pedestal casting | No's | 32 | 0 | 32 | 0% | 0
9 | Slab Shuttering & Reinforcement | No's | 4 | 0 | 4 | 0% | 0
10 | Slab Casting | No's | 4 | 0 | 4 | 0% | 0
11 | B/W | No's | 4 | 0 | 4 | 0% | 0
12 | Canopy | No's | 4 | 0 | 4 | 0% | 0
IDT- BESS |  |  |  | 0 |  | 0%
1 | Excavation | No's | 5 | 0 | 5 | 0% | 0
2 | Foundation PCC | No's | 5 | 0 | 5 | 0% | 0
3 | Foundation Raft Reinforcement | No's | 5 | 0 | 5 | 0% | 0
4 | Foundation Raft Shuttering | No's | 5 | 0 | 5 | 0% | 0
5 | Foundation Raft casting | No's | 5 | 0 | 5 | 0% | 0
6 | Wall Reinforcement | No's | 10 | 0 | 10 | 0% | 0
7 | Wall Shuttering | No's | 10 | 0 | 10 | 0% | 0
8 | Wall casting | No's | 10 | 0 | 10 | 0% | 0
9 | Back filling | No's | 5 | 0 | 5 | 0% | 0
10 | Cashment Wall B/W | No's | 5 | 0 | 5 | 0% | 0
11 | Fencing - IDT | No's | 5 | 0 | 5 | 0% | 0
BESS Foundation | [5 empty] | 0%
1 | Excavation of Container foundation | Nos | 10 | 0 | 10 | 0% | 0
2 | Container Foundation PCC | Nos | 80 | 0 | 80 | 0% | 0
3 | Container Foundation Reinforcement | Nos | 80 | 0 | 80 | 0% | 0
4 | Container Foundation Shuttering | Nos | 80 | 0 | 80 | 0% | 0
5 | Container Foundation Concrete Pouring | Nos | 80 | 0 | 80 | 0% | 0
6 | Container Pedestal Reinforcement | Nos | 80 | 0 | 80 | 0% | 0
7 | Container Pedestal Shuttering | Nos | 80 | 0 | 80 | 0% | 0
8 | Container Pedestal Concrete Pouring | Nos | 80 | 0 | 80 | 0% | 0
9 | Container Tie Beam & Slab Reinforcement | Nos | 10 | 0 | 10 | 0% | 0
10 | Container Tie Beam & Slab Shuttering | Nos | 10 | 0 | 10 | 0% | 0
11 | Container Tie Beam & Slab Concrete Pouring | Nos | 10 | 0 | 10 | 0% | 0
12 | B/W of Container Plartform | Nos | 10 | 0 | 10 | 0% | 0
13 | Excavation of PCS foundation | Nos | 10 | 0 | 10 | 0% | 0
14 | PCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0
15 | Reinforcement of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0
16 | Shuttering of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0
17 | RCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0
18 | Reinforcement & Shuttering of PCS Pedestal | Nos | 40 | 0 | 40 | 0% | 0
19 | RCC of PCS Pedestal | Nos | 40 | 0 | 40 | 0% | 0
20 | Reinforcement & Shuttering of PCS Tie Beam | Nos | 10 | 0 | 10 | 0% | 0
21 | RCC of PCS Tie Beam | Nos | 10 | 0 | 10 | 0% | 0
22 | B/W of PCS Plartform | Nos | 10 | 0 | 10 | 0% | 0

## ICR Pilling
ICR NO. | Scope | Piling Progress | Progress in % | time axis 2025-05-30 to 2025-10-31
Total | 27000 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 6750 | 0 | 0%
2 | 6750 | 0 | 0%
3 | 6750 | 0 | 0%
4 | 6750 | 0 | 0%

## SW Civil
Switchyard Equipment Progress
Sr. No. | Description | UOM | Weightage Scope | Weightage completion | Equipments | Foundation Scope (Nos) | Excavation |  |  |  | PCC |  |  |  | Raft Foundation |  |  |  | Column casting/J-bolt fixing
[7 empty] | Start Date | End Date | Progress | Percentage | Start Date | End Date | Progress | Percentage | Start Date | End Date | Progress | Percentage | Start Date | End Date | Progress | Percentage |  | Sr. No. | Description | Activity | Unit | Equipment | Foundation | Cummulative | Balance | time axis 2024-11-12 to 2025-05-14
1 | Tower Foundation | Nos | 15% | 0% | 14 | 14 |  |  | 0 | 0% | 1900-01-01 | 1900-01-26 | 0 | 0% | 1900-01-26 | 1900-02-15 | 0 | 0% | 1900-02-05 | 1900-02-25 | 0 | 0% | 0 | 1 | Tower Foundation | EXC | Nos | 14 | 14 | 0 | 14
2 | Power Transformer | Nos | 15% | 0% | 2 | 2 |  |  | 0 | 0% | 0 | 1900-01-05 | 0 | 0% | 1900-01-15 | 1900-01-25 | 0 | 0% | 1900-01-26 | 1900-02-20 | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 14
3 | LM Tower | Nos | 1% | 0% | 1 | 1 |  |  | 0 | 0% | 1899-12-31 | 1900-01-01 | 0 | 0% | 1900-02-16 | 1900-02-19 | 0 | 0% | 1900-02-21 | 1900-02-25 | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 14
4 | LA | Nos | 2% | 0% | 3 | 3 |  |  | 0 | 0% | 0 | 1899-12-31 | 0 | 0% | 1900-01-01 | 1900-01-03 | 0 | 0% | 1900-01-04 | 1900-01-08 | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 14
5 | HLA | Nos | 1% | 0% | 6 | 6 |  |  | 0 | 0% | 0 | 1899-12-31 | 0 | 0% | 1900-01-01 | 1900-01-02 | 0 | 0% | 1900-01-03 | 1900-01-06 | 0 | 0% | 0 | 2 | Power Transformer | EXC | Nos | 2 | 2 | 0 | 2
6 | CB | Nos | 4% | 0% | 12 | 12 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 2
7 | Wave Trap | Nos | 1% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 2
8 | LINE CVT | Nos | 2% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 2
9 | BUS CVT | Nos | 4% | 0% | 6 | 6 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 3 | LM Tower | EXC | Nos | 1 | 1 | 0 | 1
10 | MCVT | Nos | 1% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 1
11 | HCT | Nos | 4% | 0% | 12 | 12 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 1
12 | MCT | Nos | 1% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 1
13 | ISO with ES | Nos | 4% | 0% | 18 | 18 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 4 | LA | EXC | Nos | 3 | 3 | 0 | 3
14 | ISO | Nos | 8% | 0% | 42 | 42 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 3
15 | Isolator-T | Nos | 2% | 0% | 18 | 18 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 3
16 | HBPI | Nos | 3% | 0% | 6 | 6 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 3
17 | BPI | Nos | 8% | 0% | 17 | 17 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 5 | HLA | EXC | Nos | 6 | 6 | 0 | 6
18 | Aux Trafo | Nos | 1% | 0% | 2 | 2 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 6
19 | BMK | Nos | 2% | 0% | 4 | 4 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 6
20 | NIFPS | Nos | 2% | 0% | 2 | 2 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 6
21 | BOT Oil Pit | Nos | 2% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 6 | CB | EXC | Nos | 12 | 12 | 0 | 12
22 | Cable Trench | mtr | 5% | 0% | 315 | 315 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 12
23 | Rain Water Drain | Mtr | 0.5% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 12
24 | Fencing | Nos | 1% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% | [8 empty] | 0 |  |  | Column |  |  |  | 0 | 12
25 | Road | Ls | 6% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 7 | Wave Trap | EXC | Nos | 3 | 3 | 0 | 3
26 | Gravel Filling | Ls | 4% | 0% | 0 | 1
Total |  |  | 99.5% | 0% | 152 | 152 | 0 | 0 | 0 | 0% | 0 | 1900-01-26 | 0 | 0% | 1900-01-01 | 1900-02-19 | 0 | 0% | 1900-01-03 | 1900-02-25 | 0 | 0% |  |  |  | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 8 | Line-CVT | EXC | Nos | 3 | 3 | 0 | 3
[26 empty] | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 9 | BUS CVT | EXC | Nos | 6 | 6 | 0 | 6
[26 empty] | PCC |  |  |  | 0 | 6
[26 empty] | Raft |  |  |  | 0 | 6
[26 empty] | Column |  |  |  | 0 | 6
[24 empty] | 10 | MCVT | EXC | Nos | 3 | 3 | 0 | 3
[26 empty] | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 11 | HCT | EXC | Nos | 12 | 12 | 0 | 12
[26 empty] | PCC |  |  |  | 0 | 12
[26 empty] | Raft |  |  |  | 0 | 12
[26 empty] | Column |  |  |  | 0 | 12
[24 empty] | 12 | MCT | EXC | Nos | 3 | 3 | 0 | 3
[26 empty] | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 13 | ISO with ES | EXC | Nos | 18 | 18 | 0 | 18
[26 empty] | PCC |  |  |  | 0 | 18
[26 empty] | Raft |  |  |  | 0 | 18
[26 empty] | Column |  |  |  | 0 | 18
[24 empty] | 14 | ISO | EXC | Nos | 42 | 42 | 0 | 42
[26 empty] | PCC |  |  |  | 0 | 42
[26 empty] | Raft |  |  |  | 0 | 42
[26 empty] | Column |  |  |  | 0 | 42
[24 empty] | 15 | ISO -T | EXC | Nos | 18 | 18 | 0 | 18
[26 empty] | PCC |  |  |  | 0 | 18
[26 empty] | Raft |  |  |  | 0 | 18
[26 empty] | Column |  |  |  | 0 | 18
[24 empty] | 16 | HBPI | EXC | Nos | 6 | 6 | 0 | 6
[26 empty] | PCC |  |  |  | 0 | 6
[26 empty] | Raft |  |  |  | 0 | 6
[26 empty] | Column |  |  |  | 0 | 6
[24 empty] | 17 | BPI | EXC | Nos | 17 | 17 | 0 | 17
[26 empty] | PCC |  |  |  | 0 | 17
[26 empty] | Raft |  |  |  | 0 | 17
[26 empty] | Column |  |  |  | 0 | 17
[24 empty] | 18 | Aux Trafo | EXC | Nos | 2 | 2 | 0 | 2
[26 empty] | PCC |  |  |  | 0 | 2
[26 empty] | Raft |  |  |  | 0 | 2
[26 empty] | Column |  |  |  | 0 | 2
[24 empty] | 19 | BMK | EXC | Nos | 4 | 4 | 0 | 4
[26 empty] | PCC |  |  |  | 0 | 4
[26 empty] | Raft |  |  |  | 0 | 4
[26 empty] | Column |  |  |  | 0 | 4
[24 empty] | 20 | NIFPS | EXC | Nos | 2 | 2 | 0 | 2
[26 empty] | PCC |  |  |  | 0 | 2
[26 empty] | Raft |  |  |  | 0 | 2
[26 empty] | Column |  |  |  | 0 | 2
[24 empty] | 21 | BOT Oil Pit | EXC | Nos | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Wall |  |  |  | 0 | 1
[24 empty] | 22 | Cable Trench | EXC | Mtr | 315 | 315 | 0 | 315
[26 empty] | PCC |  |  |  | 0 | 315
[26 empty] | Raft |  |  |  | 0 | 315
[26 empty] | Wall |  |  |  | 0 | 315
[24 empty] | 23 | Rain Water Drain | EXC | LS | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Column |  |  |  | 0 | 1
[24 empty] | 24 | Fencing | EXC | LS | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Column |  |  |  | 0 | 1
[24 empty] | 25 | Road | EXC | LS | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Column |  |  |  | 0 | 1
[24 empty] | TOTAL |  |  |  | 496 | 496
Formulas:
PCC = [Excavation]+2
PCC = MIN(M4:[PCC, row above])
Raft Foundation = [PCC]+25
Column casting/J-bolt fixing = [Raft Foundation]+10
Excavation = MIN(I4:[Excavation, row above])

## SY ELE
Electrical Progress | [13 empty] | DAILY PROGRESS
Sr.no. | Description | UOM | Scope | Progress | Balance | % Progress | BaseLine Plan |  |  | Forecast |  |  | Remarks | Cummulative | time axis 2024-12-01 to 2025-05-31
[7 empty] | Start Date | Finish Date | Days | Start Date | Finish Date | Days
MCR | [5 empty] | 0% | 2024-03-11 | 2025-06-30 |  | 2024-03-11 | 2025-06-30
| Panel Installation | No's | 44 | 0 | 44 | 0% | 2024-03-11 | 2025-04-04 | 389 | 2024-03-11 | 2025-04-04 | 389
1 | 33KV HT & Bus Bar Panel | Set | 4 | 0 | 4 | 0% | 2025-03-20 | 2025-04-04 | 15 | 2025-03-20 | 2025-04-04 | 15 |  | 0
2 | C&R Panel | No's | 7 | 0 | 7 | 0% | 2024-03-11 | 2024-03-21 | 10 | 2024-03-11 | 2024-03-21 | 10 |  | 0
3 | Busbar Panel | No's | 1 | 0 | 1 | 0% | 2025-03-20 | 2025-03-22 | 2 | 2025-03-20 | 2025-03-22 | 2
4 | PPC | No's | 1 | 0 | 1 | 0% | 2024-03-13 | 2024-03-14 | 1 | 2024-03-13 | 2024-03-14 | 1 |  | 0
5 | MU PLC 2 | No's | 2 | 0 | 2 | 0% | 2024-03-15 | 2024-03-17 | 2 | 2024-03-15 | 2024-03-17 | 2 |  | 0
6 | Fote Panel | No's | 1 | 0 | 1 | 0% | 2024-03-18 | 2024-03-21 | 3 | 2024-03-18 | 2024-03-21 | 3 |  | 0
7 | CCTV Panel | No's | 1 | 0 | 1 | 0% | 2024-03-22 | 2024-03-24 | 2 | 2024-03-22 | 2024-03-24 | 2 |  | 0
8 | PLCC Panel | No's | 1 | 0 | 1 | 0% | 2024-03-25 | 2024-03-27 | 2 | 2024-03-25 | 2024-03-27 | 2 |  | 0
9 | RTCC Panel | No's | 2 | 0 | 2 | 0% | 2024-03-28 | 2024-03-30 | 2 | 2024-03-28 | 2024-03-30 | 2 |  | 0
10 | PLC/Scada | No's | 1 | 0 | 1 | 0% | 2024-03-31 | 2024-04-06 | 6 | 2024-03-31 | 2024-04-06 | 6
11 | SAS Panel | No's | 1 | 0 | 1 | 0% | 2024-03-31 | 2024-04-02 | 2 | 2024-03-31 | 2024-04-02 | 2 |  | 0
12 | ACDB | No's | 1 | 0 | 1 | 0% | 2024-04-03 | 2024-04-06 | 3 | 2024-04-03 | 2024-04-06 | 3 |  | 0
13 | Lighting DB | No's | 1 | 0 | 1 | 0% | 2024-04-07 | 2024-04-08 | 1 | 2024-04-07 | 2024-04-08 | 1 |  | 0
14 | ELDB | No's | 1 | 0 | 1 | 0% | 2024-04-08 | 2024-04-09 | 1 | 2024-04-08 | 2024-04-09 | 1
15 | UPS | No's | 2 | 0 | 2 | 0% | 2024-04-09 | 2024-04-14 | 5 | 2024-04-09 | 2024-04-14 | 5 |  | 0
16 | UPS DB | No's | 1 | 0 | 1 | 0% | 2024-04-10 | 2024-04-11 | 1 | 2024-04-10 | 2024-04-11 | 1 |  | 0
17 | UPS Battery | Set | 4 | 0 | 4 | 0% | 2024-04-11 | 2024-04-12 | 1 | 2024-04-11 | 2024-04-12 | 1
18 | Battery Charger & DCDB (220V) | No's | 2 | 0 | 2 | 0% | 2024-04-12 | 2024-04-14 | 2 | 2024-04-12 | 2024-04-14 | 2 |  | 0
19 | Battery Bank (220V) | No's | 2 | 0 | 2 | 0% | 2024-04-13 | 2024-04-17 | 4 | 2024-04-13 | 2024-04-17 | 4
20 | Battery Charger (48V) & DCDB | No's | 2 | 0 | 2 | 0% | 2024-04-14 | 2024-04-16 | 2 | 2024-04-14 | 2024-04-16 | 2 |  | 0
21 | Battery Bank (48V) | Set | 2 | 0 | 2 | 0% | 2024-04-15 | 2024-04-17 | 2 | 2024-04-15 | 2024-04-17 | 2 |  | 0
22 | NIFPS CP | No's | 2 | 0 | 2 | 0% | 2024-04-16 | 2024-04-17 | 1 | 2024-04-16 | 2024-04-17 | 1 |  | 0
23 | PC with Table | Lot | 1 | 0 | 1 | 0% | 2024-04-17 | 2024-04-19 | 2 | 2024-04-17 | 2024-04-19 | 2 |  | 0
24 | Illumination | Lot | 1 | 0 | 1 | 0% | 2024-04-18 | 2024-04-23 | 5 | 2024-04-18 | 2024-04-23 | 5 |  | 0
SW Electrical Works
| SW Earthing works |  | 3252.375 | 0 | 3252.375 | 0% | 2025-03-22 | 2025-04-27 | 36 | 2025-03-22 | 2025-05-21 | 60
1 | Excavation for Grid Earth Mat | Mtr | 7500 | 0 | 7500 | 0% | 2025-03-22 | 2025-03-28 | 6 | 2025-03-22 | 2025-04-09 | 18 |  | 0
2 | Grid Earthing- MS Rod (32mm) | Mtr | 7500 | 0 | 7500 | 0% | 2025-03-24 | 2025-04-01 | 8 | 2025-03-24 | 2025-04-13 | 20 |  | 0
3 | 75*12mm GI Flat for equiment earthing | Mtr | 2500 | 0 | 2500 | 0% | 2025-03-27 | 2025-04-04 | 8 | 2025-03-28 | 2025-04-12 | 15
4 | 50*6 mm GI Flat for equipment & fencing | Mtr | 900 | 0 | 900 | 0% | 2025-04-05 | 2025-04-20 | 15 | 2025-04-12 | 2025-04-16 | 4
5 | Aux Mat | Nos | 34 | 0 | 34 | 0% | 2025-04-02 | 2025-04-08 | 6 | 2025-04-19 | 2025-04-27 | 8 |  | 0
7 | Backfilling | Mtr | 7500 | 0 | 7500 | 0% | 2025-04-08 | 2025-04-23 | 15 | 2025-04-28 | 2025-05-04 | 6 |  | 0
6 | Earthing Ms Rod | Nos | 60 | 0 | 60 | 0% | 2025-04-07 | 2025-04-22 | 15 | 2025-05-05 | 2025-05-13 | 8 |  | 0
8 | Earthing Pipe GI | Nos | 25 | 0 | 25 | 0% | 2025-04-13 | 2025-04-27 | 14 | 2025-05-13 | 2025-05-21 | 8 |  | 0
| SW Structural |  | 97 | 0 | 97 | 0% | 2025-03-01 | 2025-05-03 | 63 | 2025-03-16 | 2025-04-07 | 22
1 | Tower (T-1,2,4,5) | Nos | 14 | 0 | 14 | 0% | 2025-03-01 | 2025-03-31 | 30 | 2025-03-16 | 2025-04-01 | 16 |  | 0
2 | LM Tower | Nos | 1 | 0 | 1 | 0% | 2025-04-12 | 2025-04-15 | 3 | 2025-03-16 | 2025-04-01 | 16 |  | 0
3 | HLA | Nos | 6 | 0 | 6 | 0% | 2025-04-12 | 2025-04-19 | 7 | 2025-03-27 | 2025-03-27 | 0 |  | 0
4 | HL-BPI | Nos | 6 | 0 | 6 | 0% | 2025-04-16 | 2025-04-18 | 2 | 2025-03-28 | 2025-03-28 | 0 |  | 0
5 | CT | Nos | 12 | 0 | 12 | 0% | 2025-04-01 | 2025-04-11 | 10 | 2025-03-29 | 2025-03-29 | 0 |  | 0
6 | CB | Set | 4 | 0 | 4 | 0% | 2025-04-12 | 2025-04-17 | 5 | 2025-03-30 | 2025-03-30 | 0 |  | 0
7 | BPI | Nos | 17 | 0 | 17 | 0% | 2025-04-18 | 2025-04-23 | 5 | 2025-03-31 | 2025-03-31 | 0 |  | 0
8 | CVT | Nos | 9 | 0 | 9 | 0% | 2025-04-12 | 2025-04-15 | 3 | 2025-04-01 | 2025-04-01 | 0 |  | 0
9 | 3-Ph HDB Motorized Isolator with Single motorized ES ( 3-PH) | Set | 5 | 0 | 5 | 0% | 2025-04-16 | 2025-04-20 | 4 | 2025-04-02 | 2025-04-02 | 0
10 | 3-Ph HDB Motorized Isolator with Double motorized ES (3-Ph) | Set | 5 | 0 | 5 | 0% | 2025-04-21 | 2025-04-25 | 4 | 2025-04-03 | 2025-04-03 | 0
11 | 3-Ph HDB motorized tandem Isolator | Set | 3 | 0 | 3 | 0% | 2025-04-26 | 2025-04-28 | 2 | 2025-04-04 | 2025-04-04 | 0 |  | 0
12 | MCT | NOs | 3 | 0 | 3 | 0% | 2025-04-29 | 2025-05-01 | 2 | 2025-04-05 | 2025-04-05 | 0
13 | MCVT | NOs | 3 | 0 | 3 | 0% | 2025-05-02 | 2025-05-03 | 1 | 2025-04-06 | 2025-04-06 | 0
14 | Wave Trap | Nos | 2 | 0 | 2 | 0% | 2025-04-12 | 2025-04-15 | 3 | 2025-04-07 | 2025-04-07 | 0 |  | 0
15 | LA | Nos | 3 | 0 | 3 | 0% | 2025-04-16 | 2025-04-19 | 3 | 2025-04-07 | 2025-04-07 | 0 |  | 0
16 | NIFPS Panel, piping with Support structure | Lot | 2 | 0 | 2 | 0% | 2025-04-20 | 2025-04-23 | 3 | 2025-04-04 | 2025-04-04 | 0 |  | 0
17 | Clamp & Connector | Lot | 1 | 0 | 1 | 0% | 2025-04-24 | 2025-04-29 | 5 | 2025-04-07 | 2025-04-07 | 0 |  | 0
18 | Spacers fixing | Lot | 1 | 0 | 1 | 0% | 2025-04-27 | 2025-05-02 | 5 | 2025-04-07 | 2025-04-07 | 0
| Equipment Errection |  | 97 | 0 | 97 | 0% | 2025-01-15 | 2025-05-31 | 136 | 2025-03-10 | 2025-04-26 | 47
1 | Power Transformer | Nos | 2 | 0 | 2 | 0% | 2025-01-15 | 2025-01-30 | 15 | 2025-03-10 | 2025-03-12 | 2 |  | 0
2 | HLA along with Accessories | Nos | 6 | 0 | 6 | 0% | 2025-04-19 | 2025-04-29 | 10 | 2025-04-01 | 2025-04-02 | 1 |  | 0
3 | HL-BPI | Nos | 6 | 0 | 6 | 0% | 2025-04-18 | 2025-04-22 | 4 | 2025-04-02 | 2025-04-03 | 1 |  | 0
4 | CT | Nos | 12 | 0 | 12 | 0% | 2025-04-11 | 2025-04-21 | 10 | 2025-04-03 | 2025-04-05 | 2 |  | 0
5 | CB (3-PH) | Set | 4 | 0 | 4 | 0% | 2025-04-17 | 2025-04-25 | 8 | 2025-04-05 | 2025-04-06 | 1 |  | 0
6 | BPI | Nos | 17 | 0 | 17 | 0% | 2025-04-26 | 2025-05-11 | 15 | 2025-04-06 | 2025-04-08 | 2 |  | 0
7 | CVT | Nos | 9 | 0 | 9 | 0% | 2025-04-15 | 2025-04-23 | 8 | 2025-04-08 | 2025-04-09 | 1 |  | 0
8 | 3-Ph HDB Motorized Isolator with Single motorized ES ( 3-PH) | Set | 5 | 0 | 5 | 0% | 2025-04-20 | 2025-05-05 | 15 | 2025-04-09 | 2025-04-11 | 2 |  | 0
9 | 3-Ph HDB Motorized Isolator with Double motorized ES (3-Ph) | Set | 5 | 0 | 5 | 0% | 2025-04-23 | 2025-05-08 | 15 | 2025-04-11 | 2025-04-14 | 3 |  | 0
10 | 3-Ph HDB motorized tandem Isolator | Set | 3 | 0 | 3 | 0% | 2025-04-24 | 2025-05-04 | 10 | 2025-04-14 | 2025-04-16 | 2 |  | 0
11 | MCT | Nos | 3 | 0 | 2 | 0% | 2025-05-01 | 2025-05-03 | 2 | 2025-04-16 | 2025-04-17 | 1 |  | 0
12 | MCVT | Nos | 3 | 0 | 3 | 0% | 2025-05-04 | 2025-05-08 | 4 | 2025-04-17 | 2025-04-18 | 1 |  | 0
13 | Wave Trap | Nos | 2 | 0 | 2 | 0% | 2025-04-16 | 2025-04-20 | 4 | 2025-04-18 | 2025-04-19 | 1 |  | 0
14 | LA | Nos | 3 | 0 | 3 | 0% | 2025-04-24 | 2025-04-28 | 4 | 2025-04-19 | 2025-04-21 | 2 |  | 0
15 | Aux Traffo | Nos | 2 | 0 | 2 | 0% | 2025-03-02 | 2025-03-04 | 2 | 2025-04-10 | 2025-04-15 | 5 |  | 0
16 | BMK | Nos | 4 | 0 | 4 | 0% | 2025-04-30 | 2025-05-04 | 4 | 2025-04-20 | 2025-04-26 | 6 |  | 0
17 | CT JB | Nos | 4 | 0 | 4 | 0% | 2025-05-06 | 2025-05-08 | 2 | 2025-04-20 | 2025-04-26 | 6 |  | 0
18 | CVT JB | Nos | 3 | 0 | 3 | 0% | 2025-05-09 | 2025-05-11 | 2 | 2025-04-20 | 2025-04-26 | 6 |  | 0
20 | Capacitor Bank ( SVG) | Lot | 2 | 0 | 2 | 0% | 2025-05-11 | 2025-05-19 | 8 | 2025-04-20 | 2025-04-26 | 6 |  | 0
21 | Metering Cubical | Nos | 1 | 0 | 1 | 0% | 2025-05-27 | 2025-05-31 | 4 | 2025-04-20 | 2025-04-26 | 6 |  | 0
22 | Yard illumination along with Accessories | Lot | 1 | 0 | 1 | 0% | 2025-05-15 | 2025-05-23 | 8 | 2025-04-20 | 2025-04-26 | 6 |  | 0
| Stringing, IPS Tubing & Cable tray |  | 1 | 0 | 1 | 0% | 2025-02-01 | 2025-05-28 | 116 | 2025-04-27 | 2025-05-13 | 16 |  | 0
1 | Clamp & connector | Lot | 1 | 0 | 1 | 0% | 2025-04-28 | 2025-05-13 | 15 | 2025-04-28 | 2025-05-02 | 4 |  | 0
2 | 4" IPS Al Tube installation | Lot | 1 | 0 | 1 | 0% | 2025-05-27 | 2025-05-28 | 1 | 2025-05-03 | 2025-05-05 | 2 |  | 0
3 | TWIN AL-59 Moose conductor ( Jumper) | Lot | 1 | 0 | 1 | 0% | 2025-04-28 | 2025-05-03 | 5 | 2025-05-06 | 2025-05-08 | 2 |  | 0
4 | Spacers | Lot | 1 | 0 | 1 | 0% | 2025-02-01 | 2025-03-01 | 28 | 2025-05-09 | 2025-05-11 | 2 |  | 0
5 | Sheild wire Support Cleat with tower | Lot | 1 | 0 | 1 | 0% | 2025-05-04 | 2025-05-08 | 4 | 2025-05-12 | 2025-05-13 | 1 |  | 0
6 | HDPE Pipe laying in switchyard | Lot | 1 | 0 | 1 | 0% | 2025-03-01 | 2025-03-08 | 7 | 2025-04-27 | 2025-04-30 | 3 |  | 0
7 | Cable Tray installation with support in switchyard | Lot | 1 | 0 | 1 | 0% | 2025-03-09 | 2025-03-16 | 7 | 2025-05-01 | 2025-05-05 | 4 |  | 0
8 | Cable Tray installation with support in MCR | Lot | 1 | 0 | 1 | 0% | 2025-03-01 | 2025-03-06 | 5 | 2025-05-06 | 2025-05-10 | 4 |  | 0
| SW cable laying & Termination |  | 1 | 0 | 1 | 0% | 2025-02-07 | 2025-05-22 | 104 | 2025-05-02 | 2025-05-17 | 15 |  | 0
1 | 33KV HT Cable laying ( Outgoing HT Switchgear to PTR) | Lot | 1 | 0 | 1 | 0% | 2025-02-07 | 2025-02-17 | 10 | 2025-05-02 | 2025-05-06 | 10 |  | 0
2 | LT Power cable Laying | Lot | 1 | 0 | 1 | 0% | 2025-02-25 | 2025-03-12 | 15 | 2025-05-04 | 2025-05-08 | 15 |  | 0
3 | Control cable laying | Lot | 1 | 0 | 1 | 0% | 2025-03-15 | 2025-03-25 | 10 | 2025-05-05 | 2025-05-09 | 10 |  | 0
4 | Communication cable laying | Lot | 1 | 0 | 1 | 0% | 2025-04-04 | 2025-04-09 | 5 | 2025-05-05 | 2025-05-09 | 5 |  | 0
5 | Glanding | Lot | 1 | 0 | 1 | 0% | 2025-04-29 | 2025-05-04 | 5 | 2025-05-09 | 2025-05-13 | 5 |  | 0
6 | Termination | Lot | 1 | 0 | 1 | 0% | 2025-05-12 | 2025-05-22 | 10 | 2025-05-13 | 2025-05-17 | 10 |  | 0
| Earthing |  | 52 | 0 | 52 | 0% | 2025-03-02 | 2025-04-02 | 31 | 2025-04-10 | 2025-04-26 | 16 |  | 0
1 | Drilling | Nos | 52 | 0 | 52 | 0% | 2025-03-02 | 2025-03-27 | 25 | 2025-04-10 | 2025-04-18 | 8 |  | 0
2 | Rod installtion | Nos | 52 | 0 | 52 | 0% | 2025-03-07 | 2025-04-01 | 25 | 2025-04-14 | 2025-04-22 | 8 |  | 0
3 | Pit Connection | Nos | 52 | 0 | 52 | 0% | 2025-03-08 | 2025-04-02 | 25 | 2025-04-22 | 2025-04-26 | 4 |  | 0
| Commissioning |  | 1 | 0 | 1 | 0% | 2025-04-04 | 2025-06-30 | 87 | 2025-04-27 | 2025-06-30 | 64 |  | 0
1 | Switchyard equipment Testing | Lot | 1 | 0 | 1 | 0% | 2025-05-25 | 2025-06-14 | 20 | 2025-04-27 | 2025-05-01 | 4 |  | 0
2 | MCR Equipment Testing | Lot | 1 | 0 | 1 | 0% | 2025-04-04 | 2025-04-29 | 25 | 2025-05-01 | 2025-05-09 | 8 |  | 0
3 | Schematic digram and green lining of all equipment and panel | Lot | 1 | 0 | 1 | 0% | 2025-06-02 | 2025-06-10 | 8 | 2025-05-09 | 2025-05-17 | 8 |  | 0
4 | Relay testing | Lot | 1 | 0 | 1 | 0% | 2025-06-10 | 2025-06-18 | 8 | 2025-05-10 | 2025-06-04 | 25 |  | 0
5 | Stability test | Lot | 1 | 0 | 1 | 0% | 2025-06-14 | 2025-06-22 | 8 | 2025-05-10 | 2025-06-04 | 25 |  | 0
6 | Final cleaning of all equipment & boxup | Lot | 1 | 0 | 1 | 0% | 2025-06-21 | 2025-06-23 | 2 | 2025-05-10 | 2025-06-04 | 25 |  | 0
7 | Equipment tesiling work ( Nomenclature) | Lot | 1 | 0 | 1 | 0% | 2025-05-27 | 2025-06-04 | 8 | 2025-05-27 | 2025-06-04 | 8 |  | 0
8 | Saftey Items Installation | Lot | 1 | 0 | 1 | 0% | 2025-05-25 | 2025-06-02 | 8 | 2025-05-25 | 2025-06-02 | 8 |  | 0
9 | CEIG visit | Lot | 1 | 0 | 1 | 0% | 2025-06-03 | 2025-06-05 | 2 | 2025-06-03 | 2025-06-05 | 2 |  | 0
10 | Phase sequence meter Configuration | Lot | 1 | 0 | 1 | 0% | 2025-06-22 | 2025-06-25 | 3 | 2025-06-22 | 2025-06-25 | 3 |  | 0
11 | Scada Commissioning | Lot | 1 | 0 | 1 | 0% | 2025-06-26 | 2025-06-28 | 2 | 2025-06-26 | 2025-06-28 | 2 |  | 0
12 | Final Commissioning | Lot | 1 | 0 | 1 | 0% | 2025-06-29 | 2025-06-30 | 1 | 2025-06-29 | 2025-06-30 | 1 |  | 0
Formulas:
Start Date = MIN([Start Date, row below],I32,I41,I60,I82,I91,I98,I102)
Start Date = MIN([Start Date, row below]:I30)
Finish Date = MAX([Finish Date, row below],J32,J41,J60,J82,J91,J98,J102)
Finish Date = MAX([Finish Date, row below]:J30)

## Cont Piling
S.no. | Contractor | Activity | Scope | Progress | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31
A) |  | Marking |  | 4050 | 80 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 220 | 0 | 0 | 0 | 0 | 120 | 90 | 70 | 120 | 0 | 220 | 0 | 0 | 250 | 0 | 200 | 90 | 200 | 180 | 80 | 260 | 220 | 0 | 0 | 0 | 0 | 220 | 0 | 200 | 220 | 100 | 0 | 200 | 200 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Auguring |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DTH |  | 4011 | 60 | 60 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 109 | 0 | 53 | 70 | 50 | 90 | 80 | 0 | 120 | 105 | 70 | 110 | 0 | 120 | 0 | 60 | 90 | 200 | 110 | 124 | 150 | 120 | 130 | 150 | 150 | 140 | 0 | 0 | 0 | 210 | 0 | 190 | 250 | 0 | 250 | 100 | 100 | 100 | 100 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Casting |  | 3983 | 18 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 29 | 0 | 0 | 31 | 102 | 0 | 112 | 48 | 27 | 103 | 26 | 0 | 108 | 130 | 60 | 79 | 74 | 24 | 80 | 53 | 85 | 124 | 151 | 157 | 188 | 62 | 124 | 126 | 123 | 149 | 0 | 0 | 81 | 120 | 0 | 216 | 224 | 31 | 61 | 129 | 91 | 25 | 64 | 65 | 58 | 66 | 93 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 39 | 0 | 0 | 0 | 0 | 0 | 0
B) |  | Marking |  | 5886 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 232 | 0 | 0 | 0 | 30 | 0 | 28 | 60 | 110 | 0 | 190 | 0 | 76 | 0 | 230 | 0 | 0 | 210 | 250 | 100 | 0 | 0 | 0 | 150 | 200 | 210 | 130 | 240 | 220 | 250 | 200 | 180 | 240 | 0 | 0 | 90 | 190 | 200 | 210 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 250 | 0 | 0 | 0
|  | Auguring |  | 538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 125 | 101 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 37
|  | DTH |  | 5187 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 40 | 0 | 0 | 101 | 134 | 65 | 0 | 0 | 70 | 31 | 0 | 60 | 40 | 0 | 65 | 90 | 120 | 110 | 0 | 120 | 0 | 90 | 210 | 190 | 100 | 0 | 0 | 0 | 204 | 180 | 190 | 150 | 220 | 260 | 180 | 120 | 140 | 210 | 0 | 0 | 200 | 160 | 230 | 160 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 120 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 0 | 0
|  | Casting |  | 5615 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 46 | 0 | 78 | 77 | 143 | 93 | 0 | 0 | 31 | 61 | 0 | 29 | 57 | 25 | 86 | 80 | 60 | 110 | 25 | 30 | 71 | 118 | 202 | 141 | 123 | 0 | 0 | 27 | 145 | 150 | 190 | 191 | 181 | 208 | 243 | 186 | 125 | 95 | 145 | 0 | 189 | 180 | 210 | 208 | 119 | 125 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 106 | 90 | 114 | 90 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 81 | 90 | 90
C) |  | Marking |  | 6845 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 100 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 220 | 75 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 220 | 140 | 120 | 0 | 300 | 0 | 250 | 220 | 290 | 300 | 300 | 300 | 110 | 140 | 160 | 220 | 259 | 110 | 110 | 120 | 160 | 0 | 0 | 200 | 100 | 100 | 206 | 110 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 100 | 35 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 120 | 0
|  | Auguring |  | 763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 0 | 0 | 130 | 100 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 110 | 0
|  | DTH |  | 5698 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 80 | 0 | 20 | 55 | 45 | 70 | 0 | 0 | 60 | 40 | 0 | 20 | 50 | 0 | 45 | 70 | 0 | 120 | 216 | 120 | 90 | 180 | 160 | 190 | 210 | 250 | 250 | 250 | 249 | 260 | 0 | 200 | 160 | 260 | 190 | 100 | 130 | 180 | 200 | 0 | 0 | 120 | 150 | 180 | 80 | 80 | 25 | 25 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 100 | 100 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Casting |  | 6485 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 20 | 0 | 73 | 46 | 52 | 60 | 0 | 0 | 31 | 59 | 0 | 59 | 27 | 0 | 60 | 61 | 57 | 117 | 152 | 124 | 180 | 156 | 154 | 186 | 213 | 248 | 214 | 250 | 308 | 235 | 95 | 122 | 147 | 240 | 175 | 120 | 90 | 120 | 145 | 0 | 120 | 166 | 125 | 166 | 53 | 35 | 28 | 116 | 91 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 89 | 86 | 87 | 60 | 90 | 110 | 93 | 0 | 91 | 0 | 80 | 29 | 55 | 30 | 29 | 0 | 0 | 0 | 30 | 0 | 60 | 12
D) |  | Marking |  | 873 | [34 empty] | 100 | 0 | 0 | 0 | 230 | 0 | 0 | 0 | 0 | 200 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Auguring |  | 0 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DTH |  | 943 | [34 empty] | 50 | 40 | 50 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 250 | 220 | 0 | 0 | 0 | 0 | 33 | 70 | 70 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Casting |  | 873 | [34 empty] | 27 | 27 | 58 | 0 | 0 | 60 | 60 | 61 | 60 | 61 | 60 | 60 | 0 | 88 | 60 | 55 | 56 | 29 | 30 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 27000
| Balance | 27000

## AC Progress
S.No. | AC Work | UOM | Total | [5 empty] | Base Line Plan |  |  | Forecast
Cumulative
|  |  | Scope | Waitage | Today | Cum. | Balance | % | Start Date | Finish Date | Days | Start Date | Finish Date | Days
1 | AC Trench | Mtr | 26043.8846 | 12% | 0 | 0 | 26043.8846 | 0% |  |  | 0 |  |  | 0
2 | 3CX240sqmm Cable Laying | Mtr | 18269.2308 | 3% | 0 | 0 | 18269.2308 | 0% |  |  | 0 |  |  | 0
3 | 3CX400sqmm Cable Laying | Mtr | 58461.5385 | 7% | 0 | 0 | 58461.5385 | 0% |  |  | 0 |  |  | 107
4 | 1CX400sqmm Cable Laying | LS | 38 | 10% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
5 | OFC Cable Laying | LS | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
6 | Grid Earthing | mtr | 7600 | 8% | 0 | 0 | 7600 | 0% |  |  | 0 |  |  | 0
7 | Tray support casting | No's | 38 | 0% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
8 | Tray from INV to LV Side | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
9 | Earthpit Installation | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
10 | IDT Erection | No's | 38 | 15% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
11 | ICOG Panel | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
12 | LT Panel | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
13 | UPS Panel | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
14 | Aux Trafo | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
15 | 1C*400Sqmm cable Termination | Sets | 38 | 10% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
|  |  |  | 100% |  |  |  | 0%
Description |  |  | AC Trench |  |  |  |  | 3CX240sqmm Cable Laying |  |  |  |  | 1CX400sqmm Cable Laying |  |  |  |  | 3CX400sqmm Cable Laying |  |  |  |  | OFC Cable Laying |  |  |  |  | Grid Earthing |  |  |  |  | Tray support casting |  |  |  |  | Tray from INV to LV Side |  |  |  |  | Earthpit Installation |  |  |  |  | IDT Erection |  |  |  |  | ICOG Panel |  |  |  |  | LT Panel |  |  |  |  | UPS Panel |  |  |  |  | Aux Trafo |  |  |  |  | 1C*400Sqmm cable Termination
Sr. No. | Contractor Name | ICR No. | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | %
| Total |  | 26043.8846 | 0 | 0 | 0 | 0% | 18269.2308 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 58461.5385 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 7600 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 34 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0%
1 |  | Icr-a |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
2 |  | Icr-b |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
3 |  | Icr-c |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
4 |  | Icr-e |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
5 |  | Icr-5 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
6 |  | Icr-6 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
7 |  | Icr-7 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
8 |  | Icr-8 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
9 |  | Icr-9 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
10 |  | Icr-10 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
11 |  | Icr-11 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
12 |  | Icr-12 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
13 |  | Icr-13 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
14 |  | Icr-14 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
15 |  | Icr-15 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
16 |  | Icr-16 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
17 |  | Icr-17 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
18 |  | Icr-18 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
19 |  | Icr-19 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
20 |  | Icr-20 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
21 |  | Icr-21 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
22 |  | Icr-22 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
23 |  | Icr-23 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
24 |  | Icr-24 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
25 |  | Icr-25 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
26 |  | Icr-26 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
27 |  | Icr-27 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
28 |  | Icr-28 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
29 |  | Icr-29 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
30 |  | Icr-30 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
31 |  | Icr-31 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
32 |  | Icr-32 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
33 |  | Icr-33 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
34 |  | Icr-34 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0

## DC Progress
S.No. | DC Work | UOM | Total |  |  |  |  | Base Line Plan |  |  | Forecast
|  |  | Scope | Today | Cum. | Balance | % | Start Date | Finish Date | Days | Start Date | Finish Date | Days
1 | Trench Excavation | Mtr | 171000 | 250 | 950 | 170050 | 0.5556% |  |  | 0 |  |  | 0
2 | 400Sqmm Cable laying (SCB's) | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
3 | Inverter Installation | No's | 76 | 0 | 0 | 76 | 0% |  |  | 0 |  |  | 0
4 | 400 Sqmm cable laying | mtr | 638400 | 0 | 0 | 638400 | 0% |  |  | 0 |  |  | 0
5 | SCB Stand Casting | No's | 3648 | 0 | 0 | 3648 | 0% |  |  | 0 |  |  | 0
6 | SCB Installation | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
7 | 6 Sqmm Laying(SCB's) | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
8 | Termination SCB End | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
9 | Termination Inv End | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
10 | Earthing Conductor Laying | Mtr | 95000 | 0 | 0 | 95000 | 0% |  |  | 0 |  |  | 0
11 | Earthpit Installation | No's | 912 | 0 | 0 | 912 | 0% |  |  | 0 |  |  | 0
12 | String Cable termination | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
13 | LA Installation | No's | 190 | 0 | 0 | 190 | 0% |  |  | 0 |  |  | 0
14 | LA Connection | No's | 190 | 0 | 0 | 190 | 0% |  |  | 0 |  |  | 0
15 | MMS Installation(Full+Half+Dummy) | No's | 14592 | 0 | 0 | 14592 | 0% |  |  | 0 |  |  | 0
16 | Module Mounting | No's | 846336 | 0 | 0 | 846336 | 0% |  |  | 0 |  |  | 0
0.03472%
Description |  |  | Trench Excavation |  |  |  |  | 400Sqmm Cable laying (SCB's) |  |  |  |  | Inverter Installation |  |  |  |  | SCB Stand Casting |  |  |  |  | SCB Installation |  |  |  |  | 6 Sqmm Laying(SCB's) |  |  |  |  | Termination SCB End |  |  |  |  | 400 Sqmm cable laying |  |  |  |  | Termination Inv End |  |  |  |  | Earthing Conductor Laying |  |  |  |  | Earthpit Installation |  |  |  |  | String Cable termination |  |  |  |  | LA Installation |  |  |  |  | LA Connection |  |  |  |  | MMS Installation(Full+Half+Dummy) |  |  |  |  | Module Mounting
Sr. No. | Contractor Name | ICR No. | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | %
| Total |  | 171000 | 250 | 950 | 3550 | 0.5556% | 1824 | 0 | 0 | 0 | 0% | 76 | 0 | 0 | 0 | 0% | 3648 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 638400 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 95000 | 0 | 0 | 0 | 0% | 912 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 190 | 0 | 0 | 0 | 0% | 190 | 0 | 0 | 0 | 0% | 14592 | 0 | 0 | 0 | 0% | 846336 | 0 | 0 | 0 | 0%
1 |  | Icr-1
B | Shree Krishna Enterprises | Icr-2 | 4500 | 250 | 950 | 3550 | 21.11%
3 |  | Icr-3
4 |  | Icr-4
5 |  | Icr-5
6 |  | Icr-6
7 |  | Icr-7
8 |  | Icr-8
9 |  | Icr-9
10 |  | Icr-10
11 |  | Icr-11
12 |  | Icr-12
13 |  | Icr-13
14 |  | Icr-14
15 |  | Icr-15
16 |  | Icr-16
17 |  | Icr-17
18 |  | Icr-18
19 |  | Icr-19
20 |  | Icr-20
21 |  | Icr-21
22 |  | Icr-22
23 |  | Icr-23
24 |  | Icr-24
25 |  | Icr-25
26 |  | Icr-26
27 |  | Icr-27
28 |  | Icr-28
29 |  | Icr-29
30 |  | Icr-30
31 |  | Icr-31
32 |  | Icr-32
33 |  | Icr-33
34 |  | Icr-34

## Daily tracker Work
S.No. | Activity | Work Description | UOM | Scope | Progress | Balance | % Progress | time axis 2025-04-01 to 2025-09-29
1 | DC WORK | Trench Excavation | Mtr | 171000 | 0 | 171000 | 0%
2 |  | 400Sqmm Cable laying (SCB's) | No's | 1824 | 0 | 1824 | 0%
3 |  | Inverter Installation | No's | 76 | 0 | 76 | 0%
4 |  | SCB Stand Casting | No's | 3648 | 0 | 3648 | 0%
5 |  | 400 Sqmm cable laying | mtr | 856800 | 0 | 856800 | 0%
6 |  | SCB Installation | No's | 1824 | 0 | 1824 | 0%
7 |  | 6 Sqmm Laying(SCB's) | No's | 1824 | 0 | 1824 | 0%
8 |  | Termination SCB End | No's | 1824 | 0 | 1824 | 0%
9 |  | Termination Inv End | No's | 1824 | 0 | 1824 | 0%
10 |  | Earthing Conductor Laying | Mtr | 95000 | 0 | 95000 | 0%
11 |  | Earthpit Installation | No's | 912 | 0 | 912 | 0%
12 |  | String Cable termination | No's | 1824 | 0 | 1824 | 0%
13 |  | LA Installation | No's | 190 | 0 | 190 | 0%
14 |  | LA Connection | No's | 190 | 0 | 190 | 0%
15 |  | MMS Installtion(Full+Half) | No's | 14592 | 0 | 14592 | 0%
16 |  | Module Mounting | No's | 846336 | 0 | 846336 | 0%
17 | AC Work | AC Trench Excavation | Mtr | 26043.8846 | 0 | 26043.8846 | 0%
18 |  | 3CX400/240sqmm Cable Laying | Mtr | 18269.2308 | 0 | 18269.2308 | 0%
19 |  | OFC Cable Laying | Mtr | 38 | 0 | 38 | 0%
20 |  | Grid Earthing | mtr | 10400 | 0 | 10400 | 0%
21 |  | Earthing Conductor Laying | Mtr | 38 | 0 | 38 | 0%
22 |  | Tray Support Casting | No's | 52 | 0 | 52 | 0%
23 |  | Tray from INV to LV Side | No's | 7600 | 0 | 7600 | 0%
24 |  | Earthpit Installation | No's | 38 | 0 | 38 | 0%
25 |  | IDT Erection | No's | 38 | 0 | 38 | 0%
26 |  | ICOG Panel | No's | 38 | 0 | 38 | 0%
27 |  | LT Panel | No's | 38 | 0 | 38 | 0%
28 |  | UPS & UPS DB | No's | 38 | 0 | 38 | 0%
29 |  | AUX Trafo | No's | 38 | 0 | 38 | 0%
30 |  | NIFPS panel installation | No's | 38 | 0 | 38 | 0%
31 |  | Termination | No's | 38 | 0 | 38 | 0%

## Bottleneck
Bottleneck
Engineering {E} | Procurement {P} | Construction {C}

## QC & HSE status
QC Status | [6 empty] | HSE Status
Department | Total FF | Closed | Open | Total NC | Closed | Open
Construction | 0 | 0 | 0 | 0 | 0 | 0
Engineering | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 0 | 0 | 0 | 0 | 0 | 0
97648

## Resources Status (hidden)
Sr. No. | Vendor name | Entity | Category | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25
Manpower | Total |  | 97648 | 6 | 6 | 8 | 9 | 12 | 12 | 15 | 17 | 19 | 19 | 17 | 25 | 25 | 25 | 33 | 32 | 33 | 43 | 43 | 37 | 35 | 50 | 54 | 52 | 51 | 55 | 58 | 48 | 63 | 75 | 69 | 69 | 68 | 70 | 66 | 64 | 67 | 24 | 74 | 75 | 75 | 75 | 66 | 74 | 80 | 80 | 83 | 84 | 82 | 73 | 77 | 78 | 75 | 81 | 90 | 89 | 94 | 91 | 92 | 92 | 111 | 104 | 87 | 101 | 101 | 91 | 96 | 93 | 108 | 115 | 118 | 104 | 121 | 122 | 136 | 133 | 137 | 132 | 140 | 137 | 112 | 113 | 120 | 120 | 120 | 120 | 119 | 120 | 134 | 134 | 93 | 103 | 118 | 131 | 129 | 125 | 131 | 130 | 133 | 128 | 127 | 127 | 130 | 130 | 130 | 111 | 95 | 101 | 57 | 14 | 71 | 77 | 83 | 95 | 116 | 121 | 120 | 120 | 134 | 138 | 144 | 145 | 134 | 132 | 96 | 108 | 86 | 122 | 123 | 136 | 136 | 116 | 123 | 135 | 140 | 124 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | O2 Power |  | Staff | 3 | 3 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 15 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
|  |  | Surveyor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Security | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 31
2 | Desert Infra | Energizent Power Pvt. Ltd | Staff | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 8 | 8 | 8 | 15 | 15 | 13 | 11 | 14 | 14 | 12 | 11 | 11 | 11 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 13 | 0 | 16 | 16 | 16 | 16 | 8 | 16 | 13 | 13 | 13 | 13 | 13 | 4 | 7 | 7 | 5 | 5 | 7 | 7 | 10 | 10 | 10 | 10 | 17 | 14 | 14 | 14 | 14 | 4 | 4 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 16 | 16 | 16 | 16 | 15 | 15 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 18 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 5 | 5 | 5 | 13 | 13 | 13 | 6 | 0 | 6 | 7 | 7 | 4 | 9 | 7 | 6 | 6 | 11 | 11 | 6 | 7 | 6 | 10 | 10 | 7 | 11 | 11 | 12 | 12 | 12 | 9 | 9 | 20 | 20 | 15 | 10
|  |  | Total | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 12 | 12 | 12 | 18 | 18 | 15 | 13 | 16 | 16 | 14 | 13 | 13 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 14 | 15 | 0 | 18 | 18 | 18 | 18 | 10 | 18 | 15 | 15 | 15 | 15 | 15 | 6 | 9 | 9 | 7 | 7 | 9 | 9 | 11 | 11 | 11 | 11 | 18 | 15 | 15 | 15 | 15 | 5 | 5 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 22 | 22 | 22 | 22 | 22 | 22 | 18 | 18 | 18 | 18 | 17 | 17 | 15 | 17 | 17 | 17 | 17 | 17 | 16 | 20 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 8 | 8 | 8 | 15 | 15 | 15 | 8 | 0 | 7 | 8 | 8 | 5 | 10 | 8 | 8 | 8 | 13 | 13 | 8 | 8 | 8 | 11 | 11 | 8 | 12 | 12 | 13 | 13 | 13 | 10 | 10 | 21 | 21 | 16 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Teq XVII Pvt. Ltd. | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 3 | 5 | 7 | 7 | 4 | 4 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 5
|  |  | Total | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 3 | 5 | 7 | 7 | 4 | 4 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Sanchiyay | Energizent Power Pvt. Ltd | Staff | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 10 | 9 | 9 | 9 | 9 | 9 | 13 | 13 | 9 | 9 | 8 | 9 | 9 | 10 | 13 | 13 | 4 | 13 | 13 | 8 | 8 | 7 | 7 | 2 | 5 | 7 | 0 | 12 | 12 | 12 | 12 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 22 | 20 | 20 | 20 | 20 | 20 | 20 | 17 | 17 | 17 | 17 | 16 | 16 | 16 | 26 | 20 | 12 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 6 | 0 | 0 | 2 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 4 | 4 | 8 | 10 | 8 | 8 | 4 | 4 | 4 | 4 | 9 | 9 | 11 | 11 | 11 | 11 | 11 | 12 | 12
|  |  | Total | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 12 | 12 | 12 | 12 | 11 | 11 | 15 | 15 | 11 | 11 | 10 | 12 | 12 | 13 | 16 | 15 | 6 | 15 | 16 | 11 | 11 | 9 | 9 | 4 | 7 | 9 | 0 | 14 | 15 | 15 | 15 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 23 | 23 | 23 | 23 | 23 | 23 | 20 | 20 | 20 | 20 | 19 | 19 | 19 | 29 | 23 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 12 | 12 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 12 | 12 | 12 | 14 | 14 | 14 | 14 | 14 | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 8 | 8 | 0 | 0 | 3 | 5 | 5 | 5 | 5 | 7 | 7 | 7 | 5 | 5 | 9 | 11 | 9 | 9 | 5 | 5 | 5 | 5 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | JCC | Energizent Power Pvt. Ltd | Staff | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 8 | 7 | 8 | 12 | 8 | 14 | 14 | 14 | 14 | 14 | 16 | 17 | 17 | 17 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 18 | 18 | 18 | 18 | 16 | 17 | 16 | 16 | 15 | 15 | 12 | 13 | 15 | 15 | 22 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 16 | 20 | 20 | 18 | 18 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 10 | 10 | 10 | 10 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 14 | 9 | 6 | 6 | 6 | 11 | 10 | 10 | 10 | 7 | 7 | 7 | 9 | 8 | 8 | 4 | 0 | 0 | 4 | 4 | 9 | 11 | 12 | 11 | 7 | 11 | 11 | 11 | 11 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 7 | 7 | 8 | 6
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7 | 9 | 9 | 8 | 9 | 13 | 9 | 15 | 16 | 15 | 15 | 16 | 18 | 19 | 19 | 19 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 21 | 21 | 21 | 21 | 19 | 20 | 19 | 19 | 18 | 18 | 15 | 16 | 18 | 18 | 25 | 22 | 22 | 22 | 22 | 22 | 22 | 9 | 19 | 23 | 23 | 21 | 21 | 17 | 17 | 17 | 16 | 16 | 16 | 16 | 13 | 13 | 13 | 13 | 13 | 13 | 16 | 16 | 16 | 16 | 16 | 14 | 14 | 17 | 11 | 8 | 8 | 8 | 13 | 12 | 12 | 12 | 9 | 9 | 9 | 11 | 10 | 10 | 6 | 0 | 0 | 5 | 5 | 10 | 13 | 13 | 13 | 9 | 13 | 13 | 12 | 12 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 8 | 8 | 9 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Super Construction | Energizent Power Pvt. Ltd | Staff | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Paramhans Infra | Energizent Power Pvt. Ltd | Staff | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 9 | 8 | 0 | 8 | 8 | 8 | 13 | 13 | 13 | 13 | 5 | 0 | 16 | 16 | 16 | 16 | 16 | 12 | 15 | 12 | 14 | 15 | 15 | 15 | 15 | 15 | 13 | 13 | 15 | 15 | 0 | 0 | 14 | 14 | 14 | 17 | 17 | 17 | 14 | 14 | 13 | 13 | 5 | 5 | 5 | 5 | 0 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 8 | 7 | 5 | 5 | 0 | 5 | 4 | 12 | 8 | 7 | 7 | 0 | 4 | 3 | 3 | 3 | 4
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 5 | 5 | 0 | 5 | 5 | 10 | 9 | 0 | 9 | 9 | 9 | 15 | 15 | 15 | 16 | 6 | 0 | 18 | 18 | 18 | 18 | 18 | 14 | 17 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 15 | 15 | 17 | 17 | 0 | 0 | 16 | 16 | 16 | 19 | 19 | 19 | 16 | 16 | 14 | 14 | 6 | 6 | 6 | 6 | 0 | 6 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 9 | 8 | 6 | 6 | 0 | 6 | 5 | 13 | 9 | 8 | 8 | 0 | 5 | 4 | 4 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Seema Enterprises | Energizent Power Pvt. Ltd | Staff | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1
|  |  | Worker | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 6 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 8 | 8 | 15 | 15 | 5 | 5 | 5 | 11 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 5 | 5 | 0 | 4 | 4 | 7 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 8 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 10 | 10 | 17 | 17 | 7 | 7 | 7 | 13 | 13 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 6 | 6 | 0 | 5 | 5 | 8 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Teq XV Pvt. Ltd. | Staff | [96 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | [96 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | [96 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | KC Construction | Energizent Power Pvt. Ltd | Staff | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 6 | 5 | 5 | 5 | 8 | 8 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 8 | 7 | 7 | 7 | 10 | 10 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | SR Constructions | Energizent Power Pvt. Ltd | Staff | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 6 | 6 | 6 | 11 | 11 | 8 | 13 | 13 | 17 | 17 | 5 | 5 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 5 | 5 | 5 | 0 | 0 | 4 | 6 | 5 | 5 | 9 | 10 | 10 | 11 | 12 | 6 | 13 | 6 | 6 | 6 | 6 | 6 | 0 | 5 | 5 | 11 | 7 | 8 | 5 | 10 | 10 | 4 | 10
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 7 | 7 | 7 | 12 | 12 | 9 | 14 | 14 | 18 | 18 | 6 | 6 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 6 | 6 | 6 | 0 | 0 | 5 | 7 | 6 | 6 | 10 | 11 | 11 | 12 | 13 | 7 | 14 | 7 | 7 | 7 | 7 | 7 | 0 | 6 | 6 | 12 | 8 | 9 | 6 | 11 | 11 | 5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | DS Constructions | Energizent Power Pvt. Ltd | Staff | [94 empty] | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | [94 empty] | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 5 | 5 | 5 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 6 | 6 | 6 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | NCC | Energizent Power Pvt. Ltd | Staff | [96 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | [96 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Hartek | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 3 | 0 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 0
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 9 | 0 | 9 | 5 | 8 | 9 | 7 | 13 | 9 | 9 | 9 | 14 | 10 | 10 | 9 | 6 | 9 | 10 | 0 | 10 | 10 | 10 | 12 | 7 | 10 | 10 | 10 | 7 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 17 | 17 | 17 | 17 | 11 | 0 | 11 | 7 | 10 | 11 | 9 | 15 | 11 | 11 | 11 | 16 | 13 | 13 | 12 | 8 | 12 | 13 | 0 | 13 | 13 | 13 | 15 | 9 | 13 | 13 | 13 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Sun Bright Infratech | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 6 | 7 | 6 | 7 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | JS Bhati Construction | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 0 | 2 | 0 | 2 | 2 | 6 | 6 | 7 | 5 | 5 | 5 | 6 | 6
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 0 | 3 | 0 | 3 | 3 | 7 | 7 | 8 | 6 | 6 | 6 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Baba Ramdev contraction | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 8 | 7 | 2 | 4 | 2 | 5 | 6 | 4 | 4 | 5 | 8 | 8 | 7 | 4 | 7
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 8 | 3 | 5 | 3 | 6 | 7 | 5 | 5 | 6 | 9 | 9 | 8 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Bajarang Electrical Work | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Shree Krshna Enterprises | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 9 | 9
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Machinary | Total |  | Description | 0 | 2 | 2 | 2 | 4 | 4 | 4 | 5 | 5 | 4 | 3 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 6 | 6 | 6 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Desert Infra |  | Vehicle |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Excavator/JCB | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | Sanchiyay |  | Vehicle | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Excavator/JCB | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JCC |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Excavator/JCB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 | Super Construction |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Paramhans Infra |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Seema Enterprises |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | KC Constructions |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | SR Constructions |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | DS Constructions |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | [90 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | NCC |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Hartek |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Farhana | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | JCB | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Sun Bright Infratech |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | JCB | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | JS Bhati Construction |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | JCB | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Baba Ramdev contraction |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | JCB | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Bajarang Electrical Work |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Farhana | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Crane | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Resources Requirement
Resources Required vs Actual
Sr. No. | Vendor Name | Available | Required | Balance to catch up Progress | Current Update by Contractor
1 | Vendor 1 | 0 | 20 | 20
2 | Vendor 1 | 12 | 15 | 3
3 | Vendor 1 | 6 | 15 | 9
4 | Vendor 1 | 0 | 0 | 0
5 | Vendor 1 | 4 | 15 | 11 | Will be available once piling front allocated
6 | Vendor 1 | 6 | 15 | 9
7 | Vendor 1 | 0 | 10 | 10
8 | Vendor 1 | 11 | 18 | 7
9 | Vendor 1 | 5 | 10 | 5
10 | Vendor 1 | 0 | 10 | 10
11 | Vendor 1 | 0 | 13 | 13
12 | Vendor 1 | 0 | 9 | 9
13
Total |  | 44 | 150 | 106

## Hindrance
Work Hindrance Log
Start DATE | End Date | ISSUE | START TIME | END TIME | REMARKS
2024-11-26 | 2024-12-12 | Land clearance not given for piling construction | 09.00 am | 06.00 pm
2024-11-26 | 2024-12-12 | Bush cutting pending in demarcated land | 09.00 am | 06.00 pm
2024-11-23 | 2024-11-23 | Local farmers stopped unloading works | 09.00 am | 06.00 pm | Unloading work stopped for demand of unloading work
2024-11-24 | 2024-11-24 | Local farmers stopped unloading works | 09.00 am | 11.00 am | Unloading work stopped for demand of unloading work
2024-11-26 | 2024-11-26 | Local farmers stopped switchyard works | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-11-27 | 2024-11-27 | Local farmers stopped switchyard works | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-12-06 | 2024-12-06 | Local Farmers stopped work | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-12-07 | 2024-12-07 | Local Farmers stopped work | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-12-07 | 2024-12-12 | Piling layout not received for demarcated land | 09.00 am | 06.00 pm | Piling work not started
2024-12-17 | 2024-12-18 | Security agency guards stopped the work | 09.00 am | 06.00 pm | Security guards and QRT people stopped the work
2024-12-20 | 2024-12-22 | HT Panel Drawing had design changes | 09.00 am | 06.00 pm | Design team made changes in design after releasing the foundation drwaing because of that work was on hold for 3 days
2024-12-21 | 2024-12-30 | Batching plant setup, ICR and Pilling work stoped by locals | 09.00 am | 06.00 pm | Locals has stop the work for the demand over batching plant setup
2024-12-29 | 2024-12-30 | Boundary wall work not started because of Rate disputes with locals | 09.00 am | 06.00 pm
2025-12-30 | 2025-01-06 | HT panel building Plinth beam/floor slab and roof beam/slab drawing not received. | 09.00 am | 06.00 pm | Bar bending team has no front for steel cutting
2025-01-09 | 2025-01-09 | Site work hampered due to demand of JCB hiring | 09.00 am | 05.00 pm | Manpower ideal due to ROW at site
2025-01-08 | 2025-01-10 | Piling work not started due to compansation issue to water storage tank | 09.00 am | 06.00 pm
2025-01-14 | 2025-01-15 | Piling and ICR work Stopped due to demand of JCB hiring for grading and levelling | 09.00 am | 06.00 pm
2025-01-20 | 2025-01-20 | Piling work hampered due to demand of water tank rate fixing | 09.00 am | 06.00 pm
2025-01-25 | 2025-01-27 | Piling work hampered due road work blocked by locals | 09.00 am | 06.00 pm
2025-02-27 | 2025-03-05 | Piling work hampered in s/y no 38,39,40,42,66,67 due to demarcation issue | 09.00 am | 06.00 pm
2025-03-01 | 2025-03-05 | Piling work hampered in s/y no 117 due to demarcation issue | 09.00 am | 06.00 pm
Formulas:
Start DATE = [Start DATE, row above]+1
End Date = [End Date, row above]+1