Minutes of Meeting of the Committee for deciding the CFA for setting up of the 25MWac/50MWp solar power project with 40 MWh BESS by SECI at Taru, Leh under JKPMDP-2015

Date: 4th August 2025
Venue: Room No. 711, AAUB, MNRE

Attendees:

| Committee Members | MNRE | SECI |
| --- | --- | --- |
| Sudeep Jain, AS, MNRE - Chair | Dr. Aravindh M. A. Scientist D | Sivakumar V. Vepakomma, D(PS) |
| J.V.N. Subramanyam, JS, MNRE |  | Shri. S.K. Gupta, ED (F) |
| Padam Lal Negi, JS&FA |  | Debajyoti Bordoloi, DGM (Projects) |
| Joshit Ranjan Sikidar, D(F), SECI |  | Anuja Garg, SM (F) |
| Kailash Chand, DS (IFD), MNRE |  |  |
| A. S. Parira, Scientist E, MNRE |  |  |

Points Discussed:

- SECI apprised that the EPC and O&M (10 years) contracts for the 25 MW Solar Project with 40 MWh Battery Energy Storage System (BESS) at Leh has been awarded on 20.11.2024, with a commissioning timeline of 36 months. Project execution is currently underway at the site. All efforts are being made to commission the project by the end of 2026.

- SECI informed that the tariff for the project, as per the CFA sanction order issued by MNRE, is fixed at ₹2.22/kWh. The total awarded project cost is ₹313 crore, which includes expenses to be incurred for 10 years of O&M.

- It was clarified that the BESS component will be replaced twice during the 25-year project lifetime, once in the 11th year and again in the 21st year. The cost of battery replacement has been appropriately factored into the overall project cost.

- SECI stated that it will approach the Hon’ble CERC for tariff approval in line with prevailing guidelines. The exact CFA amount will be determined post-CERC approval, which will factor in a 14% post-tax return on investment, as per the standard norms.

- SECI requested the release of the first tranche, 50% of the estimated CFA amounting to ₹114.75 crore out of the total ₹229.50 crore (estimated), at the earliest. SECI has achieved the milestone of awarding the EPC contract, making it eligible for the first tranche as per the provisions of the CFA sanction order. The second tranche (remaining 50%) may be released upon achieving the second milestone, i.e., project commissioning. Any subsequent adjustment, either payment or recovery, will be made based on the final tariff determined by CERC.

The committee agreed to the proposal, and the meeting concluded with a vote of thanks to the Chair and the committee members.