Record of discussion: Project Review Meeting by D(PS)

Project: 700 MW SPV Project, Radhanesda

Date: 04.08.2025

Attendees:

- Shreedhar Singh, AGM (Projects)

- Debajyoti Bordoloi, DGM (Projects)

- Sandeep Rana, DGM (C&P)

- Manish Kumar, DGM (Civil)

- Prashant Soni, DGM (Project Monitoring)

- Prem Kumar, DM (Civil)

Points discussed:

- Engagement of IIT, Guwahati for Geotechnical Consultancy Services:

- D(PS) talked to the Professor at IITG over phone and briefed him about the requirements.

- Professor informed that minimum 3 weeks will be required to furnish the reports from the date of award of work order. He indicated that he will try to submit the report by 25.08.2025.

- DGM (Civil) informed that the work order will be released immediately, latest by 05.08.2025.

- The Professor suggested that pre-cast piling can be considered for module mounting structure which will be easier to handle considering the soil conditions at site.

- Professor also suggested stone piling for other structures like the control room foundation etc.

- Professor requested for various structure loads to be considered while preparing the report. DGM (Civil) promised to provide the same at the earliest.

- Land for solar park:

- DGM (Projects) informed that Revenue Department, GoGJ has again sought some clarification/ compliance from DM Office at Palanpur which is awaited.

- GPCL has been constantly following up with the DM Office for expediting the compliance.

- Matters related to Solar Park:

- DGM (Projects) informed that the Request Letter for VGF under Solar Park Scheme of MNRE has been forwarded by GPCL to JS (EPD) for approval and onward submission to MNRE on 25.07.2025. However, JS (EPD) has not forwarded the letter to MNRE even after repeated follow-ups.

- D(PS) requested MD, GPCL over phone to expedite submission of the letter.

- DGM (Projects) informed that the GPCL is evaluating the PMC offers from the prospective bidders including SECI for construction of Park Pooling Sub-station and associated work and will take it up for its board approval shortly.

- Regarding requirement of water for the solar project/ park, DGM (Civil) informed that water will be purchased from GPCL, who has developed the infrastructure to source, store and supply water from a branch of the Sardar Sarovar Narmada Canal located 40 km away from the site. DGM (Civil) to calculate the volume of water requirement (in KL) which shall be communicated to GPCL through a letter.

- Evacuation of power from Solar Park:

- GETCO to construct two 220 kV lines connecting Tharad and Ghodasad S/s of STU for which necessary tendering has been done.

- GETCO is awaiting GPCL’s go ahead which has been withheld pending land allocation to the later by GoGJ.

- Tender packages and timelines:

- There will be following packages for this project

- BoS:

- It was discussed and agreed that the 700 MW capacity will be divided into 02 modules of 350 MW capacity each.

- DGM (C&P) suggested tender release target date of 05.09.2025 which was agreed to by D(PS).

- Construction timeline was discussed and agreed to be min. 15 months (at least two working seasons considering the prevalent working window in that part of Gujarat) from the date of award of contract.

- SPV Module:

- DGM (C&P) emphasized that 03 modules of 300 MW capacity each with min. 540 Wp may be considered.

- D(PS) directed that thin film SPV modules (Make: First Solar) not to be considered for this tender/ project because of land constraint, proposed robotic cleaning and usage of trackers for mounting structures.

- He also directed that necessary justification should be readied to counter contest, if any, by M/s First Solar for excluding it from participating in the tender.

- DGM (C&P) suggested target date for this tender to be 24.08.2025.

- Supply timeline to be 12 months from the date of award of contract.

- Power Transformer:

- AGM (Projects) suggested that 350 mVA x 2 nos. may be considered for this project and SECI can purchase the same out of the BoS tender.

- Target Date for release of tender was decided to be 24.08.2025.

- Cost estimation and preparation of TS for tender to be initiated at the earliest.

- Supply timeline: 12 months from the date of contract award

- Solar Park:

- D(PS) suggested that SECI should develop the solar park of its own and directed DGM (Projects) to get the clarity from GPCL by 24.08.2025.

- DGM (Projects) informed that GPCL had offered SECI could construct the peripheral bund, which as per its estimation is costing approx. INR 100 Cr. D(PS) directed DGM (Civil) to check and explore the options.

- Preparation of DPR/ Cost estimation for Solar Park, in case SECI becomes the SPD, is to be initiated by DGM (Civil).