## Project Dashbord
Project Progress Report | [8 empty] | PROGRESS ON: 12-Aug-2025
Project Name : |  | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Taru, Leh, UT of Ladakh, India
Client : |  | Solar Energy Corporation of India Ltd
SPV : |  | Prozeal Green Energy Limited
Project Start Date |  | 2024-11-20
Project COD |  | 2027-11-05
Sr. No | Description | Scope | UOM | Completed | Balance | Actual Progress Front Wise (in %) | Scope Weightage % | Progress as per weightage (in %) | Overall Project Completion Status
1 | Plant Boundary Fencing | 5690 | RM | 4851.5 | 838.5 | 85.3% | 1.2% | 1%
2 | MCR Civil Work | 1 | Lot | 0.15618 | 0.84382 | 15.6% | 9% | 1.4%
3 | MMS Pilling | 27000 | Nos | 0 | 27000 | 0% | 22.8% | 0%
4 | Switch Yard | 1 | Lot | 0 | 1 | 0% | 9% | 0%
5 | IDT - Solar | 4 | Lot | 3 | 1 | 75% | 1.2% | 0.9%
6 | IDT - BESS | 5 | Lot | 0 | 5 | 0% | 1.2% | 0%
7 | BESS-Civil | 1 | Lot | 0.13636 | 0.86364 | 13.6% | 3.6% | 0.5%
8 | LCR | 4 | Lot | 0 | 4 | 0% | 2.4% | 0%
9 | MMS Structure | 3934 | Table | 0 | 3934 | 0% | 7.2% | 0%
10 | Road | 3000 | Mtr. | 0 | 3000 | 0% | 1.2% | 0%
11 | Drain | 1000 | Mtr. | 0 | 1000 | 0% | 0.6% | 0%
12 | Misc Work | 1 | Lot | 0.2 | 0.8 | 20% | 0.6% | 0.1%
13 | AC-Electrical | 1 | Lot | 0 | 1 | 0% | 7.4% | 0%
14 | DC- Electrical | 1 | Lot | 0 | 1 | 0% | 7.4% | 0%
15 | Switchtard - Electrical | 1 | Lot | 0 | 1 | 0% | 7.4% | 0%
16 | MCR - Electrical | 1 | Lot | 0 | 1 | 0% | 3.7% | 0%
17 | Module Erection | 94416 | Nos | 0 | 94416 | 0% | 7.4% | 0%
18 | BESS - Electrical | 1 | Lot | 0 | 1 | 0% | 3.7% | 0%
19 | Transmission Line | 1 | Lot | 0 | 1 | 0% | 1% | 0%
20 | Project Charging & Commisioning | 1 | Lot | 0 | 1 | 0% | 2% | 0%
Overall Project Completion Status | [6 empty] | 100% | 3.9%

## MDL Status
Project Drawings Approval Report | [15 empty] | PROGRESS ON: 12-Aug-2025
Client Name | Solar Energy Corporation of India Ltd | [12 empty] | Total Documents | Submitted | Approved | Sub. Approved | Commented | Pending for Submission
EPC Contractor | Prozeal Green Energy Limited | [12 empty] | 100% | 42.78% | 11.76% | 1.07% | 15.51% | 57.22%
Project Name | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Taru, Leh, UT of Ladakh, India | [12 empty] | 187 | 80 | 22 | 2 | 29 | 107
Project Capacity | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System | [12 empty] | Only apporval category
Particulars | Total Documents | [9 empty] | Remaining Documents | Total Received (%) | Engineering completion (%)
|  | VOID | UNDER EPC | UNDER OE | SUB. APPROVED | APPROVED | NOTED FOR INFORMATION | NOT APPROVED | PENDING | Total Sub
I. Review Engineering Electrical
A.Basic Engineering | 11 | 0 | 2 | 3 | 0 | 2 | 4 | 0 | 0 | 11 | 0 | 100% | 0%
B.Major Electrical Equipments (GTP, GA, Type Test Reports and QAP) | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 3 | 25% | 0%
C.Cable sizing documents | 4 | 0 | 1 | 0 | 0 | 3 | 0 | 0 | 0 | 4 | 0 | 100% | 0%
D.Cable GTPs, Type Test Reports and QAP | 7 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 3 | 4 | 3 | 57.14% | 0%
E.Battery Energy Storage System (BESS) | 17 | 0 | 6 | 3 | 0 | 2 | 2 | 0 | 4 | 13 | 4 | 76.47% | 0%
F.Module Mounting structure | 12 | 0 | 7 | 0 | 0 | 0 | 3 | 0 | 2 | 10 | 2 | 83.33% | 0%
G.MCR Building | 11 | 0 | 3 | 2 | 0 | 1 | 0 | 0 | 5 | 6 | 5 | 54.55% | 0%
H.Open Plinth for LCR Equipment | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0% | 0%
I.BESS Foundation | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 2 | 5 | 28.57% | 0%
J.Equipment foundations | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0% | 0%
K.Layout, Ancillary Equipment GTP and DBR | 24 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 20 | 4 | 20 | 16.67% | 0%
M.Ancillary Systems | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0% | 0%
N.Cable Schedules | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 0% | 0%
O.System Drawings and Layouts | 14 | 0 | 3 | 1 | 1 | 2 | 0 | 0 | 7 | 7 | 7 | 50% | 0%
P.Equipment GTPs, Type test reports and Inspection Reports | 24 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 15 | 9 | 15 | 37.5% | 0%
Q.Equipment Foundation Drawings and Cable Schedules | 25 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 16 | 9 | 16 | 36% | 0%
Total documents | 187 | 0 | 29 | 27 | 2 | 13 | 9 | 0 | 107 | 80 | 107 | 42.78% | 0%
| 187 | 22 | 100% | 11.76%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sheet1 (hidden)
Sl. No. | Drawing/Document Title | Approval Category | Date Of Approval | Darwing Number | Approval Status | Proposed Submission Date
1 | Photovoltaic Module |  | 2025-02-27 | SECI-LEH25MW-GTP-ELE-1 | PGEL |  | Basic Engineering |  | Approved
2 | Power Conditioning Unit (Central) |  | 2025-01-24 | SECI-LEH25MW-GTP-ELE-2 | PGEL |  |  |  | Re-Submission
3 | System Design Basis Report (including Energy Yield Simulation and shadow analysis report) | CAT-III | 2025-05-28 | SECI-LEH25MW-DBR-ELE-3 | PGEL |  |  |  | PGEL
4 | DC SLD | CAT-IV | 2025-05-15 | SECI-LEH25MW-DWG-ELE-4 | Approved |  |  |  | SECI-Review
5 | AC SLD including BESS (upto 11 kV) | CAT-IV | 2025-07-24 | SECI-LEH25MW-DWG-ELE-5 | Approved |  |  |  | Yet To Submit
6 | Topographical Survey | CAT-IV | 2025-06-10 | SECI-LEH25MW-DWG-CIV-6 | Approved
7 | Concrete Mix Design Report |  | 2025-07-21 | SECI-LEH25MW-IR-CIV-7 | PGEL
8 | Grading and Levelling Plan |  | 2025-07-11 | SECI-LEH25MW-DWG-CIV-8 | PGEL
9 | Overall Plant Layout covering Array layout, Buildings (MCR and LCR) marking, Road Layout, Lightning protection layout, WMS Location, etc. | CAT-III | 2025-07-03 | SECI-LEH25MW-DWG-ELE-9 | PGEL
10 | Plant Boundary Fencing Layout and Details | CAT-I | 2025-05-27 | SECI-LEH25MW-DWG-CIV-10 | Approved
11 | Plant Main Gate - General Arrangement and Details | CAT-I | 2025-07-04 | SECI-LEH25MW-DWG-CIV-11 | Approved
12 | String Combiner Box (SCB) |  |  | SECI-LEH25MW-GTP-ELE-12 | Yet To Submit |  | Major Electrical Equipments (GTP, GA, Type Test Reports and QAP)
13 | Inverter Duty Transformer (IDT) |  |  | SECI-LEH25MW-GTP-ELE-13 | Yet To Submit
14 | 11kV HT ICOG Panel |  |  | SECI-LEH25MW-GTP-ELE-14 | SECI-Review
15 | 11kV HT Combiner Panel |  |  | SECI-LEH25MW-GTP-ELE-15 | Yet To Submit
16 | Solar cable (PV module to SCB) | CAT-II |  | SECI-LEH25MW-GTP-ELE-16 | Approved |  | Cable sizing documents
17 | DC cable (from SCB to PCU) | CAT-I |  | SECI-LEH25MW-GTP-ELE-17 | Approved
18 | LT cable (from PCU to IDT) | CAT-I |  | SECI-LEH25MW-GTP-ELE-18 | Approved
19 | 11kV LT Power Cable | CAT-I |  | SECI-LEH25MW-GTP-ELE-19 | Approved
20 | Solar cable (PV module to SCB) | CAT-II |  | SECI-LEH25MW-GTP-ELE-20 | Approved |  | Cable GTPs, Type Test Reports and QAP | SUB. APPROVED
21 | DC cable (from SCB to PCU) |  |  | SECI-LEH25MW-GTP-ELE-21 | Re-Submission |  |  | UNDER OE
22 | LT cable (from PCU to IDT) | CAT-I |  | SECI-LEH25MW-GTP-ELE-22 | Approved |  |  | APPROVED
23 | 11kV LT Power Cable | CAT-I |  | SECI-LEH25MW-GTP-ELE-23 | Approved |  |  | APPROVED
24 | Communication Cable |  |  | SECI-LEH25MW-GTP-ELE-24 | Yet To Submit |  |  | PENDING
25 | LT Auxiliary Power Cable |  |  | SECI-LEH25MW-GTP-ELE-25 | Yet To Submit |  |  | PENDING
26 | Control Cable |  |  | SECI-LEH25MW-GTP-ELE-26 | Yet To Submit |  |  | PENDING
27 | Design Basis Report for BESS with BESS PQR |  |  | SECI-LEH25MW-DBR-ELE-27 | SECI-Review |  | Battery Energy Storage System (BESS) | UNDER OE
28 | Battery Sizing Calculation | CAT-I |  | SECI-LEH25MW-DBR-ELE-28 | Approved |  |  | APPROVED
29 | Overall System Schematic, Equipment Layout and BoM |  |  | SECI-LEH25MW-DWG-ELE-29 | Yet To Submit |  |  | PENDING
30 | Battery Bank (GTP, Drawings, Type Test Report and QAP) Along with Battery Container GA |  |  | SECI-LEH25MW-GTP-ELE-30 | PGEL |  |  | UNDER EPC
31 | Battery Management System (GTP and Drawings) |  |  | SECI-LEH25MW-GTP-ELE-31 | PGEL |  |  | UNDER EPC
32 | Power Conditioning System (GTP, Drawings, Type Test Report and QAP) |  |  | SECI-LEH25MW-GTP-ELE-32 | SECI-Review |  |  | UNDER OE
33 | PCS Transformer (GTP, Drawings, Type Test Report and QAP) |  |  | SECI-LEH25MW-GTP-ELE-33 | Yet To Submit |  |  | PENDING
34 | PCS Transformer NIFPS (GTP, Drawings and QAP) (If Applicable) |  |  | SECI-LEH25MW-GTP-ELE-34 | Yet To Submit |  |  | PENDING
35 | HVAC System (General Arrangement and Details) |  |  | SECI-LEH25MW-DWG-ELE-35 | SECI-Review |  |  | UNDER OE
36 | BESS Auxiliary System SLD and DB Details |  |  | SECI-LEH25MW-GTP-ELE-36 | PGEL |  |  | UNDER EPC
37 | BESS Earthing Scheme |  |  | SECI-LEH25MW-DWG-ELE-37 | Yet To Submit |  |  | PENDING
38 | BESS Fire Protection Systems | CAT-III |  | SECI-LEH25MW-DWG-ELE-38 | PGEL |  |  | UNDER EPC
39 | Auxiliary Power Consumption Calculation | CAT-IV |  | SECI-LEH25MW-DBR-ELE-39 | Approved |  |  | NOTED FOR INFORMATION
40 | Heat Load Calculation of Container | CAT-IV |  | SECI-LEH25MW-DBR-CIV-40 | Approved |  |  | NOTED FOR INFORMATION
41 | Energy Management System (EMS) document (GTP, schematics,and GA) |  |  | SECI-LEH25MW-GTP-ELE-41 | Yet To Submit |  |  | PENDING
42 | DC and AC Sizing Cable Calculation | CAT-I |  | SECI-LEH25MW-DBR-ELE-42 | Approved |  |  | APPROVED
43 | DC and AC Cable GTP |  |  | SECI-LEH25MW-GTP-ELE-43 | Yet To Submit |  |  | PENDING
44 | Module Mounting Structure DBR | CAT-II |  | SECI-LEH25MW-DBR-CIV-44 | Approved |  | Module Mounting structure | UNDER EPC
44A | Module Mounting Structure DBR (Interior) | CAT-III |  | SECI-LEH25MW-DBR-CIV-44A | PGEL |  |  | UNDER OE
45 | MMS Drawing | CAT-II |  | SECI-LEH25MW-DWG-CIV-45 | Approved |  |  | UNDER EPC
45A | MMS Drawing (Interior) | CAT-III |  | SECI-LEH25MW-DWG-CIV-45A | PGEL |  |  | UNDER OE
46 | MMS Fabrication Drawing | CAT-IV |  | SECI-LEH25MW-DWG-CIV-46 | Approved |  |  | NOTED FOR INFORMATION
46A | MMS Fabrication Drawing (Interior) |  |  | SECI-LEH25MW-DWG-CIV-46A | Yet To Submit |  |  | PENDING
47 | MMS Foundation Drawing | CAT-II |  | SECI-LEH25MW-DWG-CIV-47 | Approved |  |  | UNDER EPC
47A | MMS Foundation Drawing (Interior) |  |  | SECI-LEH25MW-DWG-CIV-47A | Yet To Submit |  |  | PENDING
48 | MMS Foundation Marking Layout |  |  | SECI-LEH25MW-DWG-CIV-48 | SECI-Review |  |  | UNDER EPC
49 | Pile Test Location Drawing (if applicable) | CAT-II |  | SECI-LEH25MW-DWG-CIV-49 | Approved |  |  | UNDER EPC
50 | Pile Test Report (if applicable) |  |  | SECI-LEH25MW-IR-CIV-50 |  |  |  | UNDER OE
51 | MCR - Architectural Details, Elevations, Sections and Finishing | CAT-I |  | SECI-LEH25MW-DWG-CIV-51 |  |  | MCR Building | APPROVED
52 | MCR Foundation and Super Structure - Design Basis Report | CAT-III |  | SECI-LEH25MW-DBR-CIV-52 |  |  |  | UNDER OE
53 | MCR - Foundation General Arrangement and Reinforcement Details | CAT-III |  | SECI-LEH25MW-DWG-CIV-53 |  |  |  | UNDER OE
54 | MCR - Plinth Beam General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-54 |  |  |  | UNDER OE
55 | MCR - Lintel Beam General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-55 |  |  |  | UNDER OE
56 | MCR - Roof General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-56 |  |  |  | UNDER OE
57 | MCR - Plumbing Network and Sanitary Details |  |  | SECI-LEH25MW-DWG-CIV-57 |  |  |  | PENDING
58 | MCR Heating/HVAC Sytem - Layout, General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-58 |  |  |  | PENDING
59 | MCR Heating/HVAC System - Design Basis Report (DBR) |  |  | SECI-LEH25MW-DBR-CIV-59 |  |  |  | PENDING
60 | MCR Lighting Layout |  |  | SECI-LEH25MW-DWG-ELE-60 |  |  |  | PENDING
61 | MCR - Cable Trench General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-61 |  |  |  | PENDING
62 | LCR Equipment Layout |  |  | SECI-LEH25MW-DWG-ELE-62 |  |  | LCR Equipment Room | PENDING
63 | Inverter Foundation and Super Structure DBR |  |  | SECI-LEH25MW-DBR-CIV-63 |  |  |  | PENDING
63A | HT Container Foundation and Super Structure DBR |  |  | SECI-LEH25MW-DBR-CIV-63A |  |  |  | PENDING
64 | Inverter Foundation and Superstructure - General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-64 |  |  |  | PENDING
64A | HT Container Foundation and Superstructure - General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-64A |  |  |  | PENDING
65 | Cable Trench Layout for ICR room |  |  | SECI-LEH25MW-DWG-ELE-65 |  |  |  | PENDING
66 | BESS Transformer Foundation - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-66 |  |  | BESS Foundation | PENDING
67 | Design Basis Report (DBR) for BESS Transformer foundation |  |  | SECI-LEH25MW-DBR-CIV-67 |  |  |  | PENDING
68 | BESS Container Platform and Foundation - Design Basis Report |  |  | SECI-LEH25MW-DBR-CIV-68 |  |  |  | UNDER OE
69 | BESS Container Platform Superstructure and Foundation - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-69 |  |  |  | UNDER OE
70 | BESS Yard Fence & Gate - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-70 |  |  |  | PENDING
71 | BESS PCS Foundation - DBR |  |  | SECI-LEH25MW-DBR-CIV-71 |  |  |  | PENDING
72 | BESS PCS Foundation - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-72 |  |  |  | PENDING
73 | String Combiner Panel Structure and Foundation - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-73 |  |  | Equipment foundations | PENDING
74 | Auxiliary Tranformer Foundation DBR and GA Drawing |  |  | SECI-LEH25MW-DWG-CIV-74 |  |  |  | PENDING
75 | Inverter Transformer Foundation DBR |  |  | SECI-LEH25MW-DBR-CIV-75 |  |  |  | PENDING
76 | Inverter Transformer Foundation - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-76 |  |  |  | PENDING
77 | Cable trench Layout and Cross section (DC, AC, Lighting and CCTV system etc) |  |  | SECI-LEH25MW-DWG-ELE-77 |  |  | Layout, Ancillary Equipment GTP and DBR | PENDING
78 | DC Earthing Design and Calculation | CAT-II |  | SECI-LEH25MW-DBR-ELE-78 |  |  |  | UNDER EPC
79 | PV Array Yard Earthing Layout |  |  | SECI-LEH25MW-DWG-ELE-79 |  |  |  | PENDING
80 | AC Earthing Design and Calculation | CAT-I |  | SECI-LEH25MW-DBR-ELE-80 |  |  |  | APPROVED
81 | LCR and MCR Yard Earthing Layout |  |  | SECI-LEH25MW-DWG-ELE-81 |  |  |  | PENDING
82 | Illumination Design and Simulation Report |  |  | SECI-LEH25MW-DBR-ELE-82 |  |  |  | PENDING
83 | Plant Lighting Layout and Lighting Pole GA & Foundation |  |  | SECI-LEH25MW-DWG-ELE-83 |  |  |  | PENDING
84 | LED Luminarie and Pole with accessories |  |  | SECI-LEH25MW-GTP-ELE-84 |  |  |  | PENDING
85 | Plant Auxilary Load Calculation with UPS sizing |  |  | SECI-LEH25MW-DBR-ELE-85 |  |  |  | UNDER EPC
86 | Auxiliary SLD |  |  | SECI-LEH25MW-DWG-ELE-86 |  |  |  | PENDING
87 | UPS ( GTP, GA & Drawing, QAP and Type Test Reports |  |  | SECI-LEH25MW-GTP-ELE-87 |  |  |  | PENDING
88 | Auxiliary Transformer (GTP, GA & Drawing, QAP and Type Test Reports) |  |  | SECI-LEH25MW-GTP-ELE-88 |  |  |  | PENDING
89 | GTP and Schematics of LT distribution panel |  |  | SECI-LEH25MW-GTP-ELE-89 |  |  |  | PENDING
90 | SCADA System Architecture and IO List |  |  | SECI-LEH25MW-DBR-ELE-90 |  |  |  | PENDING
91 | SCADA Schematic |  |  | SECI-LEH25MW-DWG-ELE-91 |  |  |  | PENDING
92 | GTP of SCADA system components - Hardware & Software |  |  | SECI-LEH25MW-GTP-ELE-92 |  |  |  | PENDING
93 | CCTV Layout and General Arrangement |  |  | SECI-LEH25MW-DWG-ELE-93 |  |  |  | PENDING
94 | Solar Cable Connector (GTP and Type Test Reports) |  |  | SECI-LEH25MW-GTP-ELE-94 |  |  |  | PENDING
95 | HT Cable Termination Kit (GTP, GA Drawing and Type Test Reports) |  |  | SECI-LEH25MW-GTP-ELE-95 |  |  |  | PENDING
96 | Lightning protection system: GTP, LA Mounting and Foundation drawing |  |  | SECI-LEH25MW-GTP-ELE-96 |  |  |  | PENDING
97 | Earthing electrode and Accessories- GTP |  |  | SECI-LEH25MW-GTP-ELE-97 |  |  |  | PENDING
98 | Testing Instruments |  |  | SECI-LEH25MW-GTP-ELE-98 |  |  |  | PENDING
99 | Weather Monitoring System: GA, GTP and Mounting & Foundation drawing |  |  | SECI-LEH25MW-GTP-ELE-99 |  |  |  | PENDING
100 | CCTV System |  |  | SECI-LEH25MW-GTP-ELE-100 |  |  |  | PENDING
101 | Roads - DBR |  |  | SECI-LEH25MW-DBR-CIV-101 |  |  | Ancillary Systems | PENDING
102 | Road Layout and Sections |  |  | SECI-LEH25MW-DWG-CIV-102 |  |  |  | PENDING
103 | Drainage-DBR |  |  | SECI-LEH25MW-DBR-CIV-103 |  |  |  | PENDING
104 | Drainage Layout and Sections |  |  | SECI-LEH25MW-DWG-CIV-104 |  |  |  | PENDING
105 | PV Module Cleaning System-DBR and GA |  |  | SECI-LEH25MW-DBR-CIV-105 |  |  |  | PENDING
106 | Security Room - Architectural Plan, Elevation, Sections & Finishing |  |  | SECI-LEH25MW-DWG-CIV-106 |  |  |  | PENDING
107 | Security Room Superstructure and Foundation -Design Basis Report |  |  | SECI-LEH25MW-DBR-CIV-107 |  |  |  | PENDING
108 | Security Room Superstructure and Foundation- General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-108 |  |  |  | PENDING
109 | Security Room - Plumbing and Sanitary Layout, General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-109 |  |  |  | PENDING
110 | Security Room Heating/HVAC Sytem - Layout, General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-110 |  |  |  | PENDING
111 | Solar cable (PV module to SCB) |  |  | SECI-LEH25MW-DOC-ELE-111 |  |  | Cable Schedules | PENDING
112 | DC cable (from SCB to PCU) |  |  | SECI-LEH25MW-DOC-ELE-112 |  |  |  | PENDING
113 | LT cable (from PCU to IDT) |  |  | SECI-LEH25MW-DOC-ELE-113 |  |  |  | PENDING
114 | 11kV LT Power Cable |  |  | SECI-LEH25MW-DOC-ELE-114 |  |  |  | PENDING
115 | Communication Cable |  |  | SECI-LEH25MW-DOC-ELE-115 |  |  |  | PENDING
116 | LT Auxiliary Power Cable |  |  | SECI-LEH25MW-DOC-ELE-116 |  |  |  | PENDING
117 | Control Cable |  |  | SECI-LEH25MW-DOC-ELE-117 |  |  |  | PENDING
118 | 66kV HT Conductor Sizing Calculation | CAT-I |  | SECI-LEH25MW-DBR-ELE-118 |  |  |  | APPROVED
119 | Power Evacuation SLD (11/66kV Switchyard) | CAT-II |  | SECI-LEH25MW-DWG-ELE-119 |  |  |  | UNDER EPC
120 | Battery & Battery Charger for Switchyard - Sizing Calculations |  |  | SECI-LEH25MW-DBR-ELE-120 |  |  |  | PENDING
121 | Main Control Room UPS Sizing Calculation |  |  | SECI-LEH25MW-DBR-ELE-121 |  |  |  | PENDING
122 | Aux. Load Calculations and Aux. Transformer Sizing (Switchyard & BESS) |  |  | SECI-LEH25MW-DBR-ELE-122 |  |  |  | UNDER EPC
123 | Auxiliary System SLD and DB Details |  |  | SECI-LEH25MW-DWG-ELE-123 |  |  |  | PENDING
124 | 66 kV Switchyard - Short Circuit Force & Cantilever Strength Calculation |  |  | SECI-LEH25MW-DBR-ELE-124 |  |  |  | UNDER OE
125 | Plant End Switchyard Layout |  |  | SECI-LEH25MW-DWG-ELE-125 |  |  |  | UNDER OE
126 | Plant End Substation Earthing Design and Calculation |  |  | SECI-LEH25MW-DWG-ELE-126 |  |  |  | UNDER EPC
127 | Plant End Substation Earthing Layout |  |  | SECI-LEH25MW-DWG-ELE-127 |  |  |  | UNDER OE
128 | Switchyard Cable Trench Layout - layout, design and details |  |  | SECI-LEH25MW-DWG-ELE-128 |  |  |  | PENDING
129 | Switchyard Erection Key Diagram |  |  | SECI-LEH25MW-DWG-ELE-129 |  |  |  | PENDING
130 | Switchyard Illumination Layout |  |  | SECI-LEH25MW-DWG-ELE-130 |  |  |  | PENDING
131 | Fire & Smoke Detection Layout for Buildings and Switchyard along with GTP |  |  | SECI-LEH25MW-DWG-ELE-131 |  |  |  | PENDING
132 | Power Transformer |  |  | SECI-LEH25MW-GTP-ELE-132 |  |  |  | UNDER EPC
133 | NIFP System- Power Transformer |  |  | SECI-LEH25MW-GTP-ELE-133 |  |  |  | PENDING
134 | Lightning Arrestor - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-134 |  |  |  | UNDER OE
135 | Isolator - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-135 |  |  |  | UNDER OE
136 | BPI - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-136 |  |  |  | UNDER OE
137 | Circuit Breaker - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-137 |  |  |  | UNDER OE
138 | Current Transformer (Metering) - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-138 |  |  |  | UNDER OE
139 | Voltage Transformer (Metering) - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-139 |  |  |  | PENDING
140 | ABT Meter- GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-140 |  |  |  | PENDING
141 | Control and Relay panels (GTP, GA & Drawing, QAP and Type Test Reports) |  |  | SECI-LEH25MW-GTP-ELE-141 |  |  |  | PENDING
142 | UPS System MCR building - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-142 |  |  |  | PENDING
143 | Station Auxiliary ACDB - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-143 |  |  |  | PENDING
144 | Power and Control cables - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-144 |  |  |  | PENDING
145 | Protection CT - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-145 |  |  |  | UNDER OE
146 | Protection PT/CVT - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-146 |  |  |  | UNDER OE
147 | Switchyard Illumination - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-147 |  |  |  | PENDING
148 | BMK. JB, MB - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-148 |  |  |  | PENDING
149 | Telemetry system - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-149 |  |  |  | PENDING
150 | Transmission conductor/cable - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-150 |  |  |  | PENDING
151 | Line Disc insulator - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-151 |  |  |  | PENDING
152 | Transmission Line Earthing Details |  |  | SECI-LEH25MW-DWG-ELE-152 |  |  |  | PENDING
153 | Line Hardware Material - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-153 |  |  |  | PENDING
154 | Line Conductor - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-154 |  |  |  | PENDING
155 | Relay setting Calculation & Chart |  |  | SECI-LEH25MW-DBR-ELE-155 |  |  |  | PENDING
156 | Power Transformer Foundation and Burnt Oil Pit DBR |  |  | SECI-LEH25MW-DBR-CIV-156 |  |  |  | UNDER OE
157 | Power Transformer Foundation and Burnt Oil Pit - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-157 |  |  |  | UNDER OE
158 | GA drawing of LA support Structure |  |  | SECI-LEH25MW-DWG-CIV-158 |  |  |  | UNDER OE
159 | GA drawing of ISO support Structure |  |  | SECI-LEH25MW-DWG-CIV-159 |  |  |  | PENDING
160 | GA drawing of CT support Structure |  |  | SECI-LEH25MW-DWG-CIV-160 |  |  |  | PENDING
161 | GA drawing of PT support Structure |  |  | SECI-LEH25MW-DWG-CIV-161 |  |  |  | PENDING
162 | Isolator Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-162 |  |  |  | PENDING
163 | Circuit Breaker Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-163 |  |  |  | PENDING
164 | Current Transformer (Metering and Protection) Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-164 |  |  |  | UNDER EPC
165 | Voltage Transformer (Metering and Protection) Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-165 |  |  |  | UNDER EPC
166 | Lightning Arrestor Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-166 |  |  |  | UNDER OE
167 | ABT Meter Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-167 |  |  |  | PENDING
168 | Gantry - GA and Foundation (as applicable) |  |  | SECI-LEH25MW-DWG-CIV-168 |  |  |  | PENDING
169 | Switchyard DSLP Layout & Calculation |  |  | SECI-LEH25MW-DWG-ELE-169 |  |  |  | PENDING
170 | 66kV HT Conductor |  |  | SECI-LEH25MW-DOC-ELE-170 |  |  |  | PENDING
171 | HT and LT Cable Schedule- Switchyard |  |  | SECI-LEH25MW-DOC-ELE-171 |  |  |  | PENDING
172 | Control Scheme Cable Schedule- Switchyard |  |  | SECI-LEH25MW-DOC-ELE-172 |  |  |  | PENDING
173 | SAS Cable Schedule- Switchyard |  |  | SECI-LEH25MW-DOC-ELE-173 |  |  |  | PENDING
174 | Switchyard Fencing and Gate |  |  | SECI-LEH25MW-DWG-CIV-174 |  |  |  | PENDING
175 | LILO Switchyard Layout |  |  | SECI-LEH25MW-DWG-ELE-175 |  |  |  | PENDING
176 | Transmission line Route Layout |  |  | SECI-LEH25MW-DWG-ELE-176 |  |  |  | PENDING
177 | 66KV line Tower Schedule |  |  | SECI-LEH25MW-DWG-ELE-177 |  |  |  | PENDING
178 | 66KV Line profile |  |  | SECI-LEH25MW-DWG-ELE-178 |  |  |  | PENDING
179 | Transmission Tower- GA and Structural Drawing |  |  | SECI-LEH25MW-DWG-CIV-179 |  |  |  | PENDING
180 | Transmission Tower- Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-180 |  |  |  | PENDING

## Progress Abstract
Daily Progress Report | [9 empty] | Date:- | 2025-08-12
Project Name : |  | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Taru, Leh, UT of Ladakh, India
Client : |  | Solar Energy Corporation of India Ltd
SPV : |  | Prozeal Green Energy Limited | [11 empty] | 3905
Project Start Date |  | 2024-11-20
Project COD |  | 2027-11-05 | [9 empty] | 1080 | 815
Sr. No | Description | Work Status | UOM | Scope | Progress | Balance | %age | Status | Dashboard
CIVIL Package | [11 empty] | COMP
1 | Boundary Fencing | Boundary Demarcation and marking | Rm | 5690 | 5500 | 190 | 96.66% | COMP |  |  |  | WIP
|  | Plie Boring | Rm | 5690 | 4957.5 | 732.5 | 87.13% | WIP |  |  |  | Yet to Start
|  | Fence post Allignment and Concrete Pouring | Rm | 5690 | 5150 | 540 | 90.51% | WIP | [5 empty] | 0.36684 | 0.63316 | 32.35%
|  | Barbed wire installation | Rm | 5690 | 4315 | 1375 | 75.83% | WIP
|  | Mesh installation with connecting strip and tightening | Rm | 5690 | 4335 | 1355 | 76.19% | WIP
|  | Weightage Progress |  | 1 | 0.85264 | 0.14736 | 85.26%
2 | Main Gate | Foundation Excavation | Nos | 3 | 3 | 0 | 100% | COMP
|  | Foundation PCC | Nos | 3 | 3 | 0 | 100% | COMP
|  | Foundation RCC | Nos | 3 | 3 | 0 | 100% | COMP
|  | Columns | Nos | 3 | 3 | 0 | 100% | COMP
|  | Gate Febrication and Installation | Nos | 2 | 2 | 0 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 1 | 0 | 100%
3 | MCR | Excavation | No's | 33 | 33 | 0 | 100% | COMP
|  | Foundation PCC | No's | 33 | 33 | 0 | 100% | WIP
|  | Footing Foundation casting | No's | 33 | 17 | 16 | 51.52% | WIP
|  | Column upto Plinth Beam | No's | 33 | 0 | 33 | 0% | Yet to Start
|  | Plinth Beam Casting | Mtr | 322 | 0 | 322 | 0% | Yet to Start
|  | Column upto Lintel Beam | No's | 33 | 0 | 33 | 0% | Yet to Start
|  | Lintel and sunshade casting | Mtr | 132 | 0 | 132 | 0% | Yet to Start
|  | Column upto Roof Beam | No's | 33 | 0 | 33 | 0% | Yet to Start
|  | Roof Beam & Slab Casting | Ls | 1 | 0 | 1 | 0% | Yet to Start
|  | Cable Trench Raft Casting | Mtr | 50 | 0 | 50 | 0% | Yet to Start
|  | Cable Trench Wall casting | Mtr | 100 | 0 | 100 | 0% | Yet to Start
|  | Floor Slab Casting | Ls | 1 | 0 | 1 | 0% | Yet to Start
|  | Brick Masonry Work | Cu. Mtr | 310 | 0 | 310 | 0% | Yet to Start
|  | Wall & Celling Plaster | Sq. Mtr | 2380 | 0 | 2380 | 0% | Yet to Start
|  | Flooring | No's | 8 | 0 | 0 | 0% | Yet to Start
|  | Putty & Paint work | No's | 8 | 0 | 0 | 0% | Yet to Start
|  | Misc Work | LS | 1 | 0 | 0 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0.15618 | 0.84382 | 15.62%
4 | IDT- Solar | Excavation | No's | 4 | 3 | 1 | 75% | WIP
|  | Foundation PCC | No's | 4 | 3 | 1 | 75% | WIP
|  | Foundation Raft casting | No's | 4 | 3 | 1 | 75% | WIP
|  | Wall casting | No's | 8 | 6 | 2 | 75% | WIP
|  | Cashment Wall B/W | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Fencing - IDT | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0.54545 | 0.45455 | 54.55%
5 | LCR- Solar | Excavation | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Foundation PCC | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Foundation Raft casting | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Pedestal casting | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Slab Casting | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | B/W | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Canopy | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0 | 1 | 0%
6 |  | Pile marking | No's | 27000 | 1632 | 25368 | 6.044% | WIP
|  | Pile Boring | No's | 27000 | 0 | 27000 | 0% | Yet to Start
|  | Pile Casting | No's | 27000 | 0 | 27000 | 0% | Yet to Start
|  | Weightage Progress |  | 27000 | 544 | 26456 | 2.015%
7 | IDT- BESS | Excavation | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Foundation PCC | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Foundation Raft casting | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Wall casting | No's | 10 | 0 | 10 | 0% | Yet to Start
|  | Cashment Wall B/W | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Fencing - IDT | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0 | 1 | 0%
8 | BESS- Civil | Excavation of Container foundation | Nos | 10 | 3 | 7 | 30% | Yet to Start
|  | Container Foundation PCC | Nos | 80 | 0 | 80 | 0% | Yet to Start
|  | Container Foundation Concrete Pouring | Nos | 80 | 0 | 80 | 0% | Yet to Start
|  | Container Pedestal Concrete Pouring | Nos | 80 | 0 | 80 | 0% | Yet to Start
|  | Container Tie Beam & Slab Concrete Pouring | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | B/W of Container Plartform | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | Excavation of PCS foundation | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | PCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | Yet to Start
|  | RCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | Yet to Start
|  | RCC of PCS Pedestal | Nos | 40 | 0 | 40 | 0% | Yet to Start
|  | RCC of PCS Tie Beam | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | B/W of PCS Plartform | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | Weightage Progress | No's | 1 | 0.013636 | 0.98636 | 1.364%
ELECTRICAL Package
33 | Switchyard ELE | Structure Errection | Nos | 97 | 0 | 97 | 0%
34 |  | Equipment Errection | Nos | 97 | 0 | 97 | 0%
35 |  | Earthing Works | Mtr | 3252.375 | 0 | 3252.375 | 0%
36 |  | Cabling Works | LS | 1 | 0 | 1 | 0%
37 |  | Testing Works | LS | 1 | 0 | 1 | 0%
38 |  | Weightage Progress | LS | 689.675 | 0 | 689.675 | 0%
39 | DC Work | Trench Excavation | Mtr | 171000 | 950 | 170050 | 0.5556%
40 |  | 400sqmm Cable Laying(SCB) | No's | 1824 | 0 | 1824 | 0%
41 |  | Inv Installation | No's | 76 | 0 | 76 | 0%
42 |  | 400sqmm Cable Laying | Mtr | 638400 | 0 | 638400 | 0%
43 |  | SCB Stand Casting | No's | 3648 | 0 | 3648 | 0%
44 |  | SCB Installation | No's | 1824 | 0 | 1824 | 0%
45 |  | 6 Sq. mm Termination | No's | 1824 | 0 | 1824 | 0%
46 |  | Termination SCB End | No's | 1824 | 0 | 1824 | 0%
47 |  | Termination Inv End | No's | 1824 | 0 | 0 | 0%
48 |  | Earthing Conductor Laying | Mtr | 95000 | 0 | 95000 | 0%
49 |  | Earthpit Installation | No's | 912 | 0 | 912 | 0%
50 |  | String Cable Termination | No's | 1824 | 0 | 1824 | 0%
51 |  | LA Insatallation | No's | 190 | 0 | 190 | 0%
52 |  | LA Connection | No's | 190 | 0 | 190 | 0%
53 |  | MMS Installation | No's | 14592 | 0 | 14592 | 0%
54 |  | Module Installation | No's | 846336 | 0 | 846336 | 0%
55 |  | Weightage Progress | No's | 1 | 0.00034722 | 0.99965 | 0.03472%
56 | AC Work | AC Trench | Mtr | 26043.8846 | 0 | 26043.8846 | 0%
57 |  | 3CX240sqmm Cable Laying | Mtr | 18269.2308 | 0 | 18269.2308 | 0%
58 |  | 3CX400sqmm Cable Laying | Mtr | 58461.5385 | 0 | 58461.5385 | 0%
59 |  | 1CX400sqmm Cable Laying | LS | 38 | 0 | 38 | 0%
60 |  | OFC Cable Laying | LS | 38 | 0 | 38 | 0%
61 |  | Grid Earthing | mtr | 7600 | 0 | 7600 | 0%
62 |  | Tray support casting | No's | 38 | 0 | 38 | 0%
63 |  | Tray from INV to LV Side | No's | 38 | 0 | 38 | 0%
64 |  | Earthpit Installation | No's | 38 | 0 | 38 | 0%
65 |  | IDT Erection | No's | 38 | 0 | 38 | 0%
66 |  | ICOG Panel | No's | 38 | 0 | 38 | 0%
67 |  | LT Panel | No's | 38 | 0 | 38 | 0%
68 |  | UPS Panel | No's | 38 | 0 | 38 | 0%
69 |  | Aux Trafo | No's | 38 | 0 | 38 | 0%
70 |  | 1C*400Sqmm cable Termination | Sets | 38 | 0 | 38 | 0%
71 |  | Weightage Progress | No's | 1 | 0 | 1 | 0%
16%
MCR CIVIL Work
0%
Fencing Work
85%
100%
55%
0%
IDT- Solar Civil Work
IDT- BESS Civil Work
0%
1%
CIVIL PROGRESS%
2.015%
MMS PILLING

## Civil Progress
Civil Progress | [6 empty] | DAILY PROGRESS
Sr.no. | Description | UOM | Scope | Progress | Balance | % Progress | Cummulative | time axis 2025-05-05 to 2025-10-31
Boundary Fencing |  | Rm | 5690 | 4851.5 | 838.5 | 85.26%
1 | Boundary Demarcation and marking | Rm | 5690 | 5500 | 190 | 96.66% | 5500 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 5250; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 125; 2025-07-03: 125
2 | Plie Boring | Rm | 5690 | 4957.5 | 732.5 | 87.13% | 4957.5 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 4957.5; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
3 | Fence post Allignment and Concrete Pouring | Rm | 5690 | 5150 | 540 | 90.51% | 5150 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 1642.5; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 52; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 75.5; 2025-07-07: 0; 2025-07-08: 250; 2025-07-09: 250; 2025-07-10: 225; 2025-07-11: 272.5; 2025-07-12: 200; 2025-07-13: 250; 2025-07-14: 225; 2025-07-15: 175; 2025-07-16: 192.5; 2025-07-17: 0; 2025-07-18: 175; 2025-07-19: 187.5; 2025-07-20: 0; 2025-07-21: 155; 2025-07-22: 0; 2025-07-23: 187.5; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 35; 2025-08-08: 200; 2025-08-09: 200; 2025-08-10: 200; 2025-08-11: 0; 2025-08-12: 0
4 | Barbed wire installation | Rm | 5690 | 4315 | 1375 | 75.83% | 4315 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 1300; 2025-07-04: 180; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 290; 2025-07-12: 315; 2025-07-13: 315; 2025-07-14: 320; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 100; 2025-07-29: 100; 2025-07-30: 100; 2025-07-31: 100; 2025-08-01: 100; 2025-08-02: 100; 2025-08-03: 100; 2025-08-04: 100; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 195; 2025-08-11: 300; 2025-08-12: 300
5 | Mesh installation with connecting strip and tightening | Rm | 5690 | 4335 | 1355 | 76.19% | 4335 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 1300; 2025-07-04: 180; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 50; 2025-07-10: 60; 2025-07-11: 210; 2025-07-12: 180; 2025-07-13: 180; 2025-07-14: 220; 2025-07-15: 105; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 150; 2025-07-19: 165; 2025-07-20: 0; 2025-07-21: 180; 2025-07-22: 0; 2025-07-23: 180; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 100; 2025-07-29: 100; 2025-07-30: 100; 2025-07-31: 100; 2025-08-01: 100; 2025-08-02: 100; 2025-08-03: 100; 2025-08-04: 100; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 195; 2025-08-11: 90; 2025-08-12: 90
Main Gate |  | Nos | 2.8 | 2.8 | 0 | 100%
1 | Foundation Excavation | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 3
2 | Foundation PCC | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 3
3 | Foundation RCC | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 3
4 | Columns | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 1; 2025-07-12: 2
5 | Gate Febrication and Installation | Nos | 2 | 2 | 0 | 100% | 2 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 2
Street light Work |  | No's | 175 | 0 | 175 | 0%
1 | Pole Casting | No's | 175 | 0 | 175 | 0% | 0
2 | Light Erection | No's | 175 | 0 | 175 | 0% | 0
MCR | [5 empty] | 15.62%
1 | Excavation | No's | 33 | 33 | 0 | 100% | 33 | 2025-06-24: 33
2 | Foundation PCC | No's | 33 | 33 | 0 | 100% | 33 | 2025-06-24: 17; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 5; 2025-07-21: 11
3 | Foundation Reinforcement | No's | 33 | 17 | 16 | 51.52% | 17 | 2025-06-24: 17; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
4 | Foundation Shuttering | No's | 33 | 17 | 16 | 51.52% | 17 | 2025-06-24: 17; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
5 | Footing Foundation casting | No's | 33 | 17 | 16 | 51.52% | 17 | 2025-06-24: 17; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
6 | Back filling | No's | 33 | 17 | 16 | 51.52% | 17 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 17; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
7 | Column upto Plinth Beam | No's | 33 | 0 | 33 | 0% | 0 | 2025-06-24: 0
8 | Plinth Beam Reinforcement | Mtr | 322 | 0 | 322 | 0% | 0 | 2025-06-24: 0
9 | Plinth Beam shuttering | Mtr | 322 | 0 | 322 | 0% | 0 | 2025-06-24: 0
10 | Plinth Beam Casting | Mtr | 322 | 0 | 322 | 0% | 0 | 2025-06-24: 0
11 | Column upto Lintel Beam | No's | 33 | 0 | 33 | 0% | 0 | 2025-06-24: 0
12 | Lintel and sunshade reinforcement & shuttering | Mtr | 132 | 0 | 132 | 0% | 0 | 2025-06-24: 0
13 | Lintel and sunshade casting | Mtr | 132 | 0 | 132 | 0% | 0 | 2025-06-24: 0
14 | Cable Trench PCC Base | Mtr | 50 | 0 | 50 | 0% | 0 | 2025-06-24: 0
15 | Cable Trench Reinforcement & Shuttering | Mtr | 50 | 0 | 50 | 0% | 0 | 2025-06-24: 0
16 | Cable Trench Raft Casting | Mtr | 50 | 0 | 50 | 0% | 0 | 2025-06-24: 0
17 | Cable Trench Wall casting | Mtr | 100 | 0 | 100 | 0% | 0 | 2025-06-24: 0
18 | Column upto Roof Beam | No's | 33 | 0 | 33 | 0% | 0 | 2025-06-24: 0
19 | Roof Beam & Slab shuttering | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
20 | Roof Beam & Slab reinforcement | Ls | 1 | 0 |  |  | 0 | 2025-06-24: 0
21 | Roof Beam & Slab Casting | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
22 | Floor Slab Casting | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
23 | Brick Masonry Work | Cu. Mtr | 310 | 0 | 310 | 0% | 0 | 2025-06-24: 0
24 | Wall & Celling Plaster | Sq. Mtr | 2380 | 0 | 2380 | 0% | 0 | 2025-06-24: 0
25 | Flooring | No's | 8 | 0 | 0 | 0%
| Scada Room (10 x 7.8)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Conference Room (5.2 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Manager Room (2.5 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Store Room (2.51 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Battery Room (4.6 x 4.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| LT Panel Room (4.2 x 8.25)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Toilet (2.85 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Pantry Room (2.4 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
26 | Putty & Paint work | No's | 8 | 0 | 0 | 0%
| Scada Room (10 x 7.8)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Conference Room (5.2 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Manager Room (2.5 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Store Room (2.51 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Battery Room (4.6 x 4.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| LT Panel Room (4.2 x 8.25)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Toilet (2.85 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Pantry Room (2.4 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
27 | Misc Work | LS | 1 | 0 | 0 | 0%
| Drain | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Ramp | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Steps | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Septic Tank | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Soak Pit | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Plumbing Works | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Electrical works | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
IDT- Solar |  |  |  | 3 |  | 54.55%
1 | Excavation | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
2 | Foundation PCC | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
3 | Foundation Raft Reinforcement | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
4 | Foundation Raft Shuttering | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
5 | Foundation Raft casting | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
6 | Wall Reinforcement | No's | 8 | 6 | 2 | 75% | 6 | 2025-06-24: 6
7 | Wall Shuttering | No's | 8 | 6 | 2 | 75% | 6 | 2025-06-24: 6
8 | Wall casting | No's | 8 | 6 | 2 | 75% | 6 | 2025-06-24: 6
9 | Back filling | No's | 4 | 0 | 4 | 0% | 0 | 2025-06-24: 0
10 | Cashment Wall B/W | No's | 4 | 0 | 4 | 0% | 0 | 2025-06-24: 0
11 | Fencing - IDT | No's | 4 | 0 | 4 | 0% | 0 | 2025-06-24: 0
LCR- Solar | [5 empty] | 0%
1 | Excavation | No's | 32 | 0 | 32 | 0% | 0
2 | Foundation PCC | No's | 32 | 0 | 32 | 0% | 0
3 | Foundation Raft Reinforcement | No's | 32 | 0 | 32 | 0% | 0
4 | Foundation Raft Shuttering | No's | 32 | 0 | 32 | 0% | 0
5 | Foundation Raft casting | No's | 32 | 0 | 32 | 0% | 0
6 | Pedestal Reinforcement | No's | 32 | 0 | 32 | 0% | 0
7 | Pedestal Shuttering | No's | 32 | 0 | 32 | 0% | 0
8 | Pedestal casting | No's | 32 | 0 | 32 | 0% | 0
9 | Slab Shuttering & Reinforcement | No's | 4 | 0 | 4 | 0% | 0
10 | Slab Casting | No's | 4 | 0 | 4 | 0% | 0
11 | B/W | No's | 4 | 0 | 4 | 0% | 0
12 | Canopy | No's | 4 | 0 | 4 | 0% | 0
IDT- BESS |  |  |  | 0 |  | 0%
1 | Excavation | No's | 5 | 0 | 5 | 0% | 0
2 | Foundation PCC | No's | 5 | 0 | 5 | 0% | 0
3 | Foundation Raft Reinforcement | No's | 5 | 0 | 5 | 0% | 0
4 | Foundation Raft Shuttering | No's | 5 | 0 | 5 | 0% | 0
5 | Foundation Raft casting | No's | 5 | 0 | 5 | 0% | 0
6 | Wall Reinforcement | No's | 10 | 0 | 10 | 0% | 0
7 | Wall Shuttering | No's | 10 | 0 | 10 | 0% | 0
8 | Wall casting | No's | 10 | 0 | 10 | 0% | 0
9 | Back filling | No's | 5 | 0 | 5 | 0% | 0
10 | Cashment Wall B/W | No's | 5 | 0 | 5 | 0% | 0
11 | Fencing - IDT | No's | 5 | 0 | 5 | 0% | 0
BESS Foundation |  |  |  | 0.13636 |  | 1.364%
1 | Excavation of Container foundation | Nos | 10 | 3 | 7 | 30% | 3 | bar: 2025-08-02 to 2025-08-04
2 | Container Foundation PCC | Nos | 80 | 0 | 80 | 0% | 0
3 | Container Foundation Reinforcement | Nos | 80 | 0 | 80 | 0% | 0
4 | Container Foundation Shuttering | Nos | 80 | 0 | 80 | 0% | 0
5 | Container Foundation Concrete Pouring | Nos | 80 | 0 | 80 | 0% | 0
6 | Container Pedestal Reinforcement | Nos | 80 | 0 | 80 | 0% | 0
7 | Container Pedestal Shuttering | Nos | 80 | 0 | 80 | 0% | 0
8 | Container Pedestal Concrete Pouring | Nos | 80 | 0 | 80 | 0% | 0
9 | Container Tie Beam & Slab Reinforcement | Nos | 10 | 0 | 10 | 0% | 0
10 | Container Tie Beam & Slab Shuttering | Nos | 10 | 0 | 10 | 0% | 0
11 | Container Tie Beam & Slab Concrete Pouring | Nos | 10 | 0 | 10 | 0% | 0
12 | B/W of Container Plartform | Nos | 10 | 0 | 10 | 0% | 0
13 | Excavation of PCS foundation | Nos | 10 | 0 | 10 | 0% | 0
14 | PCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0
15 | Reinforcement of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0
16 | Shuttering of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0
17 | RCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0
18 | Reinforcement & Shuttering of PCS Pedestal | Nos | 40 | 0 | 40 | 0% | 0
19 | RCC of PCS Pedestal | Nos | 40 | 0 | 40 | 0% | 0
20 | Reinforcement & Shuttering of PCS Tie Beam | Nos | 10 | 0 | 10 | 0% | 0
21 | RCC of PCS Tie Beam | Nos | 10 | 0 | 10 | 0% | 0
22 | B/W of PCS Plartform | Nos | 10 | 0 | 10 | 0% | 0

## ICR Pilling
ICR NO. | Scope | Piling Progress | Progress in % | time axis 2025-05-30 to 2025-10-31
Total | 27000 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 6750 | 0 | 0%
2 | 6750 | 0 | 0%
3 | 6750 | 0 | 0%
4 | 6750 | 0 | 0%

## SW Civil
Switchyard Equipment Progress
Sr. No. | Description | UOM | Weightage Scope | Weightage completion | Equipments | Foundation Scope (Nos) | Excavation |  |  |  | PCC |  |  |  | Raft Foundation |  |  |  | Column casting/J-bolt fixing
[7 empty] | Start Date | End Date | Progress | Percentage | Start Date | End Date | Progress | Percentage | Start Date | End Date | Progress | Percentage | Start Date | End Date | Progress | Percentage |  | Sr. No. | Description | Activity | Unit | Equipment | Foundation | Cummulative | Balance | time axis 2024-11-12 to 2025-05-14
1 | Tower Foundation | Nos | 15% | 0% | 14 | 14 |  |  | 0 | 0% | 1900-01-01 | 1900-01-26 | 0 | 0% | 1900-01-26 | 1900-02-15 | 0 | 0% | 1900-02-05 | 1900-02-25 | 0 | 0% | 0 | 1 | Tower Foundation | EXC | Nos | 14 | 14 | 0 | 14
2 | Power Transformer | Nos | 15% | 0% | 2 | 2 |  |  | 0 | 0% | 0 | 1900-01-05 | 0 | 0% | 1900-01-15 | 1900-01-25 | 0 | 0% | 1900-01-26 | 1900-02-20 | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 14
3 | LM Tower | Nos | 1% | 0% | 1 | 1 |  |  | 0 | 0% | 1899-12-31 | 1900-01-01 | 0 | 0% | 1900-02-16 | 1900-02-19 | 0 | 0% | 1900-02-21 | 1900-02-25 | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 14
4 | LA | Nos | 2% | 0% | 3 | 3 |  |  | 0 | 0% | 0 | 1899-12-31 | 0 | 0% | 1900-01-01 | 1900-01-03 | 0 | 0% | 1900-01-04 | 1900-01-08 | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 14
5 | HLA | Nos | 1% | 0% | 6 | 6 |  |  | 0 | 0% | 0 | 1899-12-31 | 0 | 0% | 1900-01-01 | 1900-01-02 | 0 | 0% | 1900-01-03 | 1900-01-06 | 0 | 0% | 0 | 2 | Power Transformer | EXC | Nos | 2 | 2 | 0 | 2
6 | CB | Nos | 4% | 0% | 12 | 12 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 2
7 | Wave Trap | Nos | 1% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 2
8 | LINE CVT | Nos | 2% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 2
9 | BUS CVT | Nos | 4% | 0% | 6 | 6 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 3 | LM Tower | EXC | Nos | 1 | 1 | 0 | 1
10 | MCVT | Nos | 1% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 1
11 | HCT | Nos | 4% | 0% | 12 | 12 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 1
12 | MCT | Nos | 1% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 1
13 | ISO with ES | Nos | 4% | 0% | 18 | 18 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 4 | LA | EXC | Nos | 3 | 3 | 0 | 3
14 | ISO | Nos | 8% | 0% | 42 | 42 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 3
15 | Isolator-T | Nos | 2% | 0% | 18 | 18 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 3
16 | HBPI | Nos | 3% | 0% | 6 | 6 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 3
17 | BPI | Nos | 8% | 0% | 17 | 17 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 5 | HLA | EXC | Nos | 6 | 6 | 0 | 6
18 | Aux Trafo | Nos | 1% | 0% | 2 | 2 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 6
19 | BMK | Nos | 2% | 0% | 4 | 4 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 6
20 | NIFPS | Nos | 2% | 0% | 2 | 2 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 6
21 | BOT Oil Pit | Nos | 2% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 6 | CB | EXC | Nos | 12 | 12 | 0 | 12
22 | Cable Trench | mtr | 5% | 0% | 315 | 315 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 12
23 | Rain Water Drain | Mtr | 0.5% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 12
24 | Fencing | Nos | 1% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% | [8 empty] | 0 |  |  | Column |  |  |  | 0 | 12
25 | Road | Ls | 6% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 7 | Wave Trap | EXC | Nos | 3 | 3 | 0 | 3
26 | Gravel Filling | Ls | 4% | 0% | 0 | 1
Total |  |  | 99.5% | 0% | 152 | 152 | 0 | 0 | 0 | 0% | 0 | 1900-01-26 | 0 | 0% | 1900-01-01 | 1900-02-19 | 0 | 0% | 1900-01-03 | 1900-02-25 | 0 | 0% |  |  |  | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 8 | Line-CVT | EXC | Nos | 3 | 3 | 0 | 3
[26 empty] | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 9 | BUS CVT | EXC | Nos | 6 | 6 | 0 | 6
[26 empty] | PCC |  |  |  | 0 | 6
[26 empty] | Raft |  |  |  | 0 | 6
[26 empty] | Column |  |  |  | 0 | 6
[24 empty] | 10 | MCVT | EXC | Nos | 3 | 3 | 0 | 3
[26 empty] | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 11 | HCT | EXC | Nos | 12 | 12 | 0 | 12
[26 empty] | PCC |  |  |  | 0 | 12
[26 empty] | Raft |  |  |  | 0 | 12
[26 empty] | Column |  |  |  | 0 | 12
[24 empty] | 12 | MCT | EXC | Nos | 3 | 3 | 0 | 3
[26 empty] | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 13 | ISO with ES | EXC | Nos | 18 | 18 | 0 | 18
[26 empty] | PCC |  |  |  | 0 | 18
[26 empty] | Raft |  |  |  | 0 | 18
[26 empty] | Column |  |  |  | 0 | 18
[24 empty] | 14 | ISO | EXC | Nos | 42 | 42 | 0 | 42
[26 empty] | PCC |  |  |  | 0 | 42
[26 empty] | Raft |  |  |  | 0 | 42
[26 empty] | Column |  |  |  | 0 | 42
[24 empty] | 15 | ISO -T | EXC | Nos | 18 | 18 | 0 | 18
[26 empty] | PCC |  |  |  | 0 | 18
[26 empty] | Raft |  |  |  | 0 | 18
[26 empty] | Column |  |  |  | 0 | 18
[24 empty] | 16 | HBPI | EXC | Nos | 6 | 6 | 0 | 6
[26 empty] | PCC |  |  |  | 0 | 6
[26 empty] | Raft |  |  |  | 0 | 6
[26 empty] | Column |  |  |  | 0 | 6
[24 empty] | 17 | BPI | EXC | Nos | 17 | 17 | 0 | 17
[26 empty] | PCC |  |  |  | 0 | 17
[26 empty] | Raft |  |  |  | 0 | 17
[26 empty] | Column |  |  |  | 0 | 17
[24 empty] | 18 | Aux Trafo | EXC | Nos | 2 | 2 | 0 | 2
[26 empty] | PCC |  |  |  | 0 | 2
[26 empty] | Raft |  |  |  | 0 | 2
[26 empty] | Column |  |  |  | 0 | 2
[24 empty] | 19 | BMK | EXC | Nos | 4 | 4 | 0 | 4
[26 empty] | PCC |  |  |  | 0 | 4
[26 empty] | Raft |  |  |  | 0 | 4
[26 empty] | Column |  |  |  | 0 | 4
[24 empty] | 20 | NIFPS | EXC | Nos | 2 | 2 | 0 | 2
[26 empty] | PCC |  |  |  | 0 | 2
[26 empty] | Raft |  |  |  | 0 | 2
[26 empty] | Column |  |  |  | 0 | 2
[24 empty] | 21 | BOT Oil Pit | EXC | Nos | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Wall |  |  |  | 0 | 1
[24 empty] | 22 | Cable Trench | EXC | Mtr | 315 | 315 | 0 | 315
[26 empty] | PCC |  |  |  | 0 | 315
[26 empty] | Raft |  |  |  | 0 | 315
[26 empty] | Wall |  |  |  | 0 | 315
[24 empty] | 23 | Rain Water Drain | EXC | LS | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Column |  |  |  | 0 | 1
[24 empty] | 24 | Fencing | EXC | LS | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Column |  |  |  | 0 | 1
[24 empty] | 25 | Road | EXC | LS | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Column |  |  |  | 0 | 1
[24 empty] | TOTAL |  |  |  | 496 | 496
Formulas:
PCC = [Excavation]+2
PCC = MIN(M4:[PCC, row above])
Raft Foundation = [PCC]+25
Column casting/J-bolt fixing = [Raft Foundation]+10
Excavation = MIN(I4:[Excavation, row above])

## SY ELE
Electrical Progress | [13 empty] | DAILY PROGRESS
Sr.no. | Description | UOM | Scope | Progress | Balance | % Progress | BaseLine Plan |  |  | Forecast |  |  | Remarks | Cummulative | time axis 2024-12-01 to 2025-05-31
[7 empty] | Start Date | Finish Date | Days | Start Date | Finish Date | Days
MCR | [5 empty] | 0% | 2024-03-11 | 2025-06-30 |  | 2024-03-11 | 2025-06-30
| Panel Installation | No's | 44 | 0 | 44 | 0% | 2024-03-11 | 2025-04-04 | 389 | 2024-03-11 | 2025-04-04 | 389
1 | 33KV HT & Bus Bar Panel | Set | 4 | 0 | 4 | 0% | 2025-03-20 | 2025-04-04 | 15 | 2025-03-20 | 2025-04-04 | 15 |  | 0
2 | C&R Panel | No's | 7 | 0 | 7 | 0% | 2024-03-11 | 2024-03-21 | 10 | 2024-03-11 | 2024-03-21 | 10 |  | 0
3 | Busbar Panel | No's | 1 | 0 | 1 | 0% | 2025-03-20 | 2025-03-22 | 2 | 2025-03-20 | 2025-03-22 | 2
4 | PPC | No's | 1 | 0 | 1 | 0% | 2024-03-13 | 2024-03-14 | 1 | 2024-03-13 | 2024-03-14 | 1 |  | 0
5 | MU PLC 2 | No's | 2 | 0 | 2 | 0% | 2024-03-15 | 2024-03-17 | 2 | 2024-03-15 | 2024-03-17 | 2 |  | 0
6 | Fote Panel | No's | 1 | 0 | 1 | 0% | 2024-03-18 | 2024-03-21 | 3 | 2024-03-18 | 2024-03-21 | 3 |  | 0
7 | CCTV Panel | No's | 1 | 0 | 1 | 0% | 2024-03-22 | 2024-03-24 | 2 | 2024-03-22 | 2024-03-24 | 2 |  | 0
8 | PLCC Panel | No's | 1 | 0 | 1 | 0% | 2024-03-25 | 2024-03-27 | 2 | 2024-03-25 | 2024-03-27 | 2 |  | 0
9 | RTCC Panel | No's | 2 | 0 | 2 | 0% | 2024-03-28 | 2024-03-30 | 2 | 2024-03-28 | 2024-03-30 | 2 |  | 0
10 | PLC/Scada | No's | 1 | 0 | 1 | 0% | 2024-03-31 | 2024-04-06 | 6 | 2024-03-31 | 2024-04-06 | 6
11 | SAS Panel | No's | 1 | 0 | 1 | 0% | 2024-03-31 | 2024-04-02 | 2 | 2024-03-31 | 2024-04-02 | 2 |  | 0
12 | ACDB | No's | 1 | 0 | 1 | 0% | 2024-04-03 | 2024-04-06 | 3 | 2024-04-03 | 2024-04-06 | 3 |  | 0
13 | Lighting DB | No's | 1 | 0 | 1 | 0% | 2024-04-07 | 2024-04-08 | 1 | 2024-04-07 | 2024-04-08 | 1 |  | 0
14 | ELDB | No's | 1 | 0 | 1 | 0% | 2024-04-08 | 2024-04-09 | 1 | 2024-04-08 | 2024-04-09 | 1
15 | UPS | No's | 2 | 0 | 2 | 0% | 2024-04-09 | 2024-04-14 | 5 | 2024-04-09 | 2024-04-14 | 5 |  | 0
16 | UPS DB | No's | 1 | 0 | 1 | 0% | 2024-04-10 | 2024-04-11 | 1 | 2024-04-10 | 2024-04-11 | 1 |  | 0
17 | UPS Battery | Set | 4 | 0 | 4 | 0% | 2024-04-11 | 2024-04-12 | 1 | 2024-04-11 | 2024-04-12 | 1
18 | Battery Charger & DCDB (220V) | No's | 2 | 0 | 2 | 0% | 2024-04-12 | 2024-04-14 | 2 | 2024-04-12 | 2024-04-14 | 2 |  | 0
19 | Battery Bank (220V) | No's | 2 | 0 | 2 | 0% | 2024-04-13 | 2024-04-17 | 4 | 2024-04-13 | 2024-04-17 | 4
20 | Battery Charger (48V) & DCDB | No's | 2 | 0 | 2 | 0% | 2024-04-14 | 2024-04-16 | 2 | 2024-04-14 | 2024-04-16 | 2 |  | 0
21 | Battery Bank (48V) | Set | 2 | 0 | 2 | 0% | 2024-04-15 | 2024-04-17 | 2 | 2024-04-15 | 2024-04-17 | 2 |  | 0
22 | NIFPS CP | No's | 2 | 0 | 2 | 0% | 2024-04-16 | 2024-04-17 | 1 | 2024-04-16 | 2024-04-17 | 1 |  | 0
23 | PC with Table | Lot | 1 | 0 | 1 | 0% | 2024-04-17 | 2024-04-19 | 2 | 2024-04-17 | 2024-04-19 | 2 |  | 0
24 | Illumination | Lot | 1 | 0 | 1 | 0% | 2024-04-18 | 2024-04-23 | 5 | 2024-04-18 | 2024-04-23 | 5 |  | 0
SW Electrical Works
| SW Earthing works |  | 3252.375 | 0 | 3252.375 | 0% | 2025-03-22 | 2025-04-27 | 36 | 2025-03-22 | 2025-05-21 | 60
1 | Excavation for Grid Earth Mat | Mtr | 7500 | 0 | 7500 | 0% | 2025-03-22 | 2025-03-28 | 6 | 2025-03-22 | 2025-04-09 | 18 |  | 0
2 | Grid Earthing- MS Rod (32mm) | Mtr | 7500 | 0 | 7500 | 0% | 2025-03-24 | 2025-04-01 | 8 | 2025-03-24 | 2025-04-13 | 20 |  | 0
3 | 75*12mm GI Flat for equiment earthing | Mtr | 2500 | 0 | 2500 | 0% | 2025-03-27 | 2025-04-04 | 8 | 2025-03-28 | 2025-04-12 | 15
4 | 50*6 mm GI Flat for equipment & fencing | Mtr | 900 | 0 | 900 | 0% | 2025-04-05 | 2025-04-20 | 15 | 2025-04-12 | 2025-04-16 | 4
5 | Aux Mat | Nos | 34 | 0 | 34 | 0% | 2025-04-02 | 2025-04-08 | 6 | 2025-04-19 | 2025-04-27 | 8 |  | 0
7 | Backfilling | Mtr | 7500 | 0 | 7500 | 0% | 2025-04-08 | 2025-04-23 | 15 | 2025-04-28 | 2025-05-04 | 6 |  | 0
6 | Earthing Ms Rod | Nos | 60 | 0 | 60 | 0% | 2025-04-07 | 2025-04-22 | 15 | 2025-05-05 | 2025-05-13 | 8 |  | 0
8 | Earthing Pipe GI | Nos | 25 | 0 | 25 | 0% | 2025-04-13 | 2025-04-27 | 14 | 2025-05-13 | 2025-05-21 | 8 |  | 0
| SW Structural |  | 97 | 0 | 97 | 0% | 2025-03-01 | 2025-05-03 | 63 | 2025-03-16 | 2025-04-07 | 22
1 | Tower (T-1,2,4,5) | Nos | 14 | 0 | 14 | 0% | 2025-03-01 | 2025-03-31 | 30 | 2025-03-16 | 2025-04-01 | 16 |  | 0
2 | LM Tower | Nos | 1 | 0 | 1 | 0% | 2025-04-12 | 2025-04-15 | 3 | 2025-03-16 | 2025-04-01 | 16 |  | 0
3 | HLA | Nos | 6 | 0 | 6 | 0% | 2025-04-12 | 2025-04-19 | 7 | 2025-03-27 | 2025-03-27 | 0 |  | 0
4 | HL-BPI | Nos | 6 | 0 | 6 | 0% | 2025-04-16 | 2025-04-18 | 2 | 2025-03-28 | 2025-03-28 | 0 |  | 0
5 | CT | Nos | 12 | 0 | 12 | 0% | 2025-04-01 | 2025-04-11 | 10 | 2025-03-29 | 2025-03-29 | 0 |  | 0
6 | CB | Set | 4 | 0 | 4 | 0% | 2025-04-12 | 2025-04-17 | 5 | 2025-03-30 | 2025-03-30 | 0 |  | 0
7 | BPI | Nos | 17 | 0 | 17 | 0% | 2025-04-18 | 2025-04-23 | 5 | 2025-03-31 | 2025-03-31 | 0 |  | 0
8 | CVT | Nos | 9 | 0 | 9 | 0% | 2025-04-12 | 2025-04-15 | 3 | 2025-04-01 | 2025-04-01 | 0 |  | 0
9 | 3-Ph HDB Motorized Isolator with Single motorized ES ( 3-PH) | Set | 5 | 0 | 5 | 0% | 2025-04-16 | 2025-04-20 | 4 | 2025-04-02 | 2025-04-02 | 0
10 | 3-Ph HDB Motorized Isolator with Double motorized ES (3-Ph) | Set | 5 | 0 | 5 | 0% | 2025-04-21 | 2025-04-25 | 4 | 2025-04-03 | 2025-04-03 | 0
11 | 3-Ph HDB motorized tandem Isolator | Set | 3 | 0 | 3 | 0% | 2025-04-26 | 2025-04-28 | 2 | 2025-04-04 | 2025-04-04 | 0 |  | 0
12 | MCT | NOs | 3 | 0 | 3 | 0% | 2025-04-29 | 2025-05-01 | 2 | 2025-04-05 | 2025-04-05 | 0
13 | MCVT | NOs | 3 | 0 | 3 | 0% | 2025-05-02 | 2025-05-03 | 1 | 2025-04-06 | 2025-04-06 | 0
14 | Wave Trap | Nos | 2 | 0 | 2 | 0% | 2025-04-12 | 2025-04-15 | 3 | 2025-04-07 | 2025-04-07 | 0 |  | 0
15 | LA | Nos | 3 | 0 | 3 | 0% | 2025-04-16 | 2025-04-19 | 3 | 2025-04-07 | 2025-04-07 | 0 |  | 0
16 | NIFPS Panel, piping with Support structure | Lot | 2 | 0 | 2 | 0% | 2025-04-20 | 2025-04-23 | 3 | 2025-04-04 | 2025-04-04 | 0 |  | 0
17 | Clamp & Connector | Lot | 1 | 0 | 1 | 0% | 2025-04-24 | 2025-04-29 | 5 | 2025-04-07 | 2025-04-07 | 0 |  | 0
18 | Spacers fixing | Lot | 1 | 0 | 1 | 0% | 2025-04-27 | 2025-05-02 | 5 | 2025-04-07 | 2025-04-07 | 0
| Equipment Errection |  | 97 | 0 | 97 | 0% | 2025-01-15 | 2025-05-31 | 136 | 2025-03-10 | 2025-04-26 | 47
1 | Power Transformer | Nos | 2 | 0 | 2 | 0% | 2025-01-15 | 2025-01-30 | 15 | 2025-03-10 | 2025-03-12 | 2 |  | 0
2 | HLA along with Accessories | Nos | 6 | 0 | 6 | 0% | 2025-04-19 | 2025-04-29 | 10 | 2025-04-01 | 2025-04-02 | 1 |  | 0
3 | HL-BPI | Nos | 6 | 0 | 6 | 0% | 2025-04-18 | 2025-04-22 | 4 | 2025-04-02 | 2025-04-03 | 1 |  | 0
4 | CT | Nos | 12 | 0 | 12 | 0% | 2025-04-11 | 2025-04-21 | 10 | 2025-04-03 | 2025-04-05 | 2 |  | 0
5 | CB (3-PH) | Set | 4 | 0 | 4 | 0% | 2025-04-17 | 2025-04-25 | 8 | 2025-04-05 | 2025-04-06 | 1 |  | 0
6 | BPI | Nos | 17 | 0 | 17 | 0% | 2025-04-26 | 2025-05-11 | 15 | 2025-04-06 | 2025-04-08 | 2 |  | 0
7 | CVT | Nos | 9 | 0 | 9 | 0% | 2025-04-15 | 2025-04-23 | 8 | 2025-04-08 | 2025-04-09 | 1 |  | 0
8 | 3-Ph HDB Motorized Isolator with Single motorized ES ( 3-PH) | Set | 5 | 0 | 5 | 0% | 2025-04-20 | 2025-05-05 | 15 | 2025-04-09 | 2025-04-11 | 2 |  | 0
9 | 3-Ph HDB Motorized Isolator with Double motorized ES (3-Ph) | Set | 5 | 0 | 5 | 0% | 2025-04-23 | 2025-05-08 | 15 | 2025-04-11 | 2025-04-14 | 3 |  | 0
10 | 3-Ph HDB motorized tandem Isolator | Set | 3 | 0 | 3 | 0% | 2025-04-24 | 2025-05-04 | 10 | 2025-04-14 | 2025-04-16 | 2 |  | 0
11 | MCT | Nos | 3 | 0 | 2 | 0% | 2025-05-01 | 2025-05-03 | 2 | 2025-04-16 | 2025-04-17 | 1 |  | 0
12 | MCVT | Nos | 3 | 0 | 3 | 0% | 2025-05-04 | 2025-05-08 | 4 | 2025-04-17 | 2025-04-18 | 1 |  | 0
13 | Wave Trap | Nos | 2 | 0 | 2 | 0% | 2025-04-16 | 2025-04-20 | 4 | 2025-04-18 | 2025-04-19 | 1 |  | 0
14 | LA | Nos | 3 | 0 | 3 | 0% | 2025-04-24 | 2025-04-28 | 4 | 2025-04-19 | 2025-04-21 | 2 |  | 0
15 | Aux Traffo | Nos | 2 | 0 | 2 | 0% | 2025-03-02 | 2025-03-04 | 2 | 2025-04-10 | 2025-04-15 | 5 |  | 0
16 | BMK | Nos | 4 | 0 | 4 | 0% | 2025-04-30 | 2025-05-04 | 4 | 2025-04-20 | 2025-04-26 | 6 |  | 0
17 | CT JB | Nos | 4 | 0 | 4 | 0% | 2025-05-06 | 2025-05-08 | 2 | 2025-04-20 | 2025-04-26 | 6 |  | 0
18 | CVT JB | Nos | 3 | 0 | 3 | 0% | 2025-05-09 | 2025-05-11 | 2 | 2025-04-20 | 2025-04-26 | 6 |  | 0
20 | Capacitor Bank ( SVG) | Lot | 2 | 0 | 2 | 0% | 2025-05-11 | 2025-05-19 | 8 | 2025-04-20 | 2025-04-26 | 6 |  | 0
21 | Metering Cubical | Nos | 1 | 0 | 1 | 0% | 2025-05-27 | 2025-05-31 | 4 | 2025-04-20 | 2025-04-26 | 6 |  | 0
22 | Yard illumination along with Accessories | Lot | 1 | 0 | 1 | 0% | 2025-05-15 | 2025-05-23 | 8 | 2025-04-20 | 2025-04-26 | 6 |  | 0
| Stringing, IPS Tubing & Cable tray |  | 1 | 0 | 1 | 0% | 2025-02-01 | 2025-05-28 | 116 | 2025-04-27 | 2025-05-13 | 16 |  | 0
1 | Clamp & connector | Lot | 1 | 0 | 1 | 0% | 2025-04-28 | 2025-05-13 | 15 | 2025-04-28 | 2025-05-02 | 4 |  | 0
2 | 4" IPS Al Tube installation | Lot | 1 | 0 | 1 | 0% | 2025-05-27 | 2025-05-28 | 1 | 2025-05-03 | 2025-05-05 | 2 |  | 0
3 | TWIN AL-59 Moose conductor ( Jumper) | Lot | 1 | 0 | 1 | 0% | 2025-04-28 | 2025-05-03 | 5 | 2025-05-06 | 2025-05-08 | 2 |  | 0
4 | Spacers | Lot | 1 | 0 | 1 | 0% | 2025-02-01 | 2025-03-01 | 28 | 2025-05-09 | 2025-05-11 | 2 |  | 0
5 | Sheild wire Support Cleat with tower | Lot | 1 | 0 | 1 | 0% | 2025-05-04 | 2025-05-08 | 4 | 2025-05-12 | 2025-05-13 | 1 |  | 0
6 | HDPE Pipe laying in switchyard | Lot | 1 | 0 | 1 | 0% | 2025-03-01 | 2025-03-08 | 7 | 2025-04-27 | 2025-04-30 | 3 |  | 0
7 | Cable Tray installation with support in switchyard | Lot | 1 | 0 | 1 | 0% | 2025-03-09 | 2025-03-16 | 7 | 2025-05-01 | 2025-05-05 | 4 |  | 0
8 | Cable Tray installation with support in MCR | Lot | 1 | 0 | 1 | 0% | 2025-03-01 | 2025-03-06 | 5 | 2025-05-06 | 2025-05-10 | 4 |  | 0
| SW cable laying & Termination |  | 1 | 0 | 1 | 0% | 2025-02-07 | 2025-05-22 | 104 | 2025-05-02 | 2025-05-17 | 15 |  | 0
1 | 33KV HT Cable laying ( Outgoing HT Switchgear to PTR) | Lot | 1 | 0 | 1 | 0% | 2025-02-07 | 2025-02-17 | 10 | 2025-05-02 | 2025-05-06 | 10 |  | 0
2 | LT Power cable Laying | Lot | 1 | 0 | 1 | 0% | 2025-02-25 | 2025-03-12 | 15 | 2025-05-04 | 2025-05-08 | 15 |  | 0
3 | Control cable laying | Lot | 1 | 0 | 1 | 0% | 2025-03-15 | 2025-03-25 | 10 | 2025-05-05 | 2025-05-09 | 10 |  | 0
4 | Communication cable laying | Lot | 1 | 0 | 1 | 0% | 2025-04-04 | 2025-04-09 | 5 | 2025-05-05 | 2025-05-09 | 5 |  | 0
5 | Glanding | Lot | 1 | 0 | 1 | 0% | 2025-04-29 | 2025-05-04 | 5 | 2025-05-09 | 2025-05-13 | 5 |  | 0
6 | Termination | Lot | 1 | 0 | 1 | 0% | 2025-05-12 | 2025-05-22 | 10 | 2025-05-13 | 2025-05-17 | 10 |  | 0
| Earthing |  | 52 | 0 | 52 | 0% | 2025-03-02 | 2025-04-02 | 31 | 2025-04-10 | 2025-04-26 | 16 |  | 0
1 | Drilling | Nos | 52 | 0 | 52 | 0% | 2025-03-02 | 2025-03-27 | 25 | 2025-04-10 | 2025-04-18 | 8 |  | 0
2 | Rod installtion | Nos | 52 | 0 | 52 | 0% | 2025-03-07 | 2025-04-01 | 25 | 2025-04-14 | 2025-04-22 | 8 |  | 0
3 | Pit Connection | Nos | 52 | 0 | 52 | 0% | 2025-03-08 | 2025-04-02 | 25 | 2025-04-22 | 2025-04-26 | 4 |  | 0
| Commissioning |  | 1 | 0 | 1 | 0% | 2025-04-04 | 2025-06-30 | 87 | 2025-04-27 | 2025-06-30 | 64 |  | 0
1 | Switchyard equipment Testing | Lot | 1 | 0 | 1 | 0% | 2025-05-25 | 2025-06-14 | 20 | 2025-04-27 | 2025-05-01 | 4 |  | 0
2 | MCR Equipment Testing | Lot | 1 | 0 | 1 | 0% | 2025-04-04 | 2025-04-29 | 25 | 2025-05-01 | 2025-05-09 | 8 |  | 0
3 | Schematic digram and green lining of all equipment and panel | Lot | 1 | 0 | 1 | 0% | 2025-06-02 | 2025-06-10 | 8 | 2025-05-09 | 2025-05-17 | 8 |  | 0
4 | Relay testing | Lot | 1 | 0 | 1 | 0% | 2025-06-10 | 2025-06-18 | 8 | 2025-05-10 | 2025-06-04 | 25 |  | 0
5 | Stability test | Lot | 1 | 0 | 1 | 0% | 2025-06-14 | 2025-06-22 | 8 | 2025-05-10 | 2025-06-04 | 25 |  | 0
6 | Final cleaning of all equipment & boxup | Lot | 1 | 0 | 1 | 0% | 2025-06-21 | 2025-06-23 | 2 | 2025-05-10 | 2025-06-04 | 25 |  | 0
7 | Equipment tesiling work ( Nomenclature) | Lot | 1 | 0 | 1 | 0% | 2025-05-27 | 2025-06-04 | 8 | 2025-05-27 | 2025-06-04 | 8 |  | 0
8 | Saftey Items Installation | Lot | 1 | 0 | 1 | 0% | 2025-05-25 | 2025-06-02 | 8 | 2025-05-25 | 2025-06-02 | 8 |  | 0
9 | CEIG visit | Lot | 1 | 0 | 1 | 0% | 2025-06-03 | 2025-06-05 | 2 | 2025-06-03 | 2025-06-05 | 2 |  | 0
10 | Phase sequence meter Configuration | Lot | 1 | 0 | 1 | 0% | 2025-06-22 | 2025-06-25 | 3 | 2025-06-22 | 2025-06-25 | 3 |  | 0
11 | Scada Commissioning | Lot | 1 | 0 | 1 | 0% | 2025-06-26 | 2025-06-28 | 2 | 2025-06-26 | 2025-06-28 | 2 |  | 0
12 | Final Commissioning | Lot | 1 | 0 | 1 | 0% | 2025-06-29 | 2025-06-30 | 1 | 2025-06-29 | 2025-06-30 | 1 |  | 0
Formulas:
Start Date = MIN([Start Date, row below],I32,I41,I60,I82,I91,I98,I102)
Start Date = MIN([Start Date, row below]:I30)
Finish Date = MAX([Finish Date, row below],J32,J41,J60,J82,J91,J98,J102)
Finish Date = MAX([Finish Date, row below]:J30)

## Cont Piling
S.no. | Contractor | Activity | Scope | Progress | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31
A) |  | Marking |  | 4050 | 80 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 220 | 0 | 0 | 0 | 0 | 120 | 90 | 70 | 120 | 0 | 220 | 0 | 0 | 250 | 0 | 200 | 90 | 200 | 180 | 80 | 260 | 220 | 0 | 0 | 0 | 0 | 220 | 0 | 200 | 220 | 100 | 0 | 200 | 200 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Auguring |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DTH |  | 4011 | 60 | 60 | 0 | 0 | 0 | 0 | 30 | 30 | 0 | 0 | 0 | 0 | 60 | 0 | 0 | 0 | 109 | 0 | 53 | 70 | 50 | 90 | 80 | 0 | 120 | 105 | 70 | 110 | 0 | 120 | 0 | 60 | 90 | 200 | 110 | 124 | 150 | 120 | 130 | 150 | 150 | 140 | 0 | 0 | 0 | 210 | 0 | 190 | 250 | 0 | 250 | 100 | 100 | 100 | 100 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Casting |  | 3983 | 18 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51 | 29 | 0 | 0 | 31 | 102 | 0 | 112 | 48 | 27 | 103 | 26 | 0 | 108 | 130 | 60 | 79 | 74 | 24 | 80 | 53 | 85 | 124 | 151 | 157 | 188 | 62 | 124 | 126 | 123 | 149 | 0 | 0 | 81 | 120 | 0 | 216 | 224 | 31 | 61 | 129 | 91 | 25 | 64 | 65 | 58 | 66 | 93 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 39 | 0 | 0 | 0 | 0 | 0 | 0
B) |  | Marking |  | 5886 | 0 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | 0 | 0 | 0 | 0 | 232 | 0 | 0 | 0 | 30 | 0 | 28 | 60 | 110 | 0 | 190 | 0 | 76 | 0 | 230 | 0 | 0 | 210 | 250 | 100 | 0 | 0 | 0 | 150 | 200 | 210 | 130 | 240 | 220 | 250 | 200 | 180 | 240 | 0 | 0 | 90 | 190 | 200 | 210 | 100 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 250 | 0 | 0 | 0
|  | Auguring |  | 538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 125 | 101 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55 | 37
|  | DTH |  | 5187 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 40 | 0 | 0 | 101 | 134 | 65 | 0 | 0 | 70 | 31 | 0 | 60 | 40 | 0 | 65 | 90 | 120 | 110 | 0 | 120 | 0 | 90 | 210 | 190 | 100 | 0 | 0 | 0 | 204 | 180 | 190 | 150 | 220 | 260 | 180 | 120 | 140 | 210 | 0 | 0 | 200 | 160 | 230 | 160 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 120 | 0 | 20 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 0 | 0 | 0 | 0
|  | Casting |  | 5615 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 46 | 0 | 78 | 77 | 143 | 93 | 0 | 0 | 31 | 61 | 0 | 29 | 57 | 25 | 86 | 80 | 60 | 110 | 25 | 30 | 71 | 118 | 202 | 141 | 123 | 0 | 0 | 27 | 145 | 150 | 190 | 191 | 181 | 208 | 243 | 186 | 125 | 95 | 145 | 0 | 189 | 180 | 210 | 208 | 119 | 125 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 106 | 90 | 114 | 90 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 85 | 81 | 90 | 90
C) |  | Marking |  | 6845 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 100 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 220 | 75 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 220 | 140 | 120 | 0 | 300 | 0 | 250 | 220 | 290 | 300 | 300 | 300 | 110 | 140 | 160 | 220 | 259 | 110 | 110 | 120 | 160 | 0 | 0 | 200 | 100 | 100 | 206 | 110 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 440 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 100 | 35 | 40 | 40 | 0 | 0 | 0 | 0 | 0 | 120 | 0
|  | Auguring |  | 763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 127 | 0 | 0 | 130 | 100 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 20 | 20 | 0 | 0 | 0 | 0 | 0 | 110 | 0
|  | DTH |  | 5698 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 80 | 0 | 20 | 55 | 45 | 70 | 0 | 0 | 60 | 40 | 0 | 20 | 50 | 0 | 45 | 70 | 0 | 120 | 216 | 120 | 90 | 180 | 160 | 190 | 210 | 250 | 250 | 250 | 249 | 260 | 0 | 200 | 160 | 260 | 190 | 100 | 130 | 180 | 200 | 0 | 0 | 120 | 150 | 180 | 80 | 80 | 25 | 25 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 100 | 100 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Casting |  | 6485 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 20 | 0 | 73 | 46 | 52 | 60 | 0 | 0 | 31 | 59 | 0 | 59 | 27 | 0 | 60 | 61 | 57 | 117 | 152 | 124 | 180 | 156 | 154 | 186 | 213 | 248 | 214 | 250 | 308 | 235 | 95 | 122 | 147 | 240 | 175 | 120 | 90 | 120 | 145 | 0 | 120 | 166 | 125 | 166 | 53 | 35 | 28 | 116 | 91 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 89 | 86 | 87 | 60 | 90 | 110 | 93 | 0 | 91 | 0 | 80 | 29 | 55 | 30 | 29 | 0 | 0 | 0 | 30 | 0 | 60 | 12
D) |  | Marking |  | 873 | [34 empty] | 100 | 0 | 0 | 0 | 230 | 0 | 0 | 0 | 0 | 200 | 270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Auguring |  | 0 | [34 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | DTH |  | 943 | [34 empty] | 50 | 40 | 50 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 250 | 220 | 0 | 0 | 0 | 0 | 33 | 70 | 70 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Casting |  | 873 | [34 empty] | 27 | 27 | 58 | 0 | 0 | 60 | 60 | 61 | 60 | 61 | 60 | 60 | 0 | 88 | 60 | 55 | 56 | 29 | 30 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 27000
| Balance | 27000

## AC Progress
S.No. | AC Work | UOM | Total | [5 empty] | Base Line Plan |  |  | Forecast
Cumulative
|  |  | Scope | Waitage | Today | Cum. | Balance | % | Start Date | Finish Date | Days | Start Date | Finish Date | Days
1 | AC Trench | Mtr | 26043.8846 | 12% | 0 | 0 | 26043.8846 | 0% |  |  | 0 |  |  | 0
2 | 3CX240sqmm Cable Laying | Mtr | 18269.2308 | 3% | 0 | 0 | 18269.2308 | 0% |  |  | 0 |  |  | 0
3 | 3CX400sqmm Cable Laying | Mtr | 58461.5385 | 7% | 0 | 0 | 58461.5385 | 0% |  |  | 0 |  |  | 107
4 | 1CX400sqmm Cable Laying | LS | 38 | 10% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
5 | OFC Cable Laying | LS | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
6 | Grid Earthing | mtr | 7600 | 8% | 0 | 0 | 7600 | 0% |  |  | 0 |  |  | 0
7 | Tray support casting | No's | 38 | 0% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
8 | Tray from INV to LV Side | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
9 | Earthpit Installation | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
10 | IDT Erection | No's | 38 | 15% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
11 | ICOG Panel | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
12 | LT Panel | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
13 | UPS Panel | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
14 | Aux Trafo | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
15 | 1C*400Sqmm cable Termination | Sets | 38 | 10% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
|  |  |  | 100% |  |  |  | 0%
Description |  |  | AC Trench |  |  |  |  | 3CX240sqmm Cable Laying |  |  |  |  | 1CX400sqmm Cable Laying |  |  |  |  | 3CX400sqmm Cable Laying |  |  |  |  | OFC Cable Laying |  |  |  |  | Grid Earthing |  |  |  |  | Tray support casting |  |  |  |  | Tray from INV to LV Side |  |  |  |  | Earthpit Installation |  |  |  |  | IDT Erection |  |  |  |  | ICOG Panel |  |  |  |  | LT Panel |  |  |  |  | UPS Panel |  |  |  |  | Aux Trafo |  |  |  |  | 1C*400Sqmm cable Termination
Sr. No. | Contractor Name | ICR No. | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | %
| Total |  | 26043.8846 | 0 | 0 | 0 | 0% | 18269.2308 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 58461.5385 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 7600 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 34 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0%
1 |  | Icr-a |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
2 |  | Icr-b |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
3 |  | Icr-c |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
4 |  | Icr-e |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
5 |  | Icr-5 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
6 |  | Icr-6 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
7 |  | Icr-7 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
8 |  | Icr-8 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
9 |  | Icr-9 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
10 |  | Icr-10 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
11 |  | Icr-11 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
12 |  | Icr-12 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
13 |  | Icr-13 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
14 |  | Icr-14 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
15 |  | Icr-15 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
16 |  | Icr-16 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
17 |  | Icr-17 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
18 |  | Icr-18 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
19 |  | Icr-19 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
20 |  | Icr-20 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
21 |  | Icr-21 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
22 |  | Icr-22 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
23 |  | Icr-23 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
24 |  | Icr-24 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
25 |  | Icr-25 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
26 |  | Icr-26 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
27 |  | Icr-27 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
28 |  | Icr-28 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
29 |  | Icr-29 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
30 |  | Icr-30 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
31 |  | Icr-31 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
32 |  | Icr-32 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
33 |  | Icr-33 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
34 |  | Icr-34 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0

## DC Progress
S.No. | DC Work | UOM | Total |  |  |  |  | Base Line Plan |  |  | Forecast
|  |  | Scope | Today | Cum. | Balance | % | Start Date | Finish Date | Days | Start Date | Finish Date | Days
1 | Trench Excavation | Mtr | 171000 | 250 | 950 | 170050 | 0.5556% |  |  | 0 |  |  | 0
2 | 400Sqmm Cable laying (SCB's) | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
3 | Inverter Installation | No's | 76 | 0 | 0 | 76 | 0% |  |  | 0 |  |  | 0
4 | 400 Sqmm cable laying | mtr | 638400 | 0 | 0 | 638400 | 0% |  |  | 0 |  |  | 0
5 | SCB Stand Casting | No's | 3648 | 0 | 0 | 3648 | 0% |  |  | 0 |  |  | 0
6 | SCB Installation | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
7 | 6 Sqmm Laying(SCB's) | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
8 | Termination SCB End | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
9 | Termination Inv End | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
10 | Earthing Conductor Laying | Mtr | 95000 | 0 | 0 | 95000 | 0% |  |  | 0 |  |  | 0
11 | Earthpit Installation | No's | 912 | 0 | 0 | 912 | 0% |  |  | 0 |  |  | 0
12 | String Cable termination | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
13 | LA Installation | No's | 190 | 0 | 0 | 190 | 0% |  |  | 0 |  |  | 0
14 | LA Connection | No's | 190 | 0 | 0 | 190 | 0% |  |  | 0 |  |  | 0
15 | MMS Installation(Full+Half+Dummy) | No's | 14592 | 0 | 0 | 14592 | 0% |  |  | 0 |  |  | 0
16 | Module Mounting | No's | 846336 | 0 | 0 | 846336 | 0% |  |  | 0 |  |  | 0
0.03472%
Description |  |  | Trench Excavation |  |  |  |  | 400Sqmm Cable laying (SCB's) |  |  |  |  | Inverter Installation |  |  |  |  | SCB Stand Casting |  |  |  |  | SCB Installation |  |  |  |  | 6 Sqmm Laying(SCB's) |  |  |  |  | Termination SCB End |  |  |  |  | 400 Sqmm cable laying |  |  |  |  | Termination Inv End |  |  |  |  | Earthing Conductor Laying |  |  |  |  | Earthpit Installation |  |  |  |  | String Cable termination |  |  |  |  | LA Installation |  |  |  |  | LA Connection |  |  |  |  | MMS Installation(Full+Half+Dummy) |  |  |  |  | Module Mounting
Sr. No. | Contractor Name | ICR No. | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | %
| Total |  | 171000 | 250 | 950 | 3550 | 0.5556% | 1824 | 0 | 0 | 0 | 0% | 76 | 0 | 0 | 0 | 0% | 3648 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 638400 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 95000 | 0 | 0 | 0 | 0% | 912 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 190 | 0 | 0 | 0 | 0% | 190 | 0 | 0 | 0 | 0% | 14592 | 0 | 0 | 0 | 0% | 846336 | 0 | 0 | 0 | 0%
1 |  | Icr-1
B | Shree Krishna Enterprises | Icr-2 | 4500 | 250 | 950 | 3550 | 21.11%
3 |  | Icr-3
4 |  | Icr-4
5 |  | Icr-5
6 |  | Icr-6
7 |  | Icr-7
8 |  | Icr-8
9 |  | Icr-9
10 |  | Icr-10
11 |  | Icr-11
12 |  | Icr-12
13 |  | Icr-13
14 |  | Icr-14
15 |  | Icr-15
16 |  | Icr-16
17 |  | Icr-17
18 |  | Icr-18
19 |  | Icr-19
20 |  | Icr-20
21 |  | Icr-21
22 |  | Icr-22
23 |  | Icr-23
24 |  | Icr-24
25 |  | Icr-25
26 |  | Icr-26
27 |  | Icr-27
28 |  | Icr-28
29 |  | Icr-29
30 |  | Icr-30
31 |  | Icr-31
32 |  | Icr-32
33 |  | Icr-33
34 |  | Icr-34

## Daily tracker Work
S.No. | Activity | Work Description | UOM | Scope | Progress | Balance | % Progress | time axis 2025-04-01 to 2025-09-29
1 | DC WORK | Trench Excavation | Mtr | 171000 | 0 | 171000 | 0%
2 |  | 400Sqmm Cable laying (SCB's) | No's | 1824 | 0 | 1824 | 0%
3 |  | Inverter Installation | No's | 76 | 0 | 76 | 0%
4 |  | SCB Stand Casting | No's | 3648 | 0 | 3648 | 0%
5 |  | 400 Sqmm cable laying | mtr | 856800 | 0 | 856800 | 0%
6 |  | SCB Installation | No's | 1824 | 0 | 1824 | 0%
7 |  | 6 Sqmm Laying(SCB's) | No's | 1824 | 0 | 1824 | 0%
8 |  | Termination SCB End | No's | 1824 | 0 | 1824 | 0%
9 |  | Termination Inv End | No's | 1824 | 0 | 1824 | 0%
10 |  | Earthing Conductor Laying | Mtr | 95000 | 0 | 95000 | 0%
11 |  | Earthpit Installation | No's | 912 | 0 | 912 | 0%
12 |  | String Cable termination | No's | 1824 | 0 | 1824 | 0%
13 |  | LA Installation | No's | 190 | 0 | 190 | 0%
14 |  | LA Connection | No's | 190 | 0 | 190 | 0%
15 |  | MMS Installtion(Full+Half) | No's | 14592 | 0 | 14592 | 0%
16 |  | Module Mounting | No's | 846336 | 0 | 846336 | 0%
17 | AC Work | AC Trench Excavation | Mtr | 26043.8846 | 0 | 26043.8846 | 0%
18 |  | 3CX400/240sqmm Cable Laying | Mtr | 18269.2308 | 0 | 18269.2308 | 0%
19 |  | OFC Cable Laying | Mtr | 38 | 0 | 38 | 0%
20 |  | Grid Earthing | mtr | 10400 | 0 | 10400 | 0%
21 |  | Earthing Conductor Laying | Mtr | 38 | 0 | 38 | 0%
22 |  | Tray Support Casting | No's | 52 | 0 | 52 | 0%
23 |  | Tray from INV to LV Side | No's | 7600 | 0 | 7600 | 0%
24 |  | Earthpit Installation | No's | 38 | 0 | 38 | 0%
25 |  | IDT Erection | No's | 38 | 0 | 38 | 0%
26 |  | ICOG Panel | No's | 38 | 0 | 38 | 0%
27 |  | LT Panel | No's | 38 | 0 | 38 | 0%
28 |  | UPS & UPS DB | No's | 38 | 0 | 38 | 0%
29 |  | AUX Trafo | No's | 38 | 0 | 38 | 0%
30 |  | NIFPS panel installation | No's | 38 | 0 | 38 | 0%
31 |  | Termination | No's | 38 | 0 | 38 | 0%

## Bottleneck
Bottleneck
Engineering {E} | Procurement {P} | Construction {C}

## QC & HSE status
QC Status | [6 empty] | HSE Status
Department | Total FF | Closed | Open | Total NC | Closed | Open
Construction | 0 | 0 | 0 | 0 | 0 | 0
Engineering | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 0 | 0 | 0 | 0 | 0 | 0
97648

## Resources Status (hidden)
Sr. No. | Vendor name | Entity | Category | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25
Manpower | Total |  | 97648 | 6 | 6 | 8 | 9 | 12 | 12 | 15 | 17 | 19 | 19 | 17 | 25 | 25 | 25 | 33 | 32 | 33 | 43 | 43 | 37 | 35 | 50 | 54 | 52 | 51 | 55 | 58 | 48 | 63 | 75 | 69 | 69 | 68 | 70 | 66 | 64 | 67 | 24 | 74 | 75 | 75 | 75 | 66 | 74 | 80 | 80 | 83 | 84 | 82 | 73 | 77 | 78 | 75 | 81 | 90 | 89 | 94 | 91 | 92 | 92 | 111 | 104 | 87 | 101 | 101 | 91 | 96 | 93 | 108 | 115 | 118 | 104 | 121 | 122 | 136 | 133 | 137 | 132 | 140 | 137 | 112 | 113 | 120 | 120 | 120 | 120 | 119 | 120 | 134 | 134 | 93 | 103 | 118 | 131 | 129 | 125 | 131 | 130 | 133 | 128 | 127 | 127 | 130 | 130 | 130 | 111 | 95 | 101 | 57 | 14 | 71 | 77 | 83 | 95 | 116 | 121 | 120 | 120 | 134 | 138 | 144 | 145 | 134 | 132 | 96 | 108 | 86 | 122 | 123 | 136 | 136 | 116 | 123 | 135 | 140 | 124 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | O2 Power |  | Staff | 3 | 3 | 5 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 10 | 10 | 10 | 10 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 15 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 18 | 18 | 18 | 18 | 0 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
|  |  | Surveyor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Security | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 31
2 | Desert Infra | Energizent Power Pvt. Ltd | Staff | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 8 | 8 | 8 | 15 | 15 | 13 | 11 | 14 | 14 | 12 | 11 | 11 | 11 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 12 | 13 | 0 | 16 | 16 | 16 | 16 | 8 | 16 | 13 | 13 | 13 | 13 | 13 | 4 | 7 | 7 | 5 | 5 | 7 | 7 | 10 | 10 | 10 | 10 | 17 | 14 | 14 | 14 | 14 | 4 | 4 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 16 | 16 | 16 | 16 | 15 | 15 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 18 | 12 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 5 | 5 | 5 | 13 | 13 | 13 | 6 | 0 | 6 | 7 | 7 | 4 | 9 | 7 | 6 | 6 | 11 | 11 | 6 | 7 | 6 | 10 | 10 | 7 | 11 | 11 | 12 | 12 | 12 | 9 | 9 | 20 | 20 | 15 | 10
|  |  | Total | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 12 | 12 | 12 | 18 | 18 | 15 | 13 | 16 | 16 | 14 | 13 | 13 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 14 | 15 | 0 | 18 | 18 | 18 | 18 | 10 | 18 | 15 | 15 | 15 | 15 | 15 | 6 | 9 | 9 | 7 | 7 | 9 | 9 | 11 | 11 | 11 | 11 | 18 | 15 | 15 | 15 | 15 | 5 | 5 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 22 | 22 | 22 | 22 | 22 | 22 | 18 | 18 | 18 | 18 | 17 | 17 | 15 | 17 | 17 | 17 | 17 | 17 | 16 | 20 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 8 | 8 | 8 | 15 | 15 | 15 | 8 | 0 | 7 | 8 | 8 | 5 | 10 | 8 | 8 | 8 | 13 | 13 | 8 | 8 | 8 | 11 | 11 | 8 | 12 | 12 | 13 | 13 | 13 | 10 | 10 | 21 | 21 | 16 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Teq XVII Pvt. Ltd. | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 2 | 0 | 3 | 5 | 7 | 7 | 4 | 4 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 5
|  |  | Total | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 3 | 5 | 7 | 7 | 4 | 4 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | Sanchiyay | Energizent Power Pvt. Ltd | Staff | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 10 | 9 | 9 | 9 | 9 | 9 | 13 | 13 | 9 | 9 | 8 | 9 | 9 | 10 | 13 | 13 | 4 | 13 | 13 | 8 | 8 | 7 | 7 | 2 | 5 | 7 | 0 | 12 | 12 | 12 | 12 | 11 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 22 | 20 | 20 | 20 | 20 | 20 | 20 | 17 | 17 | 17 | 17 | 16 | 16 | 16 | 26 | 20 | 12 | 11 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 0 | 10 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 9 | 9 | 9 | 9 | 9 | 9 | 6 | 6 | 6 | 0 | 0 | 2 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 4 | 4 | 8 | 10 | 8 | 8 | 4 | 4 | 4 | 4 | 9 | 9 | 11 | 11 | 11 | 11 | 11 | 12 | 12
|  |  | Total | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 12 | 12 | 12 | 12 | 11 | 11 | 15 | 15 | 11 | 11 | 10 | 12 | 12 | 13 | 16 | 15 | 6 | 15 | 16 | 11 | 11 | 9 | 9 | 4 | 7 | 9 | 0 | 14 | 15 | 15 | 15 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 23 | 23 | 23 | 23 | 23 | 23 | 20 | 20 | 20 | 20 | 19 | 19 | 19 | 29 | 23 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 12 | 12 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 12 | 12 | 12 | 14 | 14 | 14 | 14 | 14 | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 8 | 8 | 0 | 0 | 3 | 5 | 5 | 5 | 5 | 7 | 7 | 7 | 5 | 5 | 9 | 11 | 9 | 9 | 5 | 5 | 5 | 5 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | JCC | Energizent Power Pvt. Ltd | Staff | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 1 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 8 | 8 | 7 | 8 | 12 | 8 | 14 | 14 | 14 | 14 | 14 | 16 | 17 | 17 | 17 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 18 | 18 | 18 | 18 | 16 | 17 | 16 | 16 | 15 | 15 | 12 | 13 | 15 | 15 | 22 | 19 | 19 | 19 | 19 | 19 | 19 | 6 | 16 | 20 | 20 | 18 | 18 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 10 | 10 | 10 | 10 | 10 | 10 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 14 | 9 | 6 | 6 | 6 | 11 | 10 | 10 | 10 | 7 | 7 | 7 | 9 | 8 | 8 | 4 | 0 | 0 | 4 | 4 | 9 | 11 | 12 | 11 | 7 | 11 | 11 | 11 | 11 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 10 | 10 | 7 | 7 | 8 | 6
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7 | 9 | 9 | 8 | 9 | 13 | 9 | 15 | 16 | 15 | 15 | 16 | 18 | 19 | 19 | 19 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 21 | 21 | 21 | 21 | 19 | 20 | 19 | 19 | 18 | 18 | 15 | 16 | 18 | 18 | 25 | 22 | 22 | 22 | 22 | 22 | 22 | 9 | 19 | 23 | 23 | 21 | 21 | 17 | 17 | 17 | 16 | 16 | 16 | 16 | 13 | 13 | 13 | 13 | 13 | 13 | 16 | 16 | 16 | 16 | 16 | 14 | 14 | 17 | 11 | 8 | 8 | 8 | 13 | 12 | 12 | 12 | 9 | 9 | 9 | 11 | 10 | 10 | 6 | 0 | 0 | 5 | 5 | 10 | 13 | 13 | 13 | 9 | 13 | 13 | 12 | 12 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 8 | 8 | 9 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Super Construction | Energizent Power Pvt. Ltd | Staff | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Paramhans Infra | Energizent Power Pvt. Ltd | Staff | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 1 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 0 | 4 | 4 | 9 | 8 | 0 | 8 | 8 | 8 | 13 | 13 | 13 | 13 | 5 | 0 | 16 | 16 | 16 | 16 | 16 | 12 | 15 | 12 | 14 | 15 | 15 | 15 | 15 | 15 | 13 | 13 | 15 | 15 | 0 | 0 | 14 | 14 | 14 | 17 | 17 | 17 | 14 | 14 | 13 | 13 | 5 | 5 | 5 | 5 | 0 | 5 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 8 | 7 | 5 | 5 | 0 | 5 | 4 | 12 | 8 | 7 | 7 | 0 | 4 | 3 | 3 | 3 | 4
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 5 | 5 | 0 | 5 | 5 | 10 | 9 | 0 | 9 | 9 | 9 | 15 | 15 | 15 | 16 | 6 | 0 | 18 | 18 | 18 | 18 | 18 | 14 | 17 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 15 | 15 | 17 | 17 | 0 | 0 | 16 | 16 | 16 | 19 | 19 | 19 | 16 | 16 | 14 | 14 | 6 | 6 | 6 | 6 | 0 | 6 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 9 | 8 | 6 | 6 | 0 | 6 | 5 | 13 | 9 | 8 | 8 | 0 | 5 | 4 | 4 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Seema Enterprises | Energizent Power Pvt. Ltd | Staff | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1
|  |  | Worker | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 6 | 6 | 6 | 5 | 5 | 5 | 5 | 5 | 6 | 12 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 8 | 8 | 15 | 15 | 5 | 5 | 5 | 11 | 11 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 7 | 5 | 5 | 0 | 4 | 4 | 7 | 5 | 5 | 5 | 0 | 0 | 0 | 5 | 5 | 5
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 8 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 10 | 10 | 17 | 17 | 7 | 7 | 7 | 13 | 13 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 6 | 6 | 0 | 5 | 5 | 8 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Teq XV Pvt. Ltd. | Staff | [96 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | [96 empty] | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | [96 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | KC Construction | Energizent Power Pvt. Ltd | Staff | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 6 | 5 | 5 | 5 | 8 | 8 | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 8 | 7 | 7 | 7 | 10 | 10 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | SR Constructions | Energizent Power Pvt. Ltd | Staff | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | [15 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 6 | 6 | 6 | 11 | 11 | 8 | 13 | 13 | 17 | 17 | 5 | 5 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 13 | 13 | 13 | 5 | 5 | 5 | 0 | 0 | 4 | 6 | 5 | 5 | 9 | 10 | 10 | 11 | 12 | 6 | 13 | 6 | 6 | 6 | 6 | 6 | 0 | 5 | 5 | 11 | 7 | 8 | 5 | 10 | 10 | 4 | 10
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 7 | 7 | 7 | 12 | 12 | 9 | 14 | 14 | 18 | 18 | 6 | 6 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 6 | 6 | 6 | 0 | 0 | 5 | 7 | 6 | 6 | 10 | 11 | 11 | 12 | 13 | 7 | 14 | 7 | 7 | 7 | 7 | 7 | 0 | 6 | 6 | 12 | 8 | 9 | 6 | 11 | 11 | 5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | DS Constructions | Energizent Power Pvt. Ltd | Staff | [94 empty] | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | [94 empty] | 6 | 6 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 5 | 5 | 5 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 4 | 4
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 6 | 6 | 6 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | NCC | Energizent Power Pvt. Ltd | Staff | [96 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | [96 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Hartek | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 3 | 3 | 0 | 3 | 3 | 3 | 3 | 2 | 3 | 3 | 3 | 2 | 0
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 9 | 0 | 9 | 5 | 8 | 9 | 7 | 13 | 9 | 9 | 9 | 14 | 10 | 10 | 9 | 6 | 9 | 10 | 0 | 10 | 10 | 10 | 12 | 7 | 10 | 10 | 10 | 7 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 17 | 17 | 17 | 17 | 11 | 0 | 11 | 7 | 10 | 11 | 9 | 15 | 11 | 11 | 11 | 16 | 13 | 13 | 12 | 8 | 12 | 13 | 0 | 13 | 13 | 13 | 15 | 9 | 13 | 13 | 13 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Sun Bright Infratech | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 6 | 7 | 6 | 7 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | JS Bhati Construction | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 4 | 4 | 4 | 0 | 2 | 0 | 2 | 2 | 6 | 6 | 7 | 5 | 5 | 5 | 6 | 6
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 0 | 3 | 0 | 3 | 3 | 7 | 7 | 8 | 6 | 6 | 6 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Baba Ramdev contraction | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 8 | 7 | 2 | 4 | 2 | 5 | 6 | 4 | 4 | 5 | 8 | 8 | 7 | 4 | 7
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 8 | 3 | 5 | 3 | 6 | 7 | 5 | 5 | 6 | 9 | 9 | 8 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Bajarang Electrical Work | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Shree Krshna Enterprises | Energizent Power Pvt. Ltd | Staff | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1
|  |  | Worker | [96 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 9 | 9
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Machinary | Total |  | Description | 0 | 2 | 2 | 2 | 4 | 4 | 4 | 5 | 5 | 4 | 3 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 6 | 6 | 6 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Desert Infra |  | Vehicle |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Excavator/JCB | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
2 | Sanchiyay |  | Vehicle | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Excavator/JCB | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JCC |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Excavator/JCB | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
4 | Super Construction |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Paramhans Infra |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Seema Enterprises |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | KC Constructions |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | SR Constructions |  | Vehicle | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | Ajax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | DS Constructions |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | [90 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | NCC |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Ajax | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Hartek |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Farhana | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | JCB | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Sun Bright Infratech |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | JCB | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | JS Bhati Construction |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | JCB | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Baba Ramdev contraction |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Auger/DTH | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  | JCB | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Bajarang Electrical Work |  | Vehicle | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Farhana | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | Crane | 0 | 0 | 0 | [90 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1

## Resources Requirement
Resources Required vs Actual
Sr. No. | Vendor Name | Available | Required | Balance to catch up Progress | Current Update by Contractor
1 | Vendor 1 | 0 | 20 | 20
2 | Vendor 1 | 12 | 15 | 3
3 | Vendor 1 | 6 | 15 | 9
4 | Vendor 1 | 0 | 0 | 0
5 | Vendor 1 | 4 | 15 | 11 | Will be available once piling front allocated
6 | Vendor 1 | 6 | 15 | 9
7 | Vendor 1 | 0 | 10 | 10
8 | Vendor 1 | 11 | 18 | 7
9 | Vendor 1 | 5 | 10 | 5
10 | Vendor 1 | 0 | 10 | 10
11 | Vendor 1 | 0 | 13 | 13
12 | Vendor 1 | 0 | 9 | 9
13
Total |  | 44 | 150 | 106

## Hindrance
Work Hindrance Log
Start DATE | End Date | ISSUE | START TIME | END TIME | REMARKS
2024-11-26 | 2024-12-12 | Land clearance not given for piling construction | 09.00 am | 06.00 pm
2024-11-26 | 2024-12-12 | Bush cutting pending in demarcated land | 09.00 am | 06.00 pm
2024-11-23 | 2024-11-23 | Local farmers stopped unloading works | 09.00 am | 06.00 pm | Unloading work stopped for demand of unloading work
2024-11-24 | 2024-11-24 | Local farmers stopped unloading works | 09.00 am | 11.00 am | Unloading work stopped for demand of unloading work
2024-11-26 | 2024-11-26 | Local farmers stopped switchyard works | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-11-27 | 2024-11-27 | Local farmers stopped switchyard works | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-12-06 | 2024-12-06 | Local Farmers stopped work | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-12-07 | 2024-12-07 | Local Farmers stopped work | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-12-07 | 2024-12-12 | Piling layout not received for demarcated land | 09.00 am | 06.00 pm | Piling work not started
2024-12-17 | 2024-12-18 | Security agency guards stopped the work | 09.00 am | 06.00 pm | Security guards and QRT people stopped the work
2024-12-20 | 2024-12-22 | HT Panel Drawing had design changes | 09.00 am | 06.00 pm | Design team made changes in design after releasing the foundation drwaing because of that work was on hold for 3 days
2024-12-21 | 2024-12-30 | Batching plant setup, ICR and Pilling work stoped by locals | 09.00 am | 06.00 pm | Locals has stop the work for the demand over batching plant setup
2024-12-29 | 2024-12-30 | Boundary wall work not started because of Rate disputes with locals | 09.00 am | 06.00 pm
2025-12-30 | 2025-01-06 | HT panel building Plinth beam/floor slab and roof beam/slab drawing not received. | 09.00 am | 06.00 pm | Bar bending team has no front for steel cutting
2025-01-09 | 2025-01-09 | Site work hampered due to demand of JCB hiring | 09.00 am | 05.00 pm | Manpower ideal due to ROW at site
2025-01-08 | 2025-01-10 | Piling work not started due to compansation issue to water storage tank | 09.00 am | 06.00 pm
2025-01-14 | 2025-01-15 | Piling and ICR work Stopped due to demand of JCB hiring for grading and levelling | 09.00 am | 06.00 pm
2025-01-20 | 2025-01-20 | Piling work hampered due to demand of water tank rate fixing | 09.00 am | 06.00 pm
2025-01-25 | 2025-01-27 | Piling work hampered due road work blocked by locals | 09.00 am | 06.00 pm
2025-02-27 | 2025-03-05 | Piling work hampered in s/y no 38,39,40,42,66,67 due to demarcation issue | 09.00 am | 06.00 pm
2025-03-01 | 2025-03-05 | Piling work hampered in s/y no 117 due to demarcation issue | 09.00 am | 06.00 pm
Formulas:
Start DATE = [Start DATE, row above]+1
End Date = [End Date, row above]+1