## DWPR
Daily Work Progress Report: 25 MW (AC) SOLAR PV POWER PLANT WITH 20 MW / 50 MWH BESS, Taru, Leh, UT of Ladakh.
Daily Work Progress Report Date | Work Details/Work area | Work execution status as on Today | Subvendor Manpower
14.06.25 | Test Pile | Test pile casting (PG No. - 1,2,3,4,6) | 20
15.06.25 | Test Pile & Boundary Fencing | PG no - 5 Fencing pole casting- 37Nos | 20
16.06.25 | Boundary Fencing | Fencing Pole Casting - 102 Nos | 21
17.06.25 | Boundary fencing & M30 Trial Mix | Fencing pole casting - 96 Nos | 21
18.06.25 | Boundary Fencing & MCR Excavation | Fencing pole casting - 112 Nos MCR Excavation WIP | 20
19.06.25 | Boundary Fencing & MCR Excavation | Fencing pole casting - 93 Nos MCR Excavation WIP | 20
20.06.25 | Boundary Fencing & MCR Excavation | Fencing pole casting - 112 Nos MCR Excavation WIP | 20
21.06.25 | Boundary Fencing & MCR Excavation | Fencing pole casting - 41 Nos MCR Excavation WIP | 20
22.06.25 | Boundary Fencing & MCR Excavation | Fencing pole casting - Ajax Breakdown MCR Excavation WIP | 20
23.06.25 | Boundary Fencing & MCR Excavation | Fencing pole casting - 64 Nos MCR Excavation WIP | 21
24.06.25 | Boundary Fencing & MCR Excavation | Fencing pole casting - Vendor out MCR Excavation WIP | 20
27.06.25 | Array Civil Yard Boundar Fencing | Pile Marking - 12 Table Mesh Chain Link Installation - 30Mtr | 16
28.06.25 | Array Civil Yard Boundar Fencing | Pile Marking - 10 Table Mesh Chain Link Installation - 110Mtr Barbed Wire Installation - 620Mtr | 16
29.06.25 | Array Civil Yard Boundar Fencing | Pile Marking - 20 Table Mesh Chain Link Installation - 170Mtr Barbed Wire Installation - 805Mtr | 20
30.06.25 | Array Civil Yard Boundar Fencing | Pile Marking - 18 Table Mesh Chain Link Installation - 150Mtr Barbed Wire Installation - 175Mtr | 20
01.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 19 Table Mesh Chain Link Installation - 225Mtr Barbed Wire Installation - 1080Mtr Main gate PCC casting | 16
02.07.25 | Boundary Fencing | Mesh Chain Link Installation - 300Mtr Barbed Wire Installation - 2520Mtr | 16
03.07.25 | Boundary Fencing | Mesh Chain Link Installation - 345Mtr Barbed Wire Installation - 2520Mtr | 16
04.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 19 Table Mesh Chain Link Installation - 225Mtr Barbed Wire Installation - 1080Mtr Concertina Wire Installation - 150Mtr | 16
05.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 15 Table Concertina Wire Installation - 562Mtr | 16
06.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 06 Table Concertina Wire Installation - 375Mtr | 16
07.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 06 Table Fencing pole casting - 30 Nos | 21
08.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 08 Table Fencing pole casting - 100 Nos Maingate coulmn castion - 03 Nos (Height 2 mtr) | 9
09.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 02 Table Mesh Chain Link Installation - 150Mtr Fencing pole castinng - 85 Nos Store area pole casting - 15 Nos | 36
10.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 02 Table Mesh Chain Link Installation - 180Mtr Fencing pole castinng - 90 Nos Store area pole casting - 17 Nos | 32
11.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 02 Table Mesh Chain Link Installation - 210Mtr Fencing pole castinng - 108 Nos Barbed Wire Installation - 1080Mtr Store area pole casting - 16 Nos | 32
12.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 02 Table Mesh Chain Link Installation - 180Mtr Fencing pole castinng - 80 Nos Barbed Wire Installation - 1260Mtr Maingate Coulmn casting | 32
13.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 07 Table Mesh Chain Link Installation - 315Mtr (180 + 135 Store) Fencing pole castinng - 100 Nos Barbed Wire Installation - 1260Mtr Concertina Wire Installation - 375Mtr | 30
14.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 02 Table Mesh Chain Link Installation - 45Mtr (Store) Fencing pole castinng - 90 Nos Barbed Wire Installation - 1260Mtr Maingate PCC Backfilling | 30
15.07.25 | Array Civil Yard Boundar Fencing | Pile Marking - 08 Table Mesh Chain Link Installation - 105Mtr Fencing pole castinng - 70 Nos Barbed Wire Installation - 180Mtr 03 Light & 02 Camera Pole casting | 18
16.07.25 | Boundary Fencing | Fencing pole casting - 77Nos Mesh Chain Link Installation - 120Mtr | 24
17.07.25 | Boundary Fencing | Fencing pole casting - 00Nos Mesh Chain Link Installation - 150Mtr | 24
18.07.25 | Boundary Fencing | Fencing pole casting - 70Nos Mesh Chain Link Installation - 150Mtr | 24
19.07.25 | Boundary Fencing | Fencing pole casting - 65Nos Mesh Chain Link Installation - 165Mtr Light & Camera pole casting - 06Nos | 24
20.07.25 | MCR Area | MCR Footing PCC - 06Nos | 12
21.07.25 | MCR Area Boundary Fencing | Fencing Pole Casting - 62 Nos MCR Footing PCC - 10Nos | 20
22.07.25 | Boundary Fencing | Mesh Chain link installation - 120Mtr | 20
23.07.25 | Boundary Fencing | Mesh chain link installation - 180Mtr Fencing pole castinng - 65 Nos Barbed Wire Installation - 1260Mtr | 20
24.07.25 | Array Civil Yard Boundar Fencing | Mesh Chain link installation - 120Mtr Test pile marking - 05 point Pile Marking - 04 Table | 20
25.07.25 | Array Civil Yard Boundary Fencing | Pile Marking - 12 Table Barbed Wire Installation - 126Mtr Concertina Wire Installation - 67.5Mtr | 20
26.07.25 | Array Civil Yard Boundary Fencing | Pile Marking - 18 Table Barbed Wire Installation - 900Mtr Concertina Wire Installation - 225Mtr | 20
27.07.25 | Boundary Fencing | Fencing Bottm patti connecting & Nut-bolt tightening work | 20
28.07.25 | Array Civil Yard Boundary Fencing | Pile Marking - 18 Table Fencing Bottm patti connecting & Nut-bolt tightening work | 20
29.07.25 | Array Civil Yard Boundary Fencing | Pile Marking - 04 Table Concertina Wire Installation - 262.5Mtr | 20
30.07.25 | Array Civil Yard Boundary Fencing | Pile Marking - 09 Table Barbed Wire Installation - 2160Mtr Concertina Wire Installation - 187.5Mtr | 24
31.07.25 | Array Civil Yard Boundary Fencing | Pile Marking - 09 Table Barbed Wire Installation - 198Mtr Concertina Wire Installation - 225Mtr | 24
01.08.25 | Array Civil Yard Boundary Fencing | Pile Marking - 09 Table Fencing Bottm patti connecting & Nut-bolt tightening work | 24
02.08.25 | Array Civil Yard Boundary Fencing | Pile Marking - 11 Table Barbed Wire Installation - 1080Mtr | 24
03.08.25 | Boundary Fencing | Mesh Chain Link Installation - 120Mtr Barbed Wire Installation - 1080Mtr Concertina Wire Installation - 262.5Mtr | 24
04.08.25 | Array Civil Yard Boundary Fencing | Pile test casting - 05point Barbed Wire Installation - 2160Mtr Concertina Wire Installation - 600Mtr | 24
05.08.25 | Array Civil Yard | Pile test casting - 14 Nos | 24
06.08.25 | Array Civil Yard Boundary Fencing | Pile test casting - 06 Nos. Mesh Chain link installation - 180Mtr Fencing pole castinng - 50 Nos | 29
07.08.25 | Array Civil Yard Boundary Fencing | Pile test capping -10 points Concertina Wire Installation - 210 Mtr Fencing pole casting - 30 Nos Light pole casting: 03 Nos. | 22
08.08.25 | Boundary Fencing | Fencing pole casting - 35 Nos Barbed Wire Installation - 1440Mtr | 22
09.08.25 | Boundary Fencing | Fencing pole casting - 80 Nos Barbed Wire Installation - 1440Mtr Main Gate Railing PCC work | 18
10.08.25 | Boundary Fencing | Fencing pole casting - 80 Nos Barbed Wire Installation - 1440Mtr Mesh Chain link installation - 195Mtr | 40
11.08.25 | Array Civil Yard Boundary Fencing | Pile Test Marking - 04 Point Concertina Wire Installation - 600Mtr Mesh Chain link installation - 180Mtr Drilling: 04 Nos. | 39
12.08.25 | Array Civil Yard Boundary Fencing MCR Area | Mesh Chain Link Installation - 300Mtr Concertina Wire Installation - 262.5Mtr Pile Test Marking - 04 Point Raft top jali binding WIP & Coulmn & Raft BBS WIP | 39
13.08.25 | Array Civil Yard Boundary Fencing BESS Area | Mesh Chain Link Installation - 180 Mtr Concertina Wire Installation - 225 Mtr Pile Test Marking - 05 Point Drilling: 5 Point BESS Footing BBS WIP | 40
14.08.25 | Array Civil Yard Boundary Fencing | Mesh Chain Link Installation - 120 Mtr Concertina Wire Installation - 150 Mtr Fencing pole casting - 40 Nos Pile Test Marking - 05 Point Drilling: 5 Point | 40
16.08.25 | Array Civil Yard | New Test pile Casting: 20 Nos. (3,4,5,8,10 point) Single leg Casting | 40
17.08.25 | Array Civil Yard | New Test pile Casting: 08 Nos. (1,11 point) Single leg Casting | 40
18.08.25 | Array Civil Yard BESS Area | New Test pile Casting: 12 Nos. (6,9,16 point) Single leg Casting BESS Zone-1 PCC Casting | 40
19.08.25 | Array Civil Yard | Pile Marking: 15 Table New Test pile Casting: 20 Nos. (2,12,13,14,15 point) Single leg Casting Drilling: 5 table | 40
20.08.25 | Array Civil Yard BESS Area | Pile Marking: 19 Table New Test pile Casting: 12 Nos. (7,17,18 point) Single leg Casting Drilling: 12 table BESS Zone-1 Footing casting - 04Nos BESS Zone 3 Excavation WIP | 40
21.08.25 | Array Civil Yard BESS & MCR Area | Pile Marking: 4 table Drilling: 45 Nos. MCR & BESS BBS WIP BESS PCC marking & Shuttering fixing | 40
22.08.25 | Array Civil Yard MCR Area BESS Area | Pile Marking: 20 table Drilling: 7 Table. MCR footing steel fixing, shuttering fixing WIP & 05Nos footing casted BESS steel cutting & binding WIP and BESS Zone-2 PCC bed marking & Casting | 40
23.08.25 | Array Civil Yard MCR Area BESS Area | Pile Marking: 21 table Drilling: 11 Table. MCR footing castig - 3.5nos BESS zone-1 footing casting 04nos & coulmn shuttering fixing, zone-2 PCC casting 08nos, Zone -3 PCC bed marking | 40
24.08.25 | Array Civil Yard MCR Area BESS Area | MCR Footing casting - 1.5 Nos BESS zone-3 PCC bed marking & PCC casting | 40
25.08.25 |  | No work due to rainfall | 0
26.08.25 |  | No work due to rainfall | 0
27.08.25 | Array Civil Yard MCR Area BESS Area | MMS table alignment WIP, piling augring WIP MCR footing shuttering removal & gunny bag covered for curing BESS footing shuttering removal & steel fixing for coulmn WIP | 40
28.05.25 | Array Civil Yard MCR Area BESS Area | MMS table coulmn alignment WIP MCR steel coulmn & top jali of footing fixing WIP BESS steel coulmn & shuttering fixing WIP | 40

## Sheet1
Detailed Project Report
PROJECT TITLE : 25 MW (AC) SOLAR PV POWER PLANT WITH 20 MW / 50 MWH BESS, Taru, Leh, UT of Ladakh.
SI. No. | Area of Work/Location | Work Description | UOM | Total Quantity | Completed | Balance | Completion in %age | Remarks
1 | Boundary Fencing Work | Chain Link Fencing- Marking | Nos | 2276 | 2200 | 76 | 96.6608
|  | Chain Link Fencing- Auguring | Nos | 2276 | 1983 | 293 | 87.1265
|  | Chain Link Fencing- Pole Casting | Nos | 2276 | 1983 | 293 | 87.1265
|  | Chain Link Fencing- Mesh Fixing with connecting strip | Mtr | 5690 | 4790 | 900 | 84.1828
|  | Chain Link Fencing-Barbed Wire Fixing | Mtr | 34140 | 29745 | 4395 | 87.1265
|  | Chain Link Fencing-Concertina Wire Fixing | Mtr | 5690 | 4440 | 1250 | 78.0316
2 | Array Yard Civil Work | Pile Marking | Nos | 25992 | 3044 | 22948 | 11.7113
|  | Pile -Auguring | Nos | 25992 | 640 | 25352 | 2.4623
|  | Pile Casting | Nos | 25992 | 0 | 25992 | 0
|  | Pile Capping | Nos | 25992 | 0 | 25992 | 0
3 | MCR Civil Work | MCR-Excavation | Cum | 1 | 1 | 0 | 100
|  | MCR-PCC | Nos | 33 | 33 | 0 | 100
|  | MCR-Footing | Nos | 33 | 27 | 6 | 81.8182
|  | MCR-Coulmn upto Plinth | Nos | 33 | 0 | 33 | 0
|  | MCR-Plinth Beam | Nos | 1 | 0 | 1 | 0
|  | MCR-Coulmn 1st Lift | Nos | 33 | 0 | 33 | 0
|  | MCR-Coulmn 2nd Lift | Nos | 33 | 0 | 33 | 0
|  | MCR-Lintel Beam | Nos | 1 | 0 | 1 | 0
|  | MCR-coulmn 3rd Lift | Nos | 33 | 0 | 33 | 0
|  | MCR-Roof Slab Casting | Nos | 1 | 0 | 1 | 0
4 | BESS Area Civil Work | BESS Container Excavation | Nos | 10 | 10 | 0 | 100
|  | BESS Container PCC | Nos | 40 | 32 | 8 | 80
|  | BESS Container Footing | Nos | 40 | 8 | 32 | 20
|  | BESS Container Coulmn | Nos | 40 | 0 | 40 | 0