## Project Dashbord
Project Progress Report | [8 empty] | PROGRESS ON: 30-Aug-2025
Project Name : |  | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Taru, Leh, UT of Ladakh, India
Client : |  | Solar Energy Corporation of India Ltd
SPV : |  | Prozeal Green Energy Limited
Project Start Date |  | 2024-11-20
Project COD |  | 2027-11-05
Sr. No | Description | Scope | UOM | Completed | Balance | Actual Progress Front Wise (in %) | Scope Weightage % | Progress as per weightage (in %) | Overall Project Completion Status
1 | Plant Boundary Fencing | 5690 | RM | 4889.5 | 800.5 | 85.9% | 1.2% | 1%
2 | MCR Civil Work | 1 | Lot | 0.21911 | 0.78089 | 21.9% | 9% | 2%
3 | MMS Pilling | 25992 | Nos | 12 | 25980 | 0% | 22.8% | 0%
4 | Switch Yard | 1 | Lot | 0 | 1 | 0% | 9% | 0%
5 | IDT - Solar | 4 | Lot | 3 | 1 | 75% | 1.2% | 0.9%
6 | IDT - BESS | 5 | Lot | 0 | 5 | 0% | 1.2% | 0%
7 | BESS-Civil | 1 | Lot | 0.14091 | 0.85909 | 14.1% | 3.6% | 0.5%
8 | LCR | 4 | Lot | 0 | 4 | 0% | 2.4% | 0%
9 | MMS Structure | 3934 | Table | 0 | 3934 | 0% | 7.2% | 0%
10 | Road | 3000 | Mtr. | 0 | 3000 | 0% | 1.2% | 0%
11 | Drain | 1000 | Mtr. | 0 | 1000 | 0% | 0.6% | 0%
12 | Misc Work | 1 | Lot | 0.2 | 0.8 | 20% | 0.6% | 0.1%
13 | AC-Electrical | 1 | Lot | 0 | 1 | 0% | 7.4% | 0%
14 | DC- Electrical | 1 | Lot | 0 | 1 | 0% | 7.4% | 0%
15 | Switchtard - Electrical | 1 | Lot | 0 | 1 | 0% | 7.4% | 0%
16 | MCR - Electrical | 1 | Lot | 0 | 1 | 0% | 3.7% | 0%
17 | Module Erection | 94416 | Nos | 0 | 94416 | 0% | 7.4% | 0%
18 | BESS - Electrical | 1 | Lot | 0 | 1 | 0% | 3.7% | 0%
19 | Transmission Line | 1 | Lot | 0 | 1 | 0% | 1% | 0%
20 | Project Charging & Commisioning | 1 | Lot | 0 | 1 | 0% | 2% | 0%
Overall Project Completion Status | [6 empty] | 100% | 4.5%

## MDL Status
Project Drawings Approval Report | [15 empty] | PROGRESS ON: 30-Aug-2025
Client Name | Solar Energy Corporation of India Ltd | [12 empty] | Total Documents | Submitted | Approved | Sub. Approved | Commented | Pending for Submission
EPC Contractor | Prozeal Green Energy Limited | [12 empty] | 100% | 43.85% | 11.76% | 6.952% | 13.37% | 56.15%
Project Name | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Taru, Leh, UT of Ladakh, India | [12 empty] | 187 | 82 | 22 | 13 | 25 | 105
Project Capacity | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System | [12 empty] | Only apporval category
Particulars | Total Documents | [9 empty] | Remaining Documents | Total Received (%) | Engineering completion (%)
|  | VOID | UNDER EPC | UNDER OE | SUB. APPROVED | APPROVED | NOTED FOR INFORMATION | NOT APPROVED | PENDING | Total Sub
I. Review Engineering Electrical
A.Basic Engineering | 11 | 0 | 3 | 2 | 0 | 2 | 4 | 0 | 0 | 11 | 0 | 100% | 0%
B.Major Electrical Equipments (GTP, GA, Type Test Reports and QAP) | 4 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 3 | 25% | 0%
C.Cable sizing documents | 4 | 0 | 0 | 0 | 1 | 3 | 0 | 0 | 0 | 4 | 0 | 100% | 0%
D.Cable GTPs, Type Test Reports and QAP | 7 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 3 | 4 | 3 | 57.14% | 0%
E.Battery Energy Storage System (BESS) | 17 | 0 | 5 | 3 | 1 | 2 | 2 | 0 | 4 | 13 | 4 | 76.47% | 0%
F.Module Mounting structure | 12 | 0 | 1 | 1 | 6 | 0 | 3 | 0 | 1 | 11 | 1 | 91.67% | 0%
G.MCR Building | 11 | 0 | 5 | 0 | 0 | 1 | 0 | 0 | 5 | 6 | 5 | 54.55% | 0%
H.Open Plinth for LCR Equipment | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 6 | 0% | 0%
I.BESS Foundation | 7 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 2 | 5 | 28.57% | 0%
J.Equipment foundations | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 4 | 0% | 0%
K.Layout, Ancillary Equipment GTP and DBR | 24 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 20 | 4 | 20 | 16.67% | 0%
M.Ancillary Systems | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 10 | 0% | 0%
N.Cable Schedules | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 7 | 0% | 0%
O.System Drawings and Layouts | 14 | 0 | 2 | 1 | 2 | 2 | 0 | 0 | 7 | 7 | 7 | 50% | 0%
P.Equipment GTPs, Type test reports and Inspection Reports | 24 | 0 | 7 | 1 | 1 | 0 | 0 | 0 | 15 | 9 | 15 | 37.5% | 0%
Q.Equipment Foundation Drawings and Cable Schedules | 25 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 15 | 10 | 15 | 40% | 0%
Total documents | 187 | 0 | 25 | 22 | 13 | 13 | 9 | 0 | 105 | 82 | 105 | 43.85% | 0%
| 187 | 22 | 100% | 11.76%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This chart isn't available in your version of Excel. Editing this shape or saving this workbook into a different file format will permanently break the chart.

## Sheet1 (hidden)
Sl. No. | Drawing/Document Title | Approval Category | Date Of Approval | Darwing Number | Approval Status | Proposed Submission Date
1 | Photovoltaic Module |  | 2025-02-27 | SECI-LEH25MW-GTP-ELE-1 | PGEL |  | Basic Engineering |  | Approved
2 | Power Conditioning Unit (Central) |  | 2025-01-24 | SECI-LEH25MW-GTP-ELE-2 | PGEL |  |  |  | Re-Submission
3 | System Design Basis Report (including Energy Yield Simulation and shadow analysis report) | CAT-III | 2025-05-28 | SECI-LEH25MW-DBR-ELE-3 | PGEL |  |  |  | PGEL
4 | DC SLD | CAT-IV | 2025-05-15 | SECI-LEH25MW-DWG-ELE-4 | Approved |  |  |  | SECI-Review
5 | AC SLD including BESS (upto 11 kV) | CAT-IV | 2025-07-24 | SECI-LEH25MW-DWG-ELE-5 | Approved |  |  |  | Yet To Submit
6 | Topographical Survey | CAT-IV | 2025-06-10 | SECI-LEH25MW-DWG-CIV-6 | Approved
7 | Concrete Mix Design Report |  | 2025-07-21 | SECI-LEH25MW-IR-CIV-7 | PGEL
8 | Grading and Levelling Plan |  | 2025-07-11 | SECI-LEH25MW-DWG-CIV-8 | PGEL
9 | Overall Plant Layout covering Array layout, Buildings (MCR and LCR) marking, Road Layout, Lightning protection layout, WMS Location, etc. | CAT-III | 2025-07-03 | SECI-LEH25MW-DWG-ELE-9 | PGEL
10 | Plant Boundary Fencing Layout and Details | CAT-I | 2025-05-27 | SECI-LEH25MW-DWG-CIV-10 | Approved
11 | Plant Main Gate - General Arrangement and Details | CAT-I | 2025-07-04 | SECI-LEH25MW-DWG-CIV-11 | Approved
12 | String Combiner Box (SCB) |  |  | SECI-LEH25MW-GTP-ELE-12 | Yet To Submit |  | Major Electrical Equipments (GTP, GA, Type Test Reports and QAP)
13 | Inverter Duty Transformer (IDT) |  |  | SECI-LEH25MW-GTP-ELE-13 | Yet To Submit
14 | 11kV HT ICOG Panel |  |  | SECI-LEH25MW-GTP-ELE-14 | SECI-Review
15 | 11kV HT Combiner Panel |  |  | SECI-LEH25MW-GTP-ELE-15 | Yet To Submit
16 | Solar cable (PV module to SCB) | CAT-II |  | SECI-LEH25MW-GTP-ELE-16 | Approved |  | Cable sizing documents
17 | DC cable (from SCB to PCU) | CAT-I |  | SECI-LEH25MW-GTP-ELE-17 | Approved
18 | LT cable (from PCU to IDT) | CAT-I |  | SECI-LEH25MW-GTP-ELE-18 | Approved
19 | 11kV LT Power Cable | CAT-I |  | SECI-LEH25MW-GTP-ELE-19 | Approved
20 | Solar cable (PV module to SCB) | CAT-II |  | SECI-LEH25MW-GTP-ELE-20 | Approved |  | Cable GTPs, Type Test Reports and QAP | SUB. APPROVED
21 | DC cable (from SCB to PCU) |  |  | SECI-LEH25MW-GTP-ELE-21 | Re-Submission |  |  | UNDER OE
22 | LT cable (from PCU to IDT) | CAT-I |  | SECI-LEH25MW-GTP-ELE-22 | Approved |  |  | APPROVED
23 | 11kV LT Power Cable | CAT-I |  | SECI-LEH25MW-GTP-ELE-23 | Approved |  |  | APPROVED
24 | Communication Cable |  |  | SECI-LEH25MW-GTP-ELE-24 | Yet To Submit |  |  | PENDING
25 | LT Auxiliary Power Cable |  |  | SECI-LEH25MW-GTP-ELE-25 | Yet To Submit |  |  | PENDING
26 | Control Cable |  |  | SECI-LEH25MW-GTP-ELE-26 | Yet To Submit |  |  | PENDING
27 | Design Basis Report for BESS with BESS PQR |  |  | SECI-LEH25MW-DBR-ELE-27 | SECI-Review |  | Battery Energy Storage System (BESS) | UNDER OE
28 | Battery Sizing Calculation | CAT-I |  | SECI-LEH25MW-DBR-ELE-28 | Approved |  |  | APPROVED
29 | Overall System Schematic, Equipment Layout and BoM |  |  | SECI-LEH25MW-DWG-ELE-29 | Yet To Submit |  |  | PENDING
30 | Battery Bank (GTP, Drawings, Type Test Report and QAP) Along with Battery Container GA |  |  | SECI-LEH25MW-GTP-ELE-30 | PGEL |  |  | UNDER EPC
31 | Battery Management System (GTP and Drawings) |  |  | SECI-LEH25MW-GTP-ELE-31 | PGEL |  |  | UNDER EPC
32 | Power Conditioning System (GTP, Drawings, Type Test Report and QAP) |  |  | SECI-LEH25MW-GTP-ELE-32 | SECI-Review |  |  | UNDER OE
33 | PCS Transformer (GTP, Drawings, Type Test Report and QAP) |  |  | SECI-LEH25MW-GTP-ELE-33 | Yet To Submit |  |  | PENDING
34 | PCS Transformer NIFPS (GTP, Drawings and QAP) (If Applicable) |  |  | SECI-LEH25MW-GTP-ELE-34 | Yet To Submit |  |  | PENDING
35 | HVAC System (General Arrangement and Details) |  |  | SECI-LEH25MW-DWG-ELE-35 | SECI-Review |  |  | UNDER OE
36 | BESS Auxiliary System SLD and DB Details |  |  | SECI-LEH25MW-GTP-ELE-36 | PGEL |  |  | UNDER EPC
37 | BESS Earthing Scheme |  |  | SECI-LEH25MW-DWG-ELE-37 | Yet To Submit |  |  | PENDING
38 | BESS Fire Protection Systems | CAT-III |  | SECI-LEH25MW-DWG-ELE-38 | PGEL |  |  | UNDER EPC
39 | Auxiliary Power Consumption Calculation | CAT-IV |  | SECI-LEH25MW-DBR-ELE-39 | Approved |  |  | NOTED FOR INFORMATION
40 | Heat Load Calculation of Container | CAT-IV |  | SECI-LEH25MW-DBR-CIV-40 | Approved |  |  | NOTED FOR INFORMATION
41 | Energy Management System (EMS) document (GTP, schematics,and GA) |  |  | SECI-LEH25MW-GTP-ELE-41 | Yet To Submit |  |  | PENDING
42 | DC and AC Sizing Cable Calculation | CAT-I |  | SECI-LEH25MW-DBR-ELE-42 | Approved |  |  | APPROVED
43 | DC and AC Cable GTP |  |  | SECI-LEH25MW-GTP-ELE-43 | Yet To Submit |  |  | PENDING
44 | Module Mounting Structure DBR | CAT-II |  | SECI-LEH25MW-DBR-CIV-44 | Approved |  | Module Mounting structure | UNDER EPC
44A | Module Mounting Structure DBR (Interior) | CAT-III |  | SECI-LEH25MW-DBR-CIV-44A | PGEL |  |  | UNDER OE
45 | MMS Drawing | CAT-II |  | SECI-LEH25MW-DWG-CIV-45 | Approved |  |  | UNDER EPC
45A | MMS Drawing (Interior) | CAT-III |  | SECI-LEH25MW-DWG-CIV-45A | PGEL |  |  | UNDER OE
46 | MMS Fabrication Drawing | CAT-IV |  | SECI-LEH25MW-DWG-CIV-46 | Approved |  |  | NOTED FOR INFORMATION
46A | MMS Fabrication Drawing (Interior) |  |  | SECI-LEH25MW-DWG-CIV-46A | Yet To Submit |  |  | PENDING
47 | MMS Foundation Drawing | CAT-II |  | SECI-LEH25MW-DWG-CIV-47 | Approved |  |  | UNDER EPC
47A | MMS Foundation Drawing (Interior) |  |  | SECI-LEH25MW-DWG-CIV-47A | Yet To Submit |  |  | PENDING
48 | MMS Foundation Marking Layout |  |  | SECI-LEH25MW-DWG-CIV-48 | SECI-Review |  |  | UNDER EPC
49 | Pile Test Location Drawing (if applicable) | CAT-II |  | SECI-LEH25MW-DWG-CIV-49 | Approved |  |  | UNDER EPC
50 | Pile Test Report (if applicable) |  |  | SECI-LEH25MW-IR-CIV-50 |  |  |  | UNDER OE
51 | MCR - Architectural Details, Elevations, Sections and Finishing | CAT-I |  | SECI-LEH25MW-DWG-CIV-51 |  |  | MCR Building | APPROVED
52 | MCR Foundation and Super Structure - Design Basis Report | CAT-III |  | SECI-LEH25MW-DBR-CIV-52 |  |  |  | UNDER OE
53 | MCR - Foundation General Arrangement and Reinforcement Details | CAT-III |  | SECI-LEH25MW-DWG-CIV-53 |  |  |  | UNDER OE
54 | MCR - Plinth Beam General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-54 |  |  |  | UNDER OE
55 | MCR - Lintel Beam General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-55 |  |  |  | UNDER OE
56 | MCR - Roof General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-56 |  |  |  | UNDER OE
57 | MCR - Plumbing Network and Sanitary Details |  |  | SECI-LEH25MW-DWG-CIV-57 |  |  |  | PENDING
58 | MCR Heating/HVAC Sytem - Layout, General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-58 |  |  |  | PENDING
59 | MCR Heating/HVAC System - Design Basis Report (DBR) |  |  | SECI-LEH25MW-DBR-CIV-59 |  |  |  | PENDING
60 | MCR Lighting Layout |  |  | SECI-LEH25MW-DWG-ELE-60 |  |  |  | PENDING
61 | MCR - Cable Trench General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-61 |  |  |  | PENDING
62 | LCR Equipment Layout |  |  | SECI-LEH25MW-DWG-ELE-62 |  |  | LCR Equipment Room | PENDING
63 | Inverter Foundation and Super Structure DBR |  |  | SECI-LEH25MW-DBR-CIV-63 |  |  |  | PENDING
63A | HT Container Foundation and Super Structure DBR |  |  | SECI-LEH25MW-DBR-CIV-63A |  |  |  | PENDING
64 | Inverter Foundation and Superstructure - General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-64 |  |  |  | PENDING
64A | HT Container Foundation and Superstructure - General Arrangement and Reinforcement Details |  |  | SECI-LEH25MW-DWG-CIV-64A |  |  |  | PENDING
65 | Cable Trench Layout for ICR room |  |  | SECI-LEH25MW-DWG-ELE-65 |  |  |  | PENDING
66 | BESS Transformer Foundation - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-66 |  |  | BESS Foundation | PENDING
67 | Design Basis Report (DBR) for BESS Transformer foundation |  |  | SECI-LEH25MW-DBR-CIV-67 |  |  |  | PENDING
68 | BESS Container Platform and Foundation - Design Basis Report |  |  | SECI-LEH25MW-DBR-CIV-68 |  |  |  | UNDER OE
69 | BESS Container Platform Superstructure and Foundation - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-69 |  |  |  | UNDER OE
70 | BESS Yard Fence & Gate - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-70 |  |  |  | PENDING
71 | BESS PCS Foundation - DBR |  |  | SECI-LEH25MW-DBR-CIV-71 |  |  |  | PENDING
72 | BESS PCS Foundation - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-72 |  |  |  | PENDING
73 | String Combiner Panel Structure and Foundation - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-73 |  |  | Equipment foundations | PENDING
74 | Auxiliary Tranformer Foundation DBR and GA Drawing |  |  | SECI-LEH25MW-DWG-CIV-74 |  |  |  | PENDING
75 | Inverter Transformer Foundation DBR |  |  | SECI-LEH25MW-DBR-CIV-75 |  |  |  | PENDING
76 | Inverter Transformer Foundation - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-76 |  |  |  | PENDING
77 | Cable trench Layout and Cross section (DC, AC, Lighting and CCTV system etc) |  |  | SECI-LEH25MW-DWG-ELE-77 |  |  | Layout, Ancillary Equipment GTP and DBR | PENDING
78 | DC Earthing Design and Calculation | CAT-II |  | SECI-LEH25MW-DBR-ELE-78 |  |  |  | UNDER EPC
79 | PV Array Yard Earthing Layout |  |  | SECI-LEH25MW-DWG-ELE-79 |  |  |  | PENDING
80 | AC Earthing Design and Calculation | CAT-I |  | SECI-LEH25MW-DBR-ELE-80 |  |  |  | APPROVED
81 | LCR and MCR Yard Earthing Layout |  |  | SECI-LEH25MW-DWG-ELE-81 |  |  |  | PENDING
82 | Illumination Design and Simulation Report |  |  | SECI-LEH25MW-DBR-ELE-82 |  |  |  | PENDING
83 | Plant Lighting Layout and Lighting Pole GA & Foundation |  |  | SECI-LEH25MW-DWG-ELE-83 |  |  |  | PENDING
84 | LED Luminarie and Pole with accessories |  |  | SECI-LEH25MW-GTP-ELE-84 |  |  |  | PENDING
85 | Plant Auxilary Load Calculation with UPS sizing |  |  | SECI-LEH25MW-DBR-ELE-85 |  |  |  | UNDER EPC
86 | Auxiliary SLD |  |  | SECI-LEH25MW-DWG-ELE-86 |  |  |  | PENDING
87 | UPS ( GTP, GA & Drawing, QAP and Type Test Reports |  |  | SECI-LEH25MW-GTP-ELE-87 |  |  |  | PENDING
88 | Auxiliary Transformer (GTP, GA & Drawing, QAP and Type Test Reports) |  |  | SECI-LEH25MW-GTP-ELE-88 |  |  |  | PENDING
89 | GTP and Schematics of LT distribution panel |  |  | SECI-LEH25MW-GTP-ELE-89 |  |  |  | PENDING
90 | SCADA System Architecture and IO List |  |  | SECI-LEH25MW-DBR-ELE-90 |  |  |  | PENDING
91 | SCADA Schematic |  |  | SECI-LEH25MW-DWG-ELE-91 |  |  |  | PENDING
92 | GTP of SCADA system components - Hardware & Software |  |  | SECI-LEH25MW-GTP-ELE-92 |  |  |  | PENDING
93 | CCTV Layout and General Arrangement |  |  | SECI-LEH25MW-DWG-ELE-93 |  |  |  | PENDING
94 | Solar Cable Connector (GTP and Type Test Reports) |  |  | SECI-LEH25MW-GTP-ELE-94 |  |  |  | PENDING
95 | HT Cable Termination Kit (GTP, GA Drawing and Type Test Reports) |  |  | SECI-LEH25MW-GTP-ELE-95 |  |  |  | PENDING
96 | Lightning protection system: GTP, LA Mounting and Foundation drawing |  |  | SECI-LEH25MW-GTP-ELE-96 |  |  |  | PENDING
97 | Earthing electrode and Accessories- GTP |  |  | SECI-LEH25MW-GTP-ELE-97 |  |  |  | PENDING
98 | Testing Instruments |  |  | SECI-LEH25MW-GTP-ELE-98 |  |  |  | PENDING
99 | Weather Monitoring System: GA, GTP and Mounting & Foundation drawing |  |  | SECI-LEH25MW-GTP-ELE-99 |  |  |  | PENDING
100 | CCTV System |  |  | SECI-LEH25MW-GTP-ELE-100 |  |  |  | PENDING
101 | Roads - DBR |  |  | SECI-LEH25MW-DBR-CIV-101 |  |  | Ancillary Systems | PENDING
102 | Road Layout and Sections |  |  | SECI-LEH25MW-DWG-CIV-102 |  |  |  | PENDING
103 | Drainage-DBR |  |  | SECI-LEH25MW-DBR-CIV-103 |  |  |  | PENDING
104 | Drainage Layout and Sections |  |  | SECI-LEH25MW-DWG-CIV-104 |  |  |  | PENDING
105 | PV Module Cleaning System-DBR and GA |  |  | SECI-LEH25MW-DBR-CIV-105 |  |  |  | PENDING
106 | Security Room - Architectural Plan, Elevation, Sections & Finishing |  |  | SECI-LEH25MW-DWG-CIV-106 |  |  |  | PENDING
107 | Security Room Superstructure and Foundation -Design Basis Report |  |  | SECI-LEH25MW-DBR-CIV-107 |  |  |  | PENDING
108 | Security Room Superstructure and Foundation- General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-108 |  |  |  | PENDING
109 | Security Room - Plumbing and Sanitary Layout, General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-109 |  |  |  | PENDING
110 | Security Room Heating/HVAC Sytem - Layout, General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-110 |  |  |  | PENDING
111 | Solar cable (PV module to SCB) |  |  | SECI-LEH25MW-DOC-ELE-111 |  |  | Cable Schedules | PENDING
112 | DC cable (from SCB to PCU) |  |  | SECI-LEH25MW-DOC-ELE-112 |  |  |  | PENDING
113 | LT cable (from PCU to IDT) |  |  | SECI-LEH25MW-DOC-ELE-113 |  |  |  | PENDING
114 | 11kV LT Power Cable |  |  | SECI-LEH25MW-DOC-ELE-114 |  |  |  | PENDING
115 | Communication Cable |  |  | SECI-LEH25MW-DOC-ELE-115 |  |  |  | PENDING
116 | LT Auxiliary Power Cable |  |  | SECI-LEH25MW-DOC-ELE-116 |  |  |  | PENDING
117 | Control Cable |  |  | SECI-LEH25MW-DOC-ELE-117 |  |  |  | PENDING
118 | 66kV HT Conductor Sizing Calculation | CAT-I |  | SECI-LEH25MW-DBR-ELE-118 |  |  |  | APPROVED
119 | Power Evacuation SLD (11/66kV Switchyard) | CAT-II |  | SECI-LEH25MW-DWG-ELE-119 |  |  |  | UNDER EPC
120 | Battery & Battery Charger for Switchyard - Sizing Calculations |  |  | SECI-LEH25MW-DBR-ELE-120 |  |  |  | PENDING
121 | Main Control Room UPS Sizing Calculation |  |  | SECI-LEH25MW-DBR-ELE-121 |  |  |  | PENDING
122 | Aux. Load Calculations and Aux. Transformer Sizing (Switchyard & BESS) |  |  | SECI-LEH25MW-DBR-ELE-122 |  |  |  | UNDER EPC
123 | Auxiliary System SLD and DB Details |  |  | SECI-LEH25MW-DWG-ELE-123 |  |  |  | PENDING
124 | 66 kV Switchyard - Short Circuit Force & Cantilever Strength Calculation |  |  | SECI-LEH25MW-DBR-ELE-124 |  |  |  | UNDER OE
125 | Plant End Switchyard Layout |  |  | SECI-LEH25MW-DWG-ELE-125 |  |  |  | UNDER OE
126 | Plant End Substation Earthing Design and Calculation |  |  | SECI-LEH25MW-DWG-ELE-126 |  |  |  | UNDER EPC
127 | Plant End Substation Earthing Layout |  |  | SECI-LEH25MW-DWG-ELE-127 |  |  |  | UNDER OE
128 | Switchyard Cable Trench Layout - layout, design and details |  |  | SECI-LEH25MW-DWG-ELE-128 |  |  |  | PENDING
129 | Switchyard Erection Key Diagram |  |  | SECI-LEH25MW-DWG-ELE-129 |  |  |  | PENDING
130 | Switchyard Illumination Layout |  |  | SECI-LEH25MW-DWG-ELE-130 |  |  |  | PENDING
131 | Fire & Smoke Detection Layout for Buildings and Switchyard along with GTP |  |  | SECI-LEH25MW-DWG-ELE-131 |  |  |  | PENDING
132 | Power Transformer |  |  | SECI-LEH25MW-GTP-ELE-132 |  |  |  | UNDER EPC
133 | NIFP System- Power Transformer |  |  | SECI-LEH25MW-GTP-ELE-133 |  |  |  | PENDING
134 | Lightning Arrestor - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-134 |  |  |  | UNDER OE
135 | Isolator - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-135 |  |  |  | UNDER OE
136 | BPI - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-136 |  |  |  | UNDER OE
137 | Circuit Breaker - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-137 |  |  |  | UNDER OE
138 | Current Transformer (Metering) - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-138 |  |  |  | UNDER OE
139 | Voltage Transformer (Metering) - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-139 |  |  |  | PENDING
140 | ABT Meter- GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-140 |  |  |  | PENDING
141 | Control and Relay panels (GTP, GA & Drawing, QAP and Type Test Reports) |  |  | SECI-LEH25MW-GTP-ELE-141 |  |  |  | PENDING
142 | UPS System MCR building - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-142 |  |  |  | PENDING
143 | Station Auxiliary ACDB - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-143 |  |  |  | PENDING
144 | Power and Control cables - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-144 |  |  |  | PENDING
145 | Protection CT - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-145 |  |  |  | UNDER OE
146 | Protection PT/CVT - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-146 |  |  |  | UNDER OE
147 | Switchyard Illumination - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-147 |  |  |  | PENDING
148 | BMK. JB, MB - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-148 |  |  |  | PENDING
149 | Telemetry system - GTP and drawing |  |  | SECI-LEH25MW-GTP-ELE-149 |  |  |  | PENDING
150 | Transmission conductor/cable - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-150 |  |  |  | PENDING
151 | Line Disc insulator - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-151 |  |  |  | PENDING
152 | Transmission Line Earthing Details |  |  | SECI-LEH25MW-DWG-ELE-152 |  |  |  | PENDING
153 | Line Hardware Material - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-153 |  |  |  | PENDING
154 | Line Conductor - GTP and Drawing |  |  | SECI-LEH25MW-GTP-ELE-154 |  |  |  | PENDING
155 | Relay setting Calculation & Chart |  |  | SECI-LEH25MW-DBR-ELE-155 |  |  |  | PENDING
156 | Power Transformer Foundation and Burnt Oil Pit DBR |  |  | SECI-LEH25MW-DBR-CIV-156 |  |  |  | UNDER OE
157 | Power Transformer Foundation and Burnt Oil Pit - General Arrangement and Details |  |  | SECI-LEH25MW-DWG-CIV-157 |  |  |  | UNDER OE
158 | GA drawing of LA support Structure |  |  | SECI-LEH25MW-DWG-CIV-158 |  |  |  | UNDER OE
159 | GA drawing of ISO support Structure |  |  | SECI-LEH25MW-DWG-CIV-159 |  |  |  | PENDING
160 | GA drawing of CT support Structure |  |  | SECI-LEH25MW-DWG-CIV-160 |  |  |  | PENDING
161 | GA drawing of PT support Structure |  |  | SECI-LEH25MW-DWG-CIV-161 |  |  |  | PENDING
162 | Isolator Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-162 |  |  |  | PENDING
163 | Circuit Breaker Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-163 |  |  |  | PENDING
164 | Current Transformer (Metering and Protection) Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-164 |  |  |  | UNDER EPC
165 | Voltage Transformer (Metering and Protection) Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-165 |  |  |  | UNDER EPC
166 | Lightning Arrestor Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-166 |  |  |  | UNDER OE
167 | ABT Meter Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-167 |  |  |  | PENDING
168 | Gantry - GA and Foundation (as applicable) |  |  | SECI-LEH25MW-DWG-CIV-168 |  |  |  | PENDING
169 | Switchyard DSLP Layout & Calculation |  |  | SECI-LEH25MW-DWG-ELE-169 |  |  |  | PENDING
170 | 66kV HT Conductor |  |  | SECI-LEH25MW-DOC-ELE-170 |  |  |  | PENDING
171 | HT and LT Cable Schedule- Switchyard |  |  | SECI-LEH25MW-DOC-ELE-171 |  |  |  | PENDING
172 | Control Scheme Cable Schedule- Switchyard |  |  | SECI-LEH25MW-DOC-ELE-172 |  |  |  | PENDING
173 | SAS Cable Schedule- Switchyard |  |  | SECI-LEH25MW-DOC-ELE-173 |  |  |  | PENDING
174 | Switchyard Fencing and Gate |  |  | SECI-LEH25MW-DWG-CIV-174 |  |  |  | PENDING
175 | LILO Switchyard Layout |  |  | SECI-LEH25MW-DWG-ELE-175 |  |  |  | PENDING
176 | Transmission line Route Layout |  |  | SECI-LEH25MW-DWG-ELE-176 |  |  |  | PENDING
177 | 66KV line Tower Schedule |  |  | SECI-LEH25MW-DWG-ELE-177 |  |  |  | PENDING
178 | 66KV Line profile |  |  | SECI-LEH25MW-DWG-ELE-178 |  |  |  | PENDING
179 | Transmission Tower- GA and Structural Drawing |  |  | SECI-LEH25MW-DWG-CIV-179 |  |  |  | PENDING
180 | Transmission Tower- Foundation Drawing |  |  | SECI-LEH25MW-DWG-CIV-180 |  |  |  | PENDING

## Progress Abstract
Daily Progress Report | [9 empty] | Date:- | 2025-08-30
Project Name : |  | 25 MW (AC) Solar PV Power Plant (50 MWp DC) with 20 MW / 50 MWh Battery Energy Storage System at Taru, Leh, UT of Ladakh, India
Client : |  | Solar Energy Corporation of India Ltd
SPV : |  | Prozeal Green Energy Limited | [11 empty] | 3905
Project Start Date |  | 2024-11-20
Project COD |  | 2027-11-05 | [9 empty] | 1080 | 797
Sr. No | Description | Work Status | UOM | Scope | Progress | Balance | %age | Status | Dashboard
CIVIL Package | [11 empty] | COMP
1 | Boundary Fencing | Boundary Demarcation and marking | Rm | 5690 | 5690 | 0 | 100% | COMP |  |  |  | WIP
|  | Plie Boring | Rm | 5690 | 4957.5 | 732.5 | 87.13% | WIP |  |  |  | Yet to Start
|  | Fence post Allignment and Concrete Pouring | Rm | 5690 | 5150 | 540 | 90.51% | WIP | [5 empty] | 0.39497 | 0.60503 | 34.99%
|  | Barbed wire installation | Rm | 5690 | 4315 | 1375 | 75.83% | WIP
|  | Mesh installation with connecting strip and tightening | Rm | 5690 | 4335 | 1355 | 76.19% | WIP
|  | Weightage Progress |  | 1 | 0.85931 | 0.14069 | 85.93%
2 | Main Gate | Foundation Excavation | Nos | 3 | 3 | 0 | 100% | COMP
|  | Foundation PCC | Nos | 3 | 3 | 0 | 100% | COMP
|  | Foundation RCC | Nos | 3 | 3 | 0 | 100% | COMP
|  | Columns | Nos | 3 | 3 | 0 | 100% | COMP
|  | Gate Febrication and Installation | Nos | 2 | 2 | 0 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 1 | 0 | 100%
3 | MCR | Excavation | No's | 33 | 33 | 0 | 100% | COMP
|  | Foundation PCC | No's | 33 | 33 | 0 | 100% | WIP
|  | Footing Foundation casting | No's | 33 | 33 | 0 | 100% | WIP
|  | Column upto Plinth Beam | No's | 33 | 0 | 33 | 0% | Yet to Start
|  | Plinth Beam Casting | Mtr | 322 | 0 | 322 | 0% | Yet to Start
|  | Column upto Lintel Beam | No's | 33 | 0 | 33 | 0% | Yet to Start
|  | Lintel and sunshade casting | Mtr | 132 | 0 | 132 | 0% | Yet to Start
|  | Column upto Roof Beam | No's | 33 | 0 | 33 | 0% | Yet to Start
|  | Roof Beam & Slab Casting | Ls | 1 | 0 | 1 | 0% | Yet to Start
|  | Cable Trench Raft Casting | Mtr | 50 | 0 | 50 | 0% | Yet to Start
|  | Cable Trench Wall casting | Mtr | 100 | 0 | 100 | 0% | Yet to Start
|  | Floor Slab Casting | Ls | 1 | 0 | 1 | 0% | Yet to Start
|  | Brick Masonry Work | Cu. Mtr | 310 | 0 | 310 | 0% | Yet to Start
|  | Wall & Celling Plaster | Sq. Mtr | 2380 | 0 | 2380 | 0% | Yet to Start
|  | Flooring | No's | 8 | 0 | 0 | 0% | Yet to Start
|  | Putty & Paint work | No's | 8 | 0 | 0 | 0% | Yet to Start
|  | Misc Work | LS | 1 | 0 | 0 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0.21911 | 0.78089 | 21.91%
4 | IDT- Solar | Excavation | No's | 4 | 3 | 1 | 75% | WIP
|  | Foundation PCC | No's | 4 | 3 | 1 | 75% | WIP
|  | Foundation Raft casting | No's | 4 | 3 | 1 | 75% | WIP
|  | Wall casting | No's | 8 | 6 | 2 | 75% | WIP
|  | Cashment Wall B/W | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Fencing - IDT | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0.54545 | 0.45455 | 54.55%
5 | LCR- Solar | Excavation | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Foundation PCC | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Foundation Raft casting | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Pedestal casting | No's | 32 | 0 | 32 | 0% | Yet to Start
|  | Slab Casting | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | B/W | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Canopy | No's | 4 | 0 | 4 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0 | 1 | 0%
6 | MMS- Pile | Pile marking | No's | 25992 | 2758 | 23234 | 10.61% | WIP
|  | Pile Boring | No's | 25992 | 811 | 25181 | 3.12% | WIP
|  | Pile Casting | No's | 25992 | 12 | 25980 | 0.04617% | Yet to Start
|  | Pile Capping | No's | 25992 | 0 | 25992 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0.034443 | 0.96556 | 3.444%
7 | IDT- BESS | Excavation | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Foundation PCC | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Foundation Raft casting | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Wall casting | No's | 10 | 0 | 10 | 0% | Yet to Start
|  | Cashment Wall B/W | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Fencing - IDT | No's | 5 | 0 | 5 | 0% | Yet to Start
|  | Weightage Progress |  | 1 | 0 | 1 | 0%
8 | BESS- Civil | Excavation of Container foundation | Nos | 10 | 10 | 0 | 100% | WIP
|  | Container Foundation PCC | Nos | 40 | 32 | 8 | 80% | WIP
|  | Container Foundation Concrete Pouring | Nos | 40 | 12 | 28 | 30% | Yet to Start
|  | Container Pedestal Concrete Pouring | Nos | 40 | 0 | 40 | 0% | Yet to Start
|  | Container Tie Beam & Slab Concrete Pouring | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | B/W of Container Plartform | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | Excavation of PCS foundation | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | PCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | Yet to Start
|  | RCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | Yet to Start
|  | RCC of PCS Pedestal | Nos | 40 | 0 | 40 | 0% | Yet to Start
|  | RCC of PCS Tie Beam | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | B/W of PCS Plartform | Nos | 10 | 0 | 10 | 0% | Yet to Start
|  | Weightage Progress | No's | 1 | 0.14091 | 0.85909 | 14.09%
ELECTRICAL Package
33 | Switchyard ELE | Structure Errection | Nos | 97 | 0 | 97 | 0%
34 |  | Equipment Errection | Nos | 97 | 0 | 97 | 0%
35 |  | Earthing Works | Mtr | 3252.375 | 0 | 3252.375 | 0%
36 |  | Cabling Works | LS | 1 | 0 | 1 | 0%
37 |  | Testing Works | LS | 1 | 0 | 1 | 0%
38 |  | Weightage Progress | LS | 689.675 | 0 | 689.675 | 0%
39 | DC Work | Trench Excavation | Mtr | 171000 | 950 | 170050 | 0.5556%
40 |  | 400sqmm Cable Laying(SCB) | No's | 1824 | 0 | 1824 | 0%
41 |  | Inv Installation | No's | 76 | 0 | 76 | 0%
42 |  | 400sqmm Cable Laying | Mtr | 638400 | 0 | 638400 | 0%
43 |  | SCB Stand Casting | No's | 3648 | 0 | 3648 | 0%
44 |  | SCB Installation | No's | 1824 | 0 | 1824 | 0%
45 |  | 6 Sq. mm Termination | No's | 1824 | 0 | 1824 | 0%
46 |  | Termination SCB End | No's | 1824 | 0 | 1824 | 0%
47 |  | Termination Inv End | No's | 1824 | 0 | 0 | 0%
48 |  | Earthing Conductor Laying | Mtr | 95000 | 0 | 95000 | 0%
49 |  | Earthpit Installation | No's | 912 | 0 | 912 | 0%
50 |  | String Cable Termination | No's | 1824 | 0 | 1824 | 0%
51 |  | LA Insatallation | No's | 190 | 0 | 190 | 0%
52 |  | LA Connection | No's | 190 | 0 | 190 | 0%
53 |  | MMS Installation | No's | 14592 | 0 | 14592 | 0%
54 |  | Module Installation | No's | 846336 | 0 | 846336 | 0%
55 |  | Weightage Progress | No's | 1 | 0.00034722 | 0.99965 | 0.03472%
56 | AC Work | AC Trench | Mtr | 26043.8846 | 0 | 26043.8846 | 0%
57 |  | 3CX240sqmm Cable Laying | Mtr | 18269.2308 | 0 | 18269.2308 | 0%
58 |  | 3CX400sqmm Cable Laying | Mtr | 58461.5385 | 0 | 58461.5385 | 0%
59 |  | 1CX400sqmm Cable Laying | LS | 38 | 0 | 38 | 0%
60 |  | OFC Cable Laying | LS | 38 | 0 | 38 | 0%
61 |  | Grid Earthing | mtr | 7600 | 0 | 7600 | 0%
62 |  | Tray support casting | No's | 38 | 0 | 38 | 0%
63 |  | Tray from INV to LV Side | No's | 38 | 0 | 38 | 0%
64 |  | Earthpit Installation | No's | 38 | 0 | 38 | 0%
65 |  | IDT Erection | No's | 38 | 0 | 38 | 0%
66 |  | ICOG Panel | No's | 38 | 0 | 38 | 0%
67 |  | LT Panel | No's | 38 | 0 | 38 | 0%
68 |  | UPS Panel | No's | 38 | 0 | 38 | 0%
69 |  | Aux Trafo | No's | 38 | 0 | 38 | 0%
70 |  | 1C*400Sqmm cable Termination | Sets | 38 | 0 | 38 | 0%
71 |  | Weightage Progress | No's | 1 | 0 | 1 | 0%
22%
MCR CIVIL Work
0%
Fencing Work
86%
100%
55%
0%
IDT- Solar Civil Work
IDT- BESS Civil Work
0%
14%
CIVIL PROGRESS%
3.444%
MMS PILLING

## Civil Progress
Civil Progress | [6 empty] | DAILY PROGRESS
Sr.no. | Description | UOM | Scope | Progress | Balance | % Progress | Cummulative | time axis 2025-05-05 to 2025-10-31
Boundary Fencing |  | Rm | 5690 | 4889.5 | 800.5 | 85.93%
1 | Boundary Demarcation and marking | Rm | 5690 | 5690 | 0 | 100% | 5690 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 5250; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 300; 2025-07-03: 140
2 | Plie Boring | Rm | 5690 | 4957.5 | 732.5 | 87.13% | 4957.5 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 4957.5; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0
3 | Fence post Allignment and Concrete Pouring | Rm | 5690 | 5150 | 540 | 90.51% | 5150 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 1642.5; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 52; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 75.5; 2025-07-07: 0; 2025-07-08: 250; 2025-07-09: 250; 2025-07-10: 225; 2025-07-11: 272.5; 2025-07-12: 200; 2025-07-13: 250; 2025-07-14: 225; 2025-07-15: 175; 2025-07-16: 192.5; 2025-07-17: 0; 2025-07-18: 175; 2025-07-19: 187.5; 2025-07-20: 0; 2025-07-21: 155; 2025-07-22: 0; 2025-07-23: 187.5; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 35; 2025-08-08: 200; 2025-08-09: 200; 2025-08-10: 200; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0
4 | Barbed wire installation | Rm | 5690 | 4315 | 1375 | 75.83% | 4315 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 1300; 2025-07-04: 180; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 290; 2025-07-12: 315; 2025-07-13: 315; 2025-07-14: 320; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 100; 2025-07-29: 100; 2025-07-30: 100; 2025-07-31: 100; 2025-08-01: 100; 2025-08-02: 100; 2025-08-03: 100; 2025-08-04: 100; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 195; 2025-08-11: 300; 2025-08-12: 300; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0
5 | Mesh installation with connecting strip and tightening | Rm | 5690 | 4335 | 1355 | 76.19% | 4335 | 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 1300; 2025-07-04: 180; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 50; 2025-07-10: 60; 2025-07-11: 210; 2025-07-12: 180; 2025-07-13: 180; 2025-07-14: 220; 2025-07-15: 105; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 150; 2025-07-19: 165; 2025-07-20: 0; 2025-07-21: 180; 2025-07-22: 0; 2025-07-23: 180; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 100; 2025-07-29: 100; 2025-07-30: 100; 2025-07-31: 100; 2025-08-01: 100; 2025-08-02: 100; 2025-08-03: 100; 2025-08-04: 100; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 195; 2025-08-11: 90; 2025-08-12: 90; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0
Main Gate |  | Nos | 2.8 | 2.8 | 0 | 100%
1 | Foundation Excavation | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 3
2 | Foundation PCC | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 3
3 | Foundation RCC | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 3
4 | Columns | Nos | 3 | 3 | 0 | 100% | 3 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 1; 2025-07-12: 2
5 | Gate Febrication and Installation | Nos | 2 | 2 | 0 | 100% | 2 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 2
Street light Work |  | No's | 175 | 0 | 175 | 0%
1 | Pole Casting | No's | 175 | 0 | 175 | 0% | 0
2 | Light Erection | No's | 175 | 0 | 175 | 0% | 0
MCR | [5 empty] | 21.91%
1 | Excavation | No's | 33 | 33 | 0 | 100% | 33 | 2025-06-24: 33
2 | Foundation PCC | No's | 33 | 33 | 0 | 100% | 33 | 2025-06-24: 17; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 5; 2025-07-21: 11
3 | Foundation Reinforcement | No's | 33 | 33 | 0 | 100% | 33 | 2025-06-24: 17; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 10; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 6; 2025-08-29: 0; 2025-08-30: 0; 2025-08-31: 0
4 | Foundation Shuttering | No's | 33 | 33 | 0 | 100% | 33 | 2025-06-24: 17; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 5; 2025-08-22: 5; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 6; 2025-08-30: 0; 2025-08-31: 0
5 | Footing Foundation casting | No's | 33 | 33 | 0 | 100% | 33 | 2025-06-24: 17; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 5; 2025-08-24: 5; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 0; 2025-08-30: 6; 2025-08-31: 0
6 | Back filling | No's | 33 | 23 | 10 | 69.7% | 23 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 17; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 0; 2025-08-30: 0; 2025-08-31: 6
7 | Column upto Plinth Beam | No's | 33 | 0 | 33 | 0% | 0 | 2025-06-24: 0
8 | Plinth Beam Reinforcement | Mtr | 322 | 0 | 322 | 0% | 0 | 2025-06-24: 0
9 | Plinth Beam shuttering | Mtr | 322 | 0 | 322 | 0% | 0 | 2025-06-24: 0
10 | Plinth Beam Casting | Mtr | 322 | 0 | 322 | 0% | 0 | 2025-06-24: 0
11 | Column upto Lintel Beam | No's | 33 | 0 | 33 | 0% | 0 | 2025-06-24: 0
12 | Lintel and sunshade reinforcement & shuttering | Mtr | 132 | 0 | 132 | 0% | 0 | 2025-06-24: 0
13 | Lintel and sunshade casting | Mtr | 132 | 0 | 132 | 0% | 0 | 2025-06-24: 0
14 | Cable Trench PCC Base | Mtr | 50 | 0 | 50 | 0% | 0 | 2025-06-24: 0
15 | Cable Trench Reinforcement & Shuttering | Mtr | 50 | 0 | 50 | 0% | 0 | 2025-06-24: 0
16 | Cable Trench Raft Casting | Mtr | 50 | 0 | 50 | 0% | 0 | 2025-06-24: 0
17 | Cable Trench Wall casting | Mtr | 100 | 0 | 100 | 0% | 0 | 2025-06-24: 0
18 | Column upto Roof Beam | No's | 33 | 0 | 33 | 0% | 0 | 2025-06-24: 0
19 | Roof Beam & Slab shuttering | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
20 | Roof Beam & Slab reinforcement | Ls | 1 | 0 |  |  | 0 | 2025-06-24: 0
21 | Roof Beam & Slab Casting | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
22 | Floor Slab Casting | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
23 | Brick Masonry Work | Cu. Mtr | 310 | 0 | 310 | 0% | 0 | 2025-06-24: 0
24 | Wall & Celling Plaster | Sq. Mtr | 2380 | 0 | 2380 | 0% | 0 | 2025-06-24: 0
25 | Flooring | No's | 8 | 0 | 0 | 0%
| Scada Room (10 x 7.8)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Conference Room (5.2 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Manager Room (2.5 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Store Room (2.51 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Battery Room (4.6 x 4.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| LT Panel Room (4.2 x 8.25)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Toilet (2.85 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Pantry Room (2.4 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
26 | Putty & Paint work | No's | 8 | 0 | 0 | 0%
| Scada Room (10 x 7.8)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Conference Room (5.2 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Manager Room (2.5 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Store Room (2.51 x 3.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Battery Room (4.6 x 4.6)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| LT Panel Room (4.2 x 8.25)mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Toilet (2.85 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Pantry Room (2.4 x 3.6) mtr | No's | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
27 | Misc Work | LS | 1 | 0 | 0 | 0%
| Drain | Ls | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Ramp | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Steps | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Septic Tank | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Soak Pit | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Plumbing Works | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
| Electrical works | LS | 1 | 0 | 1 | 0% | 0 | 2025-06-24: 0
IDT- Solar |  |  |  | 3 |  | 54.55%
1 | Excavation | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
2 | Foundation PCC | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
3 | Foundation Raft Reinforcement | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
4 | Foundation Raft Shuttering | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
5 | Foundation Raft casting | No's | 4 | 3 | 1 | 75% | 3 | 2025-06-24: 3
6 | Wall Reinforcement | No's | 8 | 6 | 2 | 75% | 6 | 2025-06-24: 6
7 | Wall Shuttering | No's | 8 | 6 | 2 | 75% | 6 | 2025-06-24: 6
8 | Wall casting | No's | 8 | 6 | 2 | 75% | 6 | 2025-06-24: 6
9 | Back filling | No's | 4 | 0 | 4 | 0% | 0 | 2025-06-24: 0
10 | Cashment Wall B/W | No's | 4 | 0 | 4 | 0% | 0 | 2025-06-24: 0
11 | Fencing - IDT | No's | 4 | 0 | 4 | 0% | 0 | 2025-06-24: 0
LCR- Solar | [5 empty] | 0%
1 | Excavation | No's | 32 | 0 | 32 | 0% | 0
2 | Foundation PCC | No's | 32 | 0 | 32 | 0% | 0
3 | Foundation Raft Reinforcement | No's | 32 | 0 | 32 | 0% | 0
4 | Foundation Raft Shuttering | No's | 32 | 0 | 32 | 0% | 0
5 | Foundation Raft casting | No's | 32 | 0 | 32 | 0% | 0
6 | Pedestal Reinforcement | No's | 32 | 0 | 32 | 0% | 0
7 | Pedestal Shuttering | No's | 32 | 0 | 32 | 0% | 0
8 | Pedestal casting | No's | 32 | 0 | 32 | 0% | 0
9 | Slab Shuttering & Reinforcement | No's | 4 | 0 | 4 | 0% | 0
10 | Slab Casting | No's | 4 | 0 | 4 | 0% | 0
11 | B/W | No's | 4 | 0 | 4 | 0% | 0
12 | Canopy | No's | 4 | 0 | 4 | 0% | 0
IDT- BESS |  |  |  | 0 |  | 0%
1 | Excavation | No's | 5 | 0 | 5 | 0% | 0
2 | Foundation PCC | No's | 5 | 0 | 5 | 0% | 0
3 | Foundation Raft Reinforcement | No's | 5 | 0 | 5 | 0% | 0
4 | Foundation Raft Shuttering | No's | 5 | 0 | 5 | 0% | 0
5 | Foundation Raft casting | No's | 5 | 0 | 5 | 0% | 0
6 | Wall Reinforcement | No's | 10 | 0 | 10 | 0% | 0
7 | Wall Shuttering | No's | 10 | 0 | 10 | 0% | 0
8 | Wall casting | No's | 10 | 0 | 10 | 0% | 0
9 | Back filling | No's | 5 | 0 | 5 | 0% | 0
10 | Cashment Wall B/W | No's | 5 | 0 | 5 | 0% | 0
11 | Fencing - IDT | No's | 5 | 0 | 5 | 0% | 0
BESS Foundation |  |  |  | 4.2727 |  | 14.09%
1 | Excavation of Container foundation | Nos | 10 | 10 | 0 | 100% | 10 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 1; 2025-08-03: 1; 2025-08-04: 1; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 0; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 1; 2025-08-17: 1; 2025-08-18: 1; 2025-08-19: 1; 2025-08-20: 2; 2025-08-21: 1; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0
2 | Container Foundation PCC | Nos | 40 | 32 | 8 | 80% | 32 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 8; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 8; 2025-08-20: 8; 2025-08-21: 8; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 0; 2025-08-30: 0
3 | Container Foundation Reinforcement | Nos | 40 | 16 | 24 | 40% | 16 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 4; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 4; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 8; 2025-08-29: 0; 2025-08-30: 0
4 | Container Foundation Shuttering | Nos | 40 | 16 | 24 | 40% | 16 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 4; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 4; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 8; 2025-08-30: 0
5 | Container Foundation Concrete Pouring | Nos | 40 | 12 | 28 | 30% | 12 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-13: 4; 2025-08-14: 0; 2025-08-15: 0; 2025-08-16: 0; 2025-08-17: 0; 2025-08-18: 0; 2025-08-19: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 4; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 0; 2025-08-30: 4
6 | Container Pedestal Reinforcement | Nos | 40 | 4 | 36 | 10% | 4 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 4; 2025-08-29: 0; 2025-08-30: 0
7 | Container Pedestal Shuttering | Nos | 40 | 4 | 36 | 10% | 4 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0; 2025-08-20: 0; 2025-08-21: 0; 2025-08-22: 0; 2025-08-23: 0; 2025-08-24: 0; 2025-08-25: 0; 2025-08-26: 0; 2025-08-27: 0; 2025-08-28: 0; 2025-08-29: 4; 2025-08-30: 0
8 | Container Pedestal Concrete Pouring | Nos | 40 | 0 | 40 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
9 | Container Tie Beam & Slab Reinforcement | Nos | 10 | 0 | 10 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
10 | Container Tie Beam & Slab Shuttering | Nos | 10 | 0 | 10 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
11 | Container Tie Beam & Slab Concrete Pouring | Nos | 10 | 0 | 10 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
12 | B/W of Container Plartform | Nos | 10 | 0 | 10 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
13 | Excavation of PCS foundation | Nos | 10 | 0 | 10 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
14 | PCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
15 | Reinforcement of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
16 | Shuttering of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
17 | RCC of PCS foundation | Nos | 40 | 0 | 40 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
18 | Reinforcement & Shuttering of PCS Pedestal | Nos | 40 | 0 | 40 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
19 | RCC of PCS Pedestal | Nos | 40 | 0 | 40 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
20 | Reinforcement & Shuttering of PCS Tie Beam | Nos | 10 | 0 | 10 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
21 | RCC of PCS Tie Beam | Nos | 10 | 0 | 10 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0
22 | B/W of PCS Plartform | Nos | 10 | 0 | 10 | 0% | 0 | 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0; 2025-08-01: 0; 2025-08-02: 0; 2025-08-03: 0; 2025-08-04: 0; 2025-08-05: 0; 2025-08-06: 0; 2025-08-07: 0; 2025-08-08: 0; 2025-08-09: 0; 2025-08-10: 0; 2025-08-11: 0; 2025-08-12: 0

## ICR Pilling
ICR NO. | Scope | Piling Progress | Progress in % | time axis 2025-05-30 to 2025-10-31
Total | 25992 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | 6498 | 0 | 0%
2 | 6498 | 0 | 0%
3 | 6498 | 0 | 0%
4 | 6498 | 0 | 0%
[9 empty] | 770 | 9240
[9 empty] | 2792 | 16752
25992
6498

## Cont Piling
S.no. | Contractor | Activity | Scope | Progress | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2024-11-01 | 2024-11-02 | 2024-11-03 | 2024-11-04 | 2024-11-05 | 2024-11-06 | 2024-11-07 | 2024-11-08 | 2024-11-09 | 2024-11-10 | 2024-11-11 | 2024-11-12 | 2024-11-13 | 2024-11-14 | 2024-11-15 | 2024-11-16 | 2024-11-17 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-21 | 2024-11-22 | 2024-11-23 | 2024-11-24 | 2024-11-25 | 2024-11-26 | 2024-11-27 | 2024-11-28 | 2024-11-29 | 2024-11-30 | 2024-12-01 | 2024-12-02 | 2024-12-03 | 2024-12-04 | 2024-12-05 | 2024-12-06 | 2024-12-07 | 2024-12-08 | 2024-12-09 | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23 | 2024-12-24 | 2024-12-25 | 2024-12-26 | 2024-12-27 | 2024-12-28 | 2024-12-29 | 2024-12-30 | 2024-12-31 | 2025-01-01 | 2025-01-02 | 2025-01-03 | 2025-01-04 | 2025-01-05 | 2025-01-06 | 2025-01-07 | 2025-01-08 | 2025-01-09 | 2025-01-10 | 2025-01-11 | 2025-01-12 | 2025-01-13 | 2025-01-14 | 2025-01-15 | 2025-01-16 | 2025-01-17 | 2025-01-18 | 2025-01-19 | 2025-01-20 | 2025-01-21 | 2025-01-22 | 2025-01-23 | 2025-01-24 | 2025-01-25 | 2025-01-26 | 2025-01-27 | 2025-01-28 | 2025-01-29 | 2025-01-30 | 2025-01-31 | 2025-02-01 | 2025-02-02 | 2025-02-03 | 2025-02-04 | 2025-02-05 | 2025-02-06 | 2025-02-07 | 2025-02-08 | 2025-02-09 | 2025-02-10 | 2025-02-11 | 2025-02-12 | 2025-02-13 | 2025-02-14 | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31
Block-01 | TBD | Marking | 6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Boring | 6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Casting | 6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capping | 6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block-02 | Yash Construction | Marking | 6498 | 2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2088
|  | Boring | 6498 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 100
|  | Casting | 6498 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0
|  | Capping | 6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block-03 | MST | Marking | 6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Boring | 6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Casting | 6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capping | 6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Block-04 | TBD | Marking | 6498 | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670
|  | Boring | 6498 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 211
|  | Casting | 6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Capping | 6498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Activity | Scope | Progress | Progress in %
| Marking | 25992 | 2758 | 10.61%
| Boring | 25992 | 811 | 3.12%
| Casting | 25992 | 12 | 0.04617%
| Capping | 25992 | 0 | 0%
0.034443

## SW Civil
Switchyard Equipment Progress
Sr. No. | Description | UOM | Weightage Scope | Weightage completion | Equipments | Foundation Scope (Nos) | Excavation |  |  |  | PCC |  |  |  | Raft Foundation |  |  |  | Column casting/J-bolt fixing
[7 empty] | Start Date | End Date | Progress | Percentage | Start Date | End Date | Progress | Percentage | Start Date | End Date | Progress | Percentage | Start Date | End Date | Progress | Percentage |  | Sr. No. | Description | Activity | Unit | Equipment | Foundation | Cummulative | Balance | time axis 2024-11-12 to 2025-05-14
1 | Tower Foundation | Nos | 15% | 0% | 14 | 14 |  |  | 0 | 0% | 1900-01-01 | 1900-01-26 | 0 | 0% | 1900-01-26 | 1900-02-15 | 0 | 0% | 1900-02-05 | 1900-02-25 | 0 | 0% | 0 | 1 | Tower Foundation | EXC | Nos | 14 | 14 | 0 | 14
2 | Power Transformer | Nos | 15% | 0% | 2 | 2 |  |  | 0 | 0% | 0 | 1900-01-05 | 0 | 0% | 1900-01-15 | 1900-01-25 | 0 | 0% | 1900-01-26 | 1900-02-20 | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 14
3 | LM Tower | Nos | 1% | 0% | 1 | 1 |  |  | 0 | 0% | 1899-12-31 | 1900-01-01 | 0 | 0% | 1900-02-16 | 1900-02-19 | 0 | 0% | 1900-02-21 | 1900-02-25 | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 14
4 | LA | Nos | 2% | 0% | 3 | 3 |  |  | 0 | 0% | 0 | 1899-12-31 | 0 | 0% | 1900-01-01 | 1900-01-03 | 0 | 0% | 1900-01-04 | 1900-01-08 | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 14
5 | HLA | Nos | 1% | 0% | 6 | 6 |  |  | 0 | 0% | 0 | 1899-12-31 | 0 | 0% | 1900-01-01 | 1900-01-02 | 0 | 0% | 1900-01-03 | 1900-01-06 | 0 | 0% | 0 | 2 | Power Transformer | EXC | Nos | 2 | 2 | 0 | 2
6 | CB | Nos | 4% | 0% | 12 | 12 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 2
7 | Wave Trap | Nos | 1% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 2
8 | LINE CVT | Nos | 2% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 2
9 | BUS CVT | Nos | 4% | 0% | 6 | 6 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 3 | LM Tower | EXC | Nos | 1 | 1 | 0 | 1
10 | MCVT | Nos | 1% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 1
11 | HCT | Nos | 4% | 0% | 12 | 12 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 1
12 | MCT | Nos | 1% | 0% | 3 | 3 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 1
13 | ISO with ES | Nos | 4% | 0% | 18 | 18 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 4 | LA | EXC | Nos | 3 | 3 | 0 | 3
14 | ISO | Nos | 8% | 0% | 42 | 42 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 3
15 | Isolator-T | Nos | 2% | 0% | 18 | 18 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 3
16 | HBPI | Nos | 3% | 0% | 6 | 6 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 3
17 | BPI | Nos | 8% | 0% | 17 | 17 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 5 | HLA | EXC | Nos | 6 | 6 | 0 | 6
18 | Aux Trafo | Nos | 1% | 0% | 2 | 2 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 6
19 | BMK | Nos | 2% | 0% | 4 | 4 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 6
20 | NIFPS | Nos | 2% | 0% | 2 | 2 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Column |  |  |  | 0 | 6
21 | BOT Oil Pit | Nos | 2% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 6 | CB | EXC | Nos | 12 | 12 | 0 | 12
22 | Cable Trench | mtr | 5% | 0% | 315 | 315 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | PCC |  |  |  | 0 | 12
23 | Rain Water Drain | Mtr | 0.5% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 |  |  | Raft |  |  |  | 0 | 12
24 | Fencing | Nos | 1% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% | [8 empty] | 0 |  |  | Column |  |  |  | 0 | 12
25 | Road | Ls | 6% | 0% | 0 | 1 |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% |  |  | 0 | 0% | 0 | 7 | Wave Trap | EXC | Nos | 3 | 3 | 0 | 3
26 | Gravel Filling | Ls | 4% | 0% | 0 | 1
Total |  |  | 99.5% | 0% | 152 | 152 | 0 | 0 | 0 | 0% | 0 | 1900-01-26 | 0 | 0% | 1900-01-01 | 1900-02-19 | 0 | 0% | 1900-01-03 | 1900-02-25 | 0 | 0% |  |  |  | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 8 | Line-CVT | EXC | Nos | 3 | 3 | 0 | 3
[26 empty] | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 9 | BUS CVT | EXC | Nos | 6 | 6 | 0 | 6
[26 empty] | PCC |  |  |  | 0 | 6
[26 empty] | Raft |  |  |  | 0 | 6
[26 empty] | Column |  |  |  | 0 | 6
[24 empty] | 10 | MCVT | EXC | Nos | 3 | 3 | 0 | 3
[26 empty] | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 11 | HCT | EXC | Nos | 12 | 12 | 0 | 12
[26 empty] | PCC |  |  |  | 0 | 12
[26 empty] | Raft |  |  |  | 0 | 12
[26 empty] | Column |  |  |  | 0 | 12
[24 empty] | 12 | MCT | EXC | Nos | 3 | 3 | 0 | 3
[26 empty] | PCC |  |  |  | 0 | 3
[26 empty] | Raft |  |  |  | 0 | 3
[26 empty] | Column |  |  |  | 0 | 3
[24 empty] | 13 | ISO with ES | EXC | Nos | 18 | 18 | 0 | 18
[26 empty] | PCC |  |  |  | 0 | 18
[26 empty] | Raft |  |  |  | 0 | 18
[26 empty] | Column |  |  |  | 0 | 18
[24 empty] | 14 | ISO | EXC | Nos | 42 | 42 | 0 | 42
[26 empty] | PCC |  |  |  | 0 | 42
[26 empty] | Raft |  |  |  | 0 | 42
[26 empty] | Column |  |  |  | 0 | 42
[24 empty] | 15 | ISO -T | EXC | Nos | 18 | 18 | 0 | 18
[26 empty] | PCC |  |  |  | 0 | 18
[26 empty] | Raft |  |  |  | 0 | 18
[26 empty] | Column |  |  |  | 0 | 18
[24 empty] | 16 | HBPI | EXC | Nos | 6 | 6 | 0 | 6
[26 empty] | PCC |  |  |  | 0 | 6
[26 empty] | Raft |  |  |  | 0 | 6
[26 empty] | Column |  |  |  | 0 | 6
[24 empty] | 17 | BPI | EXC | Nos | 17 | 17 | 0 | 17
[26 empty] | PCC |  |  |  | 0 | 17
[26 empty] | Raft |  |  |  | 0 | 17
[26 empty] | Column |  |  |  | 0 | 17
[24 empty] | 18 | Aux Trafo | EXC | Nos | 2 | 2 | 0 | 2
[26 empty] | PCC |  |  |  | 0 | 2
[26 empty] | Raft |  |  |  | 0 | 2
[26 empty] | Column |  |  |  | 0 | 2
[24 empty] | 19 | BMK | EXC | Nos | 4 | 4 | 0 | 4
[26 empty] | PCC |  |  |  | 0 | 4
[26 empty] | Raft |  |  |  | 0 | 4
[26 empty] | Column |  |  |  | 0 | 4
[24 empty] | 20 | NIFPS | EXC | Nos | 2 | 2 | 0 | 2
[26 empty] | PCC |  |  |  | 0 | 2
[26 empty] | Raft |  |  |  | 0 | 2
[26 empty] | Column |  |  |  | 0 | 2
[24 empty] | 21 | BOT Oil Pit | EXC | Nos | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Wall |  |  |  | 0 | 1
[24 empty] | 22 | Cable Trench | EXC | Mtr | 315 | 315 | 0 | 315
[26 empty] | PCC |  |  |  | 0 | 315
[26 empty] | Raft |  |  |  | 0 | 315
[26 empty] | Wall |  |  |  | 0 | 315
[24 empty] | 23 | Rain Water Drain | EXC | LS | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Column |  |  |  | 0 | 1
[24 empty] | 24 | Fencing | EXC | LS | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Column |  |  |  | 0 | 1
[24 empty] | 25 | Road | EXC | LS | 1 | 1 | 0 | 1
[26 empty] | PCC |  |  |  | 0 | 1
[26 empty] | Raft |  |  |  | 0 | 1
[26 empty] | Column |  |  |  | 0 | 1
[24 empty] | TOTAL |  |  |  | 496 | 496
Formulas:
PCC = [Excavation]+2
PCC = MIN(M4:[PCC, row above])
Raft Foundation = [PCC]+25
Column casting/J-bolt fixing = [Raft Foundation]+10
Excavation = MIN(I4:[Excavation, row above])

## SY ELE
Electrical Progress | [13 empty] | DAILY PROGRESS
Sr.no. | Description | UOM | Scope | Progress | Balance | % Progress | BaseLine Plan |  |  | Forecast |  |  | Remarks | Cummulative | time axis 2024-12-01 to 2025-05-31
[7 empty] | Start Date | Finish Date | Days | Start Date | Finish Date | Days
MCR | [5 empty] | 0% | 2024-03-11 | 2025-06-30 |  | 2024-03-11 | 2025-06-30
| Panel Installation | No's | 44 | 0 | 44 | 0% | 2024-03-11 | 2025-04-04 | 389 | 2024-03-11 | 2025-04-04 | 389
1 | 33KV HT & Bus Bar Panel | Set | 4 | 0 | 4 | 0% | 2025-03-20 | 2025-04-04 | 15 | 2025-03-20 | 2025-04-04 | 15 |  | 0
2 | C&R Panel | No's | 7 | 0 | 7 | 0% | 2024-03-11 | 2024-03-21 | 10 | 2024-03-11 | 2024-03-21 | 10 |  | 0
3 | Busbar Panel | No's | 1 | 0 | 1 | 0% | 2025-03-20 | 2025-03-22 | 2 | 2025-03-20 | 2025-03-22 | 2
4 | PPC | No's | 1 | 0 | 1 | 0% | 2024-03-13 | 2024-03-14 | 1 | 2024-03-13 | 2024-03-14 | 1 |  | 0
5 | MU PLC 2 | No's | 2 | 0 | 2 | 0% | 2024-03-15 | 2024-03-17 | 2 | 2024-03-15 | 2024-03-17 | 2 |  | 0
6 | Fote Panel | No's | 1 | 0 | 1 | 0% | 2024-03-18 | 2024-03-21 | 3 | 2024-03-18 | 2024-03-21 | 3 |  | 0
7 | CCTV Panel | No's | 1 | 0 | 1 | 0% | 2024-03-22 | 2024-03-24 | 2 | 2024-03-22 | 2024-03-24 | 2 |  | 0
8 | PLCC Panel | No's | 1 | 0 | 1 | 0% | 2024-03-25 | 2024-03-27 | 2 | 2024-03-25 | 2024-03-27 | 2 |  | 0
9 | RTCC Panel | No's | 2 | 0 | 2 | 0% | 2024-03-28 | 2024-03-30 | 2 | 2024-03-28 | 2024-03-30 | 2 |  | 0
10 | PLC/Scada | No's | 1 | 0 | 1 | 0% | 2024-03-31 | 2024-04-06 | 6 | 2024-03-31 | 2024-04-06 | 6
11 | SAS Panel | No's | 1 | 0 | 1 | 0% | 2024-03-31 | 2024-04-02 | 2 | 2024-03-31 | 2024-04-02 | 2 |  | 0
12 | ACDB | No's | 1 | 0 | 1 | 0% | 2024-04-03 | 2024-04-06 | 3 | 2024-04-03 | 2024-04-06 | 3 |  | 0
13 | Lighting DB | No's | 1 | 0 | 1 | 0% | 2024-04-07 | 2024-04-08 | 1 | 2024-04-07 | 2024-04-08 | 1 |  | 0
14 | ELDB | No's | 1 | 0 | 1 | 0% | 2024-04-08 | 2024-04-09 | 1 | 2024-04-08 | 2024-04-09 | 1
15 | UPS | No's | 2 | 0 | 2 | 0% | 2024-04-09 | 2024-04-14 | 5 | 2024-04-09 | 2024-04-14 | 5 |  | 0
16 | UPS DB | No's | 1 | 0 | 1 | 0% | 2024-04-10 | 2024-04-11 | 1 | 2024-04-10 | 2024-04-11 | 1 |  | 0
17 | UPS Battery | Set | 4 | 0 | 4 | 0% | 2024-04-11 | 2024-04-12 | 1 | 2024-04-11 | 2024-04-12 | 1
18 | Battery Charger & DCDB (220V) | No's | 2 | 0 | 2 | 0% | 2024-04-12 | 2024-04-14 | 2 | 2024-04-12 | 2024-04-14 | 2 |  | 0
19 | Battery Bank (220V) | No's | 2 | 0 | 2 | 0% | 2024-04-13 | 2024-04-17 | 4 | 2024-04-13 | 2024-04-17 | 4
20 | Battery Charger (48V) & DCDB | No's | 2 | 0 | 2 | 0% | 2024-04-14 | 2024-04-16 | 2 | 2024-04-14 | 2024-04-16 | 2 |  | 0
21 | Battery Bank (48V) | Set | 2 | 0 | 2 | 0% | 2024-04-15 | 2024-04-17 | 2 | 2024-04-15 | 2024-04-17 | 2 |  | 0
22 | NIFPS CP | No's | 2 | 0 | 2 | 0% | 2024-04-16 | 2024-04-17 | 1 | 2024-04-16 | 2024-04-17 | 1 |  | 0
23 | PC with Table | Lot | 1 | 0 | 1 | 0% | 2024-04-17 | 2024-04-19 | 2 | 2024-04-17 | 2024-04-19 | 2 |  | 0
24 | Illumination | Lot | 1 | 0 | 1 | 0% | 2024-04-18 | 2024-04-23 | 5 | 2024-04-18 | 2024-04-23 | 5 |  | 0
SW Electrical Works
| SW Earthing works |  | 3252.375 | 0 | 3252.375 | 0% | 2025-03-22 | 2025-04-27 | 36 | 2025-03-22 | 2025-05-21 | 60
1 | Excavation for Grid Earth Mat | Mtr | 7500 | 0 | 7500 | 0% | 2025-03-22 | 2025-03-28 | 6 | 2025-03-22 | 2025-04-09 | 18 |  | 0
2 | Grid Earthing- MS Rod (32mm) | Mtr | 7500 | 0 | 7500 | 0% | 2025-03-24 | 2025-04-01 | 8 | 2025-03-24 | 2025-04-13 | 20 |  | 0
3 | 75*12mm GI Flat for equiment earthing | Mtr | 2500 | 0 | 2500 | 0% | 2025-03-27 | 2025-04-04 | 8 | 2025-03-28 | 2025-04-12 | 15
4 | 50*6 mm GI Flat for equipment & fencing | Mtr | 900 | 0 | 900 | 0% | 2025-04-05 | 2025-04-20 | 15 | 2025-04-12 | 2025-04-16 | 4
5 | Aux Mat | Nos | 34 | 0 | 34 | 0% | 2025-04-02 | 2025-04-08 | 6 | 2025-04-19 | 2025-04-27 | 8 |  | 0
7 | Backfilling | Mtr | 7500 | 0 | 7500 | 0% | 2025-04-08 | 2025-04-23 | 15 | 2025-04-28 | 2025-05-04 | 6 |  | 0
6 | Earthing Ms Rod | Nos | 60 | 0 | 60 | 0% | 2025-04-07 | 2025-04-22 | 15 | 2025-05-05 | 2025-05-13 | 8 |  | 0
8 | Earthing Pipe GI | Nos | 25 | 0 | 25 | 0% | 2025-04-13 | 2025-04-27 | 14 | 2025-05-13 | 2025-05-21 | 8 |  | 0
| SW Structural |  | 97 | 0 | 97 | 0% | 2025-03-01 | 2025-05-03 | 63 | 2025-03-16 | 2025-04-07 | 22
1 | Tower (T-1,2,4,5) | Nos | 14 | 0 | 14 | 0% | 2025-03-01 | 2025-03-31 | 30 | 2025-03-16 | 2025-04-01 | 16 |  | 0
2 | LM Tower | Nos | 1 | 0 | 1 | 0% | 2025-04-12 | 2025-04-15 | 3 | 2025-03-16 | 2025-04-01 | 16 |  | 0
3 | HLA | Nos | 6 | 0 | 6 | 0% | 2025-04-12 | 2025-04-19 | 7 | 2025-03-27 | 2025-03-27 | 0 |  | 0
4 | HL-BPI | Nos | 6 | 0 | 6 | 0% | 2025-04-16 | 2025-04-18 | 2 | 2025-03-28 | 2025-03-28 | 0 |  | 0
5 | CT | Nos | 12 | 0 | 12 | 0% | 2025-04-01 | 2025-04-11 | 10 | 2025-03-29 | 2025-03-29 | 0 |  | 0
6 | CB | Set | 4 | 0 | 4 | 0% | 2025-04-12 | 2025-04-17 | 5 | 2025-03-30 | 2025-03-30 | 0 |  | 0
7 | BPI | Nos | 17 | 0 | 17 | 0% | 2025-04-18 | 2025-04-23 | 5 | 2025-03-31 | 2025-03-31 | 0 |  | 0
8 | CVT | Nos | 9 | 0 | 9 | 0% | 2025-04-12 | 2025-04-15 | 3 | 2025-04-01 | 2025-04-01 | 0 |  | 0
9 | 3-Ph HDB Motorized Isolator with Single motorized ES ( 3-PH) | Set | 5 | 0 | 5 | 0% | 2025-04-16 | 2025-04-20 | 4 | 2025-04-02 | 2025-04-02 | 0
10 | 3-Ph HDB Motorized Isolator with Double motorized ES (3-Ph) | Set | 5 | 0 | 5 | 0% | 2025-04-21 | 2025-04-25 | 4 | 2025-04-03 | 2025-04-03 | 0
11 | 3-Ph HDB motorized tandem Isolator | Set | 3 | 0 | 3 | 0% | 2025-04-26 | 2025-04-28 | 2 | 2025-04-04 | 2025-04-04 | 0 |  | 0
12 | MCT | NOs | 3 | 0 | 3 | 0% | 2025-04-29 | 2025-05-01 | 2 | 2025-04-05 | 2025-04-05 | 0
13 | MCVT | NOs | 3 | 0 | 3 | 0% | 2025-05-02 | 2025-05-03 | 1 | 2025-04-06 | 2025-04-06 | 0
14 | Wave Trap | Nos | 2 | 0 | 2 | 0% | 2025-04-12 | 2025-04-15 | 3 | 2025-04-07 | 2025-04-07 | 0 |  | 0
15 | LA | Nos | 3 | 0 | 3 | 0% | 2025-04-16 | 2025-04-19 | 3 | 2025-04-07 | 2025-04-07 | 0 |  | 0
16 | NIFPS Panel, piping with Support structure | Lot | 2 | 0 | 2 | 0% | 2025-04-20 | 2025-04-23 | 3 | 2025-04-04 | 2025-04-04 | 0 |  | 0
17 | Clamp & Connector | Lot | 1 | 0 | 1 | 0% | 2025-04-24 | 2025-04-29 | 5 | 2025-04-07 | 2025-04-07 | 0 |  | 0
18 | Spacers fixing | Lot | 1 | 0 | 1 | 0% | 2025-04-27 | 2025-05-02 | 5 | 2025-04-07 | 2025-04-07 | 0
| Equipment Errection |  | 97 | 0 | 97 | 0% | 2025-01-15 | 2025-05-31 | 136 | 2025-03-10 | 2025-04-26 | 47
1 | Power Transformer | Nos | 2 | 0 | 2 | 0% | 2025-01-15 | 2025-01-30 | 15 | 2025-03-10 | 2025-03-12 | 2 |  | 0
2 | HLA along with Accessories | Nos | 6 | 0 | 6 | 0% | 2025-04-19 | 2025-04-29 | 10 | 2025-04-01 | 2025-04-02 | 1 |  | 0
3 | HL-BPI | Nos | 6 | 0 | 6 | 0% | 2025-04-18 | 2025-04-22 | 4 | 2025-04-02 | 2025-04-03 | 1 |  | 0
4 | CT | Nos | 12 | 0 | 12 | 0% | 2025-04-11 | 2025-04-21 | 10 | 2025-04-03 | 2025-04-05 | 2 |  | 0
5 | CB (3-PH) | Set | 4 | 0 | 4 | 0% | 2025-04-17 | 2025-04-25 | 8 | 2025-04-05 | 2025-04-06 | 1 |  | 0
6 | BPI | Nos | 17 | 0 | 17 | 0% | 2025-04-26 | 2025-05-11 | 15 | 2025-04-06 | 2025-04-08 | 2 |  | 0
7 | CVT | Nos | 9 | 0 | 9 | 0% | 2025-04-15 | 2025-04-23 | 8 | 2025-04-08 | 2025-04-09 | 1 |  | 0
8 | 3-Ph HDB Motorized Isolator with Single motorized ES ( 3-PH) | Set | 5 | 0 | 5 | 0% | 2025-04-20 | 2025-05-05 | 15 | 2025-04-09 | 2025-04-11 | 2 |  | 0
9 | 3-Ph HDB Motorized Isolator with Double motorized ES (3-Ph) | Set | 5 | 0 | 5 | 0% | 2025-04-23 | 2025-05-08 | 15 | 2025-04-11 | 2025-04-14 | 3 |  | 0
10 | 3-Ph HDB motorized tandem Isolator | Set | 3 | 0 | 3 | 0% | 2025-04-24 | 2025-05-04 | 10 | 2025-04-14 | 2025-04-16 | 2 |  | 0
11 | MCT | Nos | 3 | 0 | 2 | 0% | 2025-05-01 | 2025-05-03 | 2 | 2025-04-16 | 2025-04-17 | 1 |  | 0
12 | MCVT | Nos | 3 | 0 | 3 | 0% | 2025-05-04 | 2025-05-08 | 4 | 2025-04-17 | 2025-04-18 | 1 |  | 0
13 | Wave Trap | Nos | 2 | 0 | 2 | 0% | 2025-04-16 | 2025-04-20 | 4 | 2025-04-18 | 2025-04-19 | 1 |  | 0
14 | LA | Nos | 3 | 0 | 3 | 0% | 2025-04-24 | 2025-04-28 | 4 | 2025-04-19 | 2025-04-21 | 2 |  | 0
15 | Aux Traffo | Nos | 2 | 0 | 2 | 0% | 2025-03-02 | 2025-03-04 | 2 | 2025-04-10 | 2025-04-15 | 5 |  | 0
16 | BMK | Nos | 4 | 0 | 4 | 0% | 2025-04-30 | 2025-05-04 | 4 | 2025-04-20 | 2025-04-26 | 6 |  | 0
17 | CT JB | Nos | 4 | 0 | 4 | 0% | 2025-05-06 | 2025-05-08 | 2 | 2025-04-20 | 2025-04-26 | 6 |  | 0
18 | CVT JB | Nos | 3 | 0 | 3 | 0% | 2025-05-09 | 2025-05-11 | 2 | 2025-04-20 | 2025-04-26 | 6 |  | 0
20 | Capacitor Bank ( SVG) | Lot | 2 | 0 | 2 | 0% | 2025-05-11 | 2025-05-19 | 8 | 2025-04-20 | 2025-04-26 | 6 |  | 0
21 | Metering Cubical | Nos | 1 | 0 | 1 | 0% | 2025-05-27 | 2025-05-31 | 4 | 2025-04-20 | 2025-04-26 | 6 |  | 0
22 | Yard illumination along with Accessories | Lot | 1 | 0 | 1 | 0% | 2025-05-15 | 2025-05-23 | 8 | 2025-04-20 | 2025-04-26 | 6 |  | 0
| Stringing, IPS Tubing & Cable tray |  | 1 | 0 | 1 | 0% | 2025-02-01 | 2025-05-28 | 116 | 2025-04-27 | 2025-05-13 | 16 |  | 0
1 | Clamp & connector | Lot | 1 | 0 | 1 | 0% | 2025-04-28 | 2025-05-13 | 15 | 2025-04-28 | 2025-05-02 | 4 |  | 0
2 | 4" IPS Al Tube installation | Lot | 1 | 0 | 1 | 0% | 2025-05-27 | 2025-05-28 | 1 | 2025-05-03 | 2025-05-05 | 2 |  | 0
3 | TWIN AL-59 Moose conductor ( Jumper) | Lot | 1 | 0 | 1 | 0% | 2025-04-28 | 2025-05-03 | 5 | 2025-05-06 | 2025-05-08 | 2 |  | 0
4 | Spacers | Lot | 1 | 0 | 1 | 0% | 2025-02-01 | 2025-03-01 | 28 | 2025-05-09 | 2025-05-11 | 2 |  | 0
5 | Sheild wire Support Cleat with tower | Lot | 1 | 0 | 1 | 0% | 2025-05-04 | 2025-05-08 | 4 | 2025-05-12 | 2025-05-13 | 1 |  | 0
6 | HDPE Pipe laying in switchyard | Lot | 1 | 0 | 1 | 0% | 2025-03-01 | 2025-03-08 | 7 | 2025-04-27 | 2025-04-30 | 3 |  | 0
7 | Cable Tray installation with support in switchyard | Lot | 1 | 0 | 1 | 0% | 2025-03-09 | 2025-03-16 | 7 | 2025-05-01 | 2025-05-05 | 4 |  | 0
8 | Cable Tray installation with support in MCR | Lot | 1 | 0 | 1 | 0% | 2025-03-01 | 2025-03-06 | 5 | 2025-05-06 | 2025-05-10 | 4 |  | 0
| SW cable laying & Termination |  | 1 | 0 | 1 | 0% | 2025-02-07 | 2025-05-22 | 104 | 2025-05-02 | 2025-05-17 | 15 |  | 0
1 | 33KV HT Cable laying ( Outgoing HT Switchgear to PTR) | Lot | 1 | 0 | 1 | 0% | 2025-02-07 | 2025-02-17 | 10 | 2025-05-02 | 2025-05-06 | 10 |  | 0
2 | LT Power cable Laying | Lot | 1 | 0 | 1 | 0% | 2025-02-25 | 2025-03-12 | 15 | 2025-05-04 | 2025-05-08 | 15 |  | 0
3 | Control cable laying | Lot | 1 | 0 | 1 | 0% | 2025-03-15 | 2025-03-25 | 10 | 2025-05-05 | 2025-05-09 | 10 |  | 0
4 | Communication cable laying | Lot | 1 | 0 | 1 | 0% | 2025-04-04 | 2025-04-09 | 5 | 2025-05-05 | 2025-05-09 | 5 |  | 0
5 | Glanding | Lot | 1 | 0 | 1 | 0% | 2025-04-29 | 2025-05-04 | 5 | 2025-05-09 | 2025-05-13 | 5 |  | 0
6 | Termination | Lot | 1 | 0 | 1 | 0% | 2025-05-12 | 2025-05-22 | 10 | 2025-05-13 | 2025-05-17 | 10 |  | 0
| Earthing |  | 52 | 0 | 52 | 0% | 2025-03-02 | 2025-04-02 | 31 | 2025-04-10 | 2025-04-26 | 16 |  | 0
1 | Drilling | Nos | 52 | 0 | 52 | 0% | 2025-03-02 | 2025-03-27 | 25 | 2025-04-10 | 2025-04-18 | 8 |  | 0
2 | Rod installtion | Nos | 52 | 0 | 52 | 0% | 2025-03-07 | 2025-04-01 | 25 | 2025-04-14 | 2025-04-22 | 8 |  | 0
3 | Pit Connection | Nos | 52 | 0 | 52 | 0% | 2025-03-08 | 2025-04-02 | 25 | 2025-04-22 | 2025-04-26 | 4 |  | 0
| Commissioning |  | 1 | 0 | 1 | 0% | 2025-04-04 | 2025-06-30 | 87 | 2025-04-27 | 2025-06-30 | 64 |  | 0
1 | Switchyard equipment Testing | Lot | 1 | 0 | 1 | 0% | 2025-05-25 | 2025-06-14 | 20 | 2025-04-27 | 2025-05-01 | 4 |  | 0
2 | MCR Equipment Testing | Lot | 1 | 0 | 1 | 0% | 2025-04-04 | 2025-04-29 | 25 | 2025-05-01 | 2025-05-09 | 8 |  | 0
3 | Schematic digram and green lining of all equipment and panel | Lot | 1 | 0 | 1 | 0% | 2025-06-02 | 2025-06-10 | 8 | 2025-05-09 | 2025-05-17 | 8 |  | 0
4 | Relay testing | Lot | 1 | 0 | 1 | 0% | 2025-06-10 | 2025-06-18 | 8 | 2025-05-10 | 2025-06-04 | 25 |  | 0
5 | Stability test | Lot | 1 | 0 | 1 | 0% | 2025-06-14 | 2025-06-22 | 8 | 2025-05-10 | 2025-06-04 | 25 |  | 0
6 | Final cleaning of all equipment & boxup | Lot | 1 | 0 | 1 | 0% | 2025-06-21 | 2025-06-23 | 2 | 2025-05-10 | 2025-06-04 | 25 |  | 0
7 | Equipment tesiling work ( Nomenclature) | Lot | 1 | 0 | 1 | 0% | 2025-05-27 | 2025-06-04 | 8 | 2025-05-27 | 2025-06-04 | 8 |  | 0
8 | Saftey Items Installation | Lot | 1 | 0 | 1 | 0% | 2025-05-25 | 2025-06-02 | 8 | 2025-05-25 | 2025-06-02 | 8 |  | 0
9 | CEIG visit | Lot | 1 | 0 | 1 | 0% | 2025-06-03 | 2025-06-05 | 2 | 2025-06-03 | 2025-06-05 | 2 |  | 0
10 | Phase sequence meter Configuration | Lot | 1 | 0 | 1 | 0% | 2025-06-22 | 2025-06-25 | 3 | 2025-06-22 | 2025-06-25 | 3 |  | 0
11 | Scada Commissioning | Lot | 1 | 0 | 1 | 0% | 2025-06-26 | 2025-06-28 | 2 | 2025-06-26 | 2025-06-28 | 2 |  | 0
12 | Final Commissioning | Lot | 1 | 0 | 1 | 0% | 2025-06-29 | 2025-06-30 | 1 | 2025-06-29 | 2025-06-30 | 1 |  | 0
Formulas:
Start Date = MIN([Start Date, row below],I32,I41,I60,I82,I91,I98,I102)
Start Date = MIN([Start Date, row below]:I30)
Finish Date = MAX([Finish Date, row below],J32,J41,J60,J82,J91,J98,J102)
Finish Date = MAX([Finish Date, row below]:J30)

## AC Progress
S.No. | AC Work | UOM | Total | [5 empty] | Base Line Plan |  |  | Forecast
Cumulative
|  |  | Scope | Waitage | Today | Cum. | Balance | % | Start Date | Finish Date | Days | Start Date | Finish Date | Days
1 | AC Trench | Mtr | 26043.8846 | 12% | 0 | 0 | 26043.8846 | 0% |  |  | 0 |  |  | 0
2 | 3CX240sqmm Cable Laying | Mtr | 18269.2308 | 3% | 0 | 0 | 18269.2308 | 0% |  |  | 0 |  |  | 0
3 | 3CX400sqmm Cable Laying | Mtr | 58461.5385 | 7% | 0 | 0 | 58461.5385 | 0% |  |  | 0 |  |  | 107
4 | 1CX400sqmm Cable Laying | LS | 38 | 10% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
5 | OFC Cable Laying | LS | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
6 | Grid Earthing | mtr | 7600 | 8% | 0 | 0 | 7600 | 0% |  |  | 0 |  |  | 0
7 | Tray support casting | No's | 38 | 0% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
8 | Tray from INV to LV Side | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
9 | Earthpit Installation | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
10 | IDT Erection | No's | 38 | 15% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
11 | ICOG Panel | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
12 | LT Panel | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
13 | UPS Panel | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
14 | Aux Trafo | No's | 38 | 5% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
15 | 1C*400Sqmm cable Termination | Sets | 38 | 10% | 0 | 0 | 38 | 0% |  |  | 0 |  |  | 0
|  |  |  | 100% |  |  |  | 0%
Description |  |  | AC Trench |  |  |  |  | 3CX240sqmm Cable Laying |  |  |  |  | 1CX400sqmm Cable Laying |  |  |  |  | 3CX400sqmm Cable Laying |  |  |  |  | OFC Cable Laying |  |  |  |  | Grid Earthing |  |  |  |  | Tray support casting |  |  |  |  | Tray from INV to LV Side |  |  |  |  | Earthpit Installation |  |  |  |  | IDT Erection |  |  |  |  | ICOG Panel |  |  |  |  | LT Panel |  |  |  |  | UPS Panel |  |  |  |  | Aux Trafo |  |  |  |  | 1C*400Sqmm cable Termination
Sr. No. | Contractor Name | ICR No. | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | %
| Total |  | 26043.8846 | 0 | 0 | 0 | 0% | 18269.2308 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 58461.5385 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 7600 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 34 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0% | 38 | 0 | 0 | 0 | 0%
1 |  | Icr-a |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
2 |  | Icr-b |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
3 |  | Icr-c |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
4 |  | Icr-e |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  | 0 | 1 | #DIV/0! |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
5 |  | Icr-5 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
6 |  | Icr-6 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
7 |  | Icr-7 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
8 |  | Icr-8 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
9 |  | Icr-9 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
10 |  | Icr-10 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
11 |  | Icr-11 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
12 |  | Icr-12 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
13 |  | Icr-13 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
14 |  | Icr-14 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
15 |  | Icr-15 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
16 |  | Icr-16 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
17 |  | Icr-17 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
18 |  | Icr-18 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
19 |  | Icr-19 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
20 |  | Icr-20 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
21 |  | Icr-21 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
22 |  | Icr-22 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
23 |  | Icr-23 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
24 |  | Icr-24 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
25 |  | Icr-25 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
26 |  | Icr-26 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
27 |  | Icr-27 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
28 |  | Icr-28 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
29 |  | Icr-29 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
30 |  | Icr-30 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
31 |  | Icr-31 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
32 |  | Icr-32 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
33 |  | Icr-33 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0
34 |  | Icr-34 |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  | 1 |  |  | 1 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0

## DC Progress
S.No. | DC Work | UOM | Total |  |  |  |  | Base Line Plan |  |  | Forecast
|  |  | Scope | Today | Cum. | Balance | % | Start Date | Finish Date | Days | Start Date | Finish Date | Days
1 | Trench Excavation | Mtr | 171000 | 250 | 950 | 170050 | 0.5556% |  |  | 0 |  |  | 0
2 | 400Sqmm Cable laying (SCB's) | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
3 | Inverter Installation | No's | 76 | 0 | 0 | 76 | 0% |  |  | 0 |  |  | 0
4 | 400 Sqmm cable laying | mtr | 638400 | 0 | 0 | 638400 | 0% |  |  | 0 |  |  | 0
5 | SCB Stand Casting | No's | 3648 | 0 | 0 | 3648 | 0% |  |  | 0 |  |  | 0
6 | SCB Installation | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
7 | 6 Sqmm Laying(SCB's) | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
8 | Termination SCB End | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
9 | Termination Inv End | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
10 | Earthing Conductor Laying | Mtr | 95000 | 0 | 0 | 95000 | 0% |  |  | 0 |  |  | 0
11 | Earthpit Installation | No's | 912 | 0 | 0 | 912 | 0% |  |  | 0 |  |  | 0
12 | String Cable termination | No's | 1824 | 0 | 0 | 1824 | 0% |  |  | 0 |  |  | 0
13 | LA Installation | No's | 190 | 0 | 0 | 190 | 0% |  |  | 0 |  |  | 0
14 | LA Connection | No's | 190 | 0 | 0 | 190 | 0% |  |  | 0 |  |  | 0
15 | MMS Installation(Full+Half+Dummy) | No's | 14592 | 0 | 0 | 14592 | 0% |  |  | 0 |  |  | 0
16 | Module Mounting | No's | 846336 | 0 | 0 | 846336 | 0% |  |  | 0 |  |  | 0
0.03472%
Description |  |  | Trench Excavation |  |  |  |  | 400Sqmm Cable laying (SCB's) |  |  |  |  | Inverter Installation |  |  |  |  | SCB Stand Casting |  |  |  |  | SCB Installation |  |  |  |  | 6 Sqmm Laying(SCB's) |  |  |  |  | Termination SCB End |  |  |  |  | 400 Sqmm cable laying |  |  |  |  | Termination Inv End |  |  |  |  | Earthing Conductor Laying |  |  |  |  | Earthpit Installation |  |  |  |  | String Cable termination |  |  |  |  | LA Installation |  |  |  |  | LA Connection |  |  |  |  | MMS Installation(Full+Half+Dummy) |  |  |  |  | Module Mounting
Sr. No. | Contractor Name | ICR No. | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | % | Scope | Today | Cum | Diff | %
| Total |  | 171000 | 250 | 950 | 3550 | 0.5556% | 1824 | 0 | 0 | 0 | 0% | 76 | 0 | 0 | 0 | 0% | 3648 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 638400 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 95000 | 0 | 0 | 0 | 0% | 912 | 0 | 0 | 0 | 0% | 1824 | 0 | 0 | 0 | 0% | 190 | 0 | 0 | 0 | 0% | 190 | 0 | 0 | 0 | 0% | 14592 | 0 | 0 | 0 | 0% | 846336 | 0 | 0 | 0 | 0%
1 |  | Icr-1
B | Shree Krishna Enterprises | Icr-2 | 4500 | 250 | 950 | 3550 | 21.11%
3 |  | Icr-3
4 |  | Icr-4
5 |  | Icr-5
6 |  | Icr-6
7 |  | Icr-7
8 |  | Icr-8
9 |  | Icr-9
10 |  | Icr-10
11 |  | Icr-11
12 |  | Icr-12
13 |  | Icr-13
14 |  | Icr-14
15 |  | Icr-15
16 |  | Icr-16
17 |  | Icr-17
18 |  | Icr-18
19 |  | Icr-19
20 |  | Icr-20
21 |  | Icr-21
22 |  | Icr-22
23 |  | Icr-23
24 |  | Icr-24
25 |  | Icr-25
26 |  | Icr-26
27 |  | Icr-27
28 |  | Icr-28
29 |  | Icr-29
30 |  | Icr-30
31 |  | Icr-31
32 |  | Icr-32
33 |  | Icr-33
34 |  | Icr-34

## Daily tracker Work
S.No. | Activity | Work Description | UOM | Scope | Progress | Balance | % Progress | time axis 2025-04-01 to 2025-09-29
1 | DC WORK | Trench Excavation | Mtr | 171000 | 0 | 171000 | 0%
2 |  | 400Sqmm Cable laying (SCB's) | No's | 1824 | 0 | 1824 | 0%
3 |  | Inverter Installation | No's | 76 | 0 | 76 | 0%
4 |  | SCB Stand Casting | No's | 3648 | 0 | 3648 | 0%
5 |  | 400 Sqmm cable laying | mtr | 856800 | 0 | 856800 | 0%
6 |  | SCB Installation | No's | 1824 | 0 | 1824 | 0%
7 |  | 6 Sqmm Laying(SCB's) | No's | 1824 | 0 | 1824 | 0%
8 |  | Termination SCB End | No's | 1824 | 0 | 1824 | 0%
9 |  | Termination Inv End | No's | 1824 | 0 | 1824 | 0%
10 |  | Earthing Conductor Laying | Mtr | 95000 | 0 | 95000 | 0%
11 |  | Earthpit Installation | No's | 912 | 0 | 912 | 0%
12 |  | String Cable termination | No's | 1824 | 0 | 1824 | 0%
13 |  | LA Installation | No's | 190 | 0 | 190 | 0%
14 |  | LA Connection | No's | 190 | 0 | 190 | 0%
15 |  | MMS Installtion(Full+Half) | No's | 14592 | 0 | 14592 | 0%
16 |  | Module Mounting | No's | 846336 | 0 | 846336 | 0%
17 | AC Work | AC Trench Excavation | Mtr | 26043.8846 | 0 | 26043.8846 | 0%
18 |  | 3CX400/240sqmm Cable Laying | Mtr | 18269.2308 | 0 | 18269.2308 | 0%
19 |  | OFC Cable Laying | Mtr | 38 | 0 | 38 | 0%
20 |  | Grid Earthing | mtr | 10400 | 0 | 10400 | 0%
21 |  | Earthing Conductor Laying | Mtr | 38 | 0 | 38 | 0%
22 |  | Tray Support Casting | No's | 52 | 0 | 52 | 0%
23 |  | Tray from INV to LV Side | No's | 7600 | 0 | 7600 | 0%
24 |  | Earthpit Installation | No's | 38 | 0 | 38 | 0%
25 |  | IDT Erection | No's | 38 | 0 | 38 | 0%
26 |  | ICOG Panel | No's | 38 | 0 | 38 | 0%
27 |  | LT Panel | No's | 38 | 0 | 38 | 0%
28 |  | UPS & UPS DB | No's | 38 | 0 | 38 | 0%
29 |  | AUX Trafo | No's | 38 | 0 | 38 | 0%
30 |  | NIFPS panel installation | No's | 38 | 0 | 38 | 0%
31 |  | Termination | No's | 38 | 0 | 38 | 0%

## Bottleneck
Bottleneck
Engineering {E} | Procurement {P} | Construction {C}

## QC & HSE status
QC Status | [6 empty] | HSE Status
Department | Total FF | Closed | Open | Total NC | Closed | Open
Construction | 0 | 0 | 0 | 0 | 0 | 0
Engineering | 0 | 0 | 0 | 0 | 0 | 0
Procurement | 0 | 0 | 0 | 0 | 0 | 0
97648

## Resources Status (hidden)
Sr. No. | Vendor name | Entity | Category | time axis 2024-11-25 to 2025-08-25
Manpower | Total |  | 97648 | 6 | 6 | 8 | 9 | 12 | 12 | 15 | 17 | 19 | 19 | 17 | 25 | 25 | 25 | 33 | 32 | 33 | 43 | 43 | 37 | 35 | 50 | 54 | 52 | 51 | 55 | 58 | 48 | 63 | 75 | 69 | 69 | 68 | 70 | 66 | 64 | 67 | 24 | 74 | 75 | 75 | 75 | 66 | 74 | 80 | 80 | 83 | 84 | 82 | 73 | 77 | 78 | 75 | 81 | 90 | 89 | 94 | 91 | 92 | 92 | 111 | 104 | 87 | 101 | 101 | 91 | 96 | 93 | 108 | 115 | 118 | 104 | 121 | 122 | 136 | 133 | 137 | 132 | 140 | 137 | 112 | 113 | 120 | 120 | 120 | 120 | 119 | 120 | 134 | 134 | 93 | 103 | 118 | 131 | 129 | 125 | 131 | 130 | 133 | 128 | 127 | 127 | 130 | 130 | 130 | 111 | 95 | 101 | 57 | 14 | 71 | 77 | 83 | 95 | 116 | 121 | 120 | 120 | 134 | 138 | 144 | 145 | 134 | 132 | 96 | 108 | 86 | 122 | 123 | 136 | 136 | 116 | 123 | 135 | 140 | 124 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | O2 Power |  | Staff | 2024-11-25: 3; 2024-11-26: 3; 2024-11-27: 5; 2024-11-28: 6; 2024-11-29: 7; 2024-11-30: 7; 2024-12-01: 7; 2024-12-02: 7; 2024-12-03: 7; 2024-12-04: 7; 2024-12-05: 7; 2024-12-06: 7; 2024-12-07: 7; 2024-12-08: 7; 2024-12-09: 7; 2024-12-10: 7; 2024-12-11: 8; 2024-12-12: 8; 2024-12-13: 8; 2024-12-14: 8; 2024-12-15: 8; 2024-12-16: 13; 2024-12-17: 13; 2024-12-18: 13; 2024-12-19: 13; 2024-12-20: 13; 2024-12-21: 13; 2024-12-22: 11; 2024-12-23: 11; 2024-12-24: 14; 2024-12-25: 14; 2024-12-26: 14; 2024-12-27: 14; 2024-12-28: 14; 2024-12-29: 14; 2024-12-30: 13; 2024-12-31: 13; 2025-01-01: 13; 2025-01-02: 13; 2025-01-03: 13; 2025-01-04: 13; 2025-01-05: 13; 2025-01-06: 13; 2025-01-07: 10; 2025-01-08: 10; 2025-01-09: 10; 2025-01-10: 10; 2025-01-11: 11; 2025-01-12: 11; 2025-01-13: 11; 2025-01-14: 11; 2025-01-15: 11; 2025-01-16: 11; 2025-01-17: 11; 2025-01-18: 11; 2025-01-19: 11; 2025-01-20: 12; 2025-01-21: 12; 2025-01-22: 12; 2025-01-23: 12; 2025-01-24: 12; 2025-01-25: 12; 2025-01-26: 12; 2025-01-27: 12; 2025-01-28: 12; 2025-01-29: 12; 2025-01-30: 12; 2025-01-31: 13; 2025-02-01: 13; 2025-02-02: 13; 2025-02-03: 13; 2025-02-04: 15; 2025-02-05: 17; 2025-02-06: 17; 2025-02-07: 17; 2025-02-08: 17; 2025-02-09: 17; 2025-02-10: 17; 2025-02-11: 17; 2025-02-12: 17; 2025-02-13: 17; 2025-02-14: 17; 2025-02-15: 17; 2025-02-16: 17; 2025-02-17: 17; 2025-02-18: 17; 2025-02-19: 17; 2025-02-20: 17; 2025-02-21: 17; 2025-02-22: 17; 2025-02-23: 17; 2025-02-24: 17; 2025-02-25: 17; 2025-02-26: 17; 2025-02-27: 17; 2025-02-28: 17; 2025-03-01: 17; 2025-03-02: 17; 2025-03-03: 17; 2025-03-04: 17; 2025-03-05: 17; 2025-03-06: 17; 2025-03-07: 17; 2025-03-08: 17; 2025-03-09: 17; 2025-03-10: 18; 2025-03-11: 18; 2025-03-12: 18; 2025-03-13: 18; 2025-03-14: 0; 2025-03-15: 25; 2025-03-16: 25; 2025-03-17: 25; 2025-03-18: 25; 2025-03-19: 25; 2025-03-20: 25; 2025-03-21: 25; 2025-03-22: 25; 2025-03-23: 25; 2025-03-24: 25; 2025-03-25: 25; 2025-03-26: 25; 2025-03-27: 25; 2025-03-28: 25; 2025-03-29: 25; 2025-03-30: 25; 2025-03-31: 25; 2025-04-01: 25; 2025-04-02: 25; 2025-04-03: 25; 2025-04-04: 25; 2025-04-05: 25; 2025-04-06: 25; 2025-04-07: 25; 2025-04-08: 25; 2025-04-09: 25; 2025-04-10: 25
|  |  | Surveyor | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 2; 2024-12-04: 2; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Security | 2024-11-25: 2; 2024-11-26: 2; 2024-11-27: 2; 2024-11-28: 2; 2024-11-29: 2; 2024-11-30: 2; 2024-12-01: 2; 2024-12-02: 2; 2024-12-03: 2; 2024-12-04: 2; 2024-12-05: 2; 2024-12-06: 2; 2024-12-07: 2; 2024-12-08: 2; 2024-12-09: 2; 2024-12-10: 2; 2024-12-11: 2; 2024-12-12: 2; 2024-12-13: 2; 2024-12-14: 2; 2024-12-15: 2; 2024-12-16: 4; 2024-12-17: 4; 2024-12-18: 4; 2024-12-19: 4; 2024-12-20: 4; 2024-12-21: 4; 2024-12-22: 4; 2024-12-23: 4; 2024-12-24: 11; 2024-12-25: 11; 2024-12-26: 11; 2024-12-27: 11; 2024-12-28: 11; 2024-12-29: 11; 2024-12-30: 11; 2024-12-31: 11; 2025-01-01: 11; 2025-01-02: 11; 2025-01-03: 11; 2025-01-04: 11; 2025-01-05: 11; 2025-01-06: 11; 2025-01-07: 11; 2025-01-08: 12; 2025-01-09: 12; 2025-01-10: 12; 2025-01-11: 12; 2025-01-12: 12; 2025-01-13: 12; 2025-01-14: 12; 2025-01-15: 12; 2025-01-16: 12; 2025-01-17: 12; 2025-01-18: 12; 2025-01-19: 12; 2025-01-20: 12; 2025-01-21: 15; 2025-01-22: 15; 2025-01-23: 15; 2025-01-24: 15; 2025-01-25: 15; 2025-01-26: 15; 2025-01-27: 15; 2025-01-28: 15; 2025-01-29: 15; 2025-01-30: 15; 2025-01-31: 15; 2025-02-01: 15; 2025-02-02: 15; 2025-02-03: 15; 2025-02-04: 15; 2025-02-05: 15; 2025-02-06: 15; 2025-02-07: 15; 2025-02-08: 15; 2025-02-09: 15; 2025-02-10: 15; 2025-02-11: 15; 2025-02-12: 15; 2025-02-13: 15; 2025-02-14: 15; 2025-02-15: 15; 2025-02-16: 15; 2025-02-17: 15; 2025-02-18: 15; 2025-02-19: 15; 2025-02-20: 14; 2025-02-21: 14; 2025-02-22: 14; 2025-02-23: 14; 2025-02-24: 14; 2025-02-25: 14; 2025-02-26: 14; 2025-02-27: 14; 2025-02-28: 14; 2025-03-01: 14; 2025-03-02: 14; 2025-03-03: 14; 2025-03-04: 14; 2025-03-05: 14; 2025-03-06: 14; 2025-03-07: 14; 2025-03-08: 14; 2025-03-09: 14; 2025-03-10: 14; 2025-03-11: 14; 2025-03-12: 14; 2025-03-13: 14; 2025-03-14: 14; 2025-03-15: 14; 2025-03-16: 14; 2025-03-17: 18; 2025-03-18: 18; 2025-03-19: 18; 2025-03-20: 18; 2025-03-21: 18; 2025-03-22: 18; 2025-03-23: 18; 2025-03-24: 18; 2025-03-25: 18; 2025-03-26: 18; 2025-03-27: 18; 2025-03-28: 18; 2025-03-29: 18; 2025-03-30: 18; 2025-03-31: 18; 2025-04-01: 18; 2025-04-02: 18; 2025-04-03: 18; 2025-04-04: 18; 2025-04-05: 18; 2025-04-06: 18; 2025-04-07: 18; 2025-04-08: 18; 2025-04-09: 18; 2025-04-10: 31
2 | Desert Infra | Energizent Power Pvt. Ltd | Staff | 2024-11-25: 1; 2024-11-26: 1; 2024-11-27: 1; 2024-11-28: 1; 2024-11-29: 1; 2024-11-30: 1; 2024-12-01: 1; 2024-12-02: 1; 2024-12-03: 1; 2024-12-04: 1; 2024-12-05: 1; 2024-12-06: 1; 2024-12-07: 1; 2024-12-08: 1; 2024-12-09: 4; 2024-12-10: 4; 2024-12-11: 4; 2024-12-12: 3; 2024-12-13: 3; 2024-12-14: 2; 2024-12-15: 2; 2024-12-16: 2; 2024-12-17: 2; 2024-12-18: 2; 2024-12-19: 2; 2024-12-20: 2; 2024-12-21: 2; 2024-12-22: 2; 2024-12-23: 2; 2024-12-24: 2; 2024-12-25: 2; 2024-12-26: 2; 2024-12-27: 2; 2024-12-28: 2; 2024-12-29: 2; 2024-12-30: 2; 2024-12-31: 2; 2025-01-01: 0; 2025-01-02: 2; 2025-01-03: 2; 2025-01-04: 2; 2025-01-05: 2; 2025-01-06: 2; 2025-01-07: 2; 2025-01-08: 2; 2025-01-09: 2; 2025-01-10: 2; 2025-01-11: 2; 2025-01-12: 2; 2025-01-13: 2; 2025-01-14: 2; 2025-01-15: 2; 2025-01-16: 2; 2025-01-17: 2; 2025-01-18: 2; 2025-01-19: 2; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 2; 2025-02-01: 2; 2025-02-02: 2; 2025-02-03: 2; 2025-02-04: 2; 2025-02-05: 2; 2025-02-06: 2; 2025-02-07: 4; 2025-02-08: 4; 2025-02-09: 4; 2025-02-10: 4; 2025-02-11: 4; 2025-02-12: 4; 2025-02-13: 2; 2025-02-14: 2; 2025-02-15: 2; 2025-02-16: 2; 2025-02-17: 2; 2025-02-18: 2; 2025-02-19: 3; 2025-02-20: 3; 2025-02-21: 3; 2025-02-22: 3; 2025-02-23: 3; 2025-02-24: 3; 2025-02-25: 2; 2025-02-26: 2; 2025-02-27: 2; 2025-02-28: 3; 2025-03-01: 3; 2025-03-02: 3; 2025-03-03: 3; 2025-03-04: 3; 2025-03-05: 3; 2025-03-06: 3; 2025-03-07: 3; 2025-03-08: 3; 2025-03-09: 3; 2025-03-10: 2; 2025-03-11: 2; 2025-03-12: 2; 2025-03-13: 2; 2025-03-14: 0; 2025-03-15: 1; 2025-03-16: 1; 2025-03-17: 1; 2025-03-18: 1; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 2; 2025-03-22: 2; 2025-03-23: 2; 2025-03-24: 2; 2025-03-25: 2; 2025-03-26: 1; 2025-03-27: 2; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Worker | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 3; 2024-12-02: 3; 2024-12-03: 3; 2024-12-04: 3; 2024-12-05: 3; 2024-12-06: 3; 2024-12-07: 3; 2024-12-08: 3; 2024-12-09: 8; 2024-12-10: 8; 2024-12-11: 8; 2024-12-12: 15; 2024-12-13: 15; 2024-12-14: 13; 2024-12-15: 11; 2024-12-16: 14; 2024-12-17: 14; 2024-12-18: 12; 2024-12-19: 11; 2024-12-20: 11; 2024-12-21: 11; 2024-12-22: 16; 2024-12-23: 16; 2024-12-24: 16; 2024-12-25: 16; 2024-12-26: 16; 2024-12-27: 16; 2024-12-28: 16; 2024-12-29: 16; 2024-12-30: 12; 2024-12-31: 13; 2025-01-01: 0; 2025-01-02: 16; 2025-01-03: 16; 2025-01-04: 16; 2025-01-05: 16; 2025-01-06: 8; 2025-01-07: 16; 2025-01-08: 13; 2025-01-09: 13; 2025-01-10: 13; 2025-01-11: 13; 2025-01-12: 13; 2025-01-13: 4; 2025-01-14: 7; 2025-01-15: 7; 2025-01-16: 5; 2025-01-17: 5; 2025-01-18: 7; 2025-01-19: 7; 2025-01-20: 10; 2025-01-21: 10; 2025-01-22: 10; 2025-01-23: 10; 2025-01-24: 17; 2025-01-25: 14; 2025-01-26: 14; 2025-01-27: 14; 2025-01-28: 14; 2025-01-29: 4; 2025-01-30: 4; 2025-01-31: 13; 2025-02-01: 13; 2025-02-02: 13; 2025-02-03: 13; 2025-02-04: 13; 2025-02-05: 13; 2025-02-06: 13; 2025-02-07: 18; 2025-02-08: 18; 2025-02-09: 18; 2025-02-10: 18; 2025-02-11: 18; 2025-02-12: 18; 2025-02-13: 16; 2025-02-14: 16; 2025-02-15: 16; 2025-02-16: 16; 2025-02-17: 15; 2025-02-18: 15; 2025-02-19: 12; 2025-02-20: 14; 2025-02-21: 14; 2025-02-22: 14; 2025-02-23: 14; 2025-02-24: 14; 2025-02-25: 14; 2025-02-26: 18; 2025-02-27: 12; 2025-02-28: 11; 2025-03-01: 11; 2025-03-02: 11; 2025-03-03: 11; 2025-03-04: 11; 2025-03-05: 11; 2025-03-06: 11; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 13; 2025-03-11: 13; 2025-03-12: 13; 2025-03-13: 6; 2025-03-14: 0; 2025-03-15: 6; 2025-03-16: 7; 2025-03-17: 7; 2025-03-18: 4; 2025-03-19: 9; 2025-03-20: 7; 2025-03-21: 6; 2025-03-22: 6; 2025-03-23: 11; 2025-03-24: 11; 2025-03-25: 6; 2025-03-26: 7; 2025-03-27: 6; 2025-03-28: 10; 2025-03-29: 10; 2025-03-30: 7; 2025-03-31: 11; 2025-04-01: 11; 2025-04-02: 12; 2025-04-03: 12; 2025-04-04: 12; 2025-04-05: 9; 2025-04-06: 9; 2025-04-07: 20; 2025-04-08: 20; 2025-04-09: 15; 2025-04-10: 10
|  |  | Total | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 12 | 12 | 12 | 18 | 18 | 15 | 13 | 16 | 16 | 14 | 13 | 13 | 13 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 14 | 15 | 0 | 18 | 18 | 18 | 18 | 10 | 18 | 15 | 15 | 15 | 15 | 15 | 6 | 9 | 9 | 7 | 7 | 9 | 9 | 11 | 11 | 11 | 11 | 18 | 15 | 15 | 15 | 15 | 5 | 5 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 22 | 22 | 22 | 22 | 22 | 22 | 18 | 18 | 18 | 18 | 17 | 17 | 15 | 17 | 17 | 17 | 17 | 17 | 16 | 20 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 8 | 8 | 8 | 15 | 15 | 15 | 8 | 0 | 7 | 8 | 8 | 5 | 10 | 8 | 8 | 8 | 13 | 13 | 8 | 8 | 8 | 11 | 11 | 8 | 12 | 12 | 13 | 13 | 13 | 10 | 10 | 21 | 21 | 16 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Teq XVII Pvt. Ltd. | Staff | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 1; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 1
|  |  | Worker | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 5; 2025-03-19: 2; 2025-03-20: 0; 2025-03-21: 3; 2025-03-22: 5; 2025-03-23: 7; 2025-03-24: 7; 2025-03-25: 4; 2025-03-26: 4; 2025-03-27: 3; 2025-03-28: 3; 2025-03-29: 2; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 2; 2025-04-06: 2; 2025-04-07: 2; 2025-04-08: 2; 2025-04-09: 2; 2025-04-10: 5
|  |  | Total | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 6; 2025-03-19: 2; 2025-03-20: 0; 2025-03-21: 3; 2025-03-22: 5; 2025-03-23: 7; 2025-03-24: 7; 2025-03-25: 4; 2025-03-26: 4; 2025-03-27: 3; 2025-03-28: 3; 2025-03-29: 2; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 2; 2025-04-06: 2; 2025-04-07: 2; 2025-04-08: 2; 2025-04-09: 2; 2025-04-10: 6; 2025-04-11: 0; 2025-04-12: 0; 2025-04-13: 0; 2025-04-14: 0; 2025-04-15: 0; 2025-04-16: 0; 2025-04-17: 0; 2025-04-18: 0; 2025-04-19: 0; 2025-04-20: 0; 2025-04-21: 0; 2025-04-22: 0; 2025-04-23: 0; 2025-04-24: 0; 2025-04-25: 0; 2025-04-26: 0; 2025-04-27: 0; 2025-04-28: 0; 2025-04-29: 0; 2025-04-30: 0; 2025-05-01: 0; 2025-05-02: 0; 2025-05-03: 0; 2025-05-04: 0; 2025-05-05: 0; 2025-05-06: 0; 2025-05-07: 0; 2025-05-08: 0; 2025-05-09: 0; 2025-05-10: 0; 2025-05-11: 0; 2025-05-12: 0; 2025-05-13: 0; 2025-05-14: 0; 2025-05-15: 0; 2025-05-16: 0; 2025-05-17: 0; 2025-05-18: 0; 2025-05-19: 0; 2025-05-20: 0; 2025-05-21: 0; 2025-05-22: 0; 2025-05-23: 0; 2025-05-24: 0; 2025-05-25: 0; 2025-05-26: 0; 2025-05-27: 0; 2025-05-28: 0; 2025-05-29: 0; 2025-05-30: 0; 2025-05-31: 0; 2025-06-01: 0; 2025-06-02: 0; 2025-06-03: 0; 2025-06-04: 0; 2025-06-05: 0; 2025-06-06: 0; 2025-06-07: 0; 2025-06-08: 0; 2025-06-09: 0; 2025-06-10: 0; 2025-06-11: 0; 2025-06-12: 0; 2025-06-13: 0; 2025-06-14: 0; 2025-06-15: 0; 2025-06-16: 0; 2025-06-17: 0; 2025-06-18: 0; 2025-06-19: 0; 2025-06-20: 0; 2025-06-21: 0; 2025-06-22: 0; 2025-06-23: 0; 2025-06-24: 0; 2025-06-25: 0; 2025-06-26: 0; 2025-06-27: 0; 2025-06-28: 0; 2025-06-29: 0; 2025-06-30: 0; 2025-07-01: 0; 2025-07-02: 0; 2025-07-03: 0; 2025-07-04: 0; 2025-07-05: 0; 2025-07-06: 0; 2025-07-07: 0; 2025-07-08: 0; 2025-07-09: 0; 2025-07-10: 0; 2025-07-11: 0; 2025-07-12: 0; 2025-07-13: 0; 2025-07-14: 0; 2025-07-15: 0; 2025-07-16: 0; 2025-07-17: 0; 2025-07-18: 0; 2025-07-19: 0; 2025-07-20: 0; 2025-07-21: 0; 2025-07-22: 0; 2025-07-23: 0; 2025-07-24: 0; 2025-07-25: 0; 2025-07-26: 0; 2025-07-27: 0; 2025-07-28: 0; 2025-07-29: 0; 2025-07-30: 0; 2025-07-31: 0
3 | Sanchiyay | Energizent Power Pvt. Ltd | Staff | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 2; 2024-11-30: 2; 2024-12-01: 2; 2024-12-02: 2; 2024-12-03: 2; 2024-12-04: 2; 2024-12-05: 2; 2024-12-06: 2; 2024-12-07: 3; 2024-12-08: 3; 2024-12-09: 3; 2024-12-10: 2; 2024-12-11: 2; 2024-12-12: 2; 2024-12-13: 2; 2024-12-14: 2; 2024-12-15: 2; 2024-12-16: 2; 2024-12-17: 3; 2024-12-18: 3; 2024-12-19: 3; 2024-12-20: 3; 2024-12-21: 2; 2024-12-22: 2; 2024-12-23: 2; 2024-12-24: 3; 2024-12-25: 3; 2024-12-26: 3; 2024-12-27: 2; 2024-12-28: 2; 2024-12-29: 2; 2024-12-30: 2; 2024-12-31: 2; 2025-01-01: 0; 2025-01-02: 2; 2025-01-03: 3; 2025-01-04: 3; 2025-01-05: 3; 2025-01-06: 3; 2025-01-07: 3; 2025-01-08: 3; 2025-01-09: 3; 2025-01-10: 3; 2025-01-11: 3; 2025-01-12: 3; 2025-01-13: 3; 2025-01-14: 3; 2025-01-15: 3; 2025-01-16: 3; 2025-01-17: 3; 2025-01-18: 3; 2025-01-19: 3; 2025-01-20: 3; 2025-01-21: 3; 2025-01-22: 3; 2025-01-23: 3; 2025-01-24: 3; 2025-01-25: 3; 2025-01-26: 3; 2025-01-27: 3; 2025-01-28: 3; 2025-01-29: 3; 2025-01-30: 3; 2025-01-31: 3; 2025-02-01: 3; 2025-02-02: 3; 2025-02-03: 3; 2025-02-04: 3; 2025-02-05: 2; 2025-02-06: 3; 2025-02-07: 2; 2025-02-08: 2; 2025-02-09: 2; 2025-02-10: 2; 2025-02-11: 2; 2025-02-12: 2; 2025-02-13: 2; 2025-02-14: 2; 2025-02-15: 2; 2025-02-16: 2; 2025-02-17: 2; 2025-02-18: 2; 2025-02-19: 2; 2025-02-20: 2; 2025-02-21: 2; 2025-02-22: 2; 2025-02-23: 0; 2025-02-24: 2; 2025-02-25: 2; 2025-02-26: 2; 2025-02-27: 2; 2025-02-28: 2; 2025-03-01: 2; 2025-03-02: 2; 2025-03-03: 2; 2025-03-04: 2; 2025-03-05: 2; 2025-03-06: 2; 2025-03-07: 2; 2025-03-08: 2; 2025-03-09: 2; 2025-03-10: 2; 2025-03-11: 2; 2025-03-12: 2; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 1; 2025-03-16: 1; 2025-03-17: 1; 2025-03-18: 1; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Worker | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 2; 2024-12-03: 2; 2024-12-04: 2; 2024-12-05: 2; 2024-12-06: 10; 2024-12-07: 9; 2024-12-08: 9; 2024-12-09: 9; 2024-12-10: 9; 2024-12-11: 9; 2024-12-12: 13; 2024-12-13: 13; 2024-12-14: 9; 2024-12-15: 9; 2024-12-16: 8; 2024-12-17: 9; 2024-12-18: 9; 2024-12-19: 10; 2024-12-20: 13; 2024-12-21: 13; 2024-12-22: 4; 2024-12-23: 13; 2024-12-24: 13; 2024-12-25: 8; 2024-12-26: 8; 2024-12-27: 7; 2024-12-28: 7; 2024-12-29: 2; 2024-12-30: 5; 2024-12-31: 7; 2025-01-01: 0; 2025-01-02: 12; 2025-01-03: 12; 2025-01-04: 12; 2025-01-05: 12; 2025-01-06: 11; 2025-01-07: 14; 2025-01-08: 14; 2025-01-09: 14; 2025-01-10: 14; 2025-01-11: 14; 2025-01-12: 14; 2025-01-13: 14; 2025-01-14: 17; 2025-01-15: 17; 2025-01-16: 17; 2025-01-17: 17; 2025-01-18: 17; 2025-01-19: 17; 2025-01-20: 22; 2025-01-21: 20; 2025-01-22: 20; 2025-01-23: 20; 2025-01-24: 20; 2025-01-25: 20; 2025-01-26: 20; 2025-01-27: 17; 2025-01-28: 17; 2025-01-29: 17; 2025-01-30: 17; 2025-01-31: 16; 2025-02-01: 16; 2025-02-02: 16; 2025-02-03: 26; 2025-02-04: 20; 2025-02-05: 12; 2025-02-06: 11; 2025-02-07: 12; 2025-02-08: 12; 2025-02-09: 12; 2025-02-10: 12; 2025-02-11: 12; 2025-02-12: 12; 2025-02-13: 10; 2025-02-14: 10; 2025-02-15: 10; 2025-02-16: 10; 2025-02-17: 12; 2025-02-18: 12; 2025-02-19: 12; 2025-02-20: 12; 2025-02-21: 12; 2025-02-22: 12; 2025-02-23: 0; 2025-02-24: 10; 2025-02-25: 10; 2025-02-26: 10; 2025-02-27: 12; 2025-02-28: 12; 2025-03-01: 12; 2025-03-02: 12; 2025-03-03: 12; 2025-03-04: 9; 2025-03-05: 9; 2025-03-06: 9; 2025-03-07: 9; 2025-03-08: 9; 2025-03-09: 9; 2025-03-10: 6; 2025-03-11: 6; 2025-03-12: 6; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 2; 2025-03-16: 4; 2025-03-17: 4; 2025-03-18: 4; 2025-03-19: 4; 2025-03-20: 6; 2025-03-21: 6; 2025-03-22: 6; 2025-03-23: 4; 2025-03-24: 4; 2025-03-25: 8; 2025-03-26: 10; 2025-03-27: 8; 2025-03-28: 8; 2025-03-29: 4; 2025-03-30: 4; 2025-03-31: 4; 2025-04-01: 4; 2025-04-02: 9; 2025-04-03: 9; 2025-04-04: 11; 2025-04-05: 11; 2025-04-06: 11; 2025-04-07: 11; 2025-04-08: 11; 2025-04-09: 12; 2025-04-10: 12
|  |  | Total | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 12 | 12 | 12 | 12 | 11 | 11 | 15 | 15 | 11 | 11 | 10 | 12 | 12 | 13 | 16 | 15 | 6 | 15 | 16 | 11 | 11 | 9 | 9 | 4 | 7 | 9 | 0 | 14 | 15 | 15 | 15 | 14 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 23 | 23 | 23 | 23 | 23 | 23 | 20 | 20 | 20 | 20 | 19 | 19 | 19 | 29 | 23 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 12 | 12 | 12 | 12 | 14 | 14 | 14 | 14 | 14 | 14 | 0 | 12 | 12 | 12 | 14 | 14 | 14 | 14 | 14 | 11 | 11 | 11 | 11 | 11 | 11 | 8 | 8 | 8 | 0 | 0 | 3 | 5 | 5 | 5 | 5 | 7 | 7 | 7 | 5 | 5 | 9 | 11 | 9 | 9 | 5 | 5 | 5 | 5 | 10 | 10 | 12 | 12 | 12 | 12 | 12 | 13 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | JCC | Energizent Power Pvt. Ltd | Staff | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 1; 2024-12-15: 1; 2024-12-16: 1; 2024-12-17: 1; 2024-12-18: 1; 2024-12-19: 1; 2024-12-20: 1; 2024-12-21: 1; 2024-12-22: 1; 2024-12-23: 1; 2024-12-24: 2; 2024-12-25: 1; 2024-12-26: 1; 2024-12-27: 2; 2024-12-28: 2; 2024-12-29: 2; 2024-12-30: 2; 2024-12-31: 2; 2025-01-01: 0; 2025-01-02: 3; 2025-01-03: 3; 2025-01-04: 3; 2025-01-05: 3; 2025-01-06: 3; 2025-01-07: 3; 2025-01-08: 3; 2025-01-09: 3; 2025-01-10: 3; 2025-01-11: 3; 2025-01-12: 3; 2025-01-13: 3; 2025-01-14: 3; 2025-01-15: 3; 2025-01-16: 3; 2025-01-17: 3; 2025-01-18: 3; 2025-01-19: 3; 2025-01-20: 3; 2025-01-21: 3; 2025-01-22: 3; 2025-01-23: 3; 2025-01-24: 3; 2025-01-25: 3; 2025-01-26: 3; 2025-01-27: 3; 2025-01-28: 3; 2025-01-29: 3; 2025-01-30: 3; 2025-01-31: 3; 2025-02-01: 3; 2025-02-02: 3; 2025-02-03: 3; 2025-02-04: 3; 2025-02-05: 3; 2025-02-06: 3; 2025-02-07: 3; 2025-02-08: 3; 2025-02-09: 2; 2025-02-10: 2; 2025-02-11: 2; 2025-02-12: 2; 2025-02-13: 3; 2025-02-14: 3; 2025-02-15: 3; 2025-02-16: 3; 2025-02-17: 3; 2025-02-18: 3; 2025-02-19: 3; 2025-02-20: 3; 2025-02-21: 3; 2025-02-22: 3; 2025-02-23: 3; 2025-02-24: 3; 2025-02-25: 3; 2025-02-26: 3; 2025-02-27: 2; 2025-02-28: 2; 2025-03-01: 2; 2025-03-02: 2; 2025-03-03: 2; 2025-03-04: 2; 2025-03-05: 2; 2025-03-06: 2; 2025-03-07: 2; 2025-03-08: 2; 2025-03-09: 2; 2025-03-10: 2; 2025-03-11: 2; 2025-03-12: 2; 2025-03-13: 2; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 1; 2025-03-17: 1; 2025-03-18: 1; 2025-03-19: 2; 2025-03-20: 1; 2025-03-21: 2; 2025-03-22: 2; 2025-03-23: 2; 2025-03-24: 2; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Worker | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 6; 2024-12-17: 8; 2024-12-18: 8; 2024-12-19: 7; 2024-12-20: 8; 2024-12-21: 12; 2024-12-22: 8; 2024-12-23: 14; 2024-12-24: 14; 2024-12-25: 14; 2024-12-26: 14; 2024-12-27: 14; 2024-12-28: 16; 2024-12-29: 17; 2024-12-30: 17; 2024-12-31: 17; 2025-01-01: 0; 2025-01-02: 15; 2025-01-03: 15; 2025-01-04: 15; 2025-01-05: 15; 2025-01-06: 15; 2025-01-07: 15; 2025-01-08: 15; 2025-01-09: 15; 2025-01-10: 18; 2025-01-11: 18; 2025-01-12: 18; 2025-01-13: 18; 2025-01-14: 16; 2025-01-15: 17; 2025-01-16: 16; 2025-01-17: 16; 2025-01-18: 15; 2025-01-19: 15; 2025-01-20: 12; 2025-01-21: 13; 2025-01-22: 15; 2025-01-23: 15; 2025-01-24: 22; 2025-01-25: 19; 2025-01-26: 19; 2025-01-27: 19; 2025-01-28: 19; 2025-01-29: 19; 2025-01-30: 19; 2025-01-31: 6; 2025-02-01: 16; 2025-02-02: 20; 2025-02-03: 20; 2025-02-04: 18; 2025-02-05: 18; 2025-02-06: 14; 2025-02-07: 14; 2025-02-08: 14; 2025-02-09: 14; 2025-02-10: 14; 2025-02-11: 14; 2025-02-12: 14; 2025-02-13: 10; 2025-02-14: 10; 2025-02-15: 10; 2025-02-16: 10; 2025-02-17: 10; 2025-02-18: 10; 2025-02-19: 13; 2025-02-20: 13; 2025-02-21: 13; 2025-02-22: 13; 2025-02-23: 13; 2025-02-24: 11; 2025-02-25: 11; 2025-02-26: 14; 2025-02-27: 9; 2025-02-28: 6; 2025-03-01: 6; 2025-03-02: 6; 2025-03-03: 11; 2025-03-04: 10; 2025-03-05: 10; 2025-03-06: 10; 2025-03-07: 7; 2025-03-08: 7; 2025-03-09: 7; 2025-03-10: 9; 2025-03-11: 8; 2025-03-12: 8; 2025-03-13: 4; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 4; 2025-03-17: 4; 2025-03-18: 9; 2025-03-19: 11; 2025-03-20: 12; 2025-03-21: 11; 2025-03-22: 7; 2025-03-23: 11; 2025-03-24: 11; 2025-03-25: 11; 2025-03-26: 11; 2025-03-27: 10; 2025-03-28: 10; 2025-03-29: 12; 2025-03-30: 12; 2025-03-31: 12; 2025-04-01: 12; 2025-04-02: 12; 2025-04-03: 12; 2025-04-04: 12; 2025-04-05: 10; 2025-04-06: 10; 2025-04-07: 7; 2025-04-08: 7; 2025-04-09: 8; 2025-04-10: 6
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 7 | 9 | 9 | 8 | 9 | 13 | 9 | 15 | 16 | 15 | 15 | 16 | 18 | 19 | 19 | 19 | 0 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 21 | 21 | 21 | 21 | 19 | 20 | 19 | 19 | 18 | 18 | 15 | 16 | 18 | 18 | 25 | 22 | 22 | 22 | 22 | 22 | 22 | 9 | 19 | 23 | 23 | 21 | 21 | 17 | 17 | 17 | 16 | 16 | 16 | 16 | 13 | 13 | 13 | 13 | 13 | 13 | 16 | 16 | 16 | 16 | 16 | 14 | 14 | 17 | 11 | 8 | 8 | 8 | 13 | 12 | 12 | 12 | 9 | 9 | 9 | 11 | 10 | 10 | 6 | 0 | 0 | 5 | 5 | 10 | 13 | 13 | 13 | 9 | 13 | 13 | 12 | 12 | 11 | 11 | 13 | 13 | 13 | 13 | 13 | 13 | 13 | 11 | 11 | 8 | 8 | 9 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Super Construction | Energizent Power Pvt. Ltd | Staff | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 2; 2025-01-09: 2; 2025-01-10: 2; 2025-01-11: 2; 2025-01-12: 0; 2025-01-13: 1; 2025-01-14: 1; 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 1; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Worker | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 6; 2025-01-09: 6; 2025-01-10: 6; 2025-01-11: 6; 2025-01-12: 6; 2025-01-13: 5; 2025-01-14: 5; 2025-01-15: 5; 2025-01-16: 5; 2025-01-17: 5; 2025-01-18: 5; 2025-01-19: 5; 2025-01-20: 5; 2025-01-21: 5; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 2; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Paramhans Infra | Energizent Power Pvt. Ltd | Staff | 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 2; 2025-01-18: 2; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 0; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 0; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 2; 2025-01-31: 2; 2025-02-01: 2; 2025-02-02: 3; 2025-02-03: 1; 2025-02-04: 0; 2025-02-05: 2; 2025-02-06: 2; 2025-02-07: 2; 2025-02-08: 2; 2025-02-09: 2; 2025-02-10: 2; 2025-02-11: 2; 2025-02-12: 2; 2025-02-13: 2; 2025-02-14: 2; 2025-02-15: 2; 2025-02-16: 2; 2025-02-17: 2; 2025-02-18: 2; 2025-02-19: 2; 2025-02-20: 2; 2025-02-21: 2; 2025-02-22: 2; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 2; 2025-02-26: 2; 2025-02-27: 2; 2025-02-28: 2; 2025-03-01: 2; 2025-03-02: 2; 2025-03-03: 2; 2025-03-04: 2; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 0; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 1; 2025-03-16: 1; 2025-03-17: 1; 2025-03-18: 1; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 0; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 0; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Worker | 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 4; 2025-01-18: 4; 2025-01-19: 4; 2025-01-20: 4; 2025-01-21: 0; 2025-01-22: 4; 2025-01-23: 4; 2025-01-24: 9; 2025-01-25: 8; 2025-01-26: 0; 2025-01-27: 8; 2025-01-28: 8; 2025-01-29: 8; 2025-01-30: 13; 2025-01-31: 13; 2025-02-01: 13; 2025-02-02: 13; 2025-02-03: 5; 2025-02-04: 0; 2025-02-05: 16; 2025-02-06: 16; 2025-02-07: 16; 2025-02-08: 16; 2025-02-09: 16; 2025-02-10: 12; 2025-02-11: 15; 2025-02-12: 12; 2025-02-13: 14; 2025-02-14: 15; 2025-02-15: 15; 2025-02-16: 15; 2025-02-17: 15; 2025-02-18: 15; 2025-02-19: 13; 2025-02-20: 13; 2025-02-21: 15; 2025-02-22: 15; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 14; 2025-02-26: 14; 2025-02-27: 14; 2025-02-28: 17; 2025-03-01: 17; 2025-03-02: 17; 2025-03-03: 14; 2025-03-04: 14; 2025-03-05: 13; 2025-03-06: 13; 2025-03-07: 5; 2025-03-08: 5; 2025-03-09: 5; 2025-03-10: 5; 2025-03-11: 0; 2025-03-12: 5; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 5; 2025-03-16: 5; 2025-03-17: 5; 2025-03-18: 5; 2025-03-19: 5; 2025-03-20: 5; 2025-03-21: 5; 2025-03-22: 5; 2025-03-23: 5; 2025-03-24: 5; 2025-03-25: 8; 2025-03-26: 7; 2025-03-27: 5; 2025-03-28: 5; 2025-03-29: 0; 2025-03-30: 5; 2025-03-31: 4; 2025-04-01: 12; 2025-04-02: 8; 2025-04-03: 7; 2025-04-04: 7; 2025-04-05: 0; 2025-04-06: 4; 2025-04-07: 3; 2025-04-08: 3; 2025-04-09: 3; 2025-04-10: 4
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 5 | 5 | 0 | 5 | 5 | 10 | 9 | 0 | 9 | 9 | 9 | 15 | 15 | 15 | 16 | 6 | 0 | 18 | 18 | 18 | 18 | 18 | 14 | 17 | 14 | 16 | 17 | 17 | 17 | 17 | 17 | 15 | 15 | 17 | 17 | 0 | 0 | 16 | 16 | 16 | 19 | 19 | 19 | 16 | 16 | 14 | 14 | 6 | 6 | 6 | 6 | 0 | 6 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 9 | 8 | 6 | 6 | 0 | 6 | 5 | 13 | 9 | 8 | 8 | 0 | 5 | 4 | 4 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Seema Enterprises | Energizent Power Pvt. Ltd | Staff | 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 2; 2025-01-19: 2; 2025-01-20: 2; 2025-01-21: 2; 2025-01-22: 2; 2025-01-23: 2; 2025-01-24: 2; 2025-01-25: 2; 2025-01-26: 0; 2025-01-27: 2; 2025-01-28: 2; 2025-01-29: 2; 2025-01-30: 2; 2025-01-31: 2; 2025-02-01: 2; 2025-02-02: 2; 2025-02-03: 2; 2025-02-04: 2; 2025-02-05: 2; 2025-02-06: 2; 2025-02-07: 2; 2025-02-08: 2; 2025-02-09: 2; 2025-02-10: 2; 2025-02-11: 2; 2025-02-12: 2; 2025-02-13: 2; 2025-02-14: 2; 2025-02-15: 2; 2025-02-16: 2; 2025-02-17: 1; 2025-02-18: 1; 2025-02-19: 2; 2025-02-20: 2; 2025-02-21: 2; 2025-02-22: 2; 2025-02-23: 2; 2025-02-24: 2; 2025-02-25: 2; 2025-02-26: 2; 2025-02-27: 2; 2025-02-28: 2; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 1; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 0; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Worker | 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 6; 2025-01-19: 6; 2025-01-20: 6; 2025-01-21: 6; 2025-01-22: 6; 2025-01-23: 6; 2025-01-24: 6; 2025-01-25: 6; 2025-01-26: 0; 2025-01-27: 6; 2025-01-28: 6; 2025-01-29: 6; 2025-01-30: 5; 2025-01-31: 5; 2025-02-01: 5; 2025-02-02: 5; 2025-02-03: 5; 2025-02-04: 6; 2025-02-05: 12; 2025-02-06: 12; 2025-02-07: 12; 2025-02-08: 12; 2025-02-09: 12; 2025-02-10: 12; 2025-02-11: 13; 2025-02-12: 13; 2025-02-13: 13; 2025-02-14: 13; 2025-02-15: 13; 2025-02-16: 13; 2025-02-17: 13; 2025-02-18: 13; 2025-02-19: 8; 2025-02-20: 8; 2025-02-21: 15; 2025-02-22: 15; 2025-02-23: 5; 2025-02-24: 5; 2025-02-25: 5; 2025-02-26: 11; 2025-02-27: 11; 2025-02-28: 8; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 2; 2025-03-19: 5; 2025-03-20: 5; 2025-03-21: 5; 2025-03-22: 5; 2025-03-23: 6; 2025-03-24: 6; 2025-03-25: 6; 2025-03-26: 7; 2025-03-27: 5; 2025-03-28: 5; 2025-03-29: 0; 2025-03-30: 4; 2025-03-31: 4; 2025-04-01: 7; 2025-04-02: 5; 2025-04-03: 5; 2025-04-04: 5; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 5; 2025-04-09: 5; 2025-04-10: 5
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 8 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 8 | 14 | 14 | 14 | 14 | 14 | 14 | 15 | 15 | 15 | 15 | 15 | 15 | 14 | 14 | 10 | 10 | 17 | 17 | 7 | 7 | 7 | 13 | 13 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 6 | 6 | 6 | 7 | 7 | 7 | 8 | 6 | 6 | 0 | 5 | 5 | 8 | 6 | 6 | 6 | 0 | 0 | 0 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Teq XV Pvt. Ltd. | Staff | 2025-03-01: 2; 2025-03-02: 2; 2025-03-03: 2; 2025-03-04: 2; 2025-03-05: 2; 2025-03-06: 2; 2025-03-07: 2; 2025-03-08: 2; 2025-03-09: 2; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Worker | 2025-03-01: 8; 2025-03-02: 8; 2025-03-03: 8; 2025-03-04: 8; 2025-03-05: 8; 2025-03-06: 8; 2025-03-07: 8; 2025-03-08: 8; 2025-03-09: 8; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Total | 2025-03-01: 10; 2025-03-02: 10; 2025-03-03: 10; 2025-03-04: 10; 2025-03-05: 10; 2025-03-06: 10; 2025-03-07: 10; 2025-03-08: 10; 2025-03-09: 10; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0; 2025-04-11: 0; 2025-04-12: 0; 2025-04-13: 0; 2025-04-14: 0; 2025-04-15: 0; 2025-04-16: 0; 2025-04-17: 0; 2025-04-18: 0; 2025-04-19: 0; 2025-04-20: 0; 2025-04-21: 0; 2025-04-22: 0; 2025-04-23: 0; 2025-04-24: 0; 2025-04-25: 0; 2025-04-26: 0
8 | KC Construction | Energizent Power Pvt. Ltd | Staff | 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 2; 2025-02-08: 2; 2025-02-09: 2; 2025-02-10: 2; 2025-02-11: 2; 2025-02-12: 2; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 1; 2025-02-20: 1; 2025-02-21: 2; 2025-02-22: 2; 2025-02-23: 2; 2025-02-24: 2; 2025-02-25: 2; 2025-02-26: 2; 2025-02-27: 2; 2025-02-28: 2; 2025-03-01: 2; 2025-03-02: 2; 2025-03-03: 2; 2025-03-04: 2; 2025-03-05: 2; 2025-03-06: 2; 2025-03-07: 2; 2025-03-08: 2; 2025-03-09: 2; 2025-03-10: 2; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Worker | 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 5; 2025-02-08: 5; 2025-02-09: 5; 2025-02-10: 4; 2025-02-11: 4; 2025-02-12: 4; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 2; 2025-02-20: 2; 2025-02-21: 6; 2025-02-22: 6; 2025-02-23: 6; 2025-02-24: 6; 2025-02-25: 6; 2025-02-26: 6; 2025-02-27: 6; 2025-02-28: 6; 2025-03-01: 6; 2025-03-02: 5; 2025-03-03: 6; 2025-03-04: 5; 2025-03-05: 5; 2025-03-06: 5; 2025-03-07: 8; 2025-03-08: 8; 2025-03-09: 8; 2025-03-10: 5; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 3; 2025-03-25: 5; 2025-03-26: 5; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 8 | 7 | 7 | 7 | 10 | 10 | 10 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | SR Constructions | Energizent Power Pvt. Ltd | Staff | 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-02-19: 1; 2025-02-20: 1; 2025-02-21: 1; 2025-02-22: 1; 2025-02-23: 1; 2025-02-24: 1; 2025-02-25: 1; 2025-02-26: 1; 2025-02-27: 1; 2025-02-28: 1; 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 1; 2025-03-16: 1; 2025-03-17: 1; 2025-03-18: 1; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 0; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Worker | 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 4; 2025-02-02: 6; 2025-02-03: 6; 2025-02-04: 6; 2025-02-05: 6; 2025-02-06: 11; 2025-02-07: 11; 2025-02-08: 8; 2025-02-09: 13; 2025-02-10: 13; 2025-02-11: 17; 2025-02-12: 17; 2025-02-13: 5; 2025-02-14: 5; 2025-02-15: 12; 2025-02-16: 12; 2025-02-17: 12; 2025-02-18: 12; 2025-02-19: 13; 2025-02-20: 13; 2025-02-21: 13; 2025-02-22: 13; 2025-02-23: 13; 2025-02-24: 13; 2025-02-25: 13; 2025-02-26: 13; 2025-02-27: 13; 2025-02-28: 12; 2025-03-01: 12; 2025-03-02: 12; 2025-03-03: 12; 2025-03-04: 12; 2025-03-05: 13; 2025-03-06: 13; 2025-03-07: 13; 2025-03-08: 13; 2025-03-09: 13; 2025-03-10: 5; 2025-03-11: 5; 2025-03-12: 5; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 4; 2025-03-16: 6; 2025-03-17: 5; 2025-03-18: 5; 2025-03-19: 9; 2025-03-20: 10; 2025-03-21: 10; 2025-03-22: 11; 2025-03-23: 12; 2025-03-24: 6; 2025-03-25: 13; 2025-03-26: 6; 2025-03-27: 6; 2025-03-28: 6; 2025-03-29: 6; 2025-03-30: 6; 2025-03-31: 0; 2025-04-01: 5; 2025-04-02: 5; 2025-04-03: 11; 2025-04-04: 7; 2025-04-05: 8; 2025-04-06: 5; 2025-04-07: 10; 2025-04-08: 10; 2025-04-09: 4; 2025-04-10: 10
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 7 | 7 | 7 | 7 | 12 | 12 | 9 | 14 | 14 | 18 | 18 | 6 | 6 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 13 | 13 | 13 | 13 | 13 | 14 | 14 | 14 | 14 | 14 | 6 | 6 | 6 | 0 | 0 | 5 | 7 | 6 | 6 | 10 | 11 | 11 | 12 | 13 | 7 | 14 | 7 | 7 | 7 | 7 | 7 | 0 | 6 | 6 | 12 | 8 | 9 | 6 | 11 | 11 | 5 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | DS Constructions | Energizent Power Pvt. Ltd | Staff | 2025-02-27: 2; 2025-02-28: 2; 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Worker | 2025-02-27: 6; 2025-02-28: 6; 2025-03-01: 8; 2025-03-02: 8; 2025-03-03: 8; 2025-03-04: 8; 2025-03-05: 8; 2025-03-06: 8; 2025-03-07: 8; 2025-03-08: 8; 2025-03-09: 8; 2025-03-10: 8; 2025-03-11: 6; 2025-03-12: 6; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 4; 2025-03-20: 4; 2025-03-21: 4; 2025-03-22: 5; 2025-03-23: 5; 2025-03-24: 5; 2025-03-25: 8; 2025-03-26: 8; 2025-03-27: 8; 2025-03-28: 8; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 5; 2025-04-04: 5; 2025-04-05: 5; 2025-04-06: 5; 2025-04-07: 5; 2025-04-08: 5; 2025-04-09: 4; 2025-04-10: 4
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 6 | 6 | 6 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | NCC | Energizent Power Pvt. Ltd | Staff | 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Worker | 2025-03-01: 4; 2025-03-02: 4; 2025-03-03: 4; 2025-03-04: 4; 2025-03-05: 4; 2025-03-06: 4; 2025-03-07: 4; 2025-03-08: 4; 2025-03-09: 4; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Hartek | Energizent Power Pvt. Ltd | Staff | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 2; 2025-03-08: 2; 2025-03-09: 2; 2025-03-10: 2; 2025-03-11: 2; 2025-03-12: 2; 2025-03-13: 2; 2025-03-14: 0; 2025-03-15: 2; 2025-03-16: 2; 2025-03-17: 2; 2025-03-18: 2; 2025-03-19: 2; 2025-03-20: 2; 2025-03-21: 2; 2025-03-22: 2; 2025-03-23: 2; 2025-03-24: 2; 2025-03-25: 3; 2025-03-26: 3; 2025-03-27: 3; 2025-03-28: 2; 2025-03-29: 3; 2025-03-30: 3; 2025-03-31: 0; 2025-04-01: 3; 2025-04-02: 3; 2025-04-03: 3; 2025-04-04: 3; 2025-04-05: 2; 2025-04-06: 3; 2025-04-07: 3; 2025-04-08: 3; 2025-04-09: 2; 2025-04-10: 0
|  |  | Worker | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 15; 2025-03-08: 15; 2025-03-09: 15; 2025-03-10: 15; 2025-03-11: 15; 2025-03-12: 15; 2025-03-13: 9; 2025-03-14: 0; 2025-03-15: 9; 2025-03-16: 5; 2025-03-17: 8; 2025-03-18: 9; 2025-03-19: 7; 2025-03-20: 13; 2025-03-21: 9; 2025-03-22: 9; 2025-03-23: 9; 2025-03-24: 14; 2025-03-25: 10; 2025-03-26: 10; 2025-03-27: 9; 2025-03-28: 6; 2025-03-29: 9; 2025-03-30: 10; 2025-03-31: 0; 2025-04-01: 10; 2025-04-02: 10; 2025-04-03: 10; 2025-04-04: 12; 2025-04-05: 7; 2025-04-06: 10; 2025-04-07: 10; 2025-04-08: 10; 2025-04-09: 7; 2025-04-10: 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 17 | 17 | 17 | 17 | 17 | 11 | 0 | 11 | 7 | 10 | 11 | 9 | 15 | 11 | 11 | 11 | 16 | 13 | 13 | 12 | 8 | 12 | 13 | 0 | 13 | 13 | 13 | 15 | 9 | 13 | 13 | 13 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Sun Bright Infratech | Energizent Power Pvt. Ltd | Staff | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 2; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Worker | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 2; 2025-03-20: 2; 2025-03-21: 2; 2025-03-22: 2; 2025-03-23: 5; 2025-03-24: 5; 2025-03-25: 5; 2025-03-26: 6; 2025-03-27: 5; 2025-03-28: 5; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 6 | 7 | 6 | 7 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | JS Bhati Construction | Energizent Power Pvt. Ltd | Staff | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 0; 2025-03-30: 1; 2025-03-31: 0; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Worker | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 3; 2025-03-20: 3; 2025-03-21: 3; 2025-03-22: 3; 2025-03-23: 3; 2025-03-24: 3; 2025-03-25: 3; 2025-03-26: 4; 2025-03-27: 4; 2025-03-28: 4; 2025-03-29: 0; 2025-03-30: 2; 2025-03-31: 0; 2025-04-01: 2; 2025-04-02: 2; 2025-04-03: 6; 2025-04-04: 6; 2025-04-05: 7; 2025-04-06: 5; 2025-04-07: 5; 2025-04-08: 5; 2025-04-09: 6; 2025-04-10: 6
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 0 | 3 | 0 | 3 | 3 | 7 | 7 | 8 | 6 | 6 | 6 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Baba Ramdev contraction | Energizent Power Pvt. Ltd | Staff | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Worker | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 3; 2025-03-27: 8; 2025-03-28: 7; 2025-03-29: 2; 2025-03-30: 4; 2025-03-31: 2; 2025-04-01: 5; 2025-04-02: 6; 2025-04-03: 4; 2025-04-04: 4; 2025-04-05: 5; 2025-04-06: 8; 2025-04-07: 8; 2025-04-08: 7; 2025-04-09: 4; 2025-04-10: 7
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 9 | 8 | 3 | 5 | 3 | 6 | 7 | 5 | 5 | 6 | 9 | 9 | 8 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Bajarang Electrical Work | Energizent Power Pvt. Ltd | Staff | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Worker | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 8; 2025-04-04: 8; 2025-04-05: 8; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Shree Krshna Enterprises | Energizent Power Pvt. Ltd | Staff | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Worker | 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 6; 2025-04-08: 6; 2025-04-09: 9; 2025-04-10: 9
|  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Machinary | Total |  | Description | 0 | 2 | 2 | 2 | 4 | 4 | 4 | 5 | 5 | 4 | 3 | 2 | 2 | 2 | 3 | 3 | 4 | 4 | 4 | 6 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 1 | 1 | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 8 | 7 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 7 | 7 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 9 | 0 | 0 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 6 | 6 | 6 | 6 | 8 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Desert Infra |  | Vehicle | 2024-11-26: 1; 2024-11-27: 1; 2024-11-28: 1; 2024-11-29: 1; 2024-11-30: 1; 2024-12-01: 1; 2024-12-02: 1; 2024-12-03: 1; 2024-12-04: 1; 2024-12-05: 1; 2024-12-06: 1; 2024-12-07: 1; 2024-12-08: 1; 2024-12-09: 1; 2024-12-10: 1; 2024-12-11: 1; 2024-12-12: 1; 2024-12-13: 1; 2024-12-14: 1; 2024-12-15: 1; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Ajax | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 1; 2024-12-03: 0; 2024-12-04: 1; 2024-12-05: 1; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 1; 2024-12-12: 1; 2024-12-13: 1; 2024-12-14: 1; 2024-12-15: 1; 2024-12-16: 1; 2024-12-17: 1; 2024-12-18: 1; 2024-12-19: 1; 2024-12-20: 1; 2024-12-21: 1; 2024-12-22: 1; 2024-12-23: 1; 2024-12-24: 1; 2024-12-25: 1; 2024-12-26: 1; 2024-12-27: 1; 2024-12-28: 1; 2024-12-29: 1; 2024-12-30: 1; 2024-12-31: 1; 2025-01-01: 1; 2025-01-02: 1; 2025-01-03: 1; 2025-01-04: 1; 2025-01-05: 1; 2025-01-06: 1; 2025-01-07: 1; 2025-01-08: 1; 2025-01-09: 1; 2025-01-10: 1; 2025-01-11: 1; 2025-01-12: 1; 2025-01-13: 1; 2025-01-14: 1; 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-02-19: 1; 2025-02-20: 1; 2025-02-21: 1; 2025-02-22: 1; 2025-02-23: 1; 2025-02-24: 1; 2025-02-25: 1; 2025-02-26: 1; 2025-02-27: 1; 2025-02-28: 1; 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Excavator/JCB | 2024-11-25: 0; 2024-11-26: 1; 2024-11-27: 1; 2024-11-28: 1; 2024-11-29: 1; 2024-11-30: 1; 2024-12-01: 1; 2024-12-02: 1; 2024-12-03: 1; 2024-12-04: 1; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 1; 2024-12-10: 1; 2024-12-11: 1; 2024-12-12: 1; 2024-12-13: 1; 2024-12-14: 1; 2024-12-15: 1; 2024-12-16: 1; 2024-12-17: 1; 2024-12-18: 1; 2024-12-19: 1; 2024-12-20: 1; 2024-12-21: 1; 2024-12-22: 1; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
2 | Sanchiyay |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 1; 2024-11-30: 1; 2024-12-01: 1; 2024-12-02: 1; 2024-12-03: 1; 2024-12-04: 1; 2024-12-05: 1; 2024-12-06: 1; 2024-12-07: 1; 2024-12-08: 1; 2024-12-09: 1; 2024-12-10: 1; 2024-12-11: 1; 2024-12-12: 1; 2024-12-13: 1; 2024-12-14: 1; 2024-12-15: 1; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Excavator/JCB | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 1; 2024-11-30: 1; 2024-12-01: 1; 2024-12-02: 1; 2024-12-03: 1; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 1; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Ajax | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 1; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 1; 2024-12-15: 1; 2024-12-16: 1; 2024-12-17: 1; 2024-12-18: 1; 2024-12-19: 1; 2024-12-20: 1; 2024-12-21: 1; 2024-12-22: 1; 2024-12-23: 1; 2024-12-24: 1; 2024-12-25: 1; 2024-12-26: 1; 2024-12-27: 1; 2024-12-28: 1; 2024-12-29: 1; 2024-12-30: 1; 2024-12-31: 1; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 1; 2025-01-04: 1; 2025-01-05: 1; 2025-01-06: 1; 2025-01-07: 1; 2025-01-08: 1; 2025-01-09: 1; 2025-01-10: 1; 2025-01-11: 1; 2025-01-12: 1; 2025-01-13: 1; 2025-01-14: 1; 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-02-19: 1; 2025-02-20: 1; 2025-02-21: 1; 2025-02-22: 1; 2025-02-23: 1; 2025-02-24: 1; 2025-02-25: 1; 2025-02-26: 1; 2025-02-27: 1; 2025-02-28: 1; 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
3 | JCC |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 1; 2024-12-17: 1; 2024-12-18: 1; 2024-12-19: 1; 2024-12-20: 1; 2024-12-21: 1; 2024-12-22: 1; 2024-12-23: 1; 2024-12-24: 1; 2024-12-25: 1; 2024-12-26: 1; 2024-12-27: 1; 2024-12-28: 1; 2024-12-29: 1; 2024-12-30: 1; 2024-12-31: 1; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Excavator/JCB | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 1; 2024-12-15: 1; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 1; 2025-01-08: 1; 2025-01-09: 1; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 1; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Ajax | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 1; 2024-12-24: 1; 2024-12-25: 1; 2024-12-26: 1; 2024-12-27: 1; 2024-12-28: 1; 2024-12-29: 1; 2024-12-30: 1; 2024-12-31: 1; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 1; 2025-01-04: 1; 2025-01-05: 1; 2025-01-06: 1; 2025-01-07: 1; 2025-01-08: 1; 2025-01-09: 1; 2025-01-10: 1; 2025-01-11: 1; 2025-01-12: 1; 2025-01-13: 1; 2025-01-14: 1; 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-02-19: 1; 2025-02-20: 1; 2025-02-21: 1; 2025-02-22: 1; 2025-02-23: 1; 2025-02-24: 1; 2025-02-25: 1; 2025-02-26: 1; 2025-02-27: 1; 2025-02-28: 1; 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
4 | Super Construction |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Auger/DTH | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 1; 2025-01-04: 1; 2025-01-05: 1; 2025-01-06: 1; 2025-01-07: 1; 2025-01-08: 1; 2025-01-09: 1; 2025-01-10: 1; 2025-01-11: 1; 2025-01-12: 1; 2025-01-13: 1; 2025-01-14: 1; 2025-01-15: 1; 2025-01-16: 1; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Ajax | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
5 | Paramhans Infra |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Auger/DTH | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 1; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-02-19: 1; 2025-02-20: 1; 2025-02-21: 1; 2025-02-22: 1; 2025-02-23: 1; 2025-02-24: 1; 2025-02-25: 1; 2025-02-26: 1; 2025-02-27: 1; 2025-02-28: 1; 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Ajax | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
6 | Seema Enterprises |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Auger/DTH | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Ajax | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
7 | KC Constructions |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Auger/DTH | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-02-19: 1; 2025-02-20: 1; 2025-02-21: 1; 2025-02-22: 1; 2025-02-23: 1; 2025-02-24: 1; 2025-02-25: 1; 2025-02-26: 1; 2025-02-27: 1; 2025-02-28: 1; 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Ajax | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
8 | SR Constructions |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Auger/DTH | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 1; 2025-01-19: 1; 2025-01-20: 1; 2025-01-21: 1; 2025-01-22: 1; 2025-01-23: 1; 2025-01-24: 1; 2025-01-25: 1; 2025-01-26: 1; 2025-01-27: 1; 2025-01-28: 1; 2025-01-29: 1; 2025-01-30: 1; 2025-01-31: 1; 2025-02-01: 1; 2025-02-02: 1; 2025-02-03: 1; 2025-02-04: 1; 2025-02-05: 1; 2025-02-06: 1; 2025-02-07: 1; 2025-02-08: 1; 2025-02-09: 1; 2025-02-10: 1; 2025-02-11: 1; 2025-02-12: 1; 2025-02-13: 1; 2025-02-14: 1; 2025-02-15: 1; 2025-02-16: 1; 2025-02-17: 1; 2025-02-18: 1; 2025-02-19: 1; 2025-02-20: 1; 2025-02-21: 1; 2025-02-22: 1; 2025-02-23: 1; 2025-02-24: 1; 2025-02-25: 1; 2025-02-26: 1; 2025-02-27: 1; 2025-02-28: 1; 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | Ajax | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2024-11-28: 0; 2024-11-29: 0; 2024-11-30: 0; 2024-12-01: 0; 2024-12-02: 0; 2024-12-03: 0; 2024-12-04: 0; 2024-12-05: 0; 2024-12-06: 0; 2024-12-07: 0; 2024-12-08: 0; 2024-12-09: 0; 2024-12-10: 0; 2024-12-11: 0; 2024-12-12: 0; 2024-12-13: 0; 2024-12-14: 0; 2024-12-15: 0; 2024-12-16: 0; 2024-12-17: 0; 2024-12-18: 0; 2024-12-19: 0; 2024-12-20: 0; 2024-12-21: 0; 2024-12-22: 0; 2024-12-23: 0; 2024-12-24: 0; 2024-12-25: 0; 2024-12-26: 0; 2024-12-27: 0; 2024-12-28: 0; 2024-12-29: 0; 2024-12-30: 0; 2024-12-31: 0; 2025-01-01: 0; 2025-01-02: 0; 2025-01-03: 0; 2025-01-04: 0; 2025-01-05: 0; 2025-01-06: 0; 2025-01-07: 0; 2025-01-08: 0; 2025-01-09: 0; 2025-01-10: 0; 2025-01-11: 0; 2025-01-12: 0; 2025-01-13: 0; 2025-01-14: 0; 2025-01-15: 0; 2025-01-16: 0; 2025-01-17: 0; 2025-01-18: 0; 2025-01-19: 0; 2025-01-20: 0; 2025-01-21: 0; 2025-01-22: 0; 2025-01-23: 0; 2025-01-24: 0; 2025-01-25: 0; 2025-01-26: 0; 2025-01-27: 0; 2025-01-28: 0; 2025-01-29: 0; 2025-01-30: 0; 2025-01-31: 0; 2025-02-01: 0; 2025-02-02: 0; 2025-02-03: 0; 2025-02-04: 0; 2025-02-05: 0; 2025-02-06: 0; 2025-02-07: 0; 2025-02-08: 0; 2025-02-09: 0; 2025-02-10: 0; 2025-02-11: 0; 2025-02-12: 0; 2025-02-13: 0; 2025-02-14: 0; 2025-02-15: 0; 2025-02-16: 0; 2025-02-17: 0; 2025-02-18: 0; 2025-02-19: 0; 2025-02-20: 0; 2025-02-21: 0; 2025-02-22: 0; 2025-02-23: 0; 2025-02-24: 0; 2025-02-25: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
9 | DS Constructions |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Auger/DTH | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 1; 2025-02-28: 1; 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Ajax | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
10 | NCC |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Auger/DTH | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 1; 2025-03-02: 1; 2025-03-03: 1; 2025-03-04: 1; 2025-03-05: 1; 2025-03-06: 1; 2025-03-07: 1; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Ajax | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
11 | Hartek |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Farhana | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 1; 2025-03-09: 1; 2025-03-10: 1; 2025-03-11: 1; 2025-03-12: 1; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 1; 2025-03-16: 1; 2025-03-17: 1; 2025-03-18: 1; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | JCB | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
12 | Sun Bright Infratech |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Auger/DTH | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | JCB | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
13 | JS Bhati Construction |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Auger/DTH | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 1; 2025-03-20: 1; 2025-03-21: 1; 2025-03-22: 1; 2025-03-23: 1; 2025-03-24: 1; 2025-03-25: 1; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | JCB | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
14 | Baba Ramdev contraction |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Auger/DTH | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 1; 2025-03-27: 1; 2025-03-28: 1; 2025-03-29: 1; 2025-03-30: 1; 2025-03-31: 1; 2025-04-01: 1; 2025-04-02: 1; 2025-04-03: 1; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1
|  |  | JCB | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
15 | Bajarang Electrical Work |  | Vehicle | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Farhana | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 0; 2025-04-05: 0; 2025-04-06: 0; 2025-04-07: 0; 2025-04-08: 0; 2025-04-09: 0; 2025-04-10: 0
|  |  | Crane | 2024-11-25: 0; 2024-11-26: 0; 2024-11-27: 0; 2025-02-26: 0; 2025-02-27: 0; 2025-02-28: 0; 2025-03-01: 0; 2025-03-02: 0; 2025-03-03: 0; 2025-03-04: 0; 2025-03-05: 0; 2025-03-06: 0; 2025-03-07: 0; 2025-03-08: 0; 2025-03-09: 0; 2025-03-10: 0; 2025-03-11: 0; 2025-03-12: 0; 2025-03-13: 0; 2025-03-14: 0; 2025-03-15: 0; 2025-03-16: 0; 2025-03-17: 0; 2025-03-18: 0; 2025-03-19: 0; 2025-03-20: 0; 2025-03-21: 0; 2025-03-22: 0; 2025-03-23: 0; 2025-03-24: 0; 2025-03-25: 0; 2025-03-26: 0; 2025-03-27: 0; 2025-03-28: 0; 2025-03-29: 0; 2025-03-30: 0; 2025-03-31: 0; 2025-04-01: 0; 2025-04-02: 0; 2025-04-03: 0; 2025-04-04: 1; 2025-04-05: 1; 2025-04-06: 1; 2025-04-07: 1; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1

## Resources Requirement
Resources Required vs Actual
Sr. No. | Vendor Name | Available | Required | Balance to catch up Progress | Current Update by Contractor
1 | Vendor 1 | 0 | 20 | 20
2 | Vendor 1 | 12 | 15 | 3
3 | Vendor 1 | 6 | 15 | 9
4 | Vendor 1 | 0 | 0 | 0
5 | Vendor 1 | 4 | 15 | 11 | Will be available once piling front allocated
6 | Vendor 1 | 6 | 15 | 9
7 | Vendor 1 | 0 | 10 | 10
8 | Vendor 1 | 11 | 18 | 7
9 | Vendor 1 | 5 | 10 | 5
10 | Vendor 1 | 0 | 10 | 10
11 | Vendor 1 | 0 | 13 | 13
12 | Vendor 1 | 0 | 9 | 9
13
Total |  | 44 | 150 | 106

## Hindrance
Work Hindrance Log
Start DATE | End Date | ISSUE | START TIME | END TIME | REMARKS
2024-11-26 | 2024-12-12 | Land clearance not given for piling construction | 09.00 am | 06.00 pm
2024-11-26 | 2024-12-12 | Bush cutting pending in demarcated land | 09.00 am | 06.00 pm
2024-11-23 | 2024-11-23 | Local farmers stopped unloading works | 09.00 am | 06.00 pm | Unloading work stopped for demand of unloading work
2024-11-24 | 2024-11-24 | Local farmers stopped unloading works | 09.00 am | 11.00 am | Unloading work stopped for demand of unloading work
2024-11-26 | 2024-11-26 | Local farmers stopped switchyard works | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-11-27 | 2024-11-27 | Local farmers stopped switchyard works | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-12-06 | 2024-12-06 | Local Farmers stopped work | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-12-07 | 2024-12-07 | Local Farmers stopped work | 09.00 am | 06.00 pm | work stopped for demand of unloading work
2024-12-07 | 2024-12-12 | Piling layout not received for demarcated land | 09.00 am | 06.00 pm | Piling work not started
2024-12-17 | 2024-12-18 | Security agency guards stopped the work | 09.00 am | 06.00 pm | Security guards and QRT people stopped the work
2024-12-20 | 2024-12-22 | HT Panel Drawing had design changes | 09.00 am | 06.00 pm | Design team made changes in design after releasing the foundation drwaing because of that work was on hold for 3 days
2024-12-21 | 2024-12-30 | Batching plant setup, ICR and Pilling work stoped by locals | 09.00 am | 06.00 pm | Locals has stop the work for the demand over batching plant setup
2024-12-29 | 2024-12-30 | Boundary wall work not started because of Rate disputes with locals | 09.00 am | 06.00 pm
2025-12-30 | 2025-01-06 | HT panel building Plinth beam/floor slab and roof beam/slab drawing not received. | 09.00 am | 06.00 pm | Bar bending team has no front for steel cutting
2025-01-09 | 2025-01-09 | Site work hampered due to demand of JCB hiring | 09.00 am | 05.00 pm | Manpower ideal due to ROW at site
2025-01-08 | 2025-01-10 | Piling work not started due to compansation issue to water storage tank | 09.00 am | 06.00 pm
2025-01-14 | 2025-01-15 | Piling and ICR work Stopped due to demand of JCB hiring for grading and levelling | 09.00 am | 06.00 pm
2025-01-20 | 2025-01-20 | Piling work hampered due to demand of water tank rate fixing | 09.00 am | 06.00 pm
2025-01-25 | 2025-01-27 | Piling work hampered due road work blocked by locals | 09.00 am | 06.00 pm
2025-02-27 | 2025-03-05 | Piling work hampered in s/y no 38,39,40,42,66,67 due to demarcation issue | 09.00 am | 06.00 pm
2025-03-01 | 2025-03-05 | Piling work hampered in s/y no 117 due to demarcation issue | 09.00 am | 06.00 pm
Formulas:
Start DATE = [Start DATE, row above]+1
End Date = [End Date, row above]+1