## Construction DASHBOARD
Daily Progress Report
Project Name | 300MW SECI Solar Project Ramagiri | [10 empty] | Week | Month
Project Capacity (in MWp) | 390 | [10 empty] | 2025-08-01 | 2025-08-01
Project Start Date | 2025-02-06 | [10 empty] | 2025-08-07 | 2025-08-31
Project Finish Date | 2026-02-05 | [8 empty] | Week Cycle | Month Cycle
Date | 2025-08-29 | [8 empty] | 2025-08-01 | 2025-08-01
[10 empty] | 2025-08-07 | 2025-08-31
Description | Scope | UoM | Completed | Balance | Weightage (in %) | Progress as per weightage (in %) | Actual Progress (in %) | Day- Actual | Today-Plan | Week- Actual | Month-Actual
Land Development
Site Levelling | 3.14 | Acre | 2.9 | 0.24 | 1% | 0.9236% | 92.36% | 0 |  | 0 | 0
Site Initials
PSS Boundry Coordinate Capturing and Layout Marking | 1 | Lot | 1 | 0 | 1% | 1% | 100% | 0 |  | 0 | 0
Countour Survey in PSS | 1 | Lot | 1 | 0 | 1% | 1% | 100% | 0 |  | 0 | 0
Soil Investigation for Back filling Purpose | 1 | Lot | 1 | 0 | 1% | 1% | 100% | 0 |  | 0 | 0
ERT Test | 1 | Lot | 1 | 0 | 1% | 1% | 100% | 0 |  | 0 | 0
Civil
Excavation & Casting for foundations for Towers | 18 | No's |  |  | 10%
Excavation & Foundations for Equipments | 183 | No's |  |  | 10%
Retaining wall construction | 150 | RMT |  |  | 2%
Power Transformer Foundation - 2 no's | 2 | No's |  |  | 2%
Grid earthing | 7.2 | km |  |  | 10%
Cable trench construction | 500 | Rmt
Drain Construction among PSS | 1124 | Rmt
Road work | 562 | Rmt
Micro leveling & Metal spreading | 14906 | Sq.M
Fencing Construction | 500 | Rmt
Electrical
Tower and Equipment Structure erection | 201 | No's |  |  | 2%
Equipment Erection | 183 | No's |  |  | 2%
Equipment Earthing | 1681 | Rmt |  |  | 4%
Transformer and Its Accessories Erection | 2 | No's |  |  | 1%
Cable Tray works | 1 | LS
HT&LT Cable laying and Termination | 1 | LS |  |  | 1%
Jumpering & Bus bar arrangement | 2 | No's |  |  | 2%
Field Equipment Testing | 1 | LS |  |  | 1%
Overall Scheme Checking | 1 | LS
Main Control Room
Control Room Marking & Excavation | 28 | nos. |  |  | 2%
PCC & Raft concrete upto Plinth Beam construction | 28 | nos. |  |  | 2%
Plinth Beam concreting | 205 | Rmt
Column raising upto lintel level(GF) | 28 | No's
Colum raising upto roof level | 28 | No's
Wall raising | 1 | LS
Roof Shuttering & Steel Placement | 1 | LS
Control Room Roof Concrete - Ground Floor | 427 | Sq.M
Control Room Inside cable Trench & duct | 60 | Rmt
Plastering work- inside & outside | 407 | Sq.M
Flooring work | 362 | Sq.M
Electrical, Plumbing works | 1 | LS
Painting , Door & Window Works | 1 | LS
Panel Erection | 1 | LS
Commissioning & HOTO
Pre-Commissioning | 1 | LS |  |  | 1%
Synchinization Approval | 1 | LS |  |  | 1%
Commissioning | 1 | LS |  |  | 1%
COD | 1 | LS |  |  | 1%
[5 empty] | 60% | 4.924%
| Scope | 60%
| Actual | 4.924%
| Balance | 55.08%
Formulas:
Week = [Week, row above]+6
Month Cycle = [Month Cycle, row above]+30

## Sheet1 (hidden)
Date | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14
No. of JCBs | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 |  |  | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 4 | 4 | 4 | 6 | 6 | 4 | 4 | 6 | 6 | 6 | 5 | 4 | 3 | 5 | 5 | 5 | 4 | 6 |  | 135
Bush Cutting | 1.5 | 3.5 | 4 | 4 | 4 | 4 | 3 | 2 | 0 | 0 | 20 | 20 | 25 | 26 | 40 | 40 | 40 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5 | 10 | 10 | 5 | 7 | 5 |  |  | 317 | 2.3481
Land Grading | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 10 | 10 | 12 | 13 | 10 | 12 | 11 | 20 | 14 | 16 | 16 | 10 | 10 | 5 | 7 | 5 |  |  | 87
Per Day Producticity | [38 empty] | 201 | 2.3103
Bush Cutting | 1.5 | 3.5 | 4 | 4 | 2 | 2 | 3 | 2 |  |  | 5 | 5 | 6.25 | 6.5 | 10 | 6.6667 | 6.6667 | 6.3333
Land Grading | [18 empty] | 1.6667 | 2.5 | 2.5 | 2.5 | 2 | 2.1667 | 2.5 | 3 | 1.8333 | 3.3333 | 2.3333 | 3.2 | 4 | 3.3333 | 2 | 1 | 1.4 | 1.25 | 0 | #DIV/0!
Manpower
Land Development | [25 empty] | 6 | 8 | 8 | 8 | 6 | 6 | 6 | 5 | 8 | 8 | 7 | 9
[28 empty] | Bushing |  | Balance | Remaining days | Per day requirement
[9 empty] | 250 | 47 | [17 empty] | 250 | 47 | 203 | 19 | 10.6842
Grading
[28 empty] | 250 | 121 | 129 | 19 | 6.7895

## Construction Status
| Date | 2025-08-29
Section | S.No | Site Activity | Planned Start | Planned Finish | No. of Days | Actual/ Expected Start | Actual/ Expected Finish | UoM | Qty | Start Date | Actual/ Expected Finish Date | No of Days | Avg/Day | Actual as on Date (%) | Comp. | Bal | Actual as on date | Till Last Month | time axis 2025-03-30 to 2025-06-30
 | time axis 2025-03-30 to 2025-06-30
L & G | 1 | Site Levelling ( Cutting Portion) | 2025-02-26 | 2025-03-28 | 30 | 2025-04-07 | 2025-08-01 | CuM | 10000 | 2025-04-07 | 2025-05-19 | 43 | 232.5581 | 100% | 10000 | 0 | 629 | 486 | 0 | 0 |  |  |  | 1.5 | 3.5 | 4 | 4 | 4 | 4 | 3 | 2 |  | 10 | 20 | 20 | 20 | 21 | 40 | 40 | 40 | 38 | [11 empty] | 5 | 10 | 10 | 10 | 5 | 7 | 5 | 0 | 0 | 7 | 0 | 17 | 19 | 24 | 9 | 12 | 0 | 16 | 0 | 0 | 0 | 0 | 6 | 16 | 15 | 18 | 14 | 16 | 15 | 14 | 18 | 14 | 15 | 10 | 11 | 16
| 2 | Site Levelling (Filling Portion) |  |  | 0 | 2025-04-07 | 2025-08-01 | CuM | 7000 | 2025-04-07 | 2025-05-19 | 43 | 162.7907 | 80.71% | 5650 | 1350 | 629 | 486 | 2025-04-25: 10; 2025-04-26: 10; 2025-04-27: 10; 2025-04-28: 10; 2025-04-29: 12; 2025-04-30: 13; 2025-05-01: 10; 2025-05-02: 12; 2025-05-03: 11; 2025-05-04: 20; 2025-05-05: 14; 2025-05-06: 16; 2025-05-07: 10; 2025-05-08: 6; 2025-05-09: 10; 2025-05-10: 5; 2025-05-11: 7; 2025-05-12: 5; 2025-05-13: 7; 2025-05-14: 7; 2025-05-15: 7; 2025-05-16: 12; 2025-05-17: 17; 2025-05-18: 19; 2025-05-19: 24; 2025-05-20: 9; 2025-05-21: 12; 2025-05-22: 18; 2025-05-23: 16; 2025-05-24: 15; 2025-05-25: 23; 2025-05-26: 22; 2025-05-27: 20; 2025-05-28: 18; 2025-05-29: 16; 2025-05-30: 15; 2025-05-31: 18; 2025-06-01: 14; 2025-06-02: 16; 2025-06-03: 15; 2025-06-04: 14; 2025-06-05: 18; 2025-06-06: 14; 2025-06-07: 15; 2025-06-08: 10; 2025-06-09: 11; 2025-06-10: 16
Site Initials | 3 | PSS Boundry Coordinate Capturing and Layout Marking | 2025-02-12 | 2025-02-21 | 9 | 2025-02-12 | 2025-02-21 | Lot. | 1 | 2025-02-12 | 2025-02-22 | 11 | 0.090909 | 100% | 1 | 0 | 1 | 1 | bar: 2025-03-30
| 4 | Countour Survey in PSS | 2025-02-23 | 2025-03-14 | 19 | 2025-02-23 | 2025-03-14 | Lot. | 1 | 2025-02-15 | 2025-03-14 | 28 | 0.035714 | 100% | 1 | 0 | 1 | 1 | bar: 2025-03-30
| 5 | Soil Investigation for Back filling Purpose | 2025-02-15 | 2025-04-15 | 59 | 2025-02-15 | 2025-04-29 | Lot. | 1 | 2025-02-23 | 2025-05-01 | 68 | 0.014706 | 100% | 1 | 0 | 1 | 1 | 2025-03-30: 52; 2025-04-03: 2; 2025-04-04: 2; 2025-04-05: 2; 2025-04-06: 2; 2025-04-07: 2; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1; 2025-04-11: 1; 2025-04-12: 1; 2025-04-13: 1; 2025-04-15: 1; 2025-04-16: 1; 2025-04-19: 1; 2025-04-20: 1; 2025-04-21: 1; 2025-04-22: 1; 2025-04-23: 1; 2025-04-26: 1; 2025-04-27: 1; 2025-04-28: 1; 2025-04-29: 1
| 6 | ERT Test | 2025-04-02 | 2025-04-13 | 11 | 2025-04-06 | 2025-04-10 | Lot. | 1 | 2025-04-06 | 2025-04-10 | 5 | 0.2 | 100% | 1 | 0 | 1 | 1 | 2025-03-30: 0; 2025-04-03: 0; 2025-04-06: 4; 2025-04-07: 8; 2025-04-08: 8; 2025-04-09: 10; 2025-04-10: 6
Civil Works | 7 | Excavation & foundations for Tower | 2025-04-02 | 2025-05-02 | 30 | 2025-04-02 | 2025-11-10 | No's | 18 |  |  |  | - | 100% | 2 | 16 | 0 | 0
| 8 | Excavation & foundations for Equipments | 2025-05-04 | 2025-06-03 | 30 | 2025-05-04 | 2025-06-03 | No's |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 9 | Retaining wall construction | 2025-07-10 | 2025-08-19 | 40 | 2025-07-10 | 2025-08-19 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 10 | Power Transformer Foundation - 2 no's | 2025-05-16 | 2025-06-30 | 45 | 2025-05-16 | 2025-06-30 | No's |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 11 | Grid earthing | 2025-06-10 | 2025-07-10 | 30 | 2025-06-10 | 2025-07-10 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 12 | Cable trench construction | 2025-06-05 | 2025-08-04 | 60 | 2025-06-05 | 2025-08-04 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 13 | Drain Construction among PSS | 2025-08-11 | 2025-09-10 | 30 | 2025-08-11 | 2025-09-10 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 14 | Road work | 2025-11-11 | 2025-12-11 | 30 | 2025-11-11 | 2025-12-11 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 15 | Micro leveling & Metal spreading | 2025-11-26 | 2026-01-05 | 40 | 2025-11-26 | 2026-01-05 | SqM |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 16 | Fencing Construction | 2025-11-21 | 2025-12-16 | 25 | 2025-11-21 | 2025-12-16 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
Electrical Works | 17 | Tower erection | 2025-06-29 | 2025-07-29 | 30 | 2025-06-29 | 2025-07-29 | No's |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 18 | Equipment Erection | 2025-08-28 | 2025-10-12 | 45 | 2025-08-28 | 2025-10-12 | No's |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 19 | Equipment Earthing | 2025-09-27 | 2025-10-22 | 25 | 2025-09-27 | 2025-10-22 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 20 | Transformer and Its Accessories Erection | 2025-08-28 | 2025-09-22 | 25 | 2025-08-28 | 2025-09-22 | No's |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 21 | Cable Tray works | 2025-08-04 | 2025-09-03 | 30 | 2025-08-04 | 2025-09-03 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 22 | Cable laying and Termination | 2025-09-03 | 2025-11-02 | 60 | 2025-09-03 | 2025-11-02 | KM |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 23 | Bus bar Formation/arrangement | 2025-08-03 | 2025-09-02 |  | 2025-08-03 | 2025-09-02 | Lot |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 26 | Switchyard Lighting | 2025-09-03 | 2025-09-15 |  | 2025-09-03 | 2025-09-15 | Lot
Main Control Room Civil Works | 27 | Control Room Marking & Excavation | 2025-04-02 | 2025-04-05 | 3 | 2025-04-02 | 2025-04-05 | No's | 28 |  |  |  | - | 100% | 28 | 0 | 0 | 0
| 28 | MCR Footing | 2025-04-05 | 2025-04-08 | 3 | 2025-04-05 | 2025-04-08 | No's | 28 |  |  |  | - | 100% | 28 | 0 | 0 | 0
| 29 | MCR Column upto Plinth Beam | 2025-04-13 | 2025-04-28 | 15 | 2025-04-13 | 2025-04-28 | No's | 28 |  |  |  | - | 100% | 28 | 0 | 0 | 0
| 30 | Plinth Beam | 2025-04-30 | 2025-05-06 | 6 | 2025-06-11 | 2025-06-17 | Lot. |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 31 | Cable Trench | 2025-05-11 | 2025-05-18 | 7 | 2025-06-12 | 2025-08-02 | Mtrs |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 32 | Column 2nd Lift | 2025-05-08 | 2025-05-11 | 3 | 2025-06-25 | 2025-08-05 | No's |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 33 | Lintel Beams | 2025-05-16 | 2025-05-26 | 10 | 2025-06-30 | 2025-08-08 | Lot. |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 34 | Roof Beam | 2025-06-05 | 2025-06-25 | 20 | 2025-06-05 | 2025-06-25 | Lot. |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 35 | Slab | 2025-07-05 | 2025-07-15 | 10 | 2025-07-05 | 2025-07-15 | Lot. |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 36 | Brick Works | 2025-08-09 | 2025-08-24 | 15 | 2025-08-09 | 2025-08-24 | Lot. |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 37 | Internal Plastering | 2025-08-19 | 2025-09-08 | 20 | 2025-08-19 | 2025-09-08 | Lot. |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 38 | Outer Plastering | 2025-08-29 | 2025-09-13 | 15 | 2025-08-29 | 2025-09-13 | Lot. |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 39 | Internal Paint Works | 2025-09-23 | 2025-10-03 |  | 2025-09-23 | 2025-10-03 | Lot.
| 40 | Outer Painting Works | 2025-09-28 | 2025-10-08 |  | 2025-09-28 | 2025-10-08 | Lot.
| 41 | MCR Miscillaneous Works | 2025-10-18 | 2025-11-01 |  | 2025-10-18 | 2025-11-01 | Lot.
| 42 | MCR Finishing Works | 2025-11-01 | 2025-11-11 |  | 2025-11-01 | 2025-11-11 | Lot.
MCR Electrical Works | 43 | HT Panel installation | 2025-10-20 | 2025-11-15 | 26 | 2025-10-20 | 2025-11-15 | Lot |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 44 | Aux. trf installation | 2025-09-19 | 2025-10-29 | 40 | 2025-09-19 | 2025-10-29 | Lot |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 45 | DB's installation | 2025-10-05 | 2025-11-10 | 36 | 2025-10-05 | 2025-11-10 | Lot |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 46 | UPS, Battery charger, battery bank installaiton | 2025-12-05 | 2026-01-05 | 31 | 2025-12-05 | 2026-01-05 | Lot |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 47 | HT cable laying from MCR to Power Trafo | 2026-01-02 | 2026-01-20 | 18 | 2026-01-02 | 2026-01-20 | Lot |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 48 | HT cable laying from HT panel to Aux. trf | 2025-12-25 | 2026-01-02 | 8 | 2025-12-25 | 2026-01-02 | Lot |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 49 | Aux t/f to LT | 2025-12-20 | 2025-12-28 | 8 | 2025-12-20 | 2025-12-28 | Lot |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 50 | SCADA installation | 2025-12-28 | 2026-01-05 | 8 | 2025-12-28 | 2026-01-05 | Lot |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 51 | Tray Works | 2025-12-25 | 2026-01-05 | 11 | 2025-12-25 | 2026-01-05 | Lot |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 52 | Equipment earthing | 2025-12-26 | 2025-12-28 |  | 2025-12-26 | 2025-12-28 | Lot |  |  |  |  | - | - | 0 | 0 | 0 | 0
ISTS Substation Civil Works |  | Area Grading | 2025-02-26 | 2025-03-28 |  | 2025-02-26 | 2025-03-28
| 53 | Excavation for foundations for Tower & Equipments | 2025-04-02 | 2025-04-12 |  | 2025-04-02 | 2025-04-12
| 54 | Foundations for Tower | 2025-04-17 | 2025-05-17 |  | 2025-04-17 | 2025-05-17
|  | Foundations for Equipments | 2025-05-19 | 2025-06-18 |  | 2025-05-19 | 2025-06-18
| 55 | Grid earthing | 2025-04-19 | 2025-05-19 |  | 2025-04-19 | 2025-05-19
| 56 | Cable trench construction | 2025-06-20 | 2025-08-19 |  | 2025-06-20 | 2025-08-19
| 57 | Micro leveling & Metal spreading | 2025-09-20 | 2025-11-04 |  | 2025-09-20 | 2025-11-04
ISTS Substation Electrical Works | 58 | Tower and Equipment Structure erection | 2025-07-08 | 2025-08-07 |  | 2025-07-08 | 2025-08-07
| 59 | Equipment Erection | 2025-08-17 | 2025-09-01 |  | 2025-08-17 | 2025-09-01
| 60 | Equipment Earthing | 2025-08-25 | 2025-09-09 |  | 2025-08-25 | 2025-09-09
| 61 | Cable Tray works | 2025-08-19 | 2025-09-18 |  | 2025-08-19 | 2025-09-18
| 62 | Cable laying and Termination | 2025-10-18 | 2025-11-17 |  | 2025-10-18 | 2025-11-17
| 63 | Jumpering & Bus bar arrangement | 2026-01-26 | 2026-02-02 |  | 2026-01-26 | 2026-02-02
| 64 | Field Equipment Testing | 2025-12-02 | 2025-12-22 |  | 2025-12-02 | 2025-12-22
| 65 | Overall Scheme Checking | 2025-12-27 | 2026-01-21 |  | 2025-12-27 | 2026-01-21
ISTS SPR Works | 66 | SPR Marking & Excavation | 2025-04-12 | 2025-04-15 |  | 2025-04-12 | 2025-04-15
| 67 | SPR Footing | 2025-04-17 | 2025-04-22 |  | 2025-04-17 | 2025-04-22
| 68 | SPR Column upto Plinth Beam | 2025-04-27 | 2025-05-02 |  | 2025-04-27 | 2025-05-02
| 69 | Plinth Beam | 2025-05-04 | 2025-05-09 |  | 2025-05-04 | 2025-05-09
| 70 | Cable Trench | 2025-05-09 | 2025-05-24 |  | 2025-05-09 | 2025-05-24
| 71 | Column 2nd Lift | 2025-05-05 | 2025-05-10 |  | 2025-05-05 | 2025-05-10
| 72 | Lintel Beams | 2025-05-15 | 2025-05-25 |  | 2025-05-15 | 2025-05-25
| 73 | Roof Beam | 2025-05-28 | 2025-06-05 |  | 2025-05-28 | 2025-06-05
| 74 | Slab | 2025-06-15 | 2025-06-25 |  | 2025-06-15 | 2025-06-25
| 75 | Brick Works | 2025-07-25 | 2025-08-04 |  | 2025-07-25 | 2025-08-04
| 76 | Internal Plastering | 2025-08-10 | 2025-08-20 |  | 2025-08-10 | 2025-08-20
| 77 | Panel Erection | 2025-08-25 | 2025-08-28 |  | 2025-08-25 | 2025-08-28
| 78 | Outer Plastering | 2025-08-20 | 2025-08-28 |  | 2025-08-20 | 2025-08-28
| 79 | Internal Paint Works | 2025-08-27 | 2025-09-01 |  | 2025-08-27 | 2025-09-01
| 80 | Outer Painting Works | 2025-09-01 | 2025-09-08 |  | 2025-09-01 | 2025-09-08
| 81 | SPR Miscillaneous Works | 2025-09-12 | 2025-09-27 |  | 2025-09-12 | 2025-09-27
| 82 | SPR Finishing Works | 2025-09-29 | 2025-10-09 |  | 2025-09-29 | 2025-10-09
EHV line works | 83 | Check Survey & Tower Spotting | 2025-04-02 | 2025-09-29 |  | 2025-04-02 | 2025-09-29
| 84 | ROW Clearances | 2026-01-28 | 2026-09-25 |  | 2026-01-28 | 2026-09-25
| 85 | Tower Foundations | 2025-06-15 | 2026-02-10 |  | 2025-06-15 | 2026-02-10
| 86 | Tower Earthing | 2025-06-15 | 2026-02-10 |  | 2025-06-15 | 2026-02-10
| 87 | Tower Erection | 2025-08-25 | 2025-11-23 |  | 2025-08-25 | 2025-11-23
| 88 | Stringing | 2025-11-23 | 2026-01-22 |  | 2025-11-23 | 2026-01-22
| 89 | OPGW Stringing | 2025-11-30 | 2025-12-28 |  | 2025-11-30 | 2025-12-28
| 90 | Accessories Fitting | 2025-12-30 | 2026-01-29 |  | 2025-12-30 | 2026-01-29
Testing and Commissioning | 91 | Pre-commissioning of Field Equipment | 2025-11-25 | 2025-12-25 | 30 | 2025-11-25 | 2025-12-25 | Block |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 92 | Power Transformers & Aux T/F Testing | 2025-11-27 | 2025-12-16 | 19 | 2025-11-27 | 2025-12-16 | Block |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 93 | Power Cable Testing | 2025-11-17 | 2025-11-23 | 6 | 2025-11-17 | 2025-11-23 | Block |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 94 | Functional Checking of Equipments | 2025-12-06 | 2026-01-06 | 31 | 2025-12-06 | 2026-01-06 | Block |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 95 | CEA Approval | 2025-12-20 | 2026-01-18 | 29 | 2025-12-20 | 2026-01-18 | % |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 96 | Synchronization Approval | 2025-12-21 | 2026-01-09 | 19 | 2025-12-21 | 2026-01-09 | % |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 97 | Commissioning | 2026-01-10 | 2026-01-25 | 15 | 2026-01-10 | 2026-01-25 | % |  |  |  |  | - | - | 0 | 0 | 0 | 0
| 98 | COD | 2026-01-26 | 2026-02-05 | 10 | 2026-01-26 | 2026-02-05 | % |  |  |  |  | - | - | 0 | 0 | 0 | 0

## Manpower (hidden)
Project Name : | 300MW SECI RAMAGIRI PROJECT
Project Size : | 300MW AC Capacity & 390 Mwp DC Capacity
Date of Report: | 2025-02-14
S No. | Contractor Name | Resources Category | Manpower Description | 2025-02-14 | Cum. Nos | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31 | 2026-01-01 | 2026-01-02 | 2026-01-03 | 2026-01-04 | 2026-01-05 | 2026-01-06 | 2026-01-07 | 2026-01-08 | 2026-01-09 | 2026-01-10 | 2026-01-11 | 2026-01-12 | 2026-01-13 | 2026-01-14 | 2026-01-15 | 2026-01-16 | 2026-01-17 | 2026-01-18 | 2026-01-19 | 2026-01-20 | 2026-01-21 | 2026-01-22 | 2026-01-23 | 2026-01-24 | 2026-01-25
|  |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 |  |  | Staff | 0 | 0
2 |  | Surveying | Suveryor | 0
3 |  |  | Suveryor | 0 | 0
4 |  | Surveying | Suveryor | 0 | 0
5 |  |  | Suveryor | 0 | 0
6 |  | Security | Security | 1 | 0
7 |  | Grading | Engineers / Supervisors | 0 | 0
8 |  |  | Workers - Skilled | 0 | 0
9 |  |  | Workers - Unskilled | 0 | 0
10 |  | Piling | Engineers / Supervisors | 0 | 0
11 |  |  | Workers - Skilled | 0 | 0
12 |  |  | Workers - Unskilled | 0 | 0
13 |  | Grading | Engineers / Supervisors | 0 | 0
14 |  |  | Workers - Skilled | 0 | 0
15 |  |  | Workers - Unskilled | 0 | 0
16 |  | Piling | Engineers / Supervisors | 0 | 0
17 |  |  | Workers - Skilled | 0 | 0
18 |  |  | Workers - Unskilled | 0 | 0
19 |  | Grading | Engineers / Supervisors | 0 | 0
20 |  |  | Workers - Skilled | 0 | 0
21 |  |  | Workers - Unskilled | 0 | 0
22 |  | Piling | Engineers / Supervisors | 0 | 0
23 |  |  | Workers - Skilled | 0 | 0
24 |  |  | Workers - Unskilled | 0 | 0
25 |  | Grading | Engineers / Supervisors | 0 | 0
26 |  |  | Workers - Skilled | 0 | 0
27 |  |  | Workers - Unskilled | 0 | 0
28 |  | Piling | Engineers / Supervisors | 0 | 0
29 |  |  | Workers - Skilled | 0 | 0
30 |  |  | Workers - Unskilled | 0 | 0
31 |  | Grading | Engineers / Supervisors | 0 | 0
32 |  |  | Workers - Skilled | 0 | 0
33 |  |  | Workers - Unskilled | 0 | 0
34 |  | Piling | Engineers / Supervisors | 0 | 0
35 |  |  | Workers - Skilled | 0 | 0
36 |  |  | Workers - Unskilled | 0 | 0
37 |  | Grading | Engineers / Supervisors | 0 | 0
38 |  |  | Workers - Skilled | 0 | 0
39 |  |  | Workers - Unskilled | 0 | 0
40 |  | Piling | Engineers / Supervisors | 0 | 0
41 |  |  | Workers - Skilled | 0 | 0
42 |  |  | Workers - Unskilled | 0 | 0
43 |  | ICR Works | ICR Engineers / Supervisors | 0 | 0
44 |  |  | ICR Workers - Skilled | 0 | 0
45 |  |  | ICR Workers - Unskilled | 0 | 0
46 |  | MCR Works | Engineers / Supervisors | 0 | 0
47 |  |  | Skilled worker | 0 | 0
48 |  |  | Unskilled worker | 0 | 0
49 |  | DC Works | Engineers / Supervisors | 0 | 0
50 |  |  | DC Technician | 0 | 0
51 |  |  | DC worker - skilled | 0 | 0
52 |  |  | DC worker - unskilled | 0 | 0
53 |  |  | Structure Team | 0 | 0
54 |  |  | safety engineer | 0 | 0
55 |  | DC Works | Engineers / Supervisors | 0 | 0
56 |  |  | DC Technician | 0 | 0
57 |  |  | DC worker - skilled | 0 | 0
58 |  |  | DC worker - unskilled | 0 | 0
59 |  |  | Structure Team | 0 | 0
60 |  |  | safety engineer | 0 | 0
61 |  |  | Engineers / Supervisors | 0 | 0
62 |  |  | DC Technician | 0 | 0
63 |  |  | DC worker - skilled | 0 | 0
64 |  |  | DC worker - unskilled | 0 | 0
65 |  |  | Structure Team | 0 | 0
66 |  |  | safety engineer | 0 | 0
67 |  |  | Engineers / Supervisors | 0 | 0
68 |  |  | DC Technician | 0 | 0
69 |  |  | DC worker - skilled | 0 | 0
70 |  |  | DC worker - unskilled | 0 | 0
71 |  |  | Structure Team | 0 | 0
72 |  |  | safety engineer | 0 | 0
73 |  |  | Engineers / Supervisors | 0 | 0
74 |  |  | DC Technician | 0 | 0
75 |  |  | DC worker - skilled | 0 | 0
76 |  |  | DC worker - unskilled | 0 | 0
77 |  |  | Structure Team | 0 | 0
78 |  |  | safety engineer | 0 | 0
79 |  |  | Engineers / Supervisors | 0 | 0
80 |  |  | DC Technician | 0 | 0
81 |  |  | DC worker - skilled | 0 | 0
82 |  |  | DC worker - unskilled | 0 | 0
83 |  |  | Structure Team | 0 | 0
84 |  |  | safety engineer | 0 | 0
85 |  |  | Engineers / Supervisors | 0 | 0
86 |  |  | DC Technician | 0 | 0
87 |  |  | DC worker - skilled | 0 | 0
88 |  |  | DC worker - unskilled | 0 | 0
89 |  |  | Structure Team | 0 | 0
90 |  |  | safety engineer | 0 | 0
91 |  |  | Engineers / Supervisors | 0 | 0
92 |  |  | DC Technician | 0 | 0
93 |  |  | DC worker - skilled | 0 | 0
94 |  |  | DC worker - unskilled | 0 | 0
95 |  |  | Structure Team | 0 | 0
96 |  |  | safety engineer | 0 | 0
97 |  |  | Engineers / Supervisors | 0 | 0
98 |  |  | DC Technician | 0 | 0
99 |  |  | DC worker - skilled | 0 | 0
100 |  |  | DC worker - unskilled | 0 | 0
101 |  |  | Structure Team | 0 | 0
102 |  |  | safety engineer | 0 | 0
103 |  |  | Engineers / Supervisors | 0 | 0
104 |  |  | DC Technician | 0 | 0
105 |  |  | DC worker - skilled | 0 | 0
106 |  |  | DC worker - unskilled | 0 | 0
107 |  |  | Structure Team | 0 | 0
108 |  |  | safety engineer | 0 | 0
109 |  |  | Engineers / Supervisors | 0 | 0
110 |  |  | DC Technician | 0 | 0
111 |  |  | DC worker - skilled | 0 | 0
112 |  |  | DC worker - unskilled | 0 | 0
113 |  |  | Structure Team | 0
114 |  |  | safety engineer | 0
115 |  |  | Engineers / Supervisors | 0
116 |  |  | DC Technician | 0
117 |  |  | DC worker - skilled | 0
118 |  |  | DC worker - unskilled | 0
119 |  |  | Structure Team | 0
120 |  |  | safety engineer | 0
121 |  |  | Engineers / Supervisors | 0 | 0
122 |  |  | Technician | 0 | 0
123 |  |  | worker - unskilled | 0 | 0
124 |  |  | safety engineer | 0 | 0
125 |  |  | Engineers / Supervisors | 0 | 0
126 |  |  | Technician | 0 | 0
127 |  |  | worker - unskilled | 0 | 0
128 |  |  | Engineers / Supervisors | 0 | 0
129 |  |  | Technician | 0 | 0
130 |  |  | worker - unskilled | 0 | 0
131 |  |  | Engineers / Supervisors | 0 | 0
132 |  |  | Technician | 0 | 0
133 |  |  | worker - unskilled | 0 | 0

## Machinery (hidden)
Project Name : | 300MW SECI RAMAGIRI PROJECT
Project Size : | 300MW AC Capacity & 390 Mwp DC Capacity
Date of Report: | 2025-02-15
S No. | Contractor Name | Resources Category | Resources Description | 2025-02-15 | Cum. Nos | 2025-02-15 | 2025-02-16 | 2025-02-17 | 2025-02-18 | 2025-02-19 | 2025-02-20 | 2025-02-21 | 2025-02-22 | 2025-02-23 | 2025-02-24 | 2025-02-25 | 2025-02-26 | 2025-02-27 | 2025-02-28 | 2025-03-01 | 2025-03-02 | 2025-03-03 | 2025-03-04 | 2025-03-05 | 2025-03-06 | 2025-03-07 | 2025-03-08 | 2025-03-09 | 2025-03-10 | 2025-03-11 | 2025-03-12 | 2025-03-13 | 2025-03-14 | 2025-03-15 | 2025-03-16 | 2025-03-17 | 2025-03-18 | 2025-03-19 | 2025-03-20 | 2025-03-21 | 2025-03-22 | 2025-03-23 | 2025-03-24 | 2025-03-25 | 2025-03-26 | 2025-03-27 | 2025-03-28 | 2025-03-29 | 2025-03-30 | 2025-03-31 | 2025-04-01 | 2025-04-02 | 2025-04-03 | 2025-04-04 | 2025-04-05 | 2025-04-06 | 2025-04-07 | 2025-04-08 | 2025-04-09 | 2025-04-10 | 2025-04-11 | 2025-04-12 | 2025-04-13 | 2025-04-14 | 2025-04-15 | 2025-04-16 | 2025-04-17 | 2025-04-18 | 2025-04-19 | 2025-04-20 | 2025-04-21 | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-25 | 2025-04-26 | 2025-04-27 | 2025-04-28 | 2025-04-29 | 2025-04-30 | 2025-05-01 | 2025-05-02 | 2025-05-03 | 2025-05-04 | 2025-05-05 | 2025-05-06 | 2025-05-07 | 2025-05-08 | 2025-05-09 | 2025-05-10 | 2025-05-11 | 2025-05-12 | 2025-05-13 | 2025-05-14 | 2025-05-15 | 2025-05-16 | 2025-05-17 | 2025-05-18 | 2025-05-19 | 2025-05-20 | 2025-05-21 | 2025-05-22 | 2025-05-23 | 2025-05-24 | 2025-05-25 | 2025-05-26 | 2025-05-27 | 2025-05-28 | 2025-05-29 | 2025-05-30 | 2025-05-31 | 2025-06-01 | 2025-06-02 | 2025-06-03 | 2025-06-04 | 2025-06-05 | 2025-06-06 | 2025-06-07 | 2025-06-08 | 2025-06-09 | 2025-06-10 | 2025-06-11 | 2025-06-12 | 2025-06-13 | 2025-06-14 | 2025-06-15 | 2025-06-16 | 2025-06-17 | 2025-06-18 | 2025-06-19 | 2025-06-20 | 2025-06-21 | 2025-06-22 | 2025-06-23 | 2025-06-24 | 2025-06-25 | 2025-06-26 | 2025-06-27 | 2025-06-28 | 2025-06-29 | 2025-06-30 | 2025-07-01 | 2025-07-02 | 2025-07-03 | 2025-07-04 | 2025-07-05 | 2025-07-06 | 2025-07-07 | 2025-07-08 | 2025-07-09 | 2025-07-10 | 2025-07-11 | 2025-07-12 | 2025-07-13 | 2025-07-14 | 2025-07-15 | 2025-07-16 | 2025-07-17 | 2025-07-18 | 2025-07-19 | 2025-07-20 | 2025-07-21 | 2025-07-22 | 2025-07-23 | 2025-07-24 | 2025-07-25 | 2025-07-26 | 2025-07-27 | 2025-07-28 | 2025-07-29 | 2025-07-30 | 2025-07-31 | 2025-08-01 | 2025-08-02 | 2025-08-03 | 2025-08-04 | 2025-08-05 | 2025-08-06 | 2025-08-07 | 2025-08-08 | 2025-08-09 | 2025-08-10 | 2025-08-11 | 2025-08-12 | 2025-08-13 | 2025-08-14 | 2025-08-15 | 2025-08-16 | 2025-08-17 | 2025-08-18 | 2025-08-19 | 2025-08-20 | 2025-08-21 | 2025-08-22 | 2025-08-23 | 2025-08-24 | 2025-08-25 | 2025-08-26 | 2025-08-27 | 2025-08-28 | 2025-08-29 | 2025-08-30 | 2025-08-31 | 2025-09-01 | 2025-09-02 | 2025-09-03 | 2025-09-04 | 2025-09-05 | 2025-09-06 | 2025-09-07 | 2025-09-08 | 2025-09-09 | 2025-09-10 | 2025-09-11 | 2025-09-12 | 2025-09-13 | 2025-09-14 | 2025-09-15 | 2025-09-16 | 2025-09-17 | 2025-09-18 | 2025-09-19 | 2025-09-20 | 2025-09-21 | 2025-09-22 | 2025-09-23 | 2025-09-24 | 2025-09-25 | 2025-09-26 | 2025-09-27 | 2025-09-28 | 2025-09-29 | 2025-09-30 | 2025-10-01 | 2025-10-02 | 2025-10-03 | 2025-10-04 | 2025-10-05 | 2025-10-06 | 2025-10-07 | 2025-10-08 | 2025-10-09 | 2025-10-10 | 2025-10-11 | 2025-10-12 | 2025-10-13 | 2025-10-14 | 2025-10-15 | 2025-10-16 | 2025-10-17 | 2025-10-18 | 2025-10-19 | 2025-10-20 | 2025-10-21 | 2025-10-22 | 2025-10-23 | 2025-10-24 | 2025-10-25 | 2025-10-26 | 2025-10-27 | 2025-10-28 | 2025-10-29 | 2025-10-30 | 2025-10-31 | 2025-11-01 | 2025-11-02 | 2025-11-03 | 2025-11-04 | 2025-11-05 | 2025-11-06 | 2025-11-07 | 2025-11-08 | 2025-11-09 | 2025-11-10 | 2025-11-11 | 2025-11-12 | 2025-11-13 | 2025-11-14 | 2025-11-15 | 2025-11-16 | 2025-11-17 | 2025-11-18 | 2025-11-19 | 2025-11-20 | 2025-11-21 | 2025-11-22 | 2025-11-23 | 2025-11-24 | 2025-11-25 | 2025-11-26 | 2025-11-27 | 2025-11-28 | 2025-11-29 | 2025-11-30 | 2025-12-01 | 2025-12-02 | 2025-12-03 | 2025-12-04 | 2025-12-05 | 2025-12-06 | 2025-12-07 | 2025-12-08 | 2025-12-09 | 2025-12-10 | 2025-12-11 | 2025-12-12 | 2025-12-13 | 2025-12-14 | 2025-12-15 | 2025-12-16 | 2025-12-17 | 2025-12-18 | 2025-12-19 | 2025-12-20 | 2025-12-21 | 2025-12-22 | 2025-12-23 | 2025-12-24 | 2025-12-25 | 2025-12-26 | 2025-12-27 | 2025-12-28 | 2025-12-29 | 2025-12-30 | 2025-12-31
|  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | PR Construction |  | JCB |  | 58 | [51 empty] | 1 | 1 | 1 | 1 | 2 | 2 | 1 | 1 |  |  | 4 | 4 | 4 | 4 | 4 | 6 | 6 | 6 | 6 | 4
2 |  |  | Tractor |  | 0
3 |  |  | Farana |  | 0
2 |  |  | Hire Vehicle | 0 | 0
3 | Boundary wall works |  | Manual Loading Transit mixer |  | 0
4 |  |  | Tractor mounted auger |  | 0
5 |  |  | Tractor with trolly |  | 0
6 |  |  | Water tanker |  | 0
7 |  |  | Pickup |  | 0
13 | Bush cleaning |  | JCB |  | 0
14 |  |  | Tractor with trolly |  | 0
18 | Internal Road works |  | JCB / Grader |  | 0
19 |  |  | Tractor Trolley |  | 0
20 |  |  | Roller |  | 0
21 |  |  | Dumper |  | 0
22 |  |  | Water tanker |  | 0
23 | Approach Road works |  | JCB / Grader |  | 0
24 |  |  | Tractor Trolley |  | 0
25 |  |  | Roller |  | 0
26 |  |  | DG |  | 0
27 |  |  | Water tanker |  | 0
33 | Piling |  | DTH |  | 0
34 |  |  | Tractor Augur |  | 0
35 |  |  | Water tanker |  | 0
36 |  |  | Tractor with trolly |  | 0
37 |  |  | JCB |  | 0
38 |  |  | DG |  | 0
77 | ICR Building |  | Total Station |  | 0
78 |  |  | Tractor with trolly |  | 0
79 |  |  | Water tanker |  | 0
80 |  |  | Tractor mounted auger |  | 0
68 | MCR CIVIL |  | Tractor mounted auger |  | 0
69 |  |  | Water tanker |  | 0
70 |  |  | Tractor with trolly |  | 0
71 |  |  | JCB |  | 0
72 |  |  | DG |  | 0
102 | DC Works |  | Tractor with trolly |  | 0
103 |  |  | Water tanker |  | 0
104 |  |  | DG |  | 0
105 |  |  | Camber |  | 0
106 |  |  | JCB |  | 0

## Ordering
SECI - RAMAGIRI STATUS - 01.07.2025
S.No | Item description | Order Status | Vendor | Drawings Submission Status | Drawings Submission Date | No of Days | Drawings Approval | MFC Status | Remarks |  |  |  |  | Delivery Dates
Substation
1 | 160 MVA Power Transformer | Closed | T & R | Submitted | 2025-05-12 | 110 | Under Approval |  | LOA issued on 1st Apr'25 | 7-8 months from date of MFC
2 | CRP & SAS | Closed | Hitachi | Pending |  |  |  |  | LOA Issued on 29th Mar'25 Inputs required from Engineering | 3-4 months from date of MFC
3 | PLCC | Closed | Hitachi | Pending |  |  |  |  | LOA Issued on 29th Mar'25 Inputs sent to supplier on 16.06.25 | 3-4 months from date of MFC
4 | Circuit Breaker | Closed | Siemens | Submitted | 2025-05-22 | 100 | Under Approval |  | LOA issued on 1st May'25 | 7-8 months from date of MFC
5 | a) Structures | Closed | Sawaria | Pending |  |  |  |  | LOA issued on 30 Apr'25 Tower schedule to be sent to supplier | 4-6 Weeks from date of MFC |  |  |  | Sep 2nd Week
| b) Foundation Bolts | Closed | Maheswari | Pending |  |  |  |  | LOA issued on 30th May'25 Ref Drawings yet to receive from engineering team | Inspection done
6 | Wave Trap | Closed | Quality Power | Submitted | 2025-06-05 | 86 | Under Approval |  | LOA issued on 30th May'25 | 6-7 months from date of MFC
7 | FOTE | Closed | Kalven/Tejas | Submitted | 2025-06-16 | 75 | Under Approval |  | LOA issued on 30th May'25 | 16 Weeks from date of MFC
8 | BPI | Closed | IEC | Submitted | 2025-06-17 | 74 | Under Approval |  | LOA issued on 22nd May'25 | In the month of Oct and Nov'25
9 | Isolator | Closed | GR Power | Submitted | 2025-06-25 | 66 |  |  | LOA issued on 04th Jun'25 (Revised LOA to be sent to supplier, due to spec got revised) | 10-12 Weeks from date of MFC |  |  |  | Sep End
10 | LA/SA | Closed | Lamco | Submitted | 2025-06-25 | 66 |  |  | LOA issued on 11th Jun'25 | 4-6 Weeks from date of MFC |  |  |  | SEP 1st week
11 | a) CT & PT | Closed | Heptacare | Pending |  |  |  |  | LOA issued on 16.06.25 | 6 months from date of MFC
| b) CVT | Closed | CG Power | Submitted | 2025-06-26 | 65 |  |  | LOA issued on 06.06.25 | 5-6 months from date of MFC
12 | Long Rod Insulators | Closed | Legion Insulators | Pending |  |  |  |  | LOA issued on 26.06.25 | 12-18 Weeks from date of MFC |  |  |  | Sep 2nd week
13 | ACSR MOOSE CONDUCTOR | [12 empty] | Sep 2nd week
14 | 500kVA Auxiliary Transformer | Underprocess | [6 empty] | Enquiry sent, awaiting offers |  |  |  |  | Sep 2nd week
15 | HARDWARE | Open | [11 empty] | Sep 2nd week
16 | Battery & Battery Charger & UPS | Open
17 | Auxiliary AC & DC System Marshalling Box | Open
18 | ABT Metering panel | Open
19 | Cables | Open
20 | Earthing Material | Open | [11 empty] | Aug End
21 | 160 KVA DG Set | Open
22 | 4" ALUMINUM IPS TUBE | Open
23 | Lightning Protection of Switchyard
24 | Lugs & Glands
25 | Cable Trays
26 | Yard Lighting
27 | Safety items
28 | Fire Fighting
29 | MISCELLANEOUS ITEMS
30 | Visual Monitoring System (VMS)
Bay
1 | CRP & SAS | Closed | Hitachi | Pending |  |  |  |  | LOA Issued on 29th Mar'25 Inputs required from Engineering | 3-4 months from date of MFC
2 | PLCC | Closed | Hitachi | Pending |  |  |  |  | LOA Issued on 29th Mar'25 Inputs sent to supplier on 16.06.25 | 3-4 months from date of MFC
3 | a) Structures | Closed | Sawaria | Pending |  |  |  |  | LOA issued on 30 Apr'25 Tower schedule to be sent to supplier | 4-6 Weeks from date of MFC |  |  |  | Sep 2nd week
| (b) Pipe Type Structures | Underprocess | [6 empty] | Enquiry sent |  |  |  |  | Sep 2nd week
| (c) Foundation Bolts | Closed | AV Forgings | Pending |  |  |  |  | LOA issued on 30th May'25 | 30 days from date of MFC
4 | Circuit Breaker | Closed | Siemens | Submitted | 2025-05-22 | 100 | Under Approval |  | LOA issued on 1st May'25
5 | Wave Trap | Closed | Quality Power | Submitted | 2025-06-05 | 86 | Under Approval |  | LOA issued on 30th May'25 | 6-7 months from date of MFC
6 | FOTE | Closed | Kalven/Tejas | Submitted | 2025-06-16 | 75 | Under Approval |  | LOA issued on 30th May'25 | 16 Weeks from date of MFC
7 | BPI | Closed | IEC | Submitted | 2025-06-17 | 74 | Under Approval |  | LOA issued on 22nd May'25 | In the month of Oct and Nov'25
8 | Isolator | Closed | GR Power | Submitted | 2025-06-25 | 66 |  |  | LOA issued on 04th Jun'25 (Revised LOA to be sent to supplier, due to spec got revised) | 10-12 Weeks from date of MFC |  |  |  | Sep End
9 | LA/SA | Closed | Lamco | Submitted | 2025-06-25 | 66 |  |  | LOA issued on 11th Jun'25 | 4-6 Weeks from date of MFC |  |  |  | Sep End
10 | CT & PT | Closed | Heptacare | Pending |  |  |  |  | LOA issued on 16.06.25 | 6 months from date of MFC
| CVT | Closed | CG Power | Pending | 2025-06-26 | 65 |  |  | LOA issued on 06.06.25 | 5-6 months from date of MFC
11 | Long Rod Insulators | Closed | Legion Insulators | Pending |  |  |  |  | LOA issued on 26.06.25 |  |  |  |  | Sep End
12 | ACSR MOOSE CONDUCTOR | [12 empty] | Sep End
13 | Hardware | [12 empty] | Sep End
14 | Battery & Battery Charger & UPS
15 | Auxiliary AC & DC System Marshalling Box
16 | Outdoor type ABT Metering panel
17 | Cables
18 | Earthing Materials for complete Switch yard | [12 empty] | Aug End
19 | 4" ALUMINUM IPS TUBE
20 | Lightning Protection
21 | Lugs & Glands
22 | Cable Trays
23 | Yard Lighting
24 | Safety items
25 | Fire Fighting
26 | MISCELLANEOUS ITEMS
Line | [10 empty] | Stubs | 1st Lot | 2nd Lot
1 | (a) Structures | Closed | Sawaria | Pending |  |  |  |  | LOA issued on 30 Apr'25 Tower schedule to be sent to supplier | 4-6 Weeks from date of MFC | 10th July | Aug 4th week | Sep 3rd Week
| (b) Template | Open
2 | 24F OPGW | Closed | Sterlite | Submitted | 19.06.25 |  |  |  | LOA issued on 21.05.25 MQP Pending | 4-5 Weeks from date of MFC |  |  | Sep 3rd Week
3 | SRC Insulator | Closed | Legion Insulators | Pending |  |  |  |  | LOA issued on 26.06.25 |  |  |  | Sep 3rd Week
4 | HTLS Conductors | Closed | Sterlite | Submitted | 01.07.25 |  |  |  | LOA issued on 30.06.25 | 6 months from date of MFC
5 | Tower accessories | [11 empty] | Sep 3rd Week
6 | Hardware | [11 empty] | Sep 3rd Week
Formulas:
No of Days = TODAY()-[Drawings Submission Date]

## Preliminary Activity
# | Contract Signing & Key Preliminary Activities | Planned | Actual/ Expected | Status
1 | Project Start Date | 2025-02-06 | 2025-02-06
2 | Contract Agreement Signing | 2025-02-10 | 2025-02-10 | Completed
3 | Kick Off meeting_SECI HO | 2025-02-10 | 2025-02-10 | Completed
4 | PBG Submission | 2025-03-05 | 2025-03-05 | Completed
5 | ABG Submission | 2025-03-14 | 2025-03-14 | Completed
6 | Boundary Coordinates Capturing | 2025-02-21 | 2025-02-21 | Completed
7 | Labor License related documents (Form 2, Form 5) | 2025-03-17 | 2025-03-17 | Completed
8 | Labor License | 2025-04-11 | 2025-04-02 | Completed
9 | Customer GST commercial registration & Address (Billing & Delivery) Details | 2025-04-07 | 2025-05-16 | Completed
10 | ERT Test | 2025-04-13 | 2025-04-10 | Completed
# | Site Establishment | Planned | Actual/ Expected | Status
1 | Area development | 2025-04-13 | 2025-04-05 | wip
2 | Construction Power arrangement | 2025-04-20 | 2025-04-20 | Completed
3 | Set up of Water source for the Construction activity | 2025-04-27 | 2025-06-15 | WIP
4 | Set up of Worker Accomodation | 2025-04-27 | 2025-06-15 | Completed
5 | Set up of material storage | 2025-04-17 | 2025-06-15 | Completed

## MDL
MDL SUMMARY - 300MW SECI PV | [13 empty] | 2025-08-30 | [5 empty] | 2025-08-30
Sl.No. | Discipline | Discipline | Document Title | Document Number | Approval Catogery | Planned Submission Date (EPCC) | Submitted/Expected Submission | Other drawing linked | Tentative approval date- linked docs. | Revision | Submission Date | Response date | CLIENT Comments / Approval(CAT-I,CAT-II CAT-III & CAT-IV) | No.of Days Reviwed by SECI | No.of Days Reviwed by ARIPL | Approved date | Submission/Review By | Approved Category | Status | Days taken for review/re-submission
1 | General | 220/33kV Ramagiri Substation Civil Drawings | Overall Civil Foundation Layout | SECI-RG300-PA-CIV-301 | Approval | 2025-06-24 |  |  |  |  | 45698
2 |  | 220/33kV Ramagiri Substation Civil Drawings | 160 MVA, 220/33-33kV Power Transformer Foundation Drawing | SECI-RG300-PA-CIV-302 | Approval | 2025-06-28 |  |  |  |  | 45700 | 45700 |  | 0 | 2
3 |  | 220/33kV Ramagiri Substation Civil Drawings | 220 kV SF6 Circuit Breaker Foundation Drawing | SECI-RG300-PA-CIV-317 | Approval | 2025-06-16 |  |  |  |  | 45702 | 45705 |  | 3 | 2
4 |  | 220/33kV Ramagiri Substation Civil Drawings | 220 kV Isolator Foundation Drawing | SECI-RG300-PA-CIV-318 | Approval | 2025-06-16 | 2025-05-16 |  |  |  | 45707
5 | General | 220/33kV Ramagiri Substation Civil Drawings | 220 kV Current Transformer -Foundation Drawing | SECI-RG300-PA-CIV-319 | Approval | 2025-06-16 | 2025-05-16 |  |  |  | 45740 | 45743 | CAT -IV R | 3 | 6 | 45755
6 |  | 220/33kV Ramagiri Substation Civil Drawings | 220 kV Metering Current Transformer Foundation Drawing | SECI-RG300-PA-CIV-320 | Approval | 2025-06-16 | 2025-05-16 |  |  |  | 45749 | 45755 | CAT -IV | 6
7 | General | 220/33kV Ramagiri Substation Civil Drawings | 220 kV CVT/Potential Transformer Foundation Drawing | SECI-RG300-PA-CIV-321 | Approval | 2025-06-16 | 2025-05-16
8 | General | 220/33kV Ramagiri Substation Civil Drawings | 220 kV Metering Potential Transformer Foundation Drawing | SECI-RG300-PA-CIV-322 | Approval | 2025-06-16 | 2025-05-16 |  |  |  | 2025-04-21 | 2025-04-29 | CAT -IV R | 8 |  | 2025-04-29
9 | General | 220/33kV Ramagiri Substation Civil Drawings | 220 kV Lightning Arrestor Foundation Drawing | SECI-RG300-PA-CIV-323 | Approval | 2025-06-16 | 2025-05-16
10 | General | 220/33kV Ramagiri Substation Civil Drawings | 220kV Bus Post insulator Foundation Drawing | SECI-RG300-PA-CIV-324 | Approval | 2025-06-16 | 2025-05-16
11 | General | 220/33kV Ramagiri Substation Civil Drawings | Wave Trap Foundation Drawing | SECI-RG300-PA-CIV-325 | Approval | 2025-06-16 | 2025-05-16 |  |  |  | 2025-03-26 | 2025-04-04 | CAT - II | 9 | 0
12 |  | 220/33kV Ramagiri Substation Civil Drawings | 220kV Gantry Tower Foundation Drawing | SECI-RG300-PA-CIV-326 | Approval | 2025-06-16 | 2025-05-16 |  |  |  | 2025-04-04 |  |  | 148
13 | General | 220/33kV Ramagiri Substation Civil Drawings | Light Mast Tower Foundation Drawing | SECI-RG300-PA-CIV-327 | Approval | 2025-06-16 | 2025-05-16 |  |  |  | 2025-04-25 |  |  | 127
14 | General | 220kV Bay Extension Civil Drawings at 400/220kV at PGCIL Substation | Overall Civil Foundation Layout | SECI-RG300-PA-CIV-401 | Approval
15 | General | 220kV Bay Extension Civil Drawings at 400/220kV at PGCIL Substation | 220kV Bay Layout & Details of Cable Trench & Road crossing culvert | SECI-RG300-PA-CIV-402 | Approval | [5 empty] | 2025-04-25 | 2025-05-01 | CAT -IV R | 6
16 | General | 220kV Bay Extension Civil Drawings at 400/220kV at PGCIL Substation | Metering box panel foundation drawing | SECI-RG300-PA-CIV-403 | Approval | [5 empty] | 2025-04-22 | 2025-04-24 | CAT - III | 2 | 6 | 2025-05-16
17 |  | 220kV Bay Extension Civil Drawings at 400/220kV at PGCIL Substation | BMK Foundation Drawing | SECI-RG300-PA-CIV-404 | Approval | [5 empty] | 2025-04-30 | 2025-05-01 | CAT - II | 1 | 8
18 |  | 220kV Bay Extension Civil Drawings at 400/220kV at PGCIL Substation | 220 kV SF6 Circuit Breaker Foundation Drawing | SECI-RG300-PA-CIV-405 | Approval | [5 empty] | 2025-05-09 | 2025-05-16 | CAT - I | 7
19 | General | 220kV Bay Extension Civil Drawings at 400/220kV at PGCIL Substation | 220 kV Equipment Support Structure Foundation Drawing | SECI-RG300-PA-CIV-406 | Approval
20 | General | 220kV Bay Extension Civil Drawings at 400/220kV at PGCIL Substation | Wave Trap Foundation Drawing | SECI-RG300-PA-CIV-407 | Approval
21 | General | 220kV Transmission Line Civil Drawings | 220kV Transmission Line Tower Foundations For DA | SECI-RG300-PA-CIV-501 | Approval | 2025-06-18
22 | Civil | 220kV Transmission Line Civil Drawings | 220kV Transmission Line Tower Foundations For DB | SECI-RG300-PA-CIV-502 | Approval | 2025-06-18 | 2025-03-11 |  |  |  | 2025-03-11 | 2025-03-20 | CAT - III | 9 | 19
23 |  | 220kV Transmission Line Civil Drawings | 220kV Transmission Line Tower Foundations For DC | SECI-RG300-PA-CIV-503 | Approval | 2025-06-18 |  |  |  |  | 2025-04-08 | 2025-04-11 | CAT - II | 3 | 47
24 |  | 220kV Transmission Line Civil Drawings | 220kV Transmission Line Tower Foundations For DD | SECI-RG300-PA-CIV-504 | Approval | 2025-06-18 |  |  |  |  | 2025-05-28 | 2025-06-02 | CAT - I | 5
25 | Civil | 220kV Transmission Line Civil Drawings | 220kV Transmission Line Tower Foundations For Gantry | SECI-RG300-PA-CIV-505 | Approval | 2025-06-18 | 2025-06-03 |  |  |  | 2025-06-03 | 2025-06-10 | CAT - III | 88
26 | Civil | 220/33kV Ramagiri Substation Erection Drawings | Substation Single line diagram | SECI-RG300-PA-ELE-001 | Approval | 2025-04-06 | 2025-04-04 |  |  |  | 2025-05-09 |  |  | 113
27 | Civil | 220/33kV Ramagiri Substation Erection Drawings | Protection SLD | SECI-RG300-PA-ELE-002 | Approval | 2025-04-06 | 2025-05-07 |  |  |  | 2025-03-11 | 2025-03-20 | CAT - II | 9 | 19 | 2025-05-07
28 |  | 220/33kV Ramagiri Substation Erection Drawings | 220/33kV SS Electrical layout (Plan & Section) | SECI-RG300-PA-ELE-003 | Approval | 2025-04-06 | 2025-04-07 |  |  |  | 2025-04-08 | 2025-04-11 | CAT - I | 3 | 25
29 |  | 220/33kV Ramagiri Substation Erection Drawings | 220/33kV SS Earthmat Design Calculation | SECI-RG300-PA-ELE-004 | Approval | 2025-05-15 | 2025-05-10 |  |  |  | 2025-05-06 | 2025-05-07 | CAT - I | 1 | 21
30 |  | 220/33kV Ramagiri Substation Erection Drawings | 220/33kV SS Earthmat layout | SECI-RG300-PA-ELE-005 | Approval | 2025-05-15 | 2025-05-25 |  |  |  | 2025-05-28 | 2025-05-30 | CAT - II | 2
31 | Civil | 220/33kV Ramagiri Substation Erection Drawings | 220/33kV SS Equipment Earthing | SECI-RG300-PA-ELE-006 | Approval | 2025-05-15 | 2025-05-12 |  |  |  | 2025-06-03 | 2025-06-10 | CAT - III | 88
32 | Civil | 220/33kV Ramagiri Substation Erection Drawings | 220/33kV EKD Plan & section View Layout | SECI-RG300-PA-ELE-007 | Information | 2025-05-15 | 2025-05-17 |  |  |  | 2025-03-11 | 2025-03-20 | CAT - III | 9 | 19 | 2025-04-11
33 |  | 220/33kV Ramagiri Substation Erection Drawings | 220/33kV SS DSLP Design Calculation | SECI-RG300-PA-ELE-008 | Approval | 2025-05-15 | 2025-05-20 |  |  |  | 2025-04-08 | 2025-04-11 | CAT - I | 3
34 | Civil | 220/33kV Ramagiri Substation Erection Drawings | 220/33kV SS DSLP Layout | SECI-RG300-PA-ELE-009 | Approval | 2025-05-15 | 2025-05-21 |  |  |  | 2025-04-22 | 2025-05-02 | CAT -IV | 10 | 3 | 2025-05-02
35 |  | 220/33kV Ramagiri Substation Erection Drawings | 220/33kV SS Outdoor Cable Trench layout | SECI-RG300-PA-ELE-010 | Approval | 2025-06-16 | 2025-06-02 |  |  |  | 2025-05-05 | 2025-05-07 | CAT -IV | 2 | 21
36 |  | 220/33kV Ramagiri Substation Erection Drawings | Power and control cable schedule | SECI-RG300-PA-ELE-011 | Information | 2025-06-16 | 2025-06-26 |  |  |  | 2025-05-28 | 2025-05-30 | CAT -IV | 2
37 | Civil | 220/33kV Ramagiri Substation Erection Drawings | Outdoor Illumination Design | SECI-RG300-PA-ELE-012 | Approval | 2025-06-16 | 2025-06-25 |  |  |  | 2025-06-03 | 2025-06-10 | CAT -IV R | 88
38 | Civil | 220/33kV Ramagiri Substation Erection Drawings | Outdoor Illumination Layout | SECI-RG300-PA-ELE-013 | Approval | 2025-06-16 | 2025-06-28
39 | Civil | 220/33kV Ramagiri Substation Erection Drawings | Single Line Diagram - AC & DC Auxiliary Supply & Distribution | SECI-RG300-PA-ELE-014 | Approval | 2025-05-15 | 2025-06-17 |  |  |  | 2025-04-16 | 2025-05-07 | CAT - III | 21 | 7
40 |  | 220/33kV Ramagiri Substation Erection Drawings | Auxillary Transformer Sizing | SECI-RG300-PA-ELE-015 | Approval | 2025-06-16 | 2025-06-21 |  |  |  | 2025-05-14 |  |  | 108
41 | Civil | 220/33kV Ramagiri Substation Erection Drawings | DG Set Sizing | SECI-RG300-PA-ELE-016 | Approval | 2025-06-16 | 2025-06-24 | MCR Architecture dwg.
42 | Civil | 220/33kV Ramagiri Substation Erection Drawings | Battery and Charger Sizing | SECI-RG300-PA-ELE-017 | Approval | 2025-06-16 | 2025-06-29
43 | Civil | 220/33kV Ramagiri Substation Erection Drawings | Relay Coordination Scheme | SECI-RG300-PA-ELE-018 | Approval | 2025-06-16 | 2025-08-04
44 | Civil | 220/33kV Ramagiri Substation Erection Drawings | SAG & Short circuit force calculation | SECI-RG300-PA-ELE-019 | Approval | 2025-06-16 | 2025-06-14
45 | Civil | 220/33kV Ramagiri Substation Erection Drawings | Conductor sizing | SECI-RG300-PA-ELE-020 | Approval | 2025-06-16 | 2025-05-28
46 | Civil | 220/33kV Ramagiri Substation Erection Drawings | IPS Tube Sizing | SECI-RG300-PA-ELE-021 | Approval | 2025-06-16 | 2025-05-28
47 | Civil | 220/33kV Ramagiri Substation Erection Drawings | 33KV Cable sizing | SECI-RG300-PA-ELE-022 | Approval | 2025-06-16 | 2025-05-28
48 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay Single line diagram | SECI-RG300-PA-ELE-101 | Approval
49 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay Protection SLD | SECI-RG300-PA-ELE-102 | Approval
50 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay Electrical Layout (Plan & Section) | SECI-RG300-PA-ELE-103 | Approval
51 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay Earthmat Design Calculation | SECI-RG300-PA-ELE-104 | Approval
52 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay Earthmat layout | SECI-RG300-PA-ELE-105 | Approval
53 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay Equipment Earthing | SECI-RG300-PA-ELE-106 | Approval
54 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV EKD Plan & section View Layout | SECI-RG300-PA-ELE-107 | Information
55 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay DSLP Design Calculation | SECI-RG300-PA-ELE-108 | Approval
56 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay DSLP Layout | SECI-RG300-PA-ELE-109 | Approval
57 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay Outdoor Cable Trench layout | SECI-RG300-PA-ELE-110 | Approval
58 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay Power and control cable schedule | SECI-RG300-PA-ELE-111 | Information | [5 empty] | 2025-05-22 | 2025-05-23 | CAT -IV R | 1 | 15
59 |  | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay Outdoor Illumination Design | SECI-RG300-PA-ELE-112 | Approval | [5 empty] | 2025-06-07 |  |  | 84
60 | Civil | 220kV Bay Extension at 400/220kV at PGCIL Substation Erection Drawings | 220kV Bay Outdoor Illumination Layout | SECI-RG300-PA-ELE-113 | Approval | [5 empty] | 2025-03-03 | 2025-03-05 | CAT - III | 2 | 15 | 45800
61 |  | 220kV Transmission Line Erection Drawings | Route Survey & Tower spotting data | SECI-RG300-PA-ELE-201 | Approval | [5 empty] | 2025-03-20 | 2025-03-22 | CAT - I | 2 | 61
62 |  | 220kV Transmission Line Erection Drawings | Stringing Chart | SECI-RG300-PA-ELE-202 | Approval | [5 empty] | 2025-05-22 | 2025-05-23 | CAT - I | 1
63 | Civil | 220kV Transmission Line Erection Drawings | Line Profile | SECI-RG300-PA-ELE-203 | Approval
64 | Civil | 220kV Transmission Line Erection Drawings | Earthing drawing | SECI-RG300-PA-ELE-204 | Approval
65 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220 kV SF6 Circuit Breaker (GTP & Drawings) | SECI-RG300-PA-ELE-301 | Approval | 2025-05-30 | 2025-06-01
66 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220 kV Isolator (GTP & Drawings) | SECI-RG300-PA-ELE-302 | Approval | 2025-05-30 | 2025-06-03
67 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220 kV Current Transformer -(GTP & Drawings) | SECI-RG300-PA-ELE-303 | Approval | 2025-05-30 | 2025-06-03
68 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220 kV Current Transformer -metering (GTP & Drawings) | SECI-RG300-PA-ELE-304 | Approval | 2025-05-30 | 2025-06-03
69 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220 kV CVT/Potential Transformer (GTP & Drawings) | SECI-RG300-PA-ELE-305 | Approval | 2025-05-30 | 2025-06-03
70 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220 kV Metering Potential Transformer (GTP & Drawings) | SECI-RG300-PA-ELE-306 | Approval | 2025-05-30 | 2025-06-03
71 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220 kV Lightning Arrestor (GTP & Drawings) | SECI-RG300-PA-ELE-307 | Approval | 2025-05-30 | 2025-06-03
72 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220kV Bus Post insulator (GTP & Drawings) | SECI-RG300-PA-ELE-308 | Approval | 2025-05-30 | 2025-06-03
73 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | Station transformer (GTP & Drawings) | SECI-RG300-PA-ELE-309 | Approval | 2025-05-30 | 2025-06-12
74 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220 kV Control & relay panels (GTP & Drawings) | SECI-RG300-PA-ELE-310 | Approval | 2025-05-30 | 2025-06-27
75 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | Substation automation system (SAS) (GTP & Drawings) | SECI-RG300-PA-ELE-311 | Approval | 2025-05-30 | 2025-06-27
76 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220V battery set (GTP & Drawings) | SECI-RG300-PA-ELE-312 | Approval | 2025-05-30 | 2025-07-01
77 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220V battery charger (GTP & Drawings) | SECI-RG300-PA-ELE-313 | Approval | 2025-05-30 | 2025-07-01
78 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 48V battery set (GTP & Drawings) | SECI-RG300-PA-ELE-314 | Approval | 2025-05-30 | 2025-07-01
79 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 48V battery charger (GTP & Drawings) | SECI-RG300-PA-ELE-315 | Approval | 2025-05-30 | 2025-07-01
80 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | DG set with amf panel (GTP & Drawings) | SECI-RG300-PA-ELE-316 | Approval | 2025-05-30 | 2025-07-15
81 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | AL-59 Moose CONDUCTOR (GTP & Drawings) | SECI-RG300-PA-ELE-317 | Approval | 2025-05-30 | 2025-07-15
82 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | IPS tube (GTP & Drawings) | SECI-RG300-PA-ELE-318 | Approval | 2025-05-30 | 2025-07-15
83 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 220 kV SRC Insulators (GTP & Drawings) | SECI-RG300-PA-ELE-319 | Approval | 2025-05-30 | 2025-07-15
84 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | Clamps & Connectors (GTP & Drawings) | SECI-RG300-PA-ELE-320 | Information | 2025-05-30 | 2025-07-15
85 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | BMK,CT & PT Junction boxes (GTP & Drawings) | SECI-RG300-PA-ELE-321 | Information | 2025-05-30 | 2025-07-22
86 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | Metering box panel as per PGCIL standard | SECI-RG300-PA-ELE-322 | Approval | 2025-05-30
87 | Civil | 220/33kV Ramagiri Substation Equipment Drawings | 1.1kV power & control cables (GTP & Drawings) | SECI-RG300-PA-ELE-323 | Information | 2025-05-30
88 | Electrical | 220/33kV Ramagiri Substation Equipment Drawings | Cable tray (GTP & Drawings) | SECI-RG300-PA-ELE-324 | Information | 2025-05-30 |  |  |  |  | 2025-02-26 | 2025-03-05 | CAT - III | 7 | 33
89 |  | 220/33kV Ramagiri Substation Equipment Drawings | Lighting materials (GTP & Drawings) | SECI-RG300-PA-ELE-325 | Approval | 2025-05-30 |  |  |  |  | 2025-04-07 | 2025-04-16 | CAT - III | 9 | 4
90 |  | 220/33kV Ramagiri Substation Equipment Drawings | Earth wire (GTP & Drawings) | SECI-RG300-PA-ELE-326 | Information | 2025-05-30 |  |  |  |  | 2025-04-20 | 2025-04-23 | CAT - II | 3 | 1
91 |  | 220/33kV Ramagiri Substation Equipment Drawings | Earth wire accessories (GTP & Drawings) | SECI-RG300-PA-ELE-327 | Information | 2025-05-30 |  |  |  |  | 2025-04-24 |  |  | 128
92 | Electrical | 220/33kV Ramagiri Substation Equipment Drawings | ACDB (GTP & Drawings) | SECI-RG300-PA-ELE-328 | Approval | 2025-05-30 | 2025-07-22 |  |  |  | 2025-04-25 | 2025-05-13 | CAT - III | 18 | 3
93 |  | 220/33kV Ramagiri Substation Equipment Drawings | 220V DCDB (GTP & Drawings) | SECI-RG300-PA-ELE-329 | Approval | 2025-05-30 | 2025-07-22 |  |  |  | 2025-05-16 |  |  | 106
94 | Electrical | 220/33kV Ramagiri Substation Equipment Drawings | PLCC & Equipment (GTP & Drawings) | SECI-RG300-PA-ELE-330 | Approval | 2025-05-30 | 2025-06-09 |  |  |  | 2025-05-13 |  |  | 109
95 | Electrical | 220/33kV Ramagiri Substation Equipment Drawings | FOTE Equipment (GTP & Drawings) | SECI-RG300-PA-ELE-331 | Approval | 2025-05-30 | 2025-06-27 |  | 45821 |  | 2025-04-11 | 2025-04-19 | CAT - III | 8 | 27
96 |  | 220/33kV Ramagiri Substation Equipment Drawings | PMU & Accessories (GTP & Drawings) | SECI-RG300-PA-ELE-332 | Approval | 2025-05-30 | 2025-06-27 |  |  |  | 2025-05-16 | 2025-05-31 | CAT - III | 106
97 | Electrical | 220/33kV Ramagiri Substation Equipment Drawings | Fire fighting accessories & others | SECI-RG300-PA-ELE-333 | Information | 2025-05-30 | 2025-08-07 | Overall layout | 45821
98 | Electrical | 220/33kV Ramagiri Substation Equipment Drawings | Wave Trap (GTP & Drawings) | SECI-RG300-PA-ELE-334 | Approval | 2025-05-30 | 2025-06-12 | Overall layout | 45821
99 | Electrical | 220/33kV Ramagiri Substation Equipment Drawings | Visual Monitoring System | SECI-RG300-PA-ELE-335 | Approval | 2025-05-30 | 2025-08-18 | Overall layout | 45821
100 | Electrical | 220/33kV Ramagiri Substation Equipment Drawings | Power Transformer (GTP & Drawings) | SECI-RG300-PA-ELE-336 | Approval | 2025-05-30 | 2025-05-10 | Overall layout | 45821
101 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | 220 kV SF6 Circuit Breaker (GTP & Drawings) | SECI-RG300-PA-ELE-401 | Approval | 2025-05-30 |  |  | 45804 |  | 2025-05-27 | 2025-06-04 | CAT - III | 8 | 87
102 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | 220 kV Isolator (GTP & Drawings) | SECI-RG300-PA-ELE-402 | Approval | 2025-05-30 |  |  |  |  | 2025-05-23 |  |  | 99
103 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | 220 kV Current Transformer -(GTP & Drawings) | SECI-RG300-PA-ELE-403 | Approval | 2025-05-30 |  | ICR Equipment layout/ AC Earthing calculation | 45814
104 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | 220 kV Current Transformer -metering (GTP & Drawings) | SECI-RG300-PA-ELE-404 | Approval | 2025-05-30 |  | ICR Equipment layout | 45814
105 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | 220 kV CVT/Potential Transformer (GTP & Drawings) | SECI-RG300-PA-ELE-405 | Approval | 2025-05-30 |  | ICR Equipment layout | 45814
106 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | 220 kV Metering Potential Transformer (GTP & Drawings) | SECI-RG300-PA-ELE-406 | Approval | 2025-05-30
107 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | 220 kV Lightning Arrestor (GTP & Drawings) | SECI-RG300-PA-ELE-407 | Approval | 2025-05-30
108 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | 220kV Bus Post insulator (GTP & Drawings) | SECI-RG300-PA-ELE-408 | Approval | 2025-05-30 |  | GA GTP- SCADA | 45828
109 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | 220 kV Control & relay panels (GTP & Drawings) | SECI-RG300-PA-ELE-409 | Approval | 2025-05-30 |  | GA GTP- SCADA | 45828
110 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | Substation automation system (SAS) (GTP & Drawings) | SECI-RG300-PA-ELE-410 | Approval | 2025-05-30 |  |  | 45835
111 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | AL-59 Moose CONDUCTOR (GTP & Drawings) | SECI-RG300-PA-ELE-411 | Approval | 2025-05-30 |  |  | 45838
112 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | IPS tube (GTP & Drawings) | SECI-RG300-PA-ELE-412 | Approval | 2025-05-30 |  |  | 45850
113 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | 220 kV SRC Insulators (GTP & Drawings) | SECI-RG300-PA-ELE-413 | Approval | 2025-05-30 |  |  | 45852
114 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | Clamps & Connectors (GTP & Drawings) | SECI-RG300-PA-ELE-414 | Information | 2025-05-30 |  |  | 45853
115 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | BMK,CT & PT Junction boxes (GTP & Drawings) | SECI-RG300-PA-ELE-415 | Information | 2025-05-30 |  |  | 45854
116 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | Metering box panel as per PGCIL standard | SECI-RG300-PA-ELE-416 | Approval | 2025-05-30 |  |  | 2025-07-22
117 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | 1.1kV power & control cables (GTP & Drawings) | SECI-RG300-PA-ELE-417 | Information | 2025-05-30 |  |  | 2025-07-28
118 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | Cable tray (GTP & Drawings) | SECI-RG300-PA-ELE-418 | Information | 2025-05-30 |  |  |  |  | 2025-02-26 |  |  | 185
119 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | Lighting materials (GTP & Drawings) | SECI-RG300-PA-ELE-419 | Approval | 2025-05-30 |  |  | 2025-08-08
120 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | Earth wire (GTP & Drawings) | SECI-RG300-PA-ELE-420 | Information | 2025-05-30 |  |  | 2025-11-26
121 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | Earth wire accessories (GTP & Drawings) | SECI-RG300-PA-ELE-421 | Information | 2025-05-30 |  |  |  |  | 2025-04-26 | 2025-04-30 | CAT - III | 4 | 14
122 |  | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | Lightning Mast (GTP & Drawings) | SECI-RG300-PA-ELE-422 | Approval | 2025-05-30 |  |  |  |  | 2025-05-14 | 2025-06-04 | CAT - I | 21
123 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | PLCC & Equipment (GTP & Drawings) | SECI-RG300-PA-ELE-423 | Approval | 2025-05-30 |  |  |  |  | 2025-05-14 | 2025-06-01 | CAT - III | 18 | 3
124 |  | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | FOTE Equipment (GTP & Drawings) | SECI-RG300-PA-ELE-424 | Approval | 2025-05-30 |  |  |  |  | 2025-06-04 |  |  | 87
125 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | PMU & Accessories (GTP & Drawings) | SECI-RG300-PA-ELE-425 | Approval | 2025-05-30 |  |  | 2025-06-20
126 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | Fire fighting accessories & others | SECI-RG300-PA-ELE-426 | Information | 2025-05-30 |  |  | 2025-06-20
127 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | Wave Trap (GTP & Drawings) | SECI-RG300-PA-ELE-427 | Approval | 2025-05-30 |  |  | 2025-06-23
128 | Electrical | 220kV Bay Extension at 400/220kV at PGCIL Substation Equipment Drawings | Visual Monitoring System | SECI-RG300-PA-ELE-428 | Approval | 2025-05-30 |  |  | 2025-06-21
129 | Electrical | 220kV Transmission Line Equipment Drawings | Conductor | SECI-RG300-PA-ELE-501 | Approval | 2025-05-30 | 2025-06-05 |  |  |  | 2025-05-15 | 2025-06-05 | CAT - III | 107 |  | 2025-06-05
130 |  | 220kV Transmission Line Equipment Drawings | OPGW Conductor | SECI-RG300-PA-ELE-502 | Approval | 2025-05-30 | 2025-06-05 |  |  |  | 2025-06-05
131 | Electrical | 220kV Transmission Line Equipment Drawings | Insulator Hardware | SECI-RG300-PA-ELE-503 | Information | 2025-05-30 | 2025-06-15 |  |  |  | 2025-05-14 |  |  | 108
132 | Electrical | 220kV Transmission Line Equipment Drawings | Earthing Set | SECI-RG300-PA-ELE-504 | Information | 2025-05-30 | 2025-06-15 |  |  |  | 2025-04-08 | 2025-04-23 | CAT - III | 15 | 18
133 |  | 220kV Transmission Line Equipment Drawings | Tower Accessories ( Number Plate , Danger Board, Circuit Plate, ACD, Barbed Wire) | SECI-RG300-PA-ELE-505 | Information | 2025-05-30 | 2025-06-15 |  |  |  | 2025-05-11 | 2025-06-01 | CAT - III | 21 | 90
134 | Electrical | 220kV Transmission Line Equipment Drawings | OPGW Hardware | SECI-RG300-PA-ELE-506 | Information | 2025-05-30 | 2025-06-15 |  |  |  | 2025-04-08 | 2025-04-23 | CAT - III | 15 | 17
135 |  | 220kV Transmission Line Equipment Drawings | Conductor Accessories | SECI-RG300-PA-ELE-507 | Information | 2025-05-30 | 2025-06-15 |  |  |  | 2025-05-10 | 2025-06-01 | CAT - III | 22 | 90
136 | Electrical | 220kV Transmission Line Equipment Drawings | OPGW Joint Box | SECI-RG300-PA-ELE-508 | Information | 2025-05-30 | 2025-06-15 |  | 2025-05-30
137 | Electrical | 220kV Transmission Line Equipment Drawings | FODB | SECI-RG300-PA-ELE-509 | Information | 2025-05-30 | 2025-06-15 |  | 2025-07-07
138 | Vendor Documents | 220kV Transmission Line Equipment Drawings | SRC Insulators | SECI-RG300-PA-ELE-510 | Approval | 2025-05-30 | 2025-06-15 |  |  |  | 2025-05-27 |  |  | 95
139 |  | 220/33kV Ramgiri Substation Structural Drawings | FABRICATION DRAWING FOR 220kV GANTRY STRUCTURES | SECI-RG300-PA-CIV-001 | Approval | 2025-06-16 | 2025-04-14 |  |  |  | 2025-06-05
140 | Vendor Documents | 220/33kV Ramgiri Substation Structural Drawings | FABRICATION DRAWING FOR 220kV Light Mast | SECI-RG300-PA-CIV-002 | Approval | 2025-06-17 |  | Ordering
141 | Vendor Documents | 220/33kV Ramgiri Substation Structural Drawings | FABRICATION DRAWING FOR 220kV LA SUPPORT STRUCTURE | SECI-RG300-PA-CIV-003 | Approval | 2025-06-18 |  | Ordering |  |  | 2025-06-09
142 | Vendor Documents | 220/33kV Ramgiri Substation Structural Drawings | FABRICATION DRAWING FOR 220kV CVT SUPPORT STRUCTURE | SECI-RG300-PA-CIV-004 | Approval | 2025-06-19 |  | Ordering |  |  | 2025-06-09
143 | Vendor Documents | 220/33kV Ramgiri Substation Structural Drawings | FABRICATION DRAWING FOR 220kV ISO SUPPORT STRUCTURE | SECI-RG300-PA-CIV-005 | Approval | 2025-06-20 |  | Ordering
144 | Vendor Documents | 220/33kV Ramgiri Substation Structural Drawings | FABRICATION DRAWING FOR 220kV LBPI SUPPORT STRUCTURE | SECI-RG300-PA-CIV-006 | Approval | 2025-06-21 |  | Ordering
145 | Vendor Documents | 220/33kV Ramgiri Substation Structural Drawings | FABRICATION DRAWING FOR 220kV HBPI SUPPORT STRUCTURE | SECI-RG300-PA-CIV-007 | Approval | 2025-06-22 |  | Ordering
146 | Vendor Documents | 220/33kV Ramgiri Substation Structural Drawings | FABRICATION DRAWING FOR 220kV WT SUPPORT STRUCTURE | SECI-RG300-PA-CIV-008 | Approval | 2025-06-23 |  | Ordering
147 | Vendor Documents | 220/33kV Ramgiri Substation Structural Drawings | FABRICATION DRAWING FOR 220kV MPT SUPPORT STRUCTURE | SECI-RG300-PA-CIV-009 | Approval | 2025-06-24 |  | Ordering | 2025-06-06
148 | Vendor Documents | 220/33kV Ramgiri Substation Structural Drawings | FABRICATION DRAWING FOR 220kV MCT SUPPORT STRUCTURE | SECI-RG300-PA-CIV-010 | Approval | 2025-06-25 |  | Ordering
149 | Vendor Documents | 220/33kV Ramgiri Substation Structural Drawings | FABRICATION DRAWING FOR 220kV CT SUPPORT STRUCTURE | SECI-RG300-PA-CIV-011 | Approval | 2025-06-26 |  | Ordering
150 | Vendor Documents | 220kV Bay Extension at 400/220kV at PGCIL Substation Structural Drawings | FABRICATION DRAWING FOR 220kV GANTRY STRUCTURES | SECI-RG300-PA-CIV-101 | Approval |  |  | Ordering
151 | Vendor Documents | 220kV Bay Extension at 400/220kV at PGCIL Substation Structural Drawings | 220kV LM | SECI-RG300-PA-CIV-102 | Approval |  |  | Ordering
152 | Vendor Documents | 220kV Bay Extension at 400/220kV at PGCIL Substation Structural Drawings | FABRICATION DRAWING FOR 220kV LA SUPPORT STRUCTURE | SECI-RG300-PA-CIV-103 | Approval |  |  | Ordering
153 | Vendor Documents | 220kV Bay Extension at 400/220kV at PGCIL Substation Structural Drawings | FABRICATION DRAWING FOR 220kV CVT SUPPORT STRUCTURE | SECI-RG300-PA-CIV-104 | Approval |  |  | Ordering
154 | Vendor Documents | 220kV Bay Extension at 400/220kV at PGCIL Substation Structural Drawings | FABRICATION DRAWING FOR 220kV ISO SUPPORT STRUCTURE | SECI-RG300-PA-CIV-105 | Approval |  |  | Ordering
155 | Vendor Documents | 220kV Bay Extension at 400/220kV at PGCIL Substation Structural Drawings | FABRICATION DRAWING FOR 220kV LBPI SUPPORT STRUCTURE | SECI-RG300-PA-CIV-106 | Approval |  |  | Ordering
156 | Vendor Documents | 220kV Bay Extension at 400/220kV at PGCIL Substation Structural Drawings | FABRICATION DRAWING FOR 220kV HBPI SUPPORT STRUCTURE | SECI-RG300-PA-CIV-107 | Approval |  |  | Ordering
157 | Vendor Documents | 220kV Bay Extension at 400/220kV at PGCIL Substation Structural Drawings | FABRICATION DRAWING FOR 220kV WT SUPPORT STRUCTURE | SECI-RG300-PA-CIV-108 | Approval |  |  | Ordering
158 | Vendor Documents | 220kV Bay Extension at 400/220kV at PGCIL Substation Structural Drawings | FABRICATION DRAWING FOR 220kV MPT SUPPORT STRUCTURE | SECI-RG300-PA-CIV-109 | Approval |  |  | Ordering
159 | Vendor Documents | 220kV Bay Extension at 400/220kV at PGCIL Substation Structural Drawings | FABRICATION DRAWING FOR 220kV MCT SUPPORT STRUCTURE | SECI-RG300-PA-CIV-110 | Approval |  |  | Ordering
160 | Vendor Documents | 220kV Bay Extension at 400/220kV at PGCIL Substation Structural Drawings | FABRICATION DRAWING FOR 220kV CT SUPPORT STRUCTURE | SECI-RG300-PA-CIV-111 | Approval |  |  | Ordering
161 | Vendor Documents | 220kV Transmission Line Structural Drawings | FABRICATION DRAWING FOR 220kV TOWER-DA | SECI-RG300-PA-CIV-201 | Approval | 2025-06-18 |  | Ordering
162 | Vendor Documents | 220kV Transmission Line Structural Drawings | FABRICATION DRAWING FOR 220kV TOWER-DB | SECI-RG300-PA-CIV-202 | Approval | 2025-06-18 |  | Ordering
163 | Vendor Documents | 220kV Transmission Line Structural Drawings | FABRICATION DRAWING FOR 220kV TOWER-DC | SECI-RG300-PA-CIV-203 | Approval | 2025-06-18 |  | Ordering
164 | Vendor Documents | 220kV Transmission Line Structural Drawings | FABRICATION DRAWING FOR 220kV TOWER-DD | SECI-RG300-PA-CIV-204 | Approval | 2025-06-18 |  | Ordering
165 | Vendor Documents | 220kV Transmission Line Structural Drawings | FABRICATION DRAWING FOR 220kV TOWER-Gantry | SECI-RG300-PA-CIV-205 | Approval | 2025-06-18 |  | Ordering
Formulas:
Approved date = [Response date]
Submitted/Expected Submission = [Submission Date]

## Daily Activities
DPR for 220 kV PSS, EHV Line and ISTS Bay Extension
Sl.No | Date | Work Location | Man Power Details | Machinery Details | Daily Activities | SUMMARY
1 | 2025-08-22 | 220 KV PSS | Civil Workers : 06 No's Operator/ Drivers : 6 No's | Hitachi- 1 No's JCB - 2 No's Tractors- 2 No's Roller - 1 No's | 1. MCR footing Backfilling and Compaction wip 2. MCR plinth beam PCC wip 3. Soil Compaction wip at filling portion of yard. 4. Grid Earthing trech excavation wip | 1. MCR: Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC up to Plinth Beam): (28/28/28/28/28) 2. 220 KV PSS: - Tower foundation: (Total/Exc/PCC/RCC footing/Pedestal RCC): (18/16/12/0/0) - PTR foundation:(Total/Exc/PCC/RCC) : (02/02/0/0) - Grid earthing : (Total/Exc/laying): (7200/200/0) 3. Site levelling : - Soil Cutting : (Total/Completed/ Balance): (10000/10000/0) - Soil filling: (Total/Completed/Balance):(1000/650/350)
|  | EHV Line | Civil Workers : 11 No's Operator/ Drivers : 4 No's | Ajax- 1 No's JCB - 1 No's Tractors- 1 No's | 1.Location 4/2 DA+6 tower foundation casting upto raft. | EHV Line: 1. Tower Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC/ Back filling):(39/08/05/05/04/04) 2. Detailed survey Completed 3. Check survey Completed 4. Trial pit excavation and soil classification has been completed.
|  | ISTS Bay |  |  | No work | 1. Gravel removed over the bay which ever spreaded 2. Marking and Excavation wip
2 | 2025-08-23 | 220 KV PSS | Civil Workers : 06 No's Operator/ Drivers : 6 No's | Hitachi- 1 No's JCB - 2 No's Tractors- 2 No's Roller - 1 No's | 1. MCR footing Backfilling and Compaction wip 2. MCR plinth beam PCC wip 3. Soil Compaction wip at filling portion of yard. 4. Grid Earthing trech excavation wip 5. MCR plinth beam reinforcement wip | 1. MCR: Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC up to Plinth Beam): (28/28/28/28/28) 2. 220 KV PSS: - Tower foundation: (Total/Exc/PCC/RCC footing/Pedestal RCC): (18/16/12/0/0) - PTR foundation:(Total/Exc/PCC/RCC) : (02/02/0/0) - Grid earthing : (Total/Exc/laying): (7200/200/0) 3. Site levelling : - Soil Cutting : (Total/Completed/ Balance): (10000/10000/0) - Soil filling: (Total/Completed/Balance):(1000/680/320)
|  | EHV Line | Civil Workers : 11 No's Operator/ Drivers : 4 No's | Ajax- 1 No's JCB - 1 No's Tractors- 1 No's | 1.Location 4/2 DA+6 tower foundation column casting completed 2. Location 5/0 DD+3 tower foundation raft casting completed. | EHV Line: 1. Tower Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC/ Back filling):(39/08/05/05/05/04) 2. Detailed survey Completed 3. Check survey Completed 4. Trial pit excavation and soil classification has been completed.
|  | ISTS Bay |  |  | No work | 1. Gravel removed over the bay which ever spreaded 2. Marking and Excavation wip
3 | 2025-08-24 | 220 KV PSS | Civil Workers : 06 No's Operator/ Drivers : 6 No's | Hitachi- 1 No's JCB - 2 No's Tractors- 2 No's Roller - 1 No's | 1. MCR footing Backfilling and Compaction wip 2. MCR plinth beam PCC wip 3. Soil Compaction wip at filling portion of yard. 4. Grid Earthing trech excavation wip 5. MCR plinth beam reinforcement wip | 1. MCR: Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC up to Plinth Beam): (28/28/28/28/28) 2. 220 KV PSS: - Tower foundation: (Total/Exc/PCC/RCC footing/Pedestal RCC): (18/16/12/0/0) - PTR foundation:(Total/Exc/PCC/RCC) : (02/02/0/0) - Grid earthing : (Total/Exc/laying): (7200/200/0) 3. Site levelling : - Soil Cutting : (Total/Completed/ Balance): (10000/10000/0) - Soil filling: (Total/Completed/Balance):(1000/710/290)
|  | EHV Line | Civil Workers : 11 No's Operator/ Drivers : 4 No's | Ajax- 1 No's JCB - 1 No's Tractors- 1 No's | 1.Location 5/0 DD+3 tower column casting completed 2. Location 5/1 tower pit dressing completed 3. Location 5/2 tower pit dressing wip | EHV Line: 1. Tower Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC/ Back filling):(39/08/06/06/06/04) 2. Detailed survey Completed 3. Check survey Completed 4. Trial pit excavation and soil classification has been completed.
|  | ISTS Bay |  |  | No work | 1. Gravel removed over the bay which ever spreaded 2. Marking and Excavation wip
4 | 2025-08-25 | 220 KV PSS | Civil Workers : 19 No's Operator/ Drivers : 6 No's | Hitachi- 1 No's JCB - 2 No's Tractors- 2 No's Roller - 1 No's | 1. MCR footing Backfilling and Compaction wip 2. MCR plinth beam steel reinforcement completed 3. Soil Compaction wip at filling portion of yard. 4. Grid Earthing trech excavation wip and grid erathing wip | 1. MCR: Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC up to Plinth Beam): (28/28/28/28/28) 2. 220 KV PSS: - Tower foundation: (Total/Exc/PCC/RCC footing/Pedestal RCC): (18/16/12/0/0) - PTR foundation:(Total/Exc/PCC/RCC) : (02/02/0/0) - Grid earthing : (Total/Exc/laying): (7200/200/0) 3. Site levelling : - Soil Cutting : (Total/Completed/ Balance): (10000/10000/0) - Soil filling: (Total/Completed/Balance):(1000/740/260) 4. Grid Earthing work:(Total/Excavation/laying): (7200/300/84)
|  | EHV Line | Civil Workers : 11 No's Operator/ Drivers : 4 No's | Ajax- 1 No's JCB - 1 No's Tractors- 1 No's | 1.Location 5/3 tower pit dressing and prope setting completed 2. Location 5/1 tower pit PCC, prope setting completed 3. Location 5/2 tower pit dressing, PCC and prope setting completed | EHV Line: 1. Tower Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC/ Back filling):(39/11/08/06/06/05) 2. Detailed survey Completed 3. Check survey Completed 4. Trial pit excavation and soil classification has been completed.
|  | ISTS Bay |  |  | No work | 1. Gravel removed over the bay which ever spreaded 2. Marking and Excavation wip
5 | 2025-08-26 | 220 KV PSS | Civil Workers : 19 No's Operator/ Drivers : 6 No's | Hitachi- 1 No's JCB - 2 No's Tractors- 2 No's Roller - 1 No's | 1. MCR footing Backfilling and Compaction wip 2. MCR plinth beam steel reinforcement completed 3. Soil Compaction wip at filling portion of yard. 4. Grid Earthing trech excavation wip and grid erathing wip | 1. MCR: Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC up to Plinth Beam): (28/28/28/28/28) 2. 220 KV PSS: - Tower foundation: (Total/Exc/PCC/RCC footing/Pedestal RCC): (18/16/12/0/0) - PTR foundation:(Total/Exc/PCC/RCC) : (02/02/0/0) - Grid earthing : (Total/Exc/laying): (7200/200/0) 3. Site levelling : - Soil Cutting : (Total/Completed/ Balance): (10000/10000/0) - Soil filling: (Total/Completed/Balance):(1000/740/260) 4. Grid Earthing work:(Total/Excavation/laying): (7200/300/84)
|  | EHV Line | Civil Workers : 11 No's Operator/ Drivers : 4 No's | Ajax- 1 No's JCB - 1 No's Tractors- 1 No's | 1.Location 5/3 tower pit PCC Completed 2. Location 5/1 tower raft RCC & Pedestal RCC completed 3. Location 5/2 tower raft RCC completed | EHV Line: 1. Tower Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC/ Back filling):(39/11/09/08/07/06) 2. Detailed survey Completed 3. Check survey Completed 4. Trial pit excavation and soil classification has been completed.
|  | ISTS Bay |  |  | No work | 1. Gravel removed over the bay which ever spreaded 2. Marking and Excavation wip
6 | 2025-08-27 | 220 KV PSS | Civil Workers : 19 No's Operator/ Drivers : 6 No's | Hitachi- 1 No's JCB - 2 No's Tractors- 2 No's Roller - 1 No's | 1. MCR footing Backfilling and Compaction wip 2. MCR plinth beam steel reinforcement completed 3. Soil Compaction wip at filling portion of yard. 4. Grid Earthing trech excavation wip and grid erathing wip | 1. MCR: Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC up to Plinth Beam): (28/28/28/28/28) 2. 220 KV PSS: - Tower foundation: (Total/Exc/PCC/RCC footing/Pedestal RCC): (18/16/12/0/0) - PTR foundation:(Total/Exc/PCC/RCC) : (02/02/0/0) - Grid earthing : (Total/Exc/laying): (7200/200/0) 3. Site levelling : - Soil Cutting : (Total/Completed/ Balance): (10000/10000/0) - Soil filling: (Total/Completed/Balance):(1000/740/260) 4. Grid Earthing work:(Total/Excavation/laying): (7200/300/84)
|  | EHV Line | Civil Workers : 11 No's Operator/ Drivers : 4 No's | Ajax- 1 No's JCB - 1 No's Tractors- 1 No's | 1.Location 5/3 tower raft RCC completed 2. Location 5/2 tower columns RCC completed | EHV Line: 1. Tower Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC/ Back filling):(39/11/09/09/08/07) 2. Detailed survey Completed 3. Check survey Completed 4. Trial pit excavation and soil classification has been completed.
|  | ISTS Bay |  |  | No work | 1. Gravel removed over the bay which ever spreaded 2. Marking and Excavation wip
7 | 2025-08-28 | 220 KV PSS | Civil Workers : 19 No's Operator/ Drivers : 6 No's | Hitachi- 1 No's JCB - 2 No's Tractors- 2 No's Roller - 1 No's | 1. Soil Compaction wip at filling portion of yard. 2. Grid Earthing trech excavation wip and grid erathing wip 3. CA Tower excavation complted for 2 No's | 1. MCR: Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC up to Plinth Beam): (28/28/28/28/28) 2. 220 KV PSS: - Tower foundation: (Total/Exc/PCC/RCC footing/Pedestal RCC): (18/16/12/0/0) - PTR foundation:(Total/Exc/PCC/RCC) : (02/02/0/0) - Grid earthing : (Total/Exc/laying): (7200/200/0) 3. Site levelling : - Soil Cutting : (Total/Completed/ Balance): (10000/10000/0) - Soil filling: (Total/Completed/Balance):(1000/740/260) 4. Grid Earthing work:(Total/Excavation/laying): (7200/440/440)
|  | EHV Line | Civil Workers : 11 No's Operator/ Drivers : 4 No's | Ajax- 1 No's JCB - 1 No's Tractors- 1 No's | 1.Location 5/3 tower pedestal RCC completed | EHV Line: 1. Tower Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC/ Back filling):(39/11/09/09/09/08) 2. Detailed survey Completed 3. Check survey Completed 4. Trial pit excavation and soil classification has been completed.
|  | ISTS Bay |  |  | No work | 1. Gravel removed over the bay which ever spreaded 2. Marking and Excavation wip
8 | 2025-08-29 | 220 KV PSS | Civil Workers : 19 No's Operator/ Drivers : 6 No's | Hitachi- 1 No's JCB - 2 No's Tractors- 2 No's Roller - 1 No's | 1. MCR plinth beam shuttering wip | 1. MCR: Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC up to Plinth Beam): (28/28/28/28/28) 2. 220 KV PSS: - Tower foundation: (Total/Exc/PCC/RCC footing/Pedestal RCC): (18/16/12/0/0) - PTR foundation:(Total/Exc/PCC/RCC) : (02/02/0/0) - Grid earthing : (Total/Exc/laying): (7200/200/0) 3. Site levelling : - Soil Cutting : (Total/Completed/ Balance): (10000/10000/0) - Soil filling: (Total/Completed/Balance):(1000/740/260) 4. Grid Earthing work:(Total/Excavation/laying): (7200/440/440)
|  | EHV Line | Civil Workers : 11 No's Operator/ Drivers : 4 No's | Ajax- 1 No's JCB - 1 No's Tractors- 1 No's | 1.Location 6/5 DA+3 tower propesetting & PCC completed | EHV Line: 1. Tower Foundations: (Total/Exc/PCC/RCC footing/Pedestal RCC/ Back filling):(39/11/10/09/09/08) 2. Detailed survey Completed 3. Check survey Completed 4. Trial pit excavation and soil classification has been completed.
|  | ISTS Bay |  |  | No work | 1. Gravel removed over the bay which ever spreaded 2. Marking and Excavation wip
25
26
27
28
29
30
31
32
33
34

## Engineering & Delivery (hidden)
# | Engineering-Key Equipment | Planned | Actual/ Expected | Status
1 | Module Mounting Structure | 2025-05-06 | 2025-05-06 | Drawing Submitted
2 | Inverter Duty Transformer | 2025-05-26 | 2025-05-30 | Drawing submitted
3 | NIFPS | 2025-06-08 | 2025-06-08
4 | ICOG/RMU PANEL | 2025-05-28 | 2025-06-09
5 | Main HT Switchgear Panel | 2025-05-28 | 2025-06-09
6 | Auxiliary LT Panel | 2025-06-12 | 2025-06-12
7 | Auxiliary Transformer | 2025-06-06 | 2025-06-10
8 | Central Inverter(PCU) | 2025-05-20 | 2025-05-13 | Drawing submitted
9 | String Combiner Box (SCB) | 2025-05-11 | #REF!
10 | DC string cable | 2025-06-05 | 2025-06-10
11 | DC power cable | 2025-05-22 | #REF!
12 | LT AC power cable | 2025-05-14 | #REF!
13 | HT AC power cable | 2025-06-05 | 2025-06-12
14 | LT power and control cables | 2025-05-28 | #REF!
15 | Communication cables | 2025-05-28 | #REF!
16 | SCADA system | 2025-05-28 | #REF!
17 | UPS and Battery System | 2025-06-05 | #REF!
18 | SVG | 2025-06-12 | 2025-06-12
19 | Harmonic Filter and its Acessories | 2025-07-01 | 2025-07-01
20 | Other BOQ (Lighting, Gland, Lungs, HT termination KIT etc.) | 2025-08-31 | 2025-08-31
# | Engineering-General Drawing | Target | Actual/ Expected | Remarks
1 | Master Document List | 2025-02-13 | Submitted | Submitted
2 | Overall Plant Layout | 2025-05-03 | 2025-05-03 | R2 to be submitted
3 | MMS Structure foundation | 2025-06-15 | 2025-06-15 | Submitted, under SECI Review
4 | MMS Design and GA diagram | 04 Apr, 25 | Submitted | Approved
5 | Lighting Fixtures with calculations | 2025-06-04 | 2025-06-20
6 | ICR Equipment Layout | 2025-04-30 | 2025-05-27 | Submitted under SECI review
7 | MCR Equipment Layout | 2025-05-17 | 2025-05-17
8 | ICR Equipment Foundation Civil Drawing | 2025-05-30 | 2025-06-11
9 | MCR Equipment Foundation Civil Drawing | 2025-06-08 | 2025-06-08
10 | AC sizing calculation | 2025-04-25 | 2025-05-10 | R1 to be submitted
11 | DC sizing calculation | 2025-04-25 | 2025-04-26 | R1 submitted for review
12 | Earthing calculation | 2025-05-06 | 2025-05-18 | R0 submitted for review
13 | DC Cable schedule, laying and sectional drawings | 2025-06-03 | 2025-06-15
14 | AC Cable schedule, laying and sectional drawings | 2025-05-31 | 2025-06-15
15 | Control and Communication Cable schedule, | 2025-05-31 | 2025-06-20
16 | AC SLD | 2025-03-03 | Submitted | Approved under CAT 2, dwg submitted for CAT 1 approval, Revised to be submitted as per discussion
17 | DC SLD | 2025-04-15 |  | R0 Submitted, Under SECI Review since 25th Apr.
18 | AUX SLD | 2025-04-25 | 2025-05-10 | R0 submitted, under SECI Revew
19 | Fencing layout & Drawing | 2025-04-25 |  | Drawing approved, Layout Submitted, under SECI Review
20 | Road Calculations, Cross sections & Layout drawing | 2025-05-20 | 2025-06-06
19 | Calc - UPS Sizing Calculation |  |  | R2 to be submitted
20 | Calc - Auxiliary Transformer Sizing Calculation |  |  | R2 to be submitted
# | Manufacturing, FAT and Delivery at site- Key Equipment | Start | Finish | Remarks
1 | Module Mounting Structure | 2025-05-08 | 2025-10-26
2 | Inverter Duty Transformer | 2025-05-28 | 2025-11-25
3 | NIFPS | 2025-06-10 | 2025-11-08
4 | ICOG/RMU PANEL | 2025-05-30 | 2025-10-28
5 | Main HT Switchgear Panel | 2025-05-30 | 2025-10-28
6 | Auxiliary LT Panel | 2025-06-14 | 2025-10-13
7 | Auxiliary Transformer | 2025-06-08 | 2025-10-07
8 | Central Inverter(PCU) | 2025-05-22 | 2025-09-19
9 | String Combiner Box (SCB) | 2025-05-13 | 2025-09-10
10 | DC string cable | 2025-06-07 | 2025-10-06
11 | DC power cable | 2025-05-24 | 2025-09-21
12 | LT AC power cable | 2025-05-16 | 2025-09-13
13 | HT AC power cable | 2025-06-07 | 2025-10-06
14 | LT power and control cables | 2025-05-30 | 2025-09-27
15 | Communication cables | 2025-05-30 | 2025-09-27
16 | SCADA system | 2025-05-30 | 2025-09-27
17 | UPS and Battery System | 2025-06-07 | 2025-10-06
18 | SVG | 2025-06-14 | 2025-10-13
19 | Harmonic Filter and its Acessories | 2025-07-03 | 2025-12-01
20 | Other BOQ (Lighting, Gland, Lungs, HT termination KIT etc.) | 2025-09-02 | 2025-12-31
Formulas:
Actual/ Expected = [Planned]

## Hinderance Register (hidden)
WORK HINDERANCE REGISTER
S. No | Effected Date | Effect Impact | Description | Remarks | Progress affected in terms of days
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
Total Days | 0 |  |  |  | 0

## Construction Status (2) (hidden)
| Date | 2025-08-29 | [14 empty] | Till 30th Mar
Section | S.No | Site Activity | Planned Start | Planned Finish | Actual/Expected Start | Actual/Expected Finish | uom | Qty | Start Date | End Date | No of Days | Avg/Day | Actual as on Date (%) | Comp. | Bal | Actual as on date | time axis 2025-03-30 to 2025-05-17
 | time axis 2025-03-30 to 2025-05-17
L & G | 1 | Land Development | 2025-04-03 | 2025-08-01 | 2025-04-05 | 2025-08-01 | Acre | 1030 | 2025-04-05 | 2025-05-19 | 45 | 22.8889 | 24.85% | 256 | 774 | 256 | 2025-03-30: 0; 2025-04-03: 0; 2025-04-07: 1.5; 2025-04-08: 3.5; 2025-04-09: 4; 2025-04-10: 4; 2025-04-11: 4; 2025-04-12: 4; 2025-04-13: 3; 2025-04-14: 2; 2025-04-17: 20; 2025-04-18: 20; 2025-04-19: 20; 2025-04-20: 20; 2025-04-21: 40; 2025-04-22: 40; 2025-04-23: 30; 2025-04-24: 20; 2025-04-25: 10; 2025-04-26: 10
Site Initials | 2 | Boundry Coordinate capturing | 2025-02-12 | 2025-02-21 | 2025-02-12 | 2025-02-21 | Lot. | 1 |  |  |  | - | 100% | 1 | 0 | 1 | bar: 2025-03-30
| 3 | Topo Survey | 2025-02-23 | 2025-03-14 | 2025-02-23 | 2025-03-14 | Lot. | 1 |  |  |  | - | 100% | 1 | 0 | 1 | bar: 2025-03-30
| 4 | Soil Investigation | 2025-02-15 | 2025-04-15 | 2025-02-15 | 2025-04-28 | Nos. | 79 | 2025-02-23 |  |  | - | 94.94% | 75 | 4 | 75 | 2025-03-30: 52; 2025-04-03: 2; 2025-04-04: 2; 2025-04-05: 2; 2025-04-06: 2; 2025-04-07: 2; 2025-04-08: 1; 2025-04-09: 1; 2025-04-10: 1; 2025-04-11: 1; 2025-04-12: 1; 2025-04-13: 1; 2025-04-15: 1; 2025-04-16: 1; 2025-04-19: 1; 2025-04-20: 1; 2025-04-21: 1; 2025-04-22: 1; 2025-04-23: 1
| 5 | ERT Test | 2025-04-02 | 2025-04-13 | 2025-04-06 | 2025-04-27 | Lot. | 36 | 2025-02-23 | 2025-03-11 | 17 | 2.1176 | 100% | 36 | 0 | 36 | 2025-03-30: 0; 2025-04-03: 0; 2025-04-06: 4; 2025-04-07: 8; 2025-04-08: 8; 2025-04-09: 10; 2025-04-10: 6
| 6 | Test Pile Casting | 2025-04-12 | 2025-04-26 | 2025-04-12 | 2025-04-26 | Lot. | 236 |  |  |  | - | 0% | 0 | 236 | 0 | 2025-03-30: 0; 2025-04-03: 0
| 7 | Pull Out Test | 2025-04-15 | 2025-05-24 | 2025-04-15 | 2025-05-24 | Lot. | 236 |  |  |  | - | 0% | 0 | 236 | 0 | 2025-03-30: 0; 2025-04-03: 0
Array Yard Civil Works | 8 | Pile Marking |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 9 | Pile -Drilling |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 10 | Pile- Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 11 | Pile-Capping |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
ICR Civil Works | 12 | HT Panel Marking & Excavation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 13 | PCC |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 14 | Footing Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 15 | Pedestal Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 16 | Beam Slab Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 17 | ICR Marking & Excavation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 18 | ICR PCC |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 19 | ICR Footing Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 20 | ICR Column Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 21 | ICR Beam Slab Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 22 | PEB Structure Installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 23 | Transformer Marking & Excavation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 24 | Transformer PCC |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 25 | Transformer Footing Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 26 | Transformer Pedestal Casting |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 27 | Transformer Support Foundation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 28 | Transformer Grade Slab |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 29 | Transformer Fencing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
MCR Civil Works | 30 | MCR Excavation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 31 | MCR Footing PCC |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 32 | MCR Footing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 33 | MCR Column upto Plinth Beam |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 34 | Plinth Beam |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 35 | Cable Trench |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 36 | Column 1st Lift |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 37 | Column 2nd Lift |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 38 | Lintel Beams |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 39 | Roof Beam |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 40 | Slab |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 41 | Brick Works |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 42 | Internal Plastering |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 43 | Outer Plastering |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 44 | Internal Paint Works |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 45 | Outer Painting Works |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 46 | MCR Miscillaneous Works |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
| 47 | MCR Finishing Works |  |  |  |  | Lot |  |  |  |  | - | - | 0 | 0 | 0
Allied Civil Works | 48 | Asphalt Road-Marking & Excavation |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 49 | Asphalt Road-GSB Filling |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 50 | Asphalt Road-WBM Layer-1 |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 51 | Asphalt Road-WBM Layer-2 |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 52 | Ashpalt Laying |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 53 | Road-Marking & Excavation |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 54 | Road-GSB Filling |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 55 | Road-WBM Layer-1 |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 56 | Road-WBM Layer-2 |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 57 | Periphary Road-Marking and Grading |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 58 | Periphary Road-Compaction |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 59 | Precast Boundary-Marking & Drilling |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 60 | Precast Boundary-Pole Casting |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 61 | Precast Boundary- Panel Fixing |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 62 | Precast Cast Boundary -Arm Fixing & Barbed Wire Laying |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 63 | Chain Link Fencing- Marking & Drilling |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 64 | Chain Link Fencing-Pole Casting |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 65 | Chain Link Fincing |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 66 | Chain Link Fencing-Barbed Wire Ficing |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 67 | Drain Excavation |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 68 | Drain Works |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 69 | Drain Finishing |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
DC System Works | 70 | Excavation For DC/Earthing Trenches Module Mounting Structures |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 71 | DC Cable Laying |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 72 | Module Mounting Structures |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 73 | PV Modules |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 74 | PVM Cables (Interconnection after module installation) |  |  |  |  | Km |  |  |  |  | - | - | 0 | 0 | 0
| 75 | Solar cable laying (6 Sq.mm) |  |  |  |  | Km |  |  |  |  | - | - | 0 | 0 | 0
| 76 | SCB - Mounting Structure |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 77 | Array yard Earthing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 78 | Earth pit installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 79 | SCB Installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
ICR Electrical Works | 80 | Inverter Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 81 | ICOG/RMU Panel Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 82 | Inverter Duty Trafo. Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 83 | Aux Trafo Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 84 | UPS & Battery Bank Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 85 | UPS +LDB'S Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 86 | Scada panel's Erection |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 87 | Tray Works |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 88 | AC Cable-Inv to Trafo. |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 89 | Control & Aux Cable Laying |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 90 | Equipment Earthing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 91 | Grid Earthing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 92 | Earth pit installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
MCR Electrical Works | 93 | HT Panel installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 94 | Aux. trf installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 95 | DB's installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 96 | UPS, Battery charger, battery bank installaiton |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 97 | FAS installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 98 | HT cable laying from MCR to Power Trafo |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 99 | HT cable laying from HT panel to Aux. trf |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 100 | Aux t/f to LT |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 101 | SCADA installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 102 | Grid earthing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 103 | Tray Works |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 104 | Earth pit installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 105 | Equipment earthing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
AC System | 106 | HT Trench Marking & Excavation |  |  |  |  | km |  |  |  |  | - | - | 0 | 0 | 0
| 107 | HT Cable Laying |  |  |  |  | km |  |  |  |  | - | - | 0 | 0 | 0
| 108 | HT Trench Backfilling & Rote Marking |  |  |  |  | km |  |  |  |  | - | - | 0 | 0 | 0
Array Area Terminations | 109 | Solar Cable Termination Table Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 110 | Solar Cable Termination SCB Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 111 | DC Power Cable Termination SCB Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
ICR Areay Terminations | 112 | DC Power Cable Termination Inverter Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 113 | AC cable Termination Inv Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 114 | AC cable Termination Trafo Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 115 | HT Cable Termination Trafo Side |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 116 | HT Cable Termination ICOG/RMU |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 117 | Control and comm. cable termination |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 118 | LT Cables termination |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
MCR Area Termination | 119 | HT Cable termiantion- MCR Panel |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 120 | MCR to Power Trafo HT cable termination |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 121 | Aux. t/f LT side cable termiantion |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 122 | Control and comm. cable termination |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 123 | LT Cables termination |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
Scada Works | 124 | FO Cable Laying |  |  |  |  | Mtrs |  |  |  |  | - | - | 0 | 0 | 0
| 125 | FO Cable Splicing |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 126 | FAS installation |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
Testing and Commissioning | 127 | Pre-commissioning of inverters |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 128 | HT panel @ blocks |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 129 | Transformers @ blocks |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 130 | Invertor, Aux T/F , ACCB, UPS |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 131 | T/F to ICOG cables IR & Hi-pot test |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 132 | ICOG to 3VCB cables IR & Hi-pot test |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 133 | 3VCB to MCR cables IR & Hi-pot test |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 134 | ERT |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 135 | FAS functionality check |  |  |  |  | % |  |  |  |  | - | - | 0 | 0 | 0
| 136 | CCTV commissioning |  |  |  |  | % |  |  |  |  | - | - | 0 | 0 | 0
| 137 | WMS commissioning |  |  |  |  | % |  |  |  |  | - | - | 0 | 0 | 0
External Works | 138 | Street Light Poles | [9 empty] | - | - | 0 | 0 | 0
| 139 | Light Fixtures | [9 empty] | - | - | 0 | 0 | 0
| 140 | External LDB | [9 empty] | - | - | 0 | 0 | 0
| 141 | LT Cables | [9 empty] | - | - | 0 | 0 | 0
| 142 | LT Termination | [9 empty] | - | - | 0 | 0 | 0
| 143 | External earthing work completion | [9 empty] | - | - | 0 | 0 | 0
Allied Works | 144 | Weather Monitoring System |  |  |  |  | Nos |  |  |  |  | - | - | 0 | 0 | 0
| 145 | Module Cleaning System( after Module installation | [9 empty] | - | - | 0 | 0 | 0
| 146 | FDS | [9 empty] | - | - | 0 | 0 | 0
| 147 | Allied work completion | [9 empty] | - | - | 0 | 0 | 0
Commissioning & Handing Over | 148 | Pre-Commissioining (DC & AC) |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0
| 149 | CEIG Approval |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0
| 150 | Synchronization Approval |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0
| 151 | Commissioning |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0
| 152 | PR Acceptance |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0
| 153 | FAT & HO |  |  |  |  | % | 100 |  |  |  | - | 0% | 0 | 100 | 0