## Overview
C&P Portion:
Project Type
Scheme
RFS
LoA
Handling of Success Fee
Project Division
PPA | Addition of Multiple PPAs
| Login to SPV-wise to manage PPA | Email to SPV with login Credentials
Milestones define/RfS
Schedule completion date
Project Monitoring
FC
LA/LC
Monthly Monitoring till CoD | What are the fields and parameters for monitoring of projects (added in Milestones at end)

## PROJECT PROFILE
PROJECT PROFILE

## SPD Progress Report Format
Project Status Report
General Details
Project Location (Vill., Tehsil., Dist., State) | Text
Project Location (Latitude) | Text
Project Location (Longitude) | Text
Interconnection Point (SS & Voltage Level) | Text
Whether Project is in Solar Park | Yes | No
If yes, detail of Solar Park | Text
Status of Agreement with SPPD/SPIA | Text
Financing Arrangement
Estimated Project Cost (Crore Rs.) | Number
Source of Fund | Text
Loan Amount (Crore Rs.) | Number
Equity Amount (Crore Rs.) | Number
Lending Agency | Text
Status of Loan | Text
Land Arrangement
Total Land Requirement (Hectare) | Number
Type of Land
Land Acquired (Hectare) | Number
Mode of Land Acquisition
Target Date of Complete Land Acquisition | Date Picker
Connectivity Details
Connectivity Application No. | Text
Date of Application | Date Picker
Application Status | Text
Date of Operationalization of Connectivity | Date Picker
Status of Connectivity with respect to SCSD/applicable Schedule | Text
PV Modules Supply Details
PV Module Details
Make | Text |  | Can be added multiple times
Model
Number
Rating
Quality
Other Details
Total Module Requirement (MWp) | Number
Order Status | Text
Date of placing order | Date Picker
Supply Status
Quantity Received at Site | Number
Expected Date of Balance Supply | Date Picker
Inverter Supply Details
Inverter Module Details
Make | Text |  | Can be added multiple times
Model
Number
Rating
Quality
Other Details
Total Module Requirement (MWp) | Number
Order Status | Text
Date of placing order | Date Picker
Supply Status
Quantity Received at Site | Number
Expected Date of Balance Supply | Date Picker
Power Transformer Supply Details
PT Module Details
Make | Text |  | Can be added multiple times
Model
Number
Rating
Quality
Other Details
Total Module Requirement (MWp) | Number
Order Status | ?
Date of placing order | Date Picker
Supply Status
Quantity Received at Site | Number
Expected Date of Balance Supply | Date Picker
WMS, SCADA & DC Cable
PT Module Details
Make | Text |  | Can be added multiple times
Model
Number
Rating
Quality
Other Details
Total Module Requirement (MWp) | Number
Order Status | Text
Date of placing order | Date Picker
Supply Status
Quantity Received at Site | Number
Expected Date of Balance Supply | Date Picker
EPC Details
Name of EPC | Text
Address of EPC
Date of EPC Contract
Contract Status
Plant Installation
MMS Installation
% completed | Number
Expected timeline for 100% completion | Date Picker
Module Installation
% completed | Number
Expected timeline for 100% completion | Date Picker
Inverter Installation
% completed | Number
Expected timeline for 100% completion | Date Picker
Main Control Civil Works
% completed | Number
Expected timeline for 100% completion | Date Picker
Pooling Substation
% completed | Number
Expected timeline for 100% completion | Date Picker
12. Tranmission Line Polling SSN to Delivery Point
12.1 Tower Foundation
% completed | Number
Expected timeline for 100% completion | Date Picker
12.2 Tower Erection
% completed | Number
Expected timeline for 100% completion | Date Picker
12.3 Tower Stringing
% completed | Number
Expected timeline for 100% completion | Date Picker
12.4 Delivery End Bay
% completed | Number
Expected timeline for 100% completion | Date Picker
Targeted Commissioning Date of Transmission Line | Date Picker
13. CEIG Inspection & Approval
Inspection and Approval status of PSS and transmission line (SSN to Delivery Point) | Text
Inspection and Approval status of the Plant | Text
14. GIB Related Information
Whether the project is GIB affected?
Whether TL is GIB affected?
Whether applied to Supreme Court's appointed committee?
If yes, provide status / If no, reason for not applying | Text
15. Commissioning Plan
Targeted Project Readiness Date | Date Picker
Targeted CEIG Certification Date
Targeted Trial Run Date
Targeted Trial Run Capacity
Status of Trial Run | Text
Targeted Commissioning Date | Date Picker

## WPD Progress Report Format
0. OEM Supply Agreement
Document Upload | File upload | File size limit: 20 MB
1. WTG Configuration
WTG Capacity (in MW) | Number |  | Can be added multiple times
Make | Text
Model | Text
Undertaking upload | File upload | File size limit: 20 MB Note: Regarding using only RLMM MNRE approved WTG Add link to RLMM list by MNRE
2. Land Details
Land parcels required | Number |  | Can be added multiple times
Land for pooling substation
2.1 MoD Approval Details
No. of land parcels | Number
Date of application | Date picker
Status
MoD approval documents | File upload
KMZ file | File upload
2.2 SNA Approval Details
No. of land parcels | Number
Date of application | Date Picker
Status
SNA approval copy | File Upload
2.3 CEA Approval Details
Remarks | Text
Document upload | File Upload
2.4 Any other approval
Remarks | Text
Document upload | File Upload
3. Grid Connectivity Details
Connection Application Date | Date Picker |  | Can be added multiple times
Application Document Upload | File Upload
As per CTU IL connection st. date | Date Picker
Letter upload | File Upload
Schedule date of GNA operationalization | Date Picker |  |  |  | 1. Give developer ability to add changes to land etc. 2. Force majeure/change in law/clearances/other activities having financial implication should be notified to SECI + DISCOM. 3. Land -> civil -> modules 4. DPS dashboard -> weekly progress from each department; issue, action, deadline, responsibility (power trading, contracts, billing, projects, engineering); land, supply, construction; (for each month) -> opening balance, closing balance, asking rate, remarks; special remarks; progress upload facility
Connectivity Agreement | File Upload
CON-4 approval date | Date Picker
CON-4 status
Dynamic VAR Compensation status
Status of PSS
PSS photo upload | File upload | File size limit: 5 MB. Allow to upload photo in .jpeg/.png format
TSA Agreement | File upload
4. Civil Works
4.1 Site levelling (Pls. fill no. of WTGs) |  |  | Can be added multiple times
Completed | Number | (Completed + Ongoing + Yet to start = Total number of land parcels)
Ongoing
Yet to start
4.2 Foundation (Pls. fill no. of WTGs)
Completed | Number | (Completed + Ongoing + Yet to start = Total number of land parcels)
Ongoing
Yet to start
4.3 Erection (Pls. fill no. of WTGs)
Completed | Number | (Completed + Ongoing + Yet to start = Total number of land parcels)
Ongoing
Yet to start
4.5 Evacuation System
a) Root Survey Status
Status
Percentage completed (%), if in process
Photo upload | File upload | File size limit: 5 MB. Allow to upload photo in .jpeg/.png format
b) EHV Line Status
Status
Percentage completed (%), if in process
Photo upload | File upload | File size limit: 5 MB. Allow to upload photo in .jpeg/.png format
c) 33KV Line Status
Status
Percentage completed (%), if in process
Photo upload | File upload | File size limit: 5 MB. Allow to upload photo in .jpeg/.png format
d) PSS & Control Room Status
Status
Percentage completed (%), if in process
Photo upload | File upload | File size limit: 5 MB. Allow to upload photo in .jpeg/.png format
5. Commissioning Plan
5.1 Table - 1
WTGs already erected and ready for commissioning | WTGs erected however not ready for commissioning or under process of pre-commissioning | FTC application already filed for capacity | Additional FTC application proposed to be filed for Capacity | Pending point w.r.t. FTC if, any | Status of Dynamic VAR Compensation | Trial Run Status (Completed /under process) | ToC Document Upload Button
Validation - The sum of these colums should not be more than number of erected WTGs |  |  |  |  | Fetched from Grid Connectivity (3) |  | File upload
5.2 Table - 2
Quarter-wise Commissioning Target:
S. No. | Month | Capacity
1
2
3

## HPD Progress Report Format
HPD = Wind-Solar Hybrid/RTC/Assured Peak Power Developer
Last updated on dd.mm.yyyy
Note: If any component is multi-located, such individual location details shall be furnished in remarks
Note: Other Remarks relevant to the specific field
1. Status of connectivity (Inter connection voltage level)
| Solar | Wind | ESS | Remarks
Connectivity application date submitted by RPD to CTU | Date Picker | Date Picker | Date Picker | Text
Connectivity application capacity submitted by RPD to CTU (MW) | Number | Number | Number | Text
Interim Connectivity Granted date by CTUIL | Date Picker | Date Picker | Date Picker | Text
Final Connectivity Granted date by CTUIL | Date Picker | Date Picker | Date Picker | Text
Name of ISTS substation | Text | Text | Text | Text
Status of ISTS substation/TL as per JCC | Text | Text | Text | Text
Any other remarks | Text | Text | Text | Text
2. Land Arrangement Status with Acquistition Details
| Solar | Wind | ESS
Identification
Location - Latitude | Text | Text | Text
Location - Longitude | Text | Text | Text
Total Area required for Project (Acres) | Number | Number | Number
Status of ownership
Extent of land acquired (Acres) | Number | Number | Number
Percentage Land Acquired | = (Extent of land acquired / Total Area required for Project) * 100 | = (Extent of land acquired / Total Area required for Project) * 100 | = (Extent of land acquired / Total Area required for Project) * 100
Any other remarks | Text | Text | Text
3. Status of Financing Arrangements
Equity Tie-up
Status of Debt
Financial Lender Details (Name of Bank/NBFC/Others; in case of yes in Status of Debt) | Text | Text | Text
Equity Amount (In Cr.) | Number | Number | Number
Debt Amount (In Cr.) | Number | Number | Number
Financial Closure Status
Financial Closure Date (If "Yes" in case of Financial Closure Status | Date Picker | Date Picker | Date Picker
Any other remarks | Text | Text | Text
4. Status of Clearances (as applicable)
| Solar | Wind | ESS
MoD Land Area
MoD Approval Process Completed (only in case of "Yes" in MoD Land Area)
Forest Land Area
Forest Land Approval Process Completed (only in case of "Yes" in Forest Land Area)
Mining Land Area
Mining Land Approval Process Completed (only in case of "Yes" in Mining Land Area)
Local Body Land Area
Local Body Land Area Process Completed (only in case of "Yes" in Local Body Land Area)
Any other clearances | Text | Text | Text
Any other remarks | Text | Text | Text
5. Status of Transmission Line (From Project PSS to CTUIL/STU Substation)
| Solar | Wind | ESS (if applicable)
Transmission line required for the project (Km) | Number | Number | Number
Transmission Line completed (Km) | Number | Number | Number
Voltage rating of transmission line | Number | Number | Number
Percentage completed | = (Transmission Line completed / Transmission line required for the project) * 100 | = (Transmission Line completed / Transmission line required for the project) * 100 | = (Transmission Line completed / Transmission line required for the project) * 100
Any other remarks | Text | Text | Text
6. Design status of Project
| Solar | Wind | ESS
Layout Drawings/Micrositing
Equipment Drawings
ALMM/RLMM |  |  | N/A
Any other remarks | Text | Text | Text
7. Supply Status
| Solar | Wind | ESS
PO/Agreement Status of Modules/WTGs/ESS
Quantity Required for Project Site | Number | Number | Number
Date of PO/Agreement (In Case Yes) | Date Picker | Date Picker | Date Picker
Make of Modules/WTGs/ESS | Text | Text | Text
Model/Ratings of Modules/WTGs/ESS | Text | Text | Text
Delivery of Power Transformer (in Nos.) | Number | Number | Number
Model/Ratings of Power Transformers | Text | Text | Text
Delivery of Modules/WTGs/ESS to Project Site | Number | Number | Number
Percentage of Modules/WTGs/ESS to Project Site | (Delivery of Modules/WTGs/ESS to Project Site / Quantity Required for Project Site) * 100 | (Delivery of Modules/WTGs/ESS to Project Site / Quantity Required for Project Site) * 100 | (Delivery of Modules/WTGs/ESS to Project Site / Quantity Required for Project Site) * 100
Delivery of Inverter (in Nos.) | Number | N/A | Number
Supply status of Inverter Transformer (%) | Number | Number | Number
No. of transmission line towers required for the Project | Number | Number | Number
Delivery of transmission line towers (in Nos.) | Number | Number | Number
Percentage of Line Towers (%) | =(Delivery of transmission line towers / No. of transmission line towers required for the Project) * 100 | =(Delivery of transmission line towers / No. of transmission line towers required for the Project) * 100 | =(Delivery of transmission line towers / No. of transmission line towers required for the Project) * 100
Overall status of supply equipments for the project (%) | Number | Number | Number
8. Civil work status
| Solar | Wind | ESS
Solar pile foundation/WTG foundation/ESS foundations required for the project (in Nos.) | Number | Number | Number
Completion Status of Solar pile foundation/WTG foundation/ESS foundations required for the project (in Nos.) | Number | Number | Number
Percentage completion of Solar pile foundation/WTG foundation/ESS foundations | (Completion Status of Solar pile foundation/WTG foundation/ESS foundations required for the project / Solar pile foundation/WTG foundation/ESS foundations required for the project) * 100 | (Completion Status of Solar pile foundation/WTG foundation/ESS foundations required for the project / Solar pile foundation/WTG foundation/ESS foundations required for the project) * 100 | (Completion Status of Solar pile foundation/WTG foundation/ESS foundations required for the project / Solar pile foundation/WTG foundation/ESS foundations required for the project) * 100
Substation-foundation works completed (%) | Number | Number | Number
Tranmission Line tower foundation completion status (in Nos.) | Number | Number | Number
Percentage of Line Tower Foundation completed (%) | (Tranmission Line tower foundation completion status / No. of transmission line towers required for the Project) * 100 | (Tranmission Line tower foundation completion status / No. of transmission line towers required for the Project) * 100 | (Tranmission Line tower foundation completion status / No. of transmission line towers required for the Project) * 100
Any other remarks | Text | Text | Text
9. Erection
| Solar | Wind | ESS
Modules/WTG/ESS (in Nos.) | Number | Number | Number
Percentage of Modules erected (%) | (Modules/WTG/ESS / Quantity Required for Project Site) * 100 | (Modules/WTG/ESS / Quantity Required for Project Site) * 100 | (Modules/WTG/ESS / Quantity Required for Project Site) * 100
Solar/Wind/ESS (completion status in MW) | Number | Number | Number
Project Pooling Substation Completion Status
Tranmission Line Towers erected (in Nos.) | Number | Number | Number
Percentage of Transmission Line Towers erected (%) | (Tranmission Line Towers erected / No. of transmission line towers required for the Project) * 100 | (Tranmission Line Towers erected / No. of transmission line towers required for the Project) * 100 | (Tranmission Line Towers erected / No. of transmission line towers required for the Project) * 100
Dedicated Transmission Line Stringing completed (in Km) | Number | Number | Number
Any other remarks | Text | Text | Text
10. Commissioning
| Solar | Wind | ESS
Cumulative Capacity till previous month of Solar/Wind/ESS (in MW) | Number | Number | Number
This month Commissioned capacity of Solar/Wind/ESS (in MW) | Number | Number | Number
Cumulative Capacity of Solar/Wind/ESS (in MW) | (Cumulative Capacity till previous month + This month Commissioned capacity) for Solar | (Cumulative Capacity till previous month + This month Commissioned capacity) for Wind | (Cumulative Capacity till previous month + This month Commissioned capacity) for ESS
Any other remarks | Text | Text | Text

## Monthly Project Progress Report
MONTHLY PROGRESS MONITORING REPORT TO SUBMITTED BY RPD
KPIs | Opening Percentage (Closing Percentage of Previous Month) | Progress Percentage (Cannot be more than (100 - current month opening percentage), can be edited in current month) | Closing Percentage ( = Progress + Opening Percentage) | Asking Rate = (100 - Closing Percentage) / (Remaining Months) | Remarks | Special Remarks
Finance Arrangement | 10 | 0 | 10 | 95%
Land Arrangement | 0 | 5 | 5 | 90%
Tie-up with OEM
Supply of Equipments | 0 | 0 | 0 | 0%
Civil Works & Construction | 0 | 7 | 7 | 50%
Connectivity | 0 | 0 | 0 | 0%
BoS | 0 | 0 | 0 | 0%
Also add status update tab to be added at any time by developer, developer will add exhaustive fields in this tab

## C&P Components
Integrated Information and Energy Management of Scheme-Based Renewable Projects
C&P Part
Manage RFS
Project Type |  |  |  |  | Scheme
RfS Number |  |  |  |  | Total Capacity Awarded (Open) (MW)
Name of the Tender |  |  |  |  | Total Capacity Awarded (DCR) (MW)
Total Capacity Tendered (MW) |  |  |  |  | RfS Issue Date (DD-MM-YYYY)
Central/State* |  |  | *If select Central then column (B14) should be grey out and if State then state list should be in B15 with multiple state selection feature |  | Last Date of Bid Submission (DD-MM-YYYY)
Name of State (if State Scheme) |  |  |  |  | e-RA Date (DD-MM-YYYY)
Solar Park/Non-solar Park |  |  |  |  | H-1 Tariff Awarded (INR/kWh)
ISTS/ non-ISTS |  |  |  |  | L-1 Tariff Awarded (INR/kWh)
Domestic/ Global Competitive Bidding |  |  |  |  | H-1 VGF/ CFA Awarded (INR/MW)
VGF/ Non-VGF |  |  |  |  | L-1 VGF/ CFA Awarded (INR/MW)
Tariff Ceiling (INR/kWh) |  |  |  |  | Remarks
| Submit |  | Code: | RFS-***-YYYY-XXX |  | ***Solar=SD, Hybrid=HY, Wind-WD, RTC-RTC, Rooftop-RT, Peak Power-PP
Manage LoA
Manage LOA ---> Select Proj Type--> Select Scheme--> Select RFS-->Manage LoAs
Authorized Representative Details:
SAP ERP Vendor Code |  | Textbox/Numeric |  |  | Type of Tariff* |  |  | *In Case of Off-Peak tariff--> Peak Tariff (INR/kWh) (ISTS-VII) should be there | Name
Name of the Bidding Company |  | automatic |  |  | Maximum VGF Eligibility (INR/MW)** |  |  | **Should not be visible in case of Non-VGF selected in D22 | Address
LoA Number |  |  |  |  | Maximum VGF Eligibility (INR)** |  |  |  | Contact Number
LoA Date (DD-MM-YYYY) |  |  |  |  | Whether Foreign Bidder |  | Yes/No |  | Email-ID
Capacity Awarded (MW) |  |  |  |  | Country of Origin of the Bidder, in case of Foreign Bidder |  |  |  | Upload LoA Doc
|  | Add LoA |  | + add multiple LoAs for RfS (All LoAs capacity should be equal or less than RfS awarded capacity)
Autogenerated number for LoA - Codification Format:
Note: PBG should be submitted with in 70 days from LoA. Email Notification
Note: Email Notifications P-A (30 days from LoA) and P-B (7 days b/f signing of PPA)
only for first time user, An automatic email will trigger to vendor on email (L37) having - UserName (SAP ERP Vendor Code) & Password (System Generated - having feature to reset/forget on first login)

## DISCOM Master sheet
DISCOM Details | ERP Vendor Code* | User Name for Login by DISCOM
| ERP Vendor Name* | DISCOM Full Name | Note: 1. Field with an asterisk (*) represents a Mandatory Field. 2. ERP Vendor Code is the username used by the DISCOM to login. 3. The Email ID field must be entered with utmost care, as it will be used for all official communications with the DISCOM.
| Abbreviated Name | e.g. APDISCOM
| Address* | Address Details
City*
State*
PIN Code
| Authorized Representative Name* | -
| Authorized Representative Designation* | -
| Email ID* | Email to be used for all communication IIEM-SRP
| Mobile No.* | Must be 10 digits
| PAN No.* | Must be 10 characters long, only alphanumeric
| GSTIN* | Must be 15 characters long, only alphanumeric
| Password* | Minimum 8 characters, 1 capital letter, 1 symbol, 1 number

## RPD Master sheet
RPD Details | ERP Vendor Code* | User Name for Login by RPD
| ERP Vendor Name* | DISCOM Full Name | Note: 1. Field with an asterisk (*) represents a Mandatory Field. 2. ERP Vendor Code is the username used by the RPD to login. 3. RPD here represents the developer of the projects for Solar, Wind, Hybrid projects. 4. The Email ID field must be entered with utmost care, as it will be used for all official communications with the RPD.
| Abbreviated Name | e.g. JBVNL
| Address* | Address Details
City*
State*
PIN Code
| Authorized Representative Name* | -
| Authorized Representative Designation* | -
| Email ID* | Email to be used for all communication IIEM-SRP
| Mobile No.* | Must be 10 digits
| PAN No.* | Must be 10 characters long, only alphanumeric
| GSTIN* | Must be 15 characters long, only alphanumeric
| Password* | Minimum 8 characters, 1 capital letter, 1 symbol, 1 number

## FI
Manage Financial Details
Filters to reach LoA as discussed
Display relevant fields - Scheme Name, RfS Name, LoA No, Award Capacity (MW), Bidder Name
Success Fee Details:
Part-A:
Invoice/Advance Reciept: | Doc uploader |  | Amount (Rs.): | Auto-Calculated |  | Payment Date: | date picker
Part-B:
Invoice/Advance Reciept: | Doc uploader |  | Amount (Rs.): | Auto-Calculated |  | Payment Date: | date picker
Submit
Performace Bank Guarantee Details:
Action Type: | drop down | Submission, Extension, Release | Amount (Rs.): | (Fill First Time only) | Valid Till/Release Date: | date picker |  | Add Btn (+)
Attachment: | upload doc |  |  | Note: Remove submission or Release avialble in dropdown only once i.e. for one entry only.
NON EDITABLE DATA - POPUP
Example Details Table
| Submitted date | 2023-11-17 | 100000000
| Extenstion date - 1 | 2024-01-01 | 100000000 | Note: Amount will be filled only in case of submission
| Extenstion date - 2 | 2024-01-01 | 100000000
| Released | 2024-01-01 | 100000000
Submit
No field is mandatory

## PPA
Power Purchase Agreement cum Project Profile
Show all PPAs and provide the filter (Rfs and LoA) and Date filter (From and To) on effective date of PPA
Add PPA
| Select Scheme-->RfS-->LoA |  | Show Details - Bidder Name, LoA Date, LoA Capacity (MW)
Validate and show below messages on LoA selection from dropdown: 1. Success Fee - "Submitted vide dated xx-xx-xxxx". (if found) or "Success Fee not found" (if not found) 2. Performance Bank Guarantee - "Submitted vide dated xx-xx-xxxx". (if found) or "PBG not found" (if not found) 3. Availability of PSA for mapping - "xxx MW of PSA signed capacity is available for PPA mapping." or "No PSA found for the selected RfS for PPA initiation and subsequent mapping." (if no PSA found for the selected RfS).
| PPA Capacity (MW) |  |  |  | Project Developer/SPV is different from Successful Bidder: | Yes/No
| Name of RPD/ Special Purpose Vehicle (SPV) |  | search field |  | Company Address
if Yes, | SPV/RPD ERP Code |  | automatic frm SPV name |  | CIN
Authorized Representative Details:
| Name |  |  |  | Designation |  | Office address
| Mobile Number |  |  |  | Email-ID
Project Location Details:
| Village |  |  |  | Tehsil/Taluka |  | District
| State |  |  |  | Logitude |  | Latitude
Pincode
Upload Documents for PPA Signing
Please furnish the relevant documents as per below:
Duly signed duplicate copy of LoA*
| Payment of Success Charges* |  |  |  |  | On Submit --> PPA number has been generated (YYYY-<Prj Type Code>-<Scm Code>-PPAXXX)
Certificate of Incorporation*
Details of promoters and their shareholding in the SPD/WPD/HPD*
Memorandum of Association (MoA)*
Article of Association (AoA)*
Board resolution from bidding company for execution of project through SPV
Board resolution from proposed SPV for execution of Project
Performance Bank Guarantee/ Payment on Order Instrument*
| Board Resolution from SPD/WPD/HPD for authorization of signing of PPA* |  |  |  |  | In case of 'Reject' --> Mandatory to submit 'Remarks'
Board Resolution from Bidding Company’s Affiliate(s) in case of submission of undertaking of equity infusion at the time of bidding
Detailed L-2 Schedule for the Project
Other documents (if any)
Details filled by SECI
Tariff & Billing Details:
PPA Tariff (Rs/kWh):
| Percentage Year-wise Escalation (if any): |  |  |  | Escalation Period (Years):
| Due days of Invoice (in days) |  |  |  | Rebate due days for 1.5%
| Rebate due days for 1% |  |  |  | Rebate due days for 2%
| Declared MUs as per PPA: |  |  |  | Minimum MUs till 10 years from SCD as per PPA:
| Maximum MUs as per PPA: |  |  |  | Minimum MUs after 10 years of SCD as per PPA:
| PPA Excess Energy Tariff (Rs/kWh) |  |  |  | Due days of LPS (in days)
Project Schedule (w.r.t Effective date of PPA)
| SECI Project ID |  |  |  | Duration of PPA (Years)
| SECI PPA Code |  |  |  | SAP PPA PO Number
| Effective Date of PPA |  |  |  | Date of Signing of PPA
| Due date for Financial Closure |  |  |  | Due date for Land Acquisition
| Scheduled Date of Commissioning |  |  |  | Upload Signed PPA Document* | Upload
[5 empty] | Upload Signed PPA Document Amendment (if any) | Upload
| Mapping of PPA to PSA | Map PPA <--> PSA
on checkbox selection, PPA cap for signing' column enabled
| Selction (Checkbox) | PSA No. | PSA Avl Cap (MW) | DISCOM Name | PPA Cap for Mapping
|  | SUBMIT |  | PPA Code | PPA_YYYY_CAP_XXX
Vendor Login
On Submit, credentails emailed to SPV for further login and project monitoring

## FC
SECI Project ID: |  |  | Project Capacity (MW): | RfS Code:
PPA Code: |  |  | Effective Date of PPA: | Due date for Financial Closure:
Manage Financial Closure/ Conditions Subsequent
Estimated Project Cost (Crore Rs.): |  |  | Source of Fund:
Loan Amount (Crore Rs.): |  |  | Lending Agency:
Status of Loan:
Please furnish the relevant documents as per below:
Necessary Certificate towards Project financing arrangements for Project(s)*
Detailed Project Report (DPR)*
Undertakings by the Project Company*
Copy of Agreement/ MOU entered into / Purchase Order with acceptance, for the supply of Plants and Equipment*
Ownership of the SPD: Latest Shareholding Pattern of the Project Company*
Deposition of Extension charges in case of delay
Additional documents if required
Remarks:
Submit
Details filled by SECI
Remarks:
| Accept |  | Reject | Generate Compliance Certificate
Capture 'Actual Date of Financial Closure' on submit |  |  | (mandatory in case of 'Reject')

## LC
SECI Project ID: |  |  | Project Capacity (MW): |  | RfS Code:
PPA Code: |  |  | Effective Date of PPA: |  | Due date Land Acquisition:
Land Arrangement/ Acquisition
Total Land Requirement (Hectare): |  |  | Type of Land: | Government | Private | Both
Land Acquired (Hectare): |  |  | Mode of Land Acquisition: | Govt. allotted, Lease, Buy
Target date of complete Land Acquisition:
Please furnish the relevant documents as per below:
Sworn Affidavit*
Land Lease Deed Documents*
Other documents if required
Remarks:
Submit
Details filled by SECI
Remarks:
| Accept |  | Reject |  | Generate Compliance Certificate
Capture 'Actual Date of Land Acquisition' on submit |  |  | (mandatory in case of 'Reject')

## CoD
SECI Project ID: |  |  | Project Capacity (MW): | RfS Code:
PPA Code: |  |  | Effective Date of PPA: | Scheduled Date of Commissioning:
Part Commissioning/ Full Commissioning of Project
Is this Part Commissioning: | Yes | No | Commissioning Capacity (MW): | if Yes then allow to add capacity till total project capaicty | Part/Full commissioning Capacity
|  |  |  | if No then display total project capacity | Date of Part/Full Commissioning
Please furnish the relevant documents as per below:
Board Resolution wrt Authorised Signatory
Connectivity and Long Term Access, along with Transmission Agreement
Metering Scheme Approval provided by CTU/POSOCO
Copy of invoices for major items such PV Modules, Inverters, Cables, Transformers etc. All supporting documents towards meeting the technical compliance along with datasheet/ warranty certificates/ contract agreement etc.
Installation report duly signed by the authorized signatory.
Plant Layout, Plant (AC & DC) SLD, along with Inverter-wise module details.
CEIG/CEA report for Project & transmission network installed by SPD along with all annexures/attachments.
Consent to operate from the concerned Authority (if required).
Connectivity Report
Synchronization Certificate.
SLDC/ RLDC acknowledging successful data communication between plant end and SLDC/RLDC
Inverter readings, Photographs of major equipment installed.
Undertakings w.r.t Performance Monitoring, Safe disposal etc
SCADA Login details
Additional documents if required
Remarks:
Submit
Details filled by SECI
Remarks:
| Accept |  | Reject | Generate Compliance Certificate
Capture 'Actual Date of Commissioning' on submit |  |  | (mandatory in case of 'Reject')

## Mask Codification Format List
Item | Mask format | Updated Mask
RfS | 2019-HPD-SBG-ISTS-PP-T7-R08 | 2019-RFS-HPD-SBG-ISTS-PP-T7-R08
PSA | PSA-SD-Hybrid_SBG_T-2024-CSPDCL-400-01 | 2024-PSA-SD-Hybrid_SBG-T-CSPDCL-400-1
PPA | 2024-ST-SBG-ISTSTT1-PPA01 | 2024-PPA-ST-SBG-ISTST-T1-1
LoA | 2019-HPD-SBG-ISTS-PP-T7-R08-L03 | 2019-LOA-HPD-SBG-ISTS-PP-T7-R08-3