## Sheet1
Tender Details | [13 empty] | eRA Details | [5 empty] | Successful Project Developers Details |  |  | LOA/LOI Details | [14 empty] | Signing of PSA Details | [5 empty] | Signing of PPA Details | [11 empty] | Under Implementation Details | [12 empty] | Commissioning Details
SI. No | Tendering Agency | Tender Title | Tender NIT | RFS Number | Capacity (MW) | Date of issue of NIT | Date of issue of RfS | Pre Bid Meeting Date | Bid Closing Date | Type of Technology | Storage | Greenshoe | Additional Information | Last Bid Opening Date | Date of eRA | Capacity awarded by eRA (MW) | Unallotted Capacity (MW) | Project Developers Participated | Total Bid Capacity Received (MW) | Cancelled Capacity (MW) | Project Developer Name | Awarded Capacity (MW) | Cancelled Capacity (MW) | Date of issue of LoA | LOA Capacity (MW) | Tariff (Rs/kWhr) | Type of Technology | Solar Capacity (MW) | Wind Capacity (MW) | Storage Capacity (MW) | Status of Connectivity | Connectivity Applied to STU/CTU | Connectivity Number | Application Date | Grant Date | Substation Name | Substation Location | Date of Final Connectivity | Date of PSA | PSA Capacity (MW) | PSA Signed State | PSA Duration (In Years) | DISCOM Name | Electricity Per Unit Cost (Rs/kWhr) | SPV Name | Contact Person Name | Contact Person Nunmber | Date of PPA | PPA Capacity (MW) | Per Unit cost of electricity as per said PPA (Rs/kWhr) | Project Location | Duration of PPA(In Years) | Financial Closure Achieved? | Date of Financial Closure | Seheduled Commissioning Date (SCOD) | Extended SCOD, If any. | Technology Type | Commissioning Capacity (MW) | Solar Capacity (MW) | Wind Capacity (MW) | Storage Capacity (MW) | Status of Connectivity (Yet to Apply/Applied/Granted) | Connectivity Applied to STU/CTU | Connectivity Number | Application Date | Grant Date | Substation Name | Substation Location | Date of final connectivity | Commissioning Date | Capacity Commissioned (MW) | Remarks, If any
1 | SECI Wind | Wind (Tranche-I) | -- | SECI/C&P/WPD/RfS/1000MW/102016 | 1000 | NA | 28-10-2016 | 29-11-2016 | 10-01-2017 | Wind | Without Storage | With Greenshoe | -- | 11-01-2017 | 23-02-2017 | 1049.9 | 0 | 13 | 2593.9 | 0 | Mytrah Energy India Private Limited | 250 | -- | 05-04-2017 | 250 | 3.46 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | [6 empty] | Mytrah Vayu (Sabarmati) Private Limited | Debasish Das | 9560872323 | 21-07-2017 | 250 | 3.46 | TAMIL NADU | 25 |  | NA | 04-10-2018 | 13-11-2018 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 400 kV Thirunelveli | Thirunelveli | NA | 2019-05-09 | 250 | , Commissioned Project
[21 empty] | Green Infra Wind Energy Limited | 249.9 | -- | 05-04-2017 | 249.9 | 3.46 | Wind |  | 249.9 | -- | Granted | -- | -- | NA | NA | -- | -- | NA | [6 empty] | Green Infra Renewable Energy Limited | Varun Agrawal | 9810828423 | 21-07-2017 | 249.9 | 3.46 | TAMIL NADU | 25 |  | NA | 04-10-2018 | 13-04-2019 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 400 kV Thirunelveli | Thirunelveli | NA | 2018-10-07 | 249.9 | , Commissioned
[21 empty] | Inox Wind Infrastructure Services Limited | 250 | -- | 05-04-2017 | 250 | 3.46 | Wind |  | 250 | -- | Granted | -- | -- | NA | NA | -- | -- | NA | [6 empty] | Wind One renergy Private Limited, Wind Two renergy Private Limited, Wind Three Renergy Private Limited, Wind Four Renergy Private Limited, Wind Five Renergy Private Limited | Venkatesh Soni, Venkatesh Soni, Venkatesh Soni, Venkatesh Soni, Venkatesh Soni | 45055226070 | 21-07-2017, 21-07-2017, 21-07-2017, 21-07-2017, 21-07-2017 | 250 | 17.3 | GUJARAT, GUJARAT, GUJARAT, , GUJARAT | 125 | , , , , | NA, NA, NA, NA, NA | 04-10-2018, 04-10-2018, 04-10-2018, 04-10-2018, 04-10-2018 | 13-06-2019, 13-06-2019, 13-06-2019, 13-06-2019, 13-06-2019 | Wind, Wind, Wind, Wind, Wind | 0 | , , , , | , , , , | , , , , | Granted, Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU , CTU | NA, NA, NA, NA, NA | NA, NA, NA, NA, NA | NA, NA, NA, NA, NA | 756/400/220 kV Bhuj, 756/400/220 kV Bhuj, 756/400/220 kV Bhuj, 756/400/220 kV Bhuj, 756/400/220 kV Bhuj | Bhuj, Bhuj, Bhuj, Bhuj, Bhuj | NA, NA, NA, NA, NA | 2019-07-02 | 50 | , , , , Commissioned , Commissioned , Commissioned , Terminated , Commissioned
[70 empty] | 2019-07-04 | 50
[70 empty] | 2019-06-29 | 50
[70 empty] | 2019-07-04 | 50
[21 empty] | Ostro Kutch Wind Private Limited | 250 | -- | 05-04-2017 | 250 | 3.46 | Wind |  | 250 | -- | Granted | -- | -- | NA | NA | -- | -- | NA | [6 empty] | Ostro Kutch Wind Private Limited | Deepak Gupta | 9958545441 | 21-07-2017 | 250 | 3.46 | GUJARAT | 25 |  | NA | 04-10-2018 | 30-03-2019 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 220/400 KV Bachau S | Bachau | NA | 2019-03-29 | 250 | , Commissioned
[21 empty] | Adani Green Energy (MP) Limited | 50 | -- | 05-04-2017 | 50 | 3.46 | Wind |  | 50 | -- | Granted | -- | -- | NA | NA | -- | -- | NA | [6 empty] | Adani Green Energy (MP) limited | Durgesh Gupta | 9711589569 | 21-07-2017 | 50 | 3.46 | GUJARAT | 25 |  | NA | 04-10-2018 | 05-11-2019 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 756/400/220 kV Bhuj | Bhuj | NA | 2019-10-20 | 50 | , Commissioned
2 |  | Wind (Tranche-II) | -- | SECI/C&P/WPD/1000MW/T2/RfS/052017 | 1000 | NA | 31-05-2017 | 23-06-2017 | 14-07-2017 | Wind | Without Storage | Without Greenshoe | -- | 14-08-2017 | 04-10-2017 | 1000 | 0 | 12 | 2892 | 0 | ReNew Power Ventures Private Limited | 250 | -- | 03-11-2017 | 250 | 2.64 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 24-11-2017, 24-11-2017, 24-11-2017 | 250 | UTTAR PRADESH, PUNJAB, GOA | 75 | UPPCL, PSPCL, GOA | 7.92 | ReNew Power Private Limited | Deepak Gupta | 2147483647 | 02-01-2018 | 250 | 2.61 | GUJARAT | 25 |  | NA | 03-05-2019 | 12-12-2019 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 220/400 KV Bachau S | Bachau | NA | 2021-02-06 | 230.1 | , 230.1 MW Commissioned, balance capacity of 19.9 MW has been cancelled.
[21 empty] | Orange Sironj Wind Power Private Limited | 200 | -- | 03-11-2017 | 200 | 2.64 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 24-11-2017, 13-12-2017 | 200 | BIHAR, HARYANA | 50 | BSPHCL, HPPC | 5.28 | Greenko Sironj Wind Power Private Limited | Anish Pasrija | 9717755423 | 19-12-2017 | 200 | 2.64 |  | 25 |  | NA | 03-05-2019 | NA | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 400/230 kV Tuticorin | Tuticorin | NA | 2019-04-13 | 200 | , Commissioned
[21 empty] | Inox Wind Infrastructure Services Limited | 250 | -- | 03-11-2017 | 250 | 2.65 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 13-12-2017, 24-11-2017 | 250 | HARYANA, UTTAR PRADESH | 50 | HPPC, UPPCL | 5.3 | Haroda Wind Energy Private Limited, Khatiyu Wind Energy Private Limited, Vigodi Wind Energy Private Limited, Ravapar Wind Energy Private Limited, Nani Virani Wind Energy Private Limited | Venkatesh Soni, Venkatesh Soni, Venkatesh Soni, Venkatesh Soni, Venkatesh Soni | 45055226070 | 27-12-2017, 27-12-2017, 27-12-2017, 27-12-2017, 27-12-2017 | 250 | 13.25 | , , , , GUJARAT | 125 | , , , , | NA, NA, NA, NA, NA | 03-05-2019, 03-05-2019, 03-05-2019, 03-05-2019, 03-05-2019 | 28-06-2021, 28-06-2021, 28-06-2021, 28-06-2021, 12-12-2021 | Wind, Wind, Wind, Wind, Wind | 0 | , , , , | , , , , | , , , , | Granted, Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU , CTU | NA, NA, NA, NA, NA | NA, NA, NA, NA, NA | NA, NA, NA, NA, NA | 756/400/220 kV Bhuj, 756/400/220 kV Bhuj, 756/400/220 kV Bhuj, 756/400/220 kV Bhuj, 756/400/220 kV Bhuj | Bhuj, Bhuj, Bhuj, Bhuj, Bhuj | NA, NA, NA, NA, NA | 2022-05-12 | 30 | , Terminated , Terminated , Terminated , Terminated , 30 MW Commissioned, balance capacity stands terminated.
[21 empty] | Green Infra Wind Energy Limited | 250 | -- | 03-11-2017 | 250 | 2.65 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 24-11-2017, 24-11-2017, 24-11-2017 | 250 | JHARKHAND, ODISHA, ASSAM | 75 | JBVNL, GRIDCO, APDCL | 7.95 | Green Infra Wind Energy Limited | Raman Gulati | 9868165784 | 02-01-2018 | 250 | 2.65 | GUJARAT | 25 |  | NA | 03-05-2019 | 03-01-2020 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 756/400/220 kV Bhuj | Bhuj | NA | 2020-02-06 | 250 | , Commissioned
[21 empty] | Adani Green Energy (MP) Limited | 50 | -- | 03-11-2017 | 50 | 2.65 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 24-11-2017 | 50 | PUNJAB | 25 | PSPCL | 2.65 | Adani Wind Energy Kutchh One Ltd | Durgesh Gupta | 9711589569 | 29-12-2017 | 50 | 2.65 | GUJARAT | 25 |  | NA | 03-05-2019 | 03-01-2020 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 756/400/220 kV Bhuj | Bhuj | NA | 2020-03-05 | 50 | , Commissioned
3 |  | Wind (Tranche-III) | -- | SECI/C&P/WPD/2000MW/T3/RfS/112017 | 2000 | NA | 12-01-2018 | NA | 02-02-2018 | Wind | Without Storage | Without Greenshoe | -- | 05-02-2018 | 13-02-2018 | 2000 | 0 | 12 | 3699.8 | 0 | ReNew Wind Energy (AP2) Private Limited | 400 | -- | 23-02-2018 | 400 | 2.44 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 17-05-2018, 23-03-2018 | 400 | HARYANA, ODISHA | 50 | HPPC, GRIDCO | 4.88 | ReNew Wind Energy (AP2) Private Limited, ReNew Wind Energy (AP2) Private Limited | Deepak Gupta, Deepak Gupta | 19917090882 | 24-05-2018, 24-05-2018 | 400 | 4.88 | , GUJARAT | 50 | , | NA, NA | 24-11-2019, 24-11-2019 | 31-08-2021, 31-08-2021 | Wind, Wind | 0 | , | , | , | Granted, Granted | CTU , CTU | NA, NA | NA, NA | NA, NA | 220/400 KV Bachau S, 220/400 KV Bhuj S/S | Bachau, Bhuj | NA, NA | 2021-03-11 | 300 | , Under Litigation , Commissioned
[21 empty] | Green Infra Wind Energy Limited | 300 | -- | 23-02-2018 | 300 | 2.44 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 06-04-2018, 23-03-2018 | 300 | BIHAR, PUNJAB | 50 | BSPHCL, PSPCL | 4.88 | Green Infra Wind Energy Limited | Raman Gulati | 9868165784 | 24-05-2018 | 300 | 2.44 | GUJARAT | 25 |  | NA | 24-11-2019 | 29-07-2020 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 756/400/220 kV Bhuj | Bhuj | NA | 2020-06-18 | 300 | , Commissioned
[21 empty] | Inox Wind Infrastructure Services Limited | 200 | -- | 23-02-2018 | 200 | 2.44 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-03-2018 | 200 | JHARKHAND | 25 | JBVNL | 2.44 | Aliento Wind Energy Private Limited, Flurry Wind Energy Private Limited, Tempest Wind Energy Private Limited, Vuelta Wind Energy Private Limited | Venkatesh Soni, Venkatesh Soni, Venkatesh Soni, Venkatesh Soni | 36044180856 | 24-05-2018, 24-05-2018, 24-05-2018, 24-05-2018 | 200 | 9.76 | , , , | 100 | , , , | NA, NA, NA, NA | 24-11-2019, 24-11-2019, 24-11-2019, 24-11-2019 | 31-08-2022, 31-08-2022, 31-08-2022, 31-08-2022 | Wind, Wind, Wind, Wind | 0 | , , , | , , , | , , , | Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU | NA, NA, NA, NA | NA, NA, NA, NA | NA, NA, NA, NA | 756/400/220 kV Bhuj-, 756/400/220 kV Bhuj-, 756/400/220 kV Bhuj-, 756/400/220 kV Bhuj- | Bhuj, Bhuj, Bhuj, Bhuj | NA, NA, NA, NA | -- | -- | --
[21 empty] | Torrent Power Limited | 499.8 | -- | 23-02-2018 | 499.8 | 2.44 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 22-03-2018, 06-04-2018 | 499.8 | MADHYA PRADESH, BIHAR | 50 | MPPMCL, BSPHCL | 4.88 | Torrent Power Limited | Jaydip achudasama | 9227410136 | 24-05-2018 | 499.8 | 2.44 |  | 25 |  | NA | 24-11-2019 | NA | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 756/400/220 kV Bhuj | Bhuj | NA | -- | -- | --
[21 empty] | Alfanar Company | 300 | -- | 23-02-2018 | 300 | 2.45 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-03-2018, 03-04-2018, 28-03-2018, 06-04-2018 | 300 | DELHI, DELHI, DELHI, BIHAR | 100 | BRPL, BYPL, TPDDL, BSPHCL | 9.8 | Alfanar Energy Private Limited | Md Irfan | 8184900786 | 24-05-2018 | 300 | 2.45 | GUJARAT | 25 |  | NA | 24-11-2019 | 29-05-2021 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 756/400/220 kV Bhuj | Bhuj | NA | 2021-03-31 | 300 | , Commissioned
[21 empty] | Adani Green Energy (MP) Limited | 250 | -- | 23-02-2018 | 250 | 2.45 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 22-05-2018, 23-03-2018, 06-04-2018 | 250 | GOA, CHHATTISGARH, BIHAR | 75 | GOA, CSPDCL, BSPHCL | 7.35 | Adani Green Energy MP limited | Durgesh Gupta | 9711589569 | 24-05-2018 | 250 | 2.45 |  | 25 |  | NA | 24-11-2019 | NA | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 756/400/220 kV Bhuj | Bhuj | NA | -- | -- | --
[21 empty] | Betam Wind Energy Private Limited | 50.2 | -- | 23-02-2018 | 50.2 | 2.45 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 06-04-2018 | 50 | BIHAR | 25 | BSPHCL | 2.45 | Vivid Solaire Energy Private Limited | Sarang Patil | 9923505000 | 24-05-2018 | 50.2 | 2.45 | TAMIL NADU | 25 |  | NA | 24-11-2019 | NA | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 400/230 kV Tuticorin | Tuticorin | NA | 2019-11-24 | 50.2 | , Commissioned
4 |  | Wind (Tranche-IV) | -- | SECI/C&P/WPD/2000MW/T4/RfS/022018 | 2000 | NA | 05-02-2018 | 15-02-2018 | 16-03-2018 | Wind | Without Storage | Without Greenshoe | -- | 16-03-2018 | 05-04-2018 | 2000 | 0 | 12 | 2933.2 | 0 | Srijan Energy Systems Private Limited | 250 | -- | 01-06-2018 | 250 | 2.51 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 13-06-2018 | 250 | MADHYA PRADESH | 25 | MPPMCL | 2.51 | Continuum Power Trading (TN) Pvt Ltd | Santosh Khairmode | 7972484155 | 30-08-2018 | 250 | 2.51 | GUJARAT | 25 |  | NA | 29-02-2020 | 21-12-2022 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 765/400/220 kV Bhuj | Bhuj | NA | 2022-04-14 | 88 | , Under litigation
[21 empty] | Sprng Energy Private Limited | 300 | -- | 01-06-2018 | 300 | 2.51 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 23-08-2018 | 300 | UTTAR PRADESH | 25 | UPPCL | 2.51 | Sprng Renewable Energy Private Limited | Sumit Joge | 9545556456 | 30-08-2018 | 300 | 2.51 | TAMIL NADU | 250 |  | NA | 29-02-2020 | 13-07-2021 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 400/230 kV Pugalur S | Pugalur | NA | 2021-10-30 | 300 | , Commissioned
[21 empty] | BLP Energy Private Limited | 285 | -- | 01-06-2018 | 285 | 2.51 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 31-08-2018, 13-06-2018 | 285 | MAHARASHTRA, MADHYA PRADESH | 50 | MSEDCL, MPPMCL | 5.02 | Avikiran Solar India Pvt Ltd. | Sandy Khera | 9899018700 | 30-08-2018 | 285 | 2.51 | GUJARAT | 25 |  | NA | 29-02-2020 | 17-03-2022 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 765/400/220 kV Bhuj | Bhuj | NA | 2022-12-14 | 168 | , 168 MW Commissioned, balance capacity has been cancelled.
[21 empty] | Betam Wind Energy Private Limited | 200 | -- | 01-06-2018 | 200 | 2.51 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-06-2018, 23-08-2018 | 200 | ODISHA, UTTAR PRADESH | 50 | GRIDCO, UPPCL | 5.02 | Vivid Solaire Energy Pvt. Ltd. | Sarang Patil | 9923505000 | 30-08-2018 | 200 | 2.51 | TAMIL NADU | 25 |  | NA | 29-02-2020 | 14-01-2022 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 400/230 kV Thirunelv | Thirunelveli | NA | 2021-10-21 | 168 | , 168 MW commissioned, balance capacity stands cancelled
[21 empty] | Inox Wind Infrastructure Services Limited | 100 | -- | 01-06-2018 | 100 | 2.51 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 31-08-2018 | 100 | MAHARASHTRA | 25 | MSEDCL | 2.51 | Suswind Power Private limited, Flutter Wind Energy Private limited | Venkatesh Soni, Venkatesh Soni | 18022090428 | 30-08-2018, 30-08-2018 | 100 | 5.02 | , | 50 | , | NA, NA | 20-02-2020, 20-02-2020 | 31-08-2022, 31-08-2022 | Wind, Wind | 0 | , | , | , | Granted, Granted | CTU , CTU | NA, NA | NA, NA | NA, NA | 765/400/220 kV Bhuj-, 765/400/220 kV Bhuj- | Bhuj, Bhuj | NA, NA | -- | -- | --
[21 empty] | Adani Green Energy (MP) Limited | 300 | -- | 01-06-2018 | 300 | 2.51 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 31-08-2021 | 300 | MAHARASHTRA | 25 | MSEDCL | 2.51 | Adani Wind Energy Kutchh Two Limited | Durgesh Gupta | 9711589569 | 30-08-2018 | 300 | 2.51 |  | 25 |  | NA | 29-02-2020 | 31-10-2021 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 765/400/220 kV Bhuj | Bhuj | NA | -- | -- | --
[21 empty] | Mytrah Energy (India) Private Limited | 300 | -- | 01-06-2018 | 300 | 2.52 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 26-06-2018, 17-07-2018, 23-08-2018 | 300 | DELHI, DELHI, UTTAR PRADESH | 75 | BYPL, TPDDL, UPPCL | 7.56 | Mytrah Vayu (Brahmaputra) Private Limited | Debasish Das | 9560872323 | 30-08-2018 | 300 | 2.52 |  | 25 |  | NA | 29-02-2020 | 28-08-2020 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 400/230 kV Palakkad | Palakkad | NA | -- | -- | --
[21 empty] | ReNew Wind Energy (TN) Private Limited | 265 | -- | 01-06-2018 | 265 | 2.52 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 23-08-2018, 29-08-2018, 13-06-2018 | 265 | UTTAR PRADESH, DADRA AND NAGAR HAVELI AND DAMAN AND DIU, MADHYA PRADESH | 75 | UPPCL, DNH, MPPPMCL | 7.56 | Renew Wind Energy Private Limited | Deepak Gupta | 9958545441 | 30-08-2018 | 265 | 2.52 |  | 25 |  | NA | 30-08-2018 | 29-02-2020 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | 765/400/220 kV Bhuj | Bhuj | NA | -- | -- | --
5 |  | Wind (Tranche-V) | -- | SECI/C&P/WPD/1200MW/T5/RfS/062018 | 1200 | NA | 30-06-2018 | NA | 24-08-2018 | Wind | Without Storage | Without Greenshoe | -- | 29-08-2018 | 25-09-2018 | 1190 | 10 | 9 | 2190 | 175 | Torrent Power Limited | 115 | -- | 24-10-2018 | 115 | 2.76 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 21-01-2019 | 115 | HARYANA | 25 | HPPC | 2.76 | Torrent Solargen Limited | Ronak Naik | 9227410210 | 22-01-2019 | 115 | 2.76 | GUJARAT | 25 |  | NA | 22-07-2020 | 25-04-2023 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Jam Khambaliya S/S | Jam Khambaliya | NA | 2023-07-14 | 115 | , Commissioned
[21 empty] | Adani Green Energy Limited | 300 | -- | 24-10-2018 | 300 | 2.76 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 08-01-2019, 21-01-2019 | 300 | BIHAR, HARYANA | 50 | BSPHCL, HPPC | 5.52 | Adani Wind Energy Kutchh Four limited | Durgesh Gupta | 9711589569 | 22-01-2019 | 300 | 2.76 |  | 25 |  | NA | 22-07-2020 | 31-10-2022 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Bhuj-II S/s | Bhuj | NA | -- | -- | --
[21 empty] | Alfanar Company | 300 | -- | 24-10-2018 | 300 | 2.77 | Wind |  | 300 | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 21-01-2019 | 300 | HARYANA | 25 | HPPC | 2.77 | Netra Wind Private limited | Md irfan | 8184900786 | 22-01-2019 | 300 | 2.77 | GUJARAT | 25 |  | NA | 22-07-2020 | 19-11-2022 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Bhuj S/S | Bhuj | NA | 2024-04-25 | 206.5 | , 206.5 MW Commissioned, balance capacity stands cancelled.
[21 empty] | Sitac Kabini Renewables Private Limited | 300 | -- | 24-10-2018 | 300 | 2.77 | Wind |  | 300 | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-02-2019, 16-01-2019, 20-12-2018 | 300 | PUDUCHERRY, DELHI, DELHI | 75 | Puducherry, BYPL, BRPL | 8.31 | Sitac Kabini Renewables Private Limited | Anjana | 9818844265 | 22-01-2019 | 300 | 2.77 | GUJARAT | 25 |  | NA | 22-07-2020 | 05-09-2022 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Bhuj-II S/S | Bhuj | NA | 2023-05-30 | 300 | , Commissioned
[21 empty] | Ecoren Energy India Private Limited | 175 | -- | 24-10-2018 | 175 | 2.77 | Wind |  | 175 | -- | -- | -- | -- | NA | NA | -- | -- | NA | 08-01-2019 | 175 | BIHAR | 25 | BSPHCL | 2.77 | Boreas Reneables Energy Private limited | KNV Ramamurthy | 8978908833 | 22-01-2019 | 175 | 2.77 |  | 25 |  | NA | 22-07-2020 | 22-12-2020 | [13 empty] | -- | -- | --
6 |  | Wind (Tranche-VI) | -- | SECI/C&P/WPD/1200MW/T6/RfS/122018 | 1200 | NA | 31-12-2018 | 11-01-2019 | 05-02-2019 | Wind | Without Storage | Without Greenshoe | -- | 06-02-2019 | 15-02-2019 | 1200 | 0 | 9 | 2325.6 | 125 | Adani Renewable Energy Park (Gujarat) Limited | 250 | -- | 17-06-2019 | 250 | 2.82 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 14-06-2019, 30-08-2019, 22-08-2019, 18-06-2019 | 250 | KERALA, CHANDIGARH, ODISHA, UTTAR PRADESH | 100 | KSEBL, Chandigarh, GRIDCO, UPPCL | 11.28 | Adani Wind Energy Kutchh Three Limited | Durgesh Gupta | 9711589569 | 15-09-2019 | 250 | 2.82 | GUJARAT | 25 |  | NA | 15-03-2021 | 28-02-2022 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Bhuj S/S | Bhuj | NA | 2021-03-06 | 250 | , Commissioned
[21 empty] | Ostro Energy Private Limited | 300 | -- | 17-06-2019 | 300 | 2.82 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 13-06-2019 | 300 | BIHAR | 25 | BSPHCL | 2.82 | Ostro Kannada Power Pvt Ltd | Deepak Gupta | 9958545441 | 15-09-2019 | 300 | 2.82 | KARNATAKA | 25 |  | NA | 15-03-2021 | 30-01-2022 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Hiryur S/S | Hiryur | NA | 2022-09-09 | 199.5 | , 199.5 MW commissioned, balance capacity stands cancelled
[21 empty] | Srijan Energy Systems Private Limited | 150 | -- | 17-06-2019 | 150 | 2.82 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 13-06-2019, 16-08-2019, 17-06-2019 | 150 | BIHAR, GOA, DELHI | 75 | BSPHCL, Goa, BRPL | 8.46 | Morjar Windfarm Development Pvt. Ltd. | Santosh Khairmode | 7972484155 | 15-09-2019 | 150 | 2.82 | GUJARAT | 25 |  | NA | 15-03-2021 | 01-12-2022 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Bhuj-II S/S | Bhuj | NA | 2023-06-16 | 148.5 | , 148.5 MW commissioned, balance capacity stands cancelled
[21 empty] | Powerica Limited | 50.6 | -- | 17-09-2019 | 50.6 | 2.82 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 18-06-2019 | 50.6 | UTTAR PRADESH | 25 | UPPCL | 2.82 | Powerica Limited | Gul Zehra | 8726350168 | 15-09-2019 | 50.6 | 2.82 | GUJARAT | 25 |  | NA | 15-03-2021 | 05-09-2022 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Jam Khambaliya S/S | Jam Khambaliya | NA | 2022-08-18 | 50.6 | , Commissioned
[21 empty] | Zenataris Renewable Energy Private Limited | 125 | -- | 17-06-2019 | 125 | 2.83 | Wind | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | SBESS Services Projectco Two Private Limited | 324.4 | -- | 17-06-2019 | 324.4 | 2.83 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 18-06-2019 | 324.4 | UTTAR PRADESH | 25 | UPPCL | 2.83 | Adani Wind Energy MP One Private Limited, Adani Wind Energy MP One Private Limited | Durgesh Gupta, Durgesh Gupta | 19423179138 | 15-09-2019, 15-09-2019 | 324.4 | 5.66 | MADHYA PRADESH, | 50 | , | NA, NA | 15-03-2021, 15-03-2021 | 26-08-2022, 26-08-2022 | Wind, Wind | 0 | , | , | , | Granted, Granted | CTU , CTU | NA, NA | NA, NA | NA, NA | Indore S/S, Indore S/S | Indore, Indore | NA, NA | 2022-09-17 | 274.4 | , Commissioned , Commissioned
[70 empty] | 2022-09-17 | 50
7 |  | Wind (Tranche-VII) | -- | SECI/C&P/WPD/1200MW/T7/RfS/022019 | 1200 | NA | 22-02-2019 | 11-03-2019 | 15-04-2019 | Wind | Without Storage | Without Greenshoe | -- | 15-04-2019 | 14-05-2019 | 480 | 720 | 4 | 600 | 200 | Betam Wind Energy Private Limited | 200 | -- | 19-06-2019 | 200 | 2.79 | Wind | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Ostro Energy Private Limited | 50 | -- | 19-06-2019 | 50 | 2.81 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-10-2019 | 50 | UTTAR PRADESH | 25 | UPPCL | 2.81 | Ostro Energy Private Limited | Deepak Gupta | 9958545441 | 18-10-2019 | 50 | 2.81 | GUJARAT | 25 |  | NA | 18-04-2021 | 05-12-2022 | Wind | 50 |  |  |  | Granted | CTU | NA | NA | NA | Bachhau S/S | Bachhau | NA | 2022-12-05 | 50 | , Commissioned
[21 empty] | Sprng Vaayu Urja Private Limited | 100 | -- | 19-06-2019 | 100 | 2.82 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 06-09-2019 | 100 | KERALA | 25 | KSEBL | 2.82 | Sprng Wind Energy Private limited | Sumit Joge | 9545556456 | 18-10-2019 | 100 | 2.82 |  | 25 |  | NA | 18-04-2021 | 18-09-2021 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Rajgarh S/S | Rajgarh | NA | -- | -- | --
[21 empty] | Adani Renewable Energy Park (Gujarat) Limited | 130 | -- | 19-06-2019 | 130 | 2.83 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-10-2019 | 130 | UTTAR PRADESH | 25 | UPPCL | 2.83 | Adani Wind Energy Kutchh Five Limited | Durgesh Gupta | 9711589569 | 18-10-2019 | 130 | 2.83 | GUJARAT | 25 |  | NA | 18-04-2021 | 02-03-2023 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Bhuj S/S | Bhuj | NA | 2023-05-25 | 130 | , Commissioned
8 |  | Wind (Tranche-VIII) | -- | SECI/C&P/WPD/1800MW/T8/RfS/062019 | 1800 | NA | 26-06-2019 | NA | 19-08-2019 | Wind | Without Storage | Without Greenshoe | -- | 20-08-2019 | 30-08-2019 | 440.8 | 1359.2 | 2 | 550.8 | 0 | CLP India Private Limited | 250.8 | -- | 28-09-2019 | 250.8 | 2.83 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 19-05-2020, 21-05-2020 | 250.71 | CHHATTISGARH, PUDUCHERRY | 50 | CSPDCL, Puducherry | 5.66 | Apraava Energy Private Limited | Gopal Eti | 8433723582 | 21-05-2020 | 250.71 | 2.83 | GUJARAT | 25 |  | NA | 21-11-2021 | 24-07-2023 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Jam Khambaliya S/S | Jam Khambaliya | NA | 2025-01-16 | 250.71 | , Commissioned
[21 empty] | Avikiran Energy India Private Limited | 190 | -- | 28-09-2019 | 190 | 2.84 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 19-05-2020, 21-02-2020 | 190 | CHHATTISGARH, PUDUCHERRY | 50 | CSPDCL, Puducherry | 5.68 | Tunga Renewable Energy Pvt Ltd | Sandy Khera | 9899018700 | 21-05-2020 | 190 | 2.84 |  | 25 |  | NA | 22-11-2021 | 05-09-2022 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Koppal S/S | Koppal | NA | -- | -- | --
9 |  | Wind (Tranche-IX) | -- | SECI/C&P/WPD/2500MW/T9/RfS/032020 | 2500 | NA | 20-03-2020 | 30-04-2020 | 28-07-2020 | Wind | Without Storage | Without Greenshoe | -- | 31-07-2020 | 14-08-2020 | 970 | 1530 | 3 | 1210 | 0 | Vena Energy Vidyuth Private Limited | 160 | -- | 25-09-2020 | 160 | 2.99 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-03-2021 | 160 | MADHYA PRADESH | 25 | MPPMCL | 2.99 | Vena Energy Vidyuth Pvt Ltd | Magalam Jyoti | 9900420524 | 31-03-2021 | 160 | 2.99 | KARNATAKA | 25 |  | NA | 31-03-2023 | 06-11-2024 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Gadag S/S | Gadag | NA | 2024-10-29 | 129.6 | , Commissioned
[70 empty] | 2024-10-29 | 30.4
[21 empty] | JSW Solar Limited | 810 | -- | 25-09-2020 | 810 | 3 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-03-2021, 02-07-2021, 30-06-2021 | 810 | MADHYA PRADESH, CHHATTISGARH, WEST BENGAL | 75 | MPPMCL, CSPDCL, WBSEDCL | 9 | JSW Renew Energy Limited, JSW Renew Energy Limited | Jatin Sharma, Jatin Sharma | 17182459396 | 31-03-2021, 15-07-2021 | 810 | 6 | TAMIL NADU, TAMIL NADU | 50 | , | NA, NA | 30-03-2023, 15-07-2023 | 01-12-2025, 29-11-2025 | Wind, Wind | 108 | , | , | , | Granted, Granted | CTU , CTU | NA, 1200003533 | NA, 16-11-2021 | NA, 03-02-2022 | Tuticorin II, Karur S/S | Tuticorin, Karur | NA, 31-01-2024 | 2025-03-31 | 540 | , , Commissioned ,
[70 empty] | 2025-05-09 | 162
10 |  | Wind (Tranche-X) | -- | SECI/C&P/WPD/1200MW/T10/RfS/122020 | 1200 | NA | 21-12-2020 | 08-01-2021 | 19-02-2021 | Wind | Without Storage | Without Greenshoe | -- | 25-02-2021 | 15-03-2021 | 1200 | 0 | 12 | 3200 | 0 | Adani Renewable Energy Holding Fifteen Limited | 300 | -- | 19-03-2021 | 300 | 2.77 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 26-08-2021 | 300 | RAJASTHAN | 25 | RUVNL | 2.77 | Adani Renewable Energy Seven Ltd | Durgesh Gupta | 9711589569 | 10-09-2021 | 300 | 2.77 |  | 25 |  | NA | 10-03-2023 | 11-06-2023 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Koppal S/S | Koppal | NA | -- | -- | --
[21 empty] | Ayana Renewable Power Six Private Limited | 300 | -- | 19-03-2021 | 300 | 2.78 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 26-08-2021 | 300 | RAJASTHAN | 25 | RUVNL | 2.78 | Ayana Renewable Power Six Pvt Ltd | Rinku Yadav | 7838753335 | 10-09-2021 | 300 | 2.78 | KARNATAKA | 25 |  | NA | 10-03-2023 | 20-02-2024 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Koppal S/S | Koppal | NA | 2024-02-19 | 300 | , Commissioned
[21 empty] | Evergreen Power Mauritius Private Limited | 150 | -- | 19-03-2021 | 150 | 2.78 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 26-08-2021 | 150 | RAJASTHAN | 25 | RUVNL | 2.78 | Viento Renewables Pvt Ltd | Hariprasad Achari | 7774053324 | 10-09-2021 | 150 | 2.78 |  | 25 |  | NA | 10-03-2023 | 09-10-2024 | Wind | 0 |  |  |  | Granted | CTU | NA | NA | NA | Kallam S/S | Kallam | NA | -- | -- | --
[21 empty] | JSW Future Energy Limited | 450 | -- | 19-03-2021 | 450 | 2.78 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 26-08-2021 | 450 | RAJASTHAN | 25 | RUVNL | 2.78 | JSW Renew Energy Two Ltd, JSW Renew Energy Two Ltd | Jatin Sharma, Jatin Sharma | 17182459396 | 10-09-2021, 10-09-2021 | 450 | 5.56 | TAMIL NADU, TAMIL NADU | 50 | , | NA, NA | 10-03-2023, 10-03-2023 | 19-11-2024, 14-09-2024 | Wind, Wind | 0 | , | , | , | Granted, Granted | CTU , CTU | NA, NA | NA, NA | NA, NA | Karur S/S, Tuticorin-II S/S | Karur, Tuticorin | NA, NA | 2024-11-19 | 150 | , , Commissioned , Commissioned
[70 empty] | 2024-09-13 | 300
11 |  | Wind (Tranche-XI) | -- | SECI/C&P/WPD/1200MW/T11/RfS/052021 | 1200 | NA | 25-05-2021 | 03-06-2021 | 06-07-2021 | Wind | Without Storage | Without Greenshoe | -- | 09-07-2021 | 02-09-2021 | 1200 | 0 | 11 | 2919.9 | 0 | ReNew Naveen Urja Private Limited | 300 | -- | 21-10-2021 | 300 | 2.69 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-06-2022, 29-04-2022, 07-11-2022, 28-06-2022 | 300 | MADHYA PRADESH, CHHATTISGARH, ODISHA, UTTAR PRADESH | 100 | MPPMCL, CSPDCL, GRIDCO, UPPCL | 10.76 | Renew Naveen Urja Private Limited | Deepak Gupta | 9958545441 | 30-06-2022 | 300 | 2.69 |  | 25 |  | NA | 30-12-2023 | 26-07-2025 | Wind | 300 |  |  |  | Granted | CTU | NA | NA | NA | Gadag S/S | Gadag | NA | -- | -- | --
[21 empty] | Green Infra Wind Energy Limited | 180 | -- | 21-10-2021 | 180 | 2.69 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-06-2022, 29-04-2022, 07-11-2022, 28-06-2022 | 180 | MADHYA PRADESH, CHHATTISGARH, ODISHA, UTTAR PRADESH | 100 | MPPMCL, CSPDCL, GRIDCO, UPPCL | 10.76 | Sembcorp Green Infra Private Limited | Raman Gulati | 9868165784 | 30-06-2022 | 180 | 2.69 | KARNATAKA | 25 |  | NA | 30-12-2023 | 26-07-2025 | Wind | 125.4 |  |  |  | Granted | CTU | 1200003500 | 21-10-2021 | 29-12-2021 | 400/220 kV Gadag S/S | Gadag | 17-09-2023 | 2025-01-17 | 54.6 | , Connectivity is yet to be operationalized
[21 empty] | Anupavan Renewables Private Limited | 150 | -- | 21-10-2021 | 150 | 2.69 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-06-2022, 29-04-2022, 07-11-2022, 28-06-2022 | 150 | MADHYA PRADESH, CHHATTISGARH, ODISHA, UTTAR PRADESH | 100 | MPPMCL, CSPDCL, GRIDCO, UPPCL | 10.76 | Anupavan Renewables Pvt Ltd | Tejas Shinde | 7798712370 | 30-06-2022 | 150 | 2.69 |  | 25 |  | NA | 30-12-2023 | 26-07-2025 | Wind | 150 |  |  |  | Granted | CTU | NA | NA | NA | Kallam S/S | Kallam | NA | -- | -- | --
[21 empty] | Adani Renewable Energy Holding Fifteen Limited | 450 | -- | 21-10-2021 | 450 | 2.7 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-06-2022, 29-04-2022, 07-11-2022, 28-06-2022 | 450 | MADHYA PRADESH, CHHATTISGARH, ODISHA, UTTAR PRADESH | 100 | MPPMCL, CSPDCL, GRIDCO, UPPCL | 10.8 | Adani Renewable Energy Four limited | Durgesh Gupta | 9711589569 | 30-06-2022 | 450 | 2.7 |  | 25 |  | NA | 30-12-2023 | 26-07-2025 | Wind | 450 |  |  |  | Granted | CTU | NA | NA | NA | Gadag S/S | Gadag | NA | -- | -- | --
[21 empty] | Azure Power India Private Limited | 120 | -- | 21-10-2021 | 120 | 2.7 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-06-2022, 29-04-2022, 07-11-2022, 28-06-2022 | 120 | MADHYA PRADESH, CHHATTISGARH, ODISHA, UTTAR PRADESH | 100 | MPPMCL, CSPDCL, GRIDCO, UPPCL | 10.8 | Two Wind Energy Pvt Ltd | Gaurang Sethi | 9654649000 | 30-06-2022 | 120 | 2.7 |  | 25 |  | NA | 30-12-2023 | 26-07-2025 | Wind | 120 |  |  |  | Granted | CTU | NA | NA | NA | Gadag S/S | Gadag | NA | -- | -- | --
12 |  | Wind (Tranche-XII) | -- | SECI/C&P/IPP/12/0002/21-22 | 1200 | NA | 22-10-2021 | 01-11-2021 | 02-12-2021 | Wind | Without Storage | Without Greenshoe | -- | 06-12-2021 | 24-05-2022 | 1100 | 100 | 15 | 3330 | 200 | NTPC Renewable Energy Limited | 200 | -- | 12-07-2022 | 200 | 2.89 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 02-02-2023, 14-03-2023 | 200 | ODISHA, UTTAR PRADESH | 50 | GRIDCO, UPPCL | 5.78 | NTPC Renewable Energy Limited | Ashish Jha | 7766862544 | 29-03-2023 | 200 | 2.89 | GUJARAT | 25 |  | NA | 29-03-2025 | 23-01-2026 | Wind | 200 |  |  |  | Granted | CTU | 2200000154 | 13-07-2023 | 19-01-2024 | Bhuj II | Bhuj | 29-03-2025 | 2026-02-25 | 50 | ,
[21 empty] | Halvad Renewables Private Limited | 300 | -- | 12-07-2022 | 300 | 2.93 | Wind | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | JSW Neo Energy Limited | 300 | -- | 12-07-2022 | 300 | 2.94 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 02-02-2023, 14-03-2023 | 300 | ODISHA, UTTAR PRADESH | 50 | GRIDCO, UPPCL | 5.88 | JSW Renew Energy Three Limited | Jatin Sharma | 8591229698 | 29-03-2023 | 300 | 2.94 | MAHARASHTRA | 25 |  | NA | 29-03-2025 | 23-01-2026 | Wind | 300 |  |  |  | Granted | CTU | 2200000718 | 23-04-2024 | 11-10-2024 | 400/220 kV Solapur S | Solapur | 31-03-2026 | -- | -- | --
[21 empty] | Torrent Power Limited | 300 | -- | 12-07-2022 | 300 | 2.94 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 02-02-2023, 14-03-2023 | 300 | ODISHA, UTTAR PRADESH | 50 | GRIDCO, UPPCL | 5.88 | Torrent Saurya Urja 2 Private Limited | Sagar Yaduvanshi | 6357470109 | 26-06-2023 | 300 | 2.94 | KARNATAKA | 25 |  | NA | 29-03-2025 | 23-01-2026 | Wind | 300 |  |  |  | Granted | CTU | 2200000058 | 18-05-2023 | 03-03-2025 | Koppal II PS | Koppal | 27-12-2025 | -- | -- | --
13 |  | Wind (Tranche-XIII) | -- | SECI/C&P/IPP/12/0006/21-22 | 1200 | NA | 12-01-2022 | 21-01-2022 | 04-07-2022 | Wind | Without Storage | Without Greenshoe | -- | 08-07-2022 | 22-12-2022 | 600 | 600 | 14 | 3010 | 0 | SJVN Limited | 100 | -- | 19-01-2023 | 100 | 2.9 | Wind | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 09-06-2023 | 100 | ODISHA | 25 | GRIDCO | 2.9 | SJVN Green Energy Limited | Abhishek Bhardwaj | 9599524440 | 26-06-2023 | 100 | 2.9 |  | 25 |  | NA | 26-06-2025 | 02-12-2025 | Wind | 100 |  |  |  | Yet to Apply |  |  | NA | NA |  |  | NA | -- | -- | --
[21 empty] | Scatec India II B.V. | 300 | -- | 19-01-2023 | 300 | 2.95 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 09-06-2023 | 300 | ODISHA | 25 | GRIDCO | 2.95 | Scatec India Renewables One Private limited | Manoj Bharti | 9899473316 | 26-06-2023 | 300 | 2.95 |  | 25 |  | NA | 26-06-2025 | 02-12-2025 | Wind | 300 |  |  |  | Granted | CTU | NA | NA | NA | Koppal-II S/S | Koppal | NA | -- | -- | --
[21 empty] | Teq Green Power XI Private Limited | 200 | -- | 19-01-2023 | 200 | 2.95 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 09-06-2023 | 200 | ODISHA | 25 | GRIDCO | 2.95 | Teq Green Power XI Pvt Ltd | Dharmender Gupta | 8587044337 | 26-06-2023 | 200 | 2.95 |  | 25 |  | NA | 26-06-2025 | 02-12-2025 | Wind | 200 |  |  |  | Granted | CTU | NA | NA | NA | Kallam S/S | Kallam | NA | -- | -- | --
14 |  | Wind (Tranche-XIV) | -- | SECI/C&P/IPP/12/0008/22-23 | 1200 | NA | 20-02-2023 | 27-02-2023 | 17-04-2023 | Wind | Without Storage | Without Greenshoe | -- | 21-04-2023 | 12-06-2023 | 690 | 510 | 7 | 1540 | 190 | Green Prairie Energy Private Limited | 190 | -- | 23-06-2023 | 190 | 3.18 | Wind | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Apraava Energy Private Limited | 300 | -- | 23-06-2023 | 300 | 3.24 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 19-10-2023 | 300 | UTTAR PRADESH | 25 | UPPCL | 3.24 | Apraava Energy Private Limited | Gopal Eti | 8433723582 | 16-11-2023 | 300 | 3.24 | KARNATAKA | 25 |  | NA | 27-12-2025 | NA | Wind | 300 |  |  |  | Granted | CTU | 2200000171 | 03-08-2023 | 01-04-2025 | Vijayapura | Vijayapura | 17-01-2027 | -- | -- | --
[21 empty] | SJVN Green Energy Limited | 200 | -- | 23-06-2023 | 200 | 3.24 | Wind | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 19-10-2023 | 200 | UTTAR PRADESH | 25 | UPPCL | 3.24 | SJVN Green Energy Limited | Abhishek Bhardwaj | 9599524440 | 16-11-2023 | 200 | 3.24 |  | 25 |  | NA | 27-12-2025 | NA | Wind | 200 |  |  |  | Yet to Apply |  |  | NA | NA |  |  | NA | -- | -- | --
15 |  | Wind (Tranche-XVI) | -- | SECI/C&P/IPP/12/0009/23-24 | 1350 | NA | 30-11-2023 | 13-12-2023 | 10-01-2024 | Wind | Without Storage | Without Greenshoe | -- | 15-01-2024 | 01-02-2024 | 1175 | 175 | 5 | 1010 | 0 | JSW Neo Energy Limited | 700 | -- | 09-02-2024 | 350 | 3.61 | Wind | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 30-05-2024 | 350 | UTTAR PRADESH | 25 | UPPCL | 3.61 | JSW Renew Energy Eight Ltd | Jatin Sharma | 8591229698 | 30-11--0001 | 350 | 3.61 | GUJARAT | 25 |  | NA | 13-06-2026 | 19-06-2026 | Wind | 350 |  |  |  | Applied | CTU | 2200000705 | 12-04-2024 | NA | Lakadia | Lakadia | NA | -- | -- | --
[24 empty] | 15-03-2024 | 350 | 3.61 | Wind | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 30-05-2024 | 350 | UTTAR PRADESH | 25 | UPPCL | 3.61 | JSW Renew Energy Eight Ltd | Jatin Sharma | 8591229698 | 13-06-2026 | 350 | 3.61 | GUJARAT | 25 |  |  | 13-06-2026 | 19-06-2026 | Wind | 350 |  |  |  | Applied | CTU | 2200000705 | 12-04-2024 | NA | Lakadia | Lakadia | NA | -- | -- | --
[21 empty] | Powerica Limited | 50 | -- | 09-02-2024 | 50 | 3.7 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 30-05-2025 | 50 | UTTAR PRADESH | 25 | UPPCL | 3.7 | Powerica Limited | Gul Zehra | 8726350168 | 13-06-2024 | 50 | 3.7 | GUJARAT | 25 |  | NA | 13-06-2026 | 19-06-2026 | Wind | 50 |  |  |  | Granted | CTU | 230700018 | 06-04-2023 | 09-02-2024 | 400/220 kV Jam Khamb | Jam Khambaliya | 31-12-2025 | 0006-02-11 | 50 | ,
[24 empty] | NA | -- | -- | -- | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Torrent Power Limited | 100 | -- | 09-02-2024 | 100 | 3.6 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 30-05-2025 | 100 | UTTAR PRADESH | 25 | UPPCL | 3.6 | Torrent Power Limited | Sagar Yaduvanshi | 6357470109 | 13-06-2024 | 100 | 3.6 | KARNATAKA | 25 |  | NA | 13-06-2026 | 19-06-2026 | Wind | 100 |  |  |  | Granted | CTU | 2200000058 | 10-01-2024 | 04-03-2025 | Koppal-II PS | Koppal | 01-02-2026 | -- | -- | --
[24 empty] | NA | -- | -- | -- | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | JSW Neo Energy Limited | 325 | -- | 09-02-2024 | 150 | 3.68 | Wind | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 30-05-2025 | 150 | UTTAR PRADESH | 25 | UPPCL | 3.68 | JSW Renew Energy Four Limited | Jatin Sharma | 8591229698 | 13-06-2024 | 150 | 3.68 | KARNATAKA | 25 |  | NA | 13-06-2026 | 19-06-2026 | Wind | 150 |  |  |  | Applied | CTU | 2200000932 | 13-06-2024 | NA | Davanagere | Davanagere | NA | -- | -- | --
[24 empty] | 15-03-2024 | 150 | 3.6 | Wind | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 30-05-2025 | 150 | UTTAR PRADESH | 25 | UPPCL | 3.6 | JSW Renew Energy Four Limited | Jatin Sharma | 8591229698 | 13-06-2024 | 25 | 3.6 | KARNATAKA | 25 |  |  | 13-06-2026 | 19-06-2026 | Wind | 25 |  |  |  | Applied | CTU | 2200000932 | 13-06-2024 | NA | Davanagere | Davanagere | NA | -- | -- | --
[24 empty] | 08-05-2024 | 25 | 3.6 | Wind | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 30-05-2025 | 25 | UTTAR PRADESH | 25 | UPPCL | 3.6 | JSW Renew Energy Four Limited | Jatin Sharma | 8591229698 | 13-06-2024 | 150 | 3.6 | KARNATAKA | 25 |  |  | 13-06-2026 | 19-06-2026 | Wind | 150 |  |  |  | Applied | CTU | 2200000932 | 13-06-2024 | NA | Davanagere | Davanagere | NA | -- | -- | --
16 |  | Wind (Tranche-XVII) | -- | SECI/C&P/IPP/12/0002/24-25 | 500 | NA | 29-05-2024 | 05-06-2024 | 05-08-2024 | Wind | Without Storage | Without Greenshoe | -- | 16-08-2024 | 13-09-2024 | 50 | 450 | 2 | 120 | 0 | Powerica Limited | 50 | -- | 28-10-2024 | 50 | 3.81 | Wind | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 14-02-2025 | 50 | BIHAR | 25 | BSPHCL | 3.81 | Powerica Limited | Gul Zehra | 8726350168 | 01-03-2025 | 50 | 3.81 | GUJARAT | 25 |  | NA | 01-03-2027 | NA | Wind | 50 |  |  |  | Granted | CTU | 2200000473 | 10-01-2024 | 22-11-2024 | Jam Khambhaliya | Jam Khambhaliya | 14-10-2026 | -- | -- | --
17 |  | Wind (Tranche-XVIII) | -- | SECI/C&P/IPP/12/0028/24-25 | 600 | NA | 18-03-2025 | 24-03-2025 | 11-04-2025 | Wind | Without Storage | Without Greenshoe | -- | 21-04-2025 | 21-05-2025 | 300 | 300 | 3 | 580 | 0 | Torrent Green Energy Private Limited | 300 | -- | 11-06-2025 | 300 | 3.97 | Wind | -- | 300 | -- | -- | -- | -- | NA | NA | -- | -- | NA | 03-10-2025 | 300 | BIHAR | 25 | BSPHCL | 4.04 | Torrent Saurya Urja Private Limited, Torrent Solar Power Private Limited | Parth Desai, Parth Desai | 19826011140 | 07-11-2025, 07-11-2025 | 300 | 7.94 | , | 50 | No, No | NA, NA | 07-11-2027, 07-11-2027 | NA, NA | [13 empty] | -- | -- | --
1 | SECI Hybrid | Hybrid (Tranche-I) | -- | SECI/C&P/HPD/1200MW/HYB/T1/RfS/062018 | 1200 | NA | 22-06-2018 | 16-07-2018 | 20-11-2018 | Hybrid | Without Storage | Without Greenshoe | -- | 20-11-2018 | 05-12-2018 | 840 | 360 | 2 | 1050 | 0 | SBE Renewables Ten Private Limited | 450 | -- | 25-01-2019 | 450 | 2.67 | Hybrid | 420 | 105 | 0 | Granted | -- | -- | NA | NA | -- | -- | NA | 11-07-2019, 23-06-2019 | 450 | HARYANA, CHHATTISGARH | 50 | HPPC, CSPDCL | 5.46 | Adani Green Energy Eighteen Limited, Adani Green Energy Eighteen Limited | Prakhar Bhardwaj, Prakhar Bhardwaj | 4294967294 | 07-11-2019, 07-11-2019 | 390 | 5.38 | , | 50 | , | NA, NA | 07-05-2021, 07-05-2021 | 27-05-2022, 27-05-2022 | Hybrid | 0 | 180 | 50 | 0 | Granted | CTU | 1200002161 | NA | 29-08-2019 | Fatehgarh-II | Jaisalmer Rajasthan | NA | 2021-08-12 | 180 | ,
[70 empty] | 2021-08-12 | 50
[70 empty] | 2022-05-26 | 180
[70 empty] | 2022-05-26 | 50
[21 empty] | Mahoba Solar (UP) Private Limited | 390 | -- | 25-01-2019 | 390 | 2.69 | Hybrid | 360 | 100 | 0 | Granted | -- | -- | NA | NA | -- | -- | NA | 20-06-2019 | 390 | CHHATTISGARH | 25 | CSPDCL | 2.73 | SBE Renewables Ten Projects Private Limited | Prakhar Bhardwaj | 2147483647 | 08-11-2019 | 450 | 2.67 |  | 25 |  | NA | 07-05-2021 | 29-09-2021 | [13 empty] | 2022-10-21 | 420 | ,
[70 empty] | 2022-10-21 | 105
2 |  | Hybrid (Tranche-II) | -- | SECI/C&P/HPD/1200MW/HYB/T2/RfS/032019 | 1200 | NA | 08-03-2019 | 02-04-2019 | 14-05-2019 | Hybrid | Without Storage | Without Greenshoe | -- | 17-05-2019 | 27-05-2019 | 600 | 600 | 2 | 900 | 0 | Adani Renewable Energy Park (Gujarat) Limited | 600 | -- | 18-06-2019 | 600 | 2.69 | Hybrid | 600 | 150 | 0 | Granted | -- | -- | NA | NA | -- | -- | NA | 03-01-2020, 15-01-2020 | 600 | PUNJAB, WEST BENGAL | 50 | PSPCL, IPCL | 5.52 | M/s Adani Green Energy Seven Limited, M/s Adani Green Energy Nine Limited | Prakhar Bhardwaj, Prakhar Bhardwaj | 4294967294 | 15-01-2020, 15-01-2020 | 600 | 5.38 | , | 50 | , | NA, NA | 15-01-2022, 15-01-2022 | 28-09-2022, 28-09-2022 | Hybrid, Hybrid | 0 | 600 | 150 | 0 | Granted, Granted | CTU , CTU | 2400004885 | 21-01-2020, 21-01-2020 | 25-06-2020, NA | Fatehgarh-II, | Fatehgarh rajasthan, | NA, NA | 2022-09-27 | 300 | , ,
[70 empty] | 2022-09-27 | 75
[70 empty] | 2022-09-27 | 300
[70 empty] | 2022-09-27 | 75
3 |  | Hybrid Peak (ISTS-VII) | -- | SECI/C&P/HPD/ISTS-VII/RfS/1200MW/082019 | 1200 | NA | 01-08-2019 | 27-09-2019 | 15-01-2020 | Hybrid | With Storage | Without Greenshoe | -- | 20-01-2020 | 31-01-2020 | 1200 | 0 | 3 | 1620 | 0 | Greenko Energies Private Limited | 900 | -- | 26-02-2020 | 900 | 6.12 | Hybrid | 1500 | 0 | 2700 | Granted | -- | -- | NA | NA | -- | -- | NA | 25-01-2022, 20-08-2021, 20-05-2022 | 900 | RAJASTHAN, WEST BENGAL, BIHAR | 75 | RUVNL, DVC, BSPHCL | 18.57 | Greenko AP01 IREP Private limited, Greenko AP01 IREP Private limited, Greenko AP01 IREP Private limited | Anish Bansal, Anish Bansal, Anish Bansal | 6442450941 | 02-02-2022, 02-02-2022, 27-05-2022 | 900 | 18.36 | ANDHRA PRADESH, , | 75 | , , | NA, NA, NA | 02-08-2023, 02-08-2023, 27-11-2023 | 30-05-2026, 30-05-2026, 30-05-2026 | Hybrid, Hybrid, Hybrid | 900 | 1500 | 0 | 2700 | Granted, Granted, Granted | CTU , CTU , CTU | 3600010992 | NA, NA, NA | NA, NA, NA | Kurnool SS, Kurnool SS, Kurnool SS | , Kurnool, | 31-03-2026, 31-03-2026, 31-03-2026 | -- | -- | --
[21 empty] | ReNew Solar Power Private Limited | 300 | -- | 26-02-2020 | 300 | 6.85 | Hybrid | 81 | 322.25 | 150 | Granted | -- | -- | NA | NA | -- | -- | NA | 22-12-2021, 26-07-2022 | 300 | GOA, HARYANA | 50 | Governor of Goa, HPPC | 13.84 | ReNew Surya Ojas Private limited | Abhishek Shringi | 2147483647 | 31-08-2022 | 300 | 6.85 | KARNATAKA, KARNATAKA | 25 |  | NA | 29-02-2024 | 11-12-2024 | Hybrid | 300 | 81 | 322.25 | 150 | Granted | CTU | 1200002993 | NA | NA | Koppal | Koppal SS | 28-10-2023 | 2025-10-22 | 81 | , , As per 51st JCC 25th September 2025 Petition No. 112 MP 2024 is under adjudication before Ld. CERC
[70 empty] | 2025-10-10 | 322.25
[70 empty] | 2024-12-06 | 75
4 |  | RTC (RTC-I) | -- | SECI/C&P/RPD/RTC-I/RfS/400MW/102019 | 400 | NA | 18-10-2019 | 18-11-2019 | 23-02-2020 | RTC | With Storage | Without Greenshoe | -- | 26-03-2020 | 08-05-2020 | 400 | 0 | 4 | 950 | 0 | ReNew Solar Power Private Limited | 400 | -- | 04-06-2020 | 400 | 2.9 | Hybrid | 400 | 900 | 8 | Granted | -- | -- | NA | NA | -- | -- | NA | 19-07-2021, 30-06-2021, 26-05-2022, 12-10-2021 | 400 | WEST BENGAL, WEST BENGAL, DELHI, UTTARAKHAND | 100 | IPCL, WBSEDCL, Indian Railways, UPCL | 11.88 | Renew Surya Roshni Private Limited | Abhishek Shringi | 2147483647 | 06-08-2021 | 400 | 2.9 | RAJASTHAN, MAHARASHTRA, KARNATAKA, KARNATAKA | 25 |  | NA | 06-08-2023 | 01-03-2026 | RTC, RTC, RTC, RTC | 1600 | 1600 | 3600 | 32 | Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU | 4800013074 | NA, NA, NA, NA | NA, NA, NA, NA | Fatehgarh, Kallam, Koppal, Gadag | Fatehgarh, Kallam, Koppal, Gadag | 31-12-2025, NA, NA, NA | 2024-06-19 | 81 | , Severe ROW issues , , , 35th JCC 24th September 2025 Connectivity likely to be operationalized 31.12.2025 , original App. No. 1200003141 is hereby closed in line with Clause 5A of the CERC Connectivity Regu , original App. No. 1200003140 is hereby closed in line with Clause 5A of the CERC Connectivity Reg , original App. No. 1200003139 is hereby closed in line with Clause 5A of the CERC Connectivity Reg
[70 empty] | 2025-09-29 | 291.06
[70 empty] | 2025-09-29 | 280.35
[70 empty] | 2025-09-29 | 108.9
5 |  | Hybrid (Tranche-III) | -- | SECI/C&P/HPD/T3/1200MW/RfS/012020 | 1200 | NA | 14-01-2020 | 28-01-2020 | 07-12-2020 | Hybrid | Without Storage | Without Greenshoe | -- | 10-12-2020 | 23-12-2020 | 1110 | 90 | 11 | 4210 | 0 | ABC Renewable Energy Private Limited | 380 | -- | 31-12-2020 | 380 | 2.41 | Hybrid | 380 | 126 | 0 | Granted | -- | -- | NA | NA | -- | -- | NA | 02-07-2021, 25-06-2021, 20-07-2021, 20-07-2021, 30-06-2021 | 380 | CHHATTISGARH, MAHARASHTRA, DELHI, DELHI, WEST BENGAL | 125 | CSPDCL, BEST, BRPL, BYPL, WBSEDCL | 12.4 | ABC Renewable Energy (RJ-03) Private limited | AB Kiran | 2147483647 | 27-07-2021 | 380 | 2.41 | RAJASTHAN | 25 |  | NA | 27-01-2023 | 30-05-2026 | Hybrid | 380 | 380 | 126 | 0 | Granted | CTU | 1200003531 | NA | NA | Fatehgarh IV |  | 31-03-2026 | -- | -- | --
[21 empty] | Adani Renewable Energy Holding Eight Limited | 600 | -- | 31-12-2020 | 600 | 2.41 | Hybrid | 570 | 200 | 0 | Granted | CTU | 230700006 | 11-11-2022 | 24-01-2023 | KPS I | Khavada Gujarat | 15-02-2026 | 02-07-2021, 25-06-2021, 20-07-2021, 20-07-2021, 30-06-2021 | 599 | CHHATTISGARH, MAHARASHTRA, DELHI, DELHI, WEST BENGAL | 125 | CSPDCL, BEST, BRPL, BYPL, WBSEDCL | 12.4 | Adani Hybrid Energy Jaisalmer Five Limited | Prakhar Bhardwaj | 2147483647 | 27-07-2021 | 600 | 2.41 | GUJARAT | 25 |  | NA | 27-01-2023 | 01-03-2026 | Hybrid | 600 | 570 | 200 | 0 | Granted | CTU | 430700007 | NA | NA | KPS1 |  | 31-12-2025 | 2025-10-17 | 600 | - , As per 49th JCC 26th September 2025 Likely Operationalization 31.12.2025
[21 empty] | AMP Energy Green Private Limited | 130 | -- | 31-12-2020 | 130 | 2.41 | Hybrid | 112.5 | 44.1 | 0 | Granted | CTU | 1200003022 | 24-08-2021 | 01-11-2021 | Fatehgarh IV | Fatehgarh | 31-03-2026 | 02-07-2021, 25-06-2021, 20-07-2021, 20-07-2021, 30-06-2021 | 131 | CHHATTISGARH, MAHARASHTRA, DELHI, DELHI, WEST BENGAL | 125 | CSPDCL, BEST, BRPL, BYPL, WBSEDCL | 12.4 | AMP Energy Green Eight Private Limited | Abhilash Yadav | 2147483647 | 19-07-2021 | 130 | 2.41 | RAJASTHAN, RAJASTHAN | 25 |  | NA | 19-01-2023 | 30-05-2026 | Hybrid | 130 | 112.5 | 44.1 | 0 | Granted | CTU | 1200003416 | NA | NA |  |  | 31-03-2026 | -- | -- | --
6 |  | RTC (RTC-II) | -- | SECI/C&P/RPD/RTC-II/RfS/5000MW/032020 | 2500 | NA | 17-03-2020 | 02-09-2020 | 03-09-2021 | RTC | Without Storage | Without Greenshoe | -- | 08-09-2021 | 14-10-2021 | 250 | 2250 | 16 | 12151 | 0 | Hindustan Thermalprojects Limited | 250 | -- | 21-01-2022 | 250 | 3.01 | RTC | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
7 |  | Hybrid (Tranche-IV) | -- | SECI/C&P/HPD/T4/1200MW/RfS/042021 | 1200 | NA | 15-04-2021 | 26-04-2021 | 16-07-2021 | Hybrid | Without Storage | Without Greenshoe | -- | 22-07-2021 | 23-08-2021 | 1200 | 0 | 19 | 6280 | 0 | NTPC Limited | 450 | -- | 08-11-2021 | 450 | 2.34 | Hybrid | 300 | 150 | 0 | Granted | CTU | 2200000076 230 | NA | NA | -- | -- | NA | 17-06-2022, 29-04-2022 | 450 | HARYANA, WEST BENGAL | 50 | HPPC, CSPDCL | 4.82 | NTPC Renewable Energy Limited | Saurabh Khare | 2147483647 | 28-06-2022 | 450 | 2.34 | GUJARAT | 25 |  | NA | 28-12-2023 | 30-06-2026 | Hybrid, Hybrid | 900 | 600 | 300 | 0 | Granted, Granted | CTU , CTU | 2430700079 | NA, NA | NA, NA | , | , | 07-06-2024, 28-02-2024 | 2025-07-30 | 146 | Govt. land to be transffered to NTPC by Govt. of Gujarat. Exact portion acquired is not confirmed yet. , As per 49th JCC 26th September 2025 Operationalization date 07.06.2024 , As per 49th JCC 26th September 2025 Operationalization date 28.02.2024
[21 empty] | NLC India Limited | 150 | -- | 08-11-2021 | 150 | 2.34 | Hybrid | 100 | 50 | 0 | Granted | -- | -- | NA | NA | -- | -- | NA | 17-06-2022, 29-04-2022 | 150 | HARYANA, WEST BENGAL | 50 | HPPC, CSPDCL | 4.82 | NLC India Limited | Devendra Pratap Singh | 2147483647 | 28-06-2022 | 150 | 2.34 | GUJARAT | 25 |  | NA | 28-12-2023 | 30-06-2025 | Hybrid, Hybrid | 300 | 200 | 100 | 0 | Granted, Granted | CTU , CTU | 4400001537 | NA, NA | NA, NA | , | , | 31-03-2027, 31-03-2027 | -- | -- | --
[21 empty] | Project Ten Renewable Power Private Limited | 450 | -- | 08-11-2021 | 450 | 2.34 | Hybrid | 350 | 150 | 0 | Granted | -- | -- | NA | NA | -- | -- | NA | 17-06-2022, 29-04-2022 | 450 | HARYANA, WEST BENGAL | 50 | HPPC, CSPDCL | 4.82 | Project Ten Renewable Power Private Limited | Lakshmi Narayanan Balasubramanian | 2147483647 | 28-06-2022 | 450 | 2.34 | KARNATAKA, KARNATAKA | 25 |  | NA | 28-12-2023 | 30-05-2026 | Hybrid, Hybrid | 900 | 700 | 300 | 0 | Granted, Granted | CTU , CTU | 902200009 | NA, NA | NA, NA | Tumkur PS, Koppal | Pavagada, Koppal | 31-03-2026, 31-03-2026 | -- | -- | --
[21 empty] | Azure Power India Private Limited | 150 | -- | 08-11-2021 | 150 | 2.35 | Hybrid | 100 | 50 | 0 | Granted | -- | -- | NA | NA | -- | -- | NA | 17-06-2022, 29-04-2022 | 150 | HARYANA, WEST BENGAL | 50 | HPPC, CSPDCL | 4.84 | Kotuma Wind parks Private limited | Nikhil Mathews | 2147483647 | 28-06-2022 | 150 | 2.35 | RAJASTHAN, KARNATAKA | 25 |  | NA | 28-12-2023 | 07-06-2024 | Hybrid, Hybrid | 300 | 200 | 100 | 0 | Granted, Granted | CTU , CTU | 824200005 | NA, NA | NA, NA | Fatehgarh 3, Gadag 1 | Fatehgarh, Gadag | 30-06-2026, 30-09-2025 | -- | -- | --
8 |  | Hybrid (Tranche-V) | -- | SECI/C&P/IPP/13/0003/21-22 | 1200 | NA | 22-10-2021 | 01-11-2021 | 04-01-2022 | Hybrid | Without Storage | Without Greenshoe | -- | 07-01-2022 | 05-05-2022 | 1170 | 30 | 13 | 4370 | 0 | TP Saurya Limited | 600 | -- | 12-07-2022 | 600 | 2.53 | Hybrid | 400 | 200 | 0 | Granted | CTU | 251100006 | 15-07-2022 | 13-09-2024 | Gadag II | Gadag Karnataka | 30-06-2026 | 05-01-2023, 11-01-2023 | 600 | GUJARAT, WEST BENGAL | 50 | MPSEZ, CESC | 5.2 | TP Saurya Limited | Abhishek Kulkarni | 9029526560 | 11-01-2023 | 600 | 2.53 | KARNATAKA, RAJASTHAN, KARNATAKA | 25 |  | NA | 11-01-2025 | 30-10-2026 | Hybrid, Hybrid, Hybrid | 1800 | 1200 | 600 | 0 | Granted, Granted, Granted | CTU , CTU , CTU | 1702203593 | NA, NA, NA | NA, NA, NA | Gadag SS, Koppal, Bikaner | , , | 30-06-2026, 31-03-2026, 31-08-2026 | 2025-10-15 | 100 | , , , 51st JCC 25th September 2025 Likely Operationalization date 30.06.2026 , 51st JCC 25th September 2025 Likely Operationalization date 31.03.2026 , As per 35th JCC 24th September 2025 Connectivity likely to be operationalized 31.08.2026
[21 empty] | AMP Energy Green Private Limited | 120 | -- | 12-07-2022 | 120 | 2.53 | Hybrid | 100 | 39.9 | 0 | Granted | CTU | -- | 01-12-2023 | 01-12-2023 | Fatehgarh IV | Fatehgarh | 30-06-2026 | 05-01-2023, 11-01-2023 | 120 | GUJARAT, WEST BENGAL | 50 | MPSEZ, CESC | 5.2 | AMP Energy Green ten Private Limited | Abhilash Yadav | 9910068527 | 11-01-2023 | 120 | 2.53 | RAJASTHAN, RAJASTHAN | 25 |  | NA | 11-01-2025 | 29-08-2029 | Hybrid | 120 | 110 | 39.9 | 0 | Granted | CTU | 412100019 | NA | NA | Fatehgarh IV | Fatehgarh | 30-06-2026 | -- | -- | --
[21 empty] | NTPC Renewable Energy Limited | 450 | -- | 12-07-2022 | 450 | 2.53 | Hybrid | 300 | 150 | 0 | Granted | CTU | 330700007 | 13-10-2022 | 22-08-2022 | Khavada II | Khavada Gujarat | 31-03-2027 | 11-01-2023 | 38 | WEST BENGAL | 25 | CESC | 2.6 | NTPC REL | Saurabh Khare | 9415234496 | 11-01-2023 | 450 | 2.53 | GUJARAT, GUJARAT | 25 |  | NA | 01-01-2025 | 30-07-2026 | Hybrid, Hybrid | 900 | 600 | 300 | 0 | Granted, Granted | CTU , CTU | 550700091 | NA, NA | NA, NA | KPS 1, Bhuj | Khavada, Bhuj | 30-06-2026, 16-05-2025 | 2025-10-18 | 262.075 | only 43/50 Nos land parcel available , , As per 49th JCC 26th September 2025 Operationalization date Jun 26 Tentative , As per 49th JCC 26th September 2025 Operationalization date 16.05.2025
10 |  | Hybrid (Tranche-VI) | -- | SECI/C&P/IPP/13/0007/22-23 | 1200 | NA | 02-11-2022 | 15-11-2022 | 10-03-2023 | Hybrid | With Storage | Without Greenshoe | -- | 15-03-2023 | 12-04-2023 | 1200 | 0 | 8 | 2390 | 0 | AMP Energy Green Private Limited | 100 | -- | 20-04-2023 | 100 | 4.64 | Hybrid | 85 | 118.8 | 100 | -- | -- | -- | NA | NA | -- | -- | NA | 15-11-2023, 02-07-2024 | 50 | ASSAM, CHHATTISGARH | 50 | APDCL, CSPDCL | 10.02 | AMP Energy Green Sixteen Pvt Ltd | Abhilash Yadav | 9910068527 | 30-06-2024 | 50 | 4.64 | ANDHRA PRADESH, ANDHRA PRADESH | 25 |  | NA | 30-06-2026 | 27-10-2026 | Hybrid | 50 | 42.5 | 59.4 | 50 | Applied | CTU | 2200000229 | 31-03-2027 | NA |  |  | 31-03-2027 | -- | -- | --
[21 empty] | ReNew Vikram Shakti Private Limited | 600 | -- | 20-04-2023 | 600 | 4.69 | Hybrid | 810 | 900 | 600 | -- | -- | -- | NA | NA | -- | -- | NA | 15-11-2023, 02-07-2024 | 300 | ASSAM, CHHATTISGARH | 50 | APDCL, CSPDCL | 10.12 | ReNew vyoman Power Pvt. ltd. | Abhishek Shringi | 9602338869 | 30-06-2024 | 300 | 4.69 | ANDHRA PRADESH | 25 |  | NA | 30-06-2026 | 27-10-2026 | Hybrid | 300 | 405 | 450 | 300 | Applied | CTU | 2200000032 | NA | NA |  |  | 31-03-2026 | -- | -- | --
[21 empty] | Hero Solar Energy Private Limited | 120 | -- | 20-04-2023 | 120 | 4.72 | Hybrid | 150 | 158.4 | 120 | -- | -- | -- | NA | NA | -- | -- | NA | 15-11-2023, 02-07-2024 | 60 | ASSAM, CHHATTISGARH | 50 | APDCL, CSPDCL | 9.58 | Clean Renewable Energy (Barmer) Pvt Ltd | Sushant Sinha | 7568353344 | 30-06-2024 | 60 | 4.72 | ANDHRA PRADESH | 25 |  | NA | 30-06-2026 | 27-10-2026 | Hybrid | 60 | 75 | 129.2 | 60 | Applied | CTU | 2200000236 | NA | NA |  |  | 31-12-2026 | -- | -- | --
[21 empty] | ACME Cleantech Solutions Private Limited | 380 | -- | 20-04-2023 | 380 | 4.73 | Hybrid | 618 | 182 | 810 | -- | -- | -- | NA | NA | -- | -- | NA | 15-11-2023, 02-07-2024 | 190 | ASSAM, CHHATTISGARH | 50 | APDCL, CSPDCL | 9.6 | ACME Urja One Pvt. Ltd. | Yogesh Sanklecha | 9867560601 | 30-06-2024 | 190 | 4.73 | ANDHRA PRADESH, MADHYA PRADESH | 25 |  | NA | 30-06-2026 | 27-10-2026 | Hybrid, Hybrid | 380 | 618 | 182 | 810 | Applied, Applied | CTU , CTU | 4400000404 | NA, NA | NA, NA | Kurnool, Anantpur PS | Kurnool, Anantpur | 31-03-2026, 31-05-2026 | -- | -- | --
11 |  | FDRE (FDRE-IV) | -- | SECI/C&P/IPP/13/0006/23-24 | 630 | NA | 15-09-2023 | 18-10-2023 | 03-07-2024 | FDRE | With Storage | Without Greenshoe | -- | 08-07-2024 | 25-07-2024 | 630 | 0 | 5 | 780 | 0 | Vena Energy Aura Private Limited | 100 | -- | 07-08-2024 | 100 | 4.98 | FDRE | 52.8 | 125.4 | 2.2 | Granted | -- | -- | NA | NA | -- | -- | NA | 30-06-2025 | 100 | RAJASTHAN | 25 | RUVITL | 5.05 | Vena Energy Aura Private Limited | Praveen Thakre | 9452000846 | 30-06-2025 | 100 | 4.98 |  | 25 |  | NA | 30-06-2027 | NA | FDRE, FDRE, FDRE | 300 | 158.4 | 376.2 | 6.6 | Granted, Granted, Granted | CTU , CTU , CTU | 6600000922 | NA, NA, NA | NA, NA, NA | Koppal 2, Koppal 2, Koppal 2 | Koppal, Koppal, Koppal | 31-12-2026, 31-12-2026, 31-12-2026 | -- | -- | --
[21 empty] | Hero Solar Energy Private Limited | 100 | -- | 07-08-2024 | 100 | 4.98 | FDRE | 40 | 99 | 60 | -- | -- | -- | NA | NA | -- | -- | NA | 30-06-2025 | 100 | RAJASTHAN | 25 | RUVITL | 5.05 | Clean Renewable Energy Hybrid Nine Private Limited | Sushant Sinha | 7568353344 | 30-06-2025 | 100 | 4.98 |  | 25 |  | NA | 30-06-2027 | NA | [13 empty] | -- | -- | --
[21 empty] | JSW Neo Energy Limited | 230 | -- | 07-08-2024 | 230 | 4.98 | FDRE | 75 | 275 | 80 | -- | -- | -- | NA | NA | -- | -- | NA | 30-06-2025 | 230 | RAJASTHAN | 25 | RUVITL | 5.05 | JSW Renew Energy Nine Limited | Jatin Sharma | 8591229698 | 30-06-2025 | 230 | 4.98 |  | 25 |  | NA | 03-06-2027 | NA | [13 empty] | -- | -- | --
[21 empty] | Hexa Climate Solutions Private Limited | 100 | -- | 07-08-2024 | 100 | 4.99 | FDRE | 30 | 84 | 20 | Granted | -- | -- | NA | NA | -- | -- | NA | 30-06-2025 | 100 | RAJASTHAN | 25 | RUVITL | 5.05 | Hexa Energy BH2 Private Limited | Rohit Ahuja | 9818995610 | 30-06-2025 | 100 | 4.99 | RAJASTHAN, GUJARAT | 25 |  | NA | 30-06-2027 | NA | FDRE, FDRE | 200 | 60 | 168 | 40 | Granted, Granted | CTU , CTU | 4400001829 | NA, NA | NA, NA | Merta 2, Bhuj | Merta, Bhuj | 30-04-2027, 31-12-2026 | -- | -- | --
[21 empty] | Serentica Renewables India 11 Private Limited | 100 | -- | 07-08-2024 | 100 | 4.99 | FDRE | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 30-06-2025 | 100 | RAJASTHAN | 25 | RUVITL | 5.06 | Serentica Renewable India 22 Private Limited | Mayank Bhatnagar | 9711206426 | 30-06-2025 | 100 | 4.99 |  | 25 |  | NA | 30-06-2027 | NA | [13 empty] | -- | -- | --
12 |  | hybrid (Tranche-VII) | -- | SECI/C&P/IPP/13/0008/23-24 | 2000 | NA | 23-10-2023 | 31-10-2023 | 08-12-2023 | Hybrid | Without Storage | Without Greenshoe | -- | 14-12-2023 | 09-01-2023 | 900 | 1100 | 5 | 1265 | 0 | NTPC Renewable Energy Limited | 300 | -- | 16-01-2024 | 300 | 3.15 | Hybrid | 200 | 100 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | 09-12-2025 | 300 | HIMACHAL PRADESH | 25 | HPSEBL | 3.85 | NTPC REL | Saurabh Khare | 9415234496 | 09-01-2025 | 300 | 3.15 | RAJASTHAN, KARNATAKA, GUJARAT | 25 |  | NA | 09-01-2027 | NA | Hybrid, Hybrid | 600 | 400 | 200 | 0 | Applied, Applied | CTU , CTU | 4400001173 | NA, NA | NA, NA | , | , | 22-09-2027, 30-06-2027 | -- | -- | --
[21 empty] | Juniper Green Energy Private Limited | 150 | -- | 16-01-2024 | 150 | 3.21 | Hybrid | 100 | 50 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | 09-01-2025 | 150 | HIMACHAL PRADESH | 25 | HPSEBL | 3.91 | Juniper Green Beta Private Limited | Pawan Kumar | 9560540654 | 09-01-2025 | 150 | 3.21 | RAJASTHAN | 25 |  | NA | 09-01-2027 | NA | Hybrid | 150 | 100 | 50 | 0 | Applied | CTU | 412100012 | NA | NA |  |  | 30-09-2026 | -- | -- | --
[21 empty] | Green Infra Wind Energy Limited | 450 | -- | 16-01-2024 | 450 | 3.21 | Hybrid | 300 | 150 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | 09-01-2025 | 450 | HIMACHAL PRADESH | 25 | HPSEBL | 3.91 | Green Infra Renewable Projects Limited (GIRPL) | Gourav Somani | 9910987587 | 09-01-2025 | 450 | 3.21 | RAJASTHAN, RAJASTHAN | 25 |  | NA | 09-01-2027 | NA | Hybrid | 150 | 300 | 150 | 0 | Applied | CTU | 2200000541 | NA | NA |  |  | 31-05-2027 | -- | -- | --
13 |  | Hybrid (Tranche-VIII) | -- | SECI/C&P/IPP/13/0020/23-24 | 1200 | NA | 20-02-2024 | 28-02-2024 | 20-05-2024 | Hybrid | Without Storage | Without Greenshoe | -- | 24-05-2024 | 14-06-2024 | 1200 | 0 | 8 | 2160 | 0 | Juniper Green Energy Private Limited | 150 | -- | 20-06-2024 | 150 | 3.43 | Hybrid | 130 | 50 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Asurari Renewables India Project Private Limited | 300 | -- | 20-06-2024 | 300 | 3.45 | Hybrid | 275 | 99 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | AMPIN Energy Utility Private Limited | 150 | -- | 20-06-2024 | 150 | 3.45 | Hybrid | 135 | 50.4 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Adyant Enersol Private Limited | 60 | -- | 20-06-2024 | 60 | 3.45 | Hybrid | 60 | 24 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | JSW Neo Energy Limited | 300 | -- | 20-06-2024 | 300 | 3.45 | Hybrid | 200 | 100 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Avaada Energy Private Limited | 240 | -- | 20-06-2024 | 240 | 3.46 | Hybrid | 240 | 80 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
14 |  | Hybrid (Tranche-IX) | -- | SECI/C&P/IPP/13/0006/24-25 | 600 | NA | 28-06-2024 | 11-07-2024 | 06-08-2024 | Hybrid | Without Storage | Without Greenshoe | -- | 09-08-2024 | 01-10-2024 | 600 | 0 | 4 | 810 | 0 | Juniper Green Energy Private Limited | 150 | -- | 15-10-2024 | 150 | 3.25 | Hybrid | 130 | 50 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | ACME Solar Holdings Limited | 300 | -- | 15-10-2024 | 300 | 3.25 | Hybrid | 300 | 100 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Sembcorp Green Infra Private Limited | 150 | -- | 15-10-2024 | 150 | 3.26 | Hybrid | 150 | 50 | 0 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
15 |  | FDRE (FDRE-VI) | -- | SECI/C&P/IPP/13/0013/24-25 | 2000 | NA | 12-09-2024 | 23-09-2024 | 14-11-2024 | FDRE | With Storage | Without Greenshoe | -- | 22-11-2024 | 02-01-2025 | 200 | 1800 | 3 | 820 | 0 | Altra Xergi Power Private Limited | 200 | -- | 14-01-2025 | 200 | 8.5 | FDRE | 136 | 0 | 800 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
16 |  | RTC (RTC-IV) | -- | SECI/C&P/IPP/13/0019/24-25 | 1200 | NA | 30-10-2024 | 14-11-2024 | 24-03-2025 | RTC | With Storage | Without Greenshoe | -- | 27-03-2025 | 26-05-2025 | 420 | 780 | 5 | 540 | 0 | Hero Solar Energy Private Limited | 120 | -- | 11-06-2025 | 120 | 5.06 | RTC | 175 | 160 | 300 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Hexa Climate Solutions Private Limited | 100 | -- | 11-06-2025 | 100 | 5.06 | RTC | 150 | 150 | 150 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Sembcorp Green Infra Private Limited | 50 | -- | 11-06-2025 | 50 | 5.07 | RTC | 78 | 68 | 166 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Jindal India Power Limited | 150 | -- | 11-06-2025 | 150 | 5.07 | RTC | 158.5 | 330 | 448 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
1 | SECI Solar | VGF Scheme (Ph-II B-I) | -- | SECI/JNNSM/SPV/P-2/B-1/RfS/102013 | 750 | NA | 28-10-2013 | 19-11-2013 | 20-01-2014 | Solar | Without Storage | Without Greenshoe | -- | 20-01-2014 | 21-02-2014 | 750 | 0 | 68 | 2170 | 40 | Swelect Energy Systems Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 06-07-2015 | 10 | TAMIL NADU | 25 | TANGEDCO | 5.5 | Swelect Energy Systems Limited | Nataraj S | 98844 4582 | 28-03-2014 | 10 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : TAMIL NADU | NA | NA | NA |  |  | NA | 2015-07-06 | 10 | ,
[21 empty] | Sharda Construction & Corporation Private Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-12-2014 | 10 | MAHARASHTRA | 25 | MSEDCL | 5.5 | Sharda Construction & Corporation Private Limited | vipul | 9503056606 | 28-03-2014 | 10 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : MAHARASHTRA | NA | NA | NA |  |  | NA | 2015-05-28 | 10 | ,
[21 empty] | Today Homes And Infrastructure Private Limited | 50 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 31-03-2015 | 10 | PUNJAB | 25 | PSPCL | 5.5 | Today Green Energy Private Limited | kunal mahajan | 8130499784 | 28-03-2014 | 10 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-10-04 | 10 | ,
[24 empty] | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 10-03-2015 | 10 | PUNJAB | 25 | PSPCL | 5.5 | Today Green Energy Private Limited | kunal mahajan | 8130499784 | 28-03-2014 | 10 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:RAJASTHAN | NA | NA | NA |  |  | NA | 2015-10-04 | 10 | ,
[24 empty] | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 03-03-2015 | 10 | PUNJAB | 25 | PSPCL | 5.5 | Today Green Energy Private Limited | kunal mahajan | 8130499784 | 28-03-2014 | 10 | 4.395 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:RAJASTHAN | NA | NA | NA |  |  | NA | 2016-05-12 | 10 | ,
[24 empty] | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 18-03-2015 | 10 | RAJASTHAN | 25 | RUVNL | 5.5 | Today Green Energy Private Limited | kunal mahajan | 8130499784 | 28-03-2014 | 10 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:RAJASTHAN | NA | NA | NA |  |  | NA | 2015-10-04 | 10 | ,
[24 empty] | 26-02-2014 | 10 | 545 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-12-2014 | 10 | MAHARASHTRA | 25 | MSEDCL | 5.5 | Today Green Energy Private Limited | kunal mahajan | 8130499784 | 28-03-2014 | 10 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:RAJASTHAN | NA | NA | NA |  |  | NA | 2015-10-04 | 10 | ,
[21 empty] | SEI Suncells Private Limited | 20 | -- | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | SEI Sitara Private Limited | 30 | -- | 26-02-2014 | 30 | 5.45 | Solar | 30 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-10-2014 | 30 | MADHYA PRADESH | 25 | MPPMCL | 5.5 | SEI Sitara Private Limited | sumit ranjan | 9643327068 | 28-03-2014 | 30 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : MADHYA PRADESH | NA | NA | NA |  |  | NA | 2015-02-26 | 30 | ,
[21 empty] | Laxmi Diamond Private limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-09-2014 | 10 | JHARKHAND | 25 | JBVNL | 5.5 | Laxmi Diamond Private Limited | Tushar | 9638957074 | 28-03-2014 | 10 | 5.3 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-09-29 | 10 | ,
[21 empty] | RDA Energy Private Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 18-03-2015 | 10 | RAJASTHAN | 25 | RUVNL | 5.5 | RDA Energy Private Limited | Gautam Jha | 9599277874 | 28-03-2014 | 10 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-03-30 | 10 | ,
[21 empty] | Palimarwar Solar Project Private Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 18-03-2015 | 10 | RAJASTHAN | 25 | RUVNL | 5.5 | Palimarwar Solar Project Private Limited | rohan jhwar | 99897 8145 | 28-03-2014 | 10 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-04-13 | 10 | ,
[21 empty] | Solairedirect Energy India Private Limited | 30 | -- | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 22-08-2014 | 20 | HARYANA | 25 | HPPC | 5.5 | Northern Solaire Prakash Private Limited | Niraj Verma | 95992 2184 | 28-03-2014 | 20 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-05-07 | 20 | ,
[24 empty] | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-08-2014 | 10 | ODISHA | 25 | GRIDCO | 5.5 | Suryauday Solaire Prakash Private Limited | Neeraj Verma | 95992 2184 | 28-03-2014 | 10 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:RAJASTHAN | NA | NA | NA |  |  | NA | 2015-04-28 | 10 | ,
[21 empty] | Azure Power India Private Limited | 100 | -- | 26-02-2014 | 40 | 5.45 | Solar | 40 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 22-08-2014 | 40 | HARYANA | 25 | HPPC | 5.5 | Azure Green Tech Private Limited | Vidya Dutt | 8800733708 | 28-03-2014 | 40 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-05-05 | 40 | ,
[24 empty] | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 22-08-2014 | 20 | HARYANA | 25 | HPPC | 5.5 | Azure Sunshine Private Limited, | Vidya Dutt | 8800733708 | 28-03-2014 | 20 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:RAJASTHAN | NA | NA | NA |  |  | NA | 2015-05-05 | 20 | ,
[24 empty] | 26-02-2014 | 40 | 5.45 | Solar | 40 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 18-03-2015 | 40 | RAJASTHAN | 25 | RUVNL | 5.5 | Azure Clean Energy Private Limited | Vidya Dutt | 8800733708 | 28-03-2014 | 40 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:RAJASTHAN | NA | NA | NA |  |  | NA | 2015-04-28 | 40 | ,
[21 empty] | Karnataka Power Corporation Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 22-08-2014 | 10 | KARNATAKA | 25 | BESCOM | 5.5 | Karnataka Power Corporation Limited | Triveni | 9538053622 | 28-03-2014 | 10 | 4.75 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : KARNATAKA | NA | NA | NA |  |  | NA | 2015-06-22 | 10 | ,
[21 empty] | Waaree Energies Private Limited | 50 | -- | 26-02-2014 | 50 | 5.45 | Solar | 50 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 30-07-2014 | 50 | CHHATTISGARH | 25 | CSPDCL | 5.5 | WAANEEP Solar Private Limited | Ashutosh Vyas | 9953314792 | 28-03-2014 | 50 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : MADHYA PRADESH | NA | NA | NA |  |  | NA | 2015-05-04 | 30 | ,
[70 empty] | 2015-05-20 | 10
[70 empty] | 2015-06-15 | 10
[21 empty] | Hero Solar Energy Private Limited | 30 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-10-2014 | 10 | MADHYA PRADESH | 25 | MPPMCL | 5.5 | Clean Solar Power Dhar Private Limited | Ashutosh Vyas | 9953314792 | 28-03-2014 | 10 | 5.45 |  | 25 | Yes | 24-10-2014 | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : MADHYA PRADESH | NA | NA | NA |  |  | NA | 2015-03-30 | 10 | ,
[24 empty] | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-10-2014 | 10 | MADHYA PRADESH | 25 | MPPMCL | 5.5 | Clean Solar Power (Dhar) Private Limited | Ashutosh Vyas | 9953314792 | 28-03-2014 | 10 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:MADHYA PRADESH | NA | NA | NA |  |  | NA | 2015-03-30 | 10 | ,
[24 empty] | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-10-2014 | 10 | MADHYA PRADESH | 25 | MPPMCL | 5.5 | Clean Solar Power (Dhar) Private Limited | Ashutosh Vyas | 9953314792 | 28-03-2014 | 10 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:MADHYA PRADESH | NA | NA | NA |  |  | NA | 2015-03-30 | 10 | ,
[21 empty] | IL&FS Energy Development Company Limited | 40 | -- | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-03-2015 | 20 | GOA | 25 | GOA | 5.5 | Malwa Solar Power Generation Private Limited (Formerly, IL&FS Energy Development Company Limited) | Rajesh Zoldeo | 8130553456 | 28-03-2014 | 20 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : MADHYA PRADESH | NA | NA | NA |  |  | NA | 2015-05-01 | 20 | ,
[24 empty] | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-03-2015, 15-12-2014 | 20 | GOA, MAHARASHTRA | 50 | Goa, MSEDCL | 11 | Malwa Solar Power Generation Private Limited (Formerly, IL&FS Energy Development Company Limited) | Rajesh Zoldeo | 8130553456 | 28-03-2014 | 20 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:MADHYA PRADESH | NA | NA | NA |  |  | NA | 2015-04-29 | 20 | ,
[21 empty] | Green Energy Development Corporation Of Odisha Limited | 20 | -- | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-08-2014 | 20 | ODISHA | 25 | GRIDCO | 5.5 | Green Energy Development Corporation of Odisha Limited | Bharat | 9937073434 | 28-03-2014 | 20 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : ODISHA | NA | NA | NA |  |  | NA | 2016-03-09 | 10 | ,
[70 empty] | 2016-06-06 | 10
[21 empty] | Ranji Solar Energy Private Limited | 20 | -- | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 29-10-2014 | 20 | ASSAM | 25 | APDCL | 5.5 | Eden Renewable Ranji Private Limited (Formerly, Ranji Solar Energy Private Limited) | Sidharth Jain | 7303821555 | 28-03-2014 | 20 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-05-18 | 20 | ,
[21 empty] | Welspun Renewables Energy Limited | 5 | -- | 26-02-2014 | 5 | 5.45 | Solar | 5 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 18-03-2015 | 5 | RAJASTHAN | 25 | RUVNL | 5.5 | Tata Power Renewable Energy Limited (Formerly, Walwhan Solar RJ Private Limited (Welspun Solar UP Private Limited)) | kirtipal Khobragade | 8879772352 | 28-03-2014 | 5 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-04-22 | 5 | ,
[21 empty] | Gujarat Power Corporation Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-08-2014 | 10 | ODISHA | 25 | GRIDCO | 5.5 | Gujarat Power Corporation Limited | Chirag | 9925212098 | 28-03-2014 | 10 | 4.75 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : GUJARAT | NA | NA | NA |  |  | NA | 2015-03-20 | 10 | ,
[21 empty] | SEI L'Volta Private Limited | 20 | -- | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-10-2014 | 20 | MADHYA PRADESH | 25 | MPPMCL | 5.5 | SEI L'Volta Private Limited | sumit ranjan | 9643327068 | 28-03-2014 | 20 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : MADHYA PRADESH | NA | NA | NA |  |  | NA | 2015-02-26 | 20 | ,
[21 empty] | Finnsurya Energy Private Limited | 40 | -- | 26-02-2014 | 30 | 5.45 | Solar | 30 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[24 empty] | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-10-2024 | 10 | MADHYA PRADESH | 25 | MPPMCL | 5.5 | Gentari Renewables Finnsurya Energy Private Limited (Formerly, Fortum Finnsurya Energy Private Limited) | Sumit Ranjan | 9643327068 | 28-03-2014 | 10 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:MADHYA PRADESH | NA | NA | NA |  |  | NA | 2014-12-31 | 10 | ,
[21 empty] | Rishabh Buildwell Private Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 18-03-2015 | 10 | RAJASTHAN | 25 | RUVNL | 5.5 | Rishabh Renergy Private Limited | Anwar | 9972244270 | 28-03-2014 | 10 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-03-25 | 10 | ,
[21 empty] | SEI Suryalabh Private Limited | 30 | -- | 26-02-2014 | 30 | 5.45 | Solar | 30 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 18-03-2015 | 30 | RAJASTHAN | 25 | RUVNL | 5.5 | SEI Suryalabh Private Limited | Sumit Ranjan | 9643327068 | 28-03-2014 | 30 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-03-25 | 30 | ,
[21 empty] | Medha Energy Private Limited | 20 | -- | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 16-10-2014 | 20 | DELHI | 25 | TPDDL | 5.5 | Medha Energy Private Limited | Sidharth Jain | 7303821555 | 28-03-2014 | 20 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-05-20 | 20 | ,
[21 empty] | Backbone Enterprises Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-09-2014 | 10 | ODISHA | 25 | GRIDCO | 5.5 | Ess Gee Real Estate Developers Private Limited (Formerly, Iron Triangle Limited (Backbone Enterprises Limited)) | Pramod Thakare | 7276119669 | 28-03-2014 | 10 | 5.355 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : GUJARAT | NA | NA | NA |  |  | NA | 2015-09-18 | 10 | ,
[21 empty] | Focal Energy Solar India Private Limited | 40 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-10-2014 | 10 | MADHYA PRADESH | 25 | MPPMCL | 5.5 | Focal Photovoltaic India Private Limited | Sumit Ranjan | 9643327068 | 28-03-2014 | 10 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : MADHYA PRADESH | NA | NA | NA |  |  | NA | 2015-06-01 | 10 | ,
[24 empty] | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 04-01-2015 | 10 | BIHAR | 25 | BSPHCL | 5.5 | Focal Renewable Energy Two India Private Limited | Sumit Ranjan | 9643327068 | 28-03-2014 | 10 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:MADHYA PRADESH | NA | NA | NA |  |  | NA | 2015-06-01 | 10 | ,
[24 empty] | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 30-07-2014 | 20 | CHHATTISGARH | 25 | CSPDCL | 5.5 | Terralight Solar Energy Patlasi Private Limited (Formerly, Focal Energy Solar One India Private Limited) | Lokendra Ranawat | 9311279183 | 28-03-2014 | 20 | 5.45 |  | 25 |  |  | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU:MADHYA PRADESH | NA | NA | NA |  |  | NA | 2015-06-01 | 10 | ,
[70 empty] | 2015-06-12 | 10
[21 empty] | Gujarat State Electricity Corporation Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-08-2014 | 10 | ODISHA | 25 | GRIDCO | 5.5 | Gujarat State Electricity Corporation Limited | Gsecl | 9687663077 | 28-03-2014 | 10 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : GUJARAT | NA | NA | NA |  |  | NA | 2015-03-20 | 10 | ,
[21 empty] | Enersan Power Private Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-08-2014 | 10 | ODISHA | 25 | GRIDCO | 5.5 | Enersan Power Private Limited | Pramod Thakare | 7276119669 | 28-03-2014 | 10 | 5.355 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : GUJARAT | NA | NA | NA |  |  | NA | 2015-09-18 | 10 | ,
[21 empty] | Acme Mumbai Power Private Limited | 20 | -- | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-02-2015 | 20 | DELHI | 25 | BYPL | 5.5 | Eden Mumbai Solar Private Limited (Formerly, Acme Mumbai Power Private Limited) | Sidharth Jain | 7303821555 | 28-03-2014 | 20 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-05-18 | 20 | ,
[21 empty] | Belectric Photovoltaic India Private Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | -- | -- | -- | NA | NA | -- | -- | NA | [6 empty] | Sunrise Energy Generation Private Limited | NA | 0 | 28-03-2014 | 10 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | [13 empty] | -- | -- | --
[21 empty] | 4G Identity Solutions Private Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | -- | -- | -- | NA | NA | -- | -- | NA | [6 empty] | 4G Identity Solutions Private Limited | NA | 0 | 28-03-2014 | 10 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | [13 empty] | -- | -- | --
[21 empty] | Acme Rajdhani Power Private Limited | 20 | -- | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 21-03-2015 | 20 | HIMACHAL PRADESH | 25 | HPSEBL | 5.5 | Eden Solar Rajdhani Private Limited (Formerly, Acme Rajdhani Power Private Limited) | Sidharth Jain | 7303821555 | 28-03-2014 | 20 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-05-20 | 20 | ,
[21 empty] | Acme Gurgaon Power Private Limited | 20 | -- | 26-02-2014 | 20 | 5.45 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 09-03-2015 | 20 | DELHI | 25 | BRPL | 5.5 | Eden Solar Energy Gurgaon Private Limited (Formerly, Acme Gurgaon Power Private Limited) | Sidharth Jain | 7303821555 | 28-03-2014 | 20 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA |  |  | NA | 2015-05-18 | 20 | ,
[21 empty] | Vishwaj Energy Private Limited | 10 | -- | 26-02-2014 | 10 | 5.45 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-12-2014 | 10 | MAHARASHTRA | 25 | MSEDCL | 5.5 | Vishwaj Energy Private Limited | Abhijit Patil | 9823470809 | 28-03-2014 | 10 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : MAHARASHTRA | NA | NA | NA |  |  | NA | 2015-04-28 | 10 | ,
[21 empty] | Sunil Hitech Engineers Limited | 5 | -- | 26-02-2014 | 5 | 5.45 | Solar | 5 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-12-2014 | 5 | MAHARASHTRA | 25 | MSEDCL | 5.5 | Solapur Solar Energy Private Limited (Formerly, Sunilhitech Solar (Dhule) Private Limited) | Venkataramana Condoor | 98196 8010 | 28-03-2014 | 5 | 5.45 |  | 25 |  | NA | 28-04-2015 | NA | Solar | 0 |  |  |  | Granted | STU : MAHARASHTRA | NA | NA | NA |  |  | NA | 2015-06-29 | 5 | ,
2 |  | 500 MW Maharashtra, (P-II, B-III) | -- | SECI/JNNSM/P-2/B-3/RfS/MH/082015 | 500 | NA | 27-08-2015 | 06-10-2015 | 06-01-2016 | Solar | Without Storage | Without Greenshoe | -- | 07-01-2016 | 22-01-2016 | 450 | 50 | 15 | 1350 | 72.288 | Bhageria Industries Limited | 30 | -- | 10-03-2016 | 30 | 4.41 | Solar | 30 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-04-2016 | 30 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Bhageria Industries Limited | Vikas | 7666188652 | 10-04-2016 | 30 | 4.41 | MAHARASHTRA | 25 |  | NA | 05-10-2017 | NA | Solar | 0 |  |  |  | Granted | STU : NA | NA | NA | NA | 132/33 kV Kombhalne |  | NA | 2017-06-17 | 30 | ,
[21 empty] | Talettutayi Solar Projects Four Private Limited | 50 | -- | 10-03-2016 | 50 | 4.43 | Solar | 50 | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-04-2016 | 50 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Talettutayi Solar Projects Four Private Limited | Kirandeep Singh | 9818807132 | 10-04-2016 | 50 | 4.425 | MAHARASHTRA | 25 |  | NA | 10-05-2017 | NA | Solar | 0 |  |  |  | Granted | STU : MAHARASHTRA | NA | NA | NA | 132/33kV, Telgaon S/ |  | NA | 2017-08-10 | 50 | ,
[21 empty] | Orange Renewable Power Private Limited | 100 | -- | 10-03-2016 | 100 | 4.43 | Solar | 100 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-04-2016 | 100 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Greenko Suvaan Energy Private Limited (Formerly, Orange Renewable Power Private Limited), Greenko Suvaan Energy Private Limited (Formerly, Orange Renewable Power Private Limited) | Pratul Gupta, Pratul Gupta | 19820817336 | 10-04-2016, 10-04-2016 | 100 | 8.86 | MAHARASHTRA, MAHARASHTRA, MAHARASHTRA | 50 | , | NA, NA | 10-05-2017, 10-05-2017 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : MAHARASHTRA , STU : MAHARASHTRA | NA, NA | NA, NA | NA, NA | 220/132/33 kV Shivaj, 220/132/33 kV Shivaj | , | NA, NA | 2017-06-16 | 50 | , , , ,
[70 empty] | 2017-06-16 | 50
[21 empty] | Sepset Constructions Limited | 40 | -- | 10-03-2016 | 40 | 4.43 | Solar | 40 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-04-2016 | 40 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Sepset Constructions Limited, Sepset Constructions Limited | Rajesh Zoldeo, Rajesh Zoldeo | 16261106912 | 10-04-2016, 10-04-2016 | 40 | 8.86 | MAHARASHTRA, MAHARASHTRA, MAHARASHTRA | 50 | , | NA, NA | 10-05-2017, 10-05-2017 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : MAHARASHTRA , STU : MAHARASHTRA | NA, NA | NA, NA | NA, NA | 132/33 kV, Katol, 132/33 kV, Katol | , | NA, NA | 2017-05-08 | 20 | , , , ,
[70 empty] | 2017-05-08 | 20
[21 empty] | Krishna Windfarms Developers Private limited | 10 | -- | 10-03-2016 | 10 | 4.43 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-04-2016 | 10 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Krishna Windfarms Developers Private Limited | Mr. Harshad Joshi | 9769211439 | 10-04-2016 | 10 | 4.425 | MAHARASHTRA | 25 |  | NA | 10-05-2017 | NA | Solar | 0 |  |  |  | Granted | STU : MAHARASHTRA | NA | NA | NA | 132/33 kV kharda |  | NA | 2017-08-11 | 10 | ,
[21 empty] | AMPL Cleantech Private Limited | 50 | -- | 10-03-2016 | 50 | 4.43 | Solar | 50 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 04-11-2016 | 50 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Solarcraft Mahasolar Private Limited (Formerly, NVR Solar Private Limited) | Gautam Jha | 9599277874 | 10-04-2016 | 50 | 4.43 | MAHARASHTRA | 25 |  | NA | 10-05-2017 | NA | Solar | 0 |  |  |  | Granted | STU : MAHARASHTRA | NA | NA | NA | 132/33 kV Mograle |  | NA | 2017-07-15 | 50 | ,
[21 empty] | Welspun Renewables Energy Private Limited | 100 | -- | 10-03-2016 | 100 | 4.43 | Solar | 100 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-04-2016 | 100 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Avaada Energy Private Limited (Formerly, Welspun Energy Private Limited) | Mr. Angshuman Rudra | 7835004673 | 10-04-2016 | 100 | 4.43 | MAHARASHTRA | 25 |  | NA | 10-05-2017 | NA | Solar | 0 |  |  |  | Granted | STU : MAHARASHTRA | NA | NA | NA | 220 KV Hivarwadi – M |  | NA | 2018-04-16 | 27.712 | ,
[21 empty] | Suzlon Energy Limited | 70 | -- | 10-03-2016 | 70 | 4.43 | Solar | 70 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-04-2016 | 70 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Gale Solarfarms Limited, Tornado Solarfarms Limited | Mr. Sunil Jain, Mr Sunil Jain | 19848286328 | 10-04-2016, 10-04-2016 | 70 | 7.775 | MAHARASHTRA, MAHARASHTRA | 50 | , | NA, NA | 10-05-2017, 10-05-2016 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : MAHARASHTRA , STU : MAHARASHTRA | NA, NA | NA, NA | NA, NA | 220/33 kV Jamde S/s, 220/33 kV Jamde S/s | , | NA, NA | 2018-01-09 | 50 | , , ,
[70 empty] | 2017-10-10 | 20
3 |  | 440 MW, Uttar Pradesh (P-II B-III) | -- | SECI/JNNSM/P-2/B-3/RfS/UP/092015 | 440 | NA | 24-09-2015 | 08-12-2015 | 19-02-2016 | Solar | Without Storage | Without Greenshoe | -- | 20-02-2016 | 15-03-2016 | 125 | 315 | 3 | 565 | 0 | Solairedirect Energy India Pvt. Ltd. | 75 | -- | 09-05-2016 | 75 | 4.43 | Solar | 75 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-10-2016 | 75 | UTTAR PRADESH | 25 | UPPCL | 4.5 | Enviro Solaire private Limited | Neeraj Verma | 9599221848 | 09-06-2016 | 75 | 4.43 | UTTAR PRADESH | 25 |  | NA | 09-07-2017 | NA | Solar | 0 |  |  |  | Granted | STU : NA | NA | NA | NA | 132/33 kV, Jigna S/s |  | NA | 2018-03-11 | 75 | ,
[21 empty] | RattanIndia Solar 2 Limited | 50 | -- | 09-05-2016 | 50 | 4.43 | Solar | 50 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-10-2016 | 50 | UTTAR PRADESH | 25 | UPPCL | 4.5 | Vector Green Prayagraj Solar Private Limited (Formerly, Rattan India Solar 2 Private Limited) | Rajesh Zoldeo | 8130553456 | 09-06-2016 | 50 | 4.43 | UTTAR PRADESH | 25 |  | NA | 09-07-2016 | NA | Solar | 0 |  |  |  | Granted | STU : NA | NA | NA | NA | 132/33 kV Meja Road, |  | NA | 2018-02-08 | 50 | ,
4 |  | 500 MW, Andhra Pradesh (P-II B-III) | -- | SECI/JNNSM/P-2/B-3/RfS/AP/122015 | 500 | NA | 02-01-2016 | 22-01-2016 | 05-04-2016 | Solar | Without Storage | Without Greenshoe | -- | 05-04-2016 | 04-05-2016 | 400 | 100 | 6 | 850 | 0 | FRV Solar Holdings XI BV | 100 | -- | 16-08-2016 | 100 | 4.43 | Solar | 100 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-10-2016 | 100 | ANDHRA PRADESH | 25 | APPCC | 4.5 | Indigrid Solar-I (AP) Private Limited (Formerly, FRV Andhra PradeshSolar Farm-I Private Limited), Indigrid Solar-II (AP) Private Limited (Formerly, FRV India Solar Park-II Private Limited ) | Lokendra Ranawat, Lokendra Ranawat | 18622558366 | 16-09-2016, 16-09-2016 | 100 | 8.86 | ANDHRA PRADESH, ANDHRA PRADESH | 50 | , | NA, NA | 16-10-2017, 16-10-2017 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | CTU , CTU | NA, NA | NA, NA | NA, NA | Galiveedu Solar Park, Galiveedu Solar Park | , | NA, NA | 2018-06-22 | 50 | , , ,
[70 empty] | 2018-10-08 | 50
[21 empty] | ACME Solar Holdings Private Limited | 150 | -- | 16-08-2016 | 150 | 4.43 | Solar | 150 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-10-2016 | 150 | ANDHRA PRADESH | 25 | APPCC | 4.5 | Athena Karnal Solar Power Private Limited (Formerly, ACME Karnal Solar Power Private Limited), Athena Hisar Solar Power Private Limited (Formerly, ACME Hisar Solar Power Private Limited), Athena Bhiwadi Solar Power Private Limited (Formerly, ACME Bhiwadi Solar Power Private Limited) | Sakshi Sharma, Sakshi Sharma, Sakshi Sharma | 29999052204 | 16-09-2016, 16-09-2016, 16-09-2016 | 150 | 13.29 | ANDHRA PRADESH, ANDHRA PRADESH, ANDHRA PRADESH | 75 | , , | NA, NA, NA | 16-10-2017, 16-10-2017, 16-10-2017 | NA, NA, NA | Solar, Solar, Solar | 0 | , , | , , | , , | Granted, Granted, Granted | CTU , CTU , CTU | NA, NA, NA | NA, NA, NA | NA, NA, NA | Galiveedu Solar Park, Galiveedu Solar Park, "Galiveedu Solar Par | , , | NA, NA, NA | 2018-06-21 | 50 | , , , , ,
[70 empty] | 2018-06-21 | 50
[70 empty] | 2018-07-05 | 50
[21 empty] | Tata Power Renewable Energy Limited | 100 | -- | 16-08-2016 | 100 | 4.43 | Solar | 100 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-10-2016 | 100 | ANDHRA PRADESH | 25 | APPCC | 4.5 | Tata Power Renewable Energy Limited, Tata Power Renewable Energy Limited | Kirtipal Khobragade, Kirtipal Khobragade | 17759544704 | 16-09-2016, 16-09-2016 | 100 | 8.86 | ANDHRA PRADESH, ANDHRA PRADESH | 50 | , | NA, NA | 16-10-2017, 16-10-2017 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | CTU , CTU | NA, NA | NA, NA | NA, NA | Galiveedu Solar Park, Galiveedu Solar Park | , | NA, NA | 2018-06-22 | 50 | , , ,
[70 empty] | 2018-06-22 | 50
[21 empty] | Azure Power India Private Limited | 50 | -- | 16-08-2016 | 50 | 4.43 | Solar | 50 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-10-2016 | 50 | ANDHRA PRADESH | 25 | APPCC | 4.5 | Azure Power Thirty Six Private limited | Vidya Dutt | 8800733708 | 16-09-2016 | 50 | 4.43 | ANDHRA PRADESH | 25 |  | NA | 16-10-2017 | NA | Solar | 0 |  |  |  | Granted | CTU | NA | NA | NA | Galiveedu Solar Park |  | NA | 2018-05-05 | 50 | ,
5 |  | 1000 MW, Karnataka (P-II, B-III) | -- | SECI/JNNSM/P-2/B-3/RfS/KA/022016 | 1000 | NA | 15-02-2016 | 01-03-2016 | 23-05-2016 | Solar | Without Storage | Without Greenshoe | -- | 26-05-2016 | 08-06-2016 | 970 | 30 | 11 | 1230 | 0 | Hero Solar Energy Private Limited | 200 | -- | 02-07-2016 | 200 | 4.43 | Solar | 200 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 29-06-2016, 29-06-2016 | 200 | KARNATAKA, KARNATAKA | 50 | BESCOM, GESCOM | 9 | Clean Solar Power (Gulbarga) Private Limited, Clean Solar Power (Gulbarga) Private Limited, Clean Solar Power (Gulbarga) Private Limited, Clean Solar Power (Gulbarga) Private Limited, Clean Solar Power (Gulbarga) Private Limited | Ashutosh Vyas;, Ashutosh Vyas, Ashutosh Vyas, Ashutosh Vyas, Ashutosh Vyas | 49766573960 | 02-08-2016, 02-08-2016, 02-08-2016, 02-08-2016, 02-08-2016 | 200 | 22.15 | KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA | 125 | , , , , | NA, NA, NA, NA, NA | 02-09-2017, 02-09-2017, 02-09-2017, 02-09-2017, 02-09-2017 | NA, NA, NA, NA, NA | Solar, Solar, Solar, Solar, Solar | 0 | , , , , | , , , , | , , , , | Granted, Granted, Granted, Granted, Granted | STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA | NA, NA, NA, NA, NA | NA, NA, NA, NA, NA | NA, NA, NA, NA, NA | 66/11 kV PD Kote s/s, 110/33/11 kV Santapu, 110/11 kV Turvihal S, 110/11 kV Margutti S, 110/33/11 kV Kurdi S | , , , , | NA, NA, NA, NA, NA | 2018-03-19 | 30 | , , , , , , , , ,
[70 empty] | 2018-07-04 | 40
[70 empty] | 2018-06-12 | 40
[70 empty] | 2018-02-07 | 50
[70 empty] | 2018-07-02 | 40
[21 empty] | J K Petroenergy Private Limited | 10 | -- | 02-07-2016 | 10 | 4.43 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 29-06-2016 | 10 | KARNATAKA | 25 | BESCOM | 4.5 | J K PETROENERGY PRIVATE LIMITED | Gaurav Gupta | 9560044566 | 02-08-2016 | 10 | 4.43 | KARNATAKA | 25 |  | NA | 02-09-2017 | NA | Solar | 0 |  |  |  | Granted | STU : KARNATAKA | NA | NA | NA | 110/33/11 kV Betager |  | NA | 2018-02-19 | 10 | ,
[21 empty] | Patil Construction & Infra Limited | 40 | -- | 02-07-2016 | 40 | 4.43 | Solar | 40 |  | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Solitaire Powertech Private Limited | 30 | -- | 02-07-2016 | 30 | 4.43 | Solar | 30 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 29-06-2016 | 30 | KARNATAKA | 25 | BESCOM | 4.5 | Solitaire Powertech Private Limited | Hajra Arshi | 7895118584 | 02-08-2016 | 30 | 4.43 | KARNATAKA | 25 |  | NA | 02-09-2017 | NA | Solar | 0 |  |  |  | Granted | STU : KARNATAKA | NA | NA | NA | 66/11 kV PD Kote s/s |  | NA | 2018-03-08 | 30 | ,
[21 empty] | Energon Soleq Ravi India Power Resources Private Limited | 100 | -- | 02-07-2016 | 100 | 4.43 | Solar | 100 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 29-06-2016 | 100 | KARNATAKA | 25 | CESC | 4.5 | Vena Energy Solar Ravi India Power Resources Private Limited (Formerly, Energon Soleq Ravi India Power Resources Private Limited) | Ashish Tiwari | 9900420524 | 02-08-2016 | 100 | 4.43 | KARNATAKA | 25 |  | NA | 02-09-2017 | NA | Solar | 0 |  |  |  | Granted | STU : KARNATAKA | NA | NA | NA | 220/110kV Vajramatti |  | NA | 2018-03-28 | 100 | ,
[21 empty] | Acme Solar Holdings Private Limited | 160 | -- | 02-07-2016 | 160 | 4.43 | Solar | 160 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 29-06-2016, 29-06-2016, 29-06-2016 | 160 | KARNATAKA, KARNATAKA, KARNATAKA | 75 | BESCOM, HESCOM, MESCOM | 13.5 | Solarcraft Koppal Private Limited (Formerly, ACME Koppal Solar Energy Private Limited), Solarcraft Kaithal Private Limited (Formerly, ACME Kaithal Solar Energy Private Limited), Solarcraft Babadham Private Limited (Formerly, ACME Babadham Solar Power Private Limited), Solarcraft Vijayapura Private Limited (Formerly, ACME Vijayapura Solar Energy Private Limited) | Gautam Jha, Gautam Jha, Gautam Jha, Gautam Jha | 38397111496 | 02-08-2016, 02-08-2016, 02-08-2016, 02-08-2016 | 160 | 17.72 | KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA | 96 | , , , | NA, NA, NA, NA | 02-09-2017, 02-09-2017, 02-09-2017, 02-09-2017 | NA, NA, NA, NA | Solar, Solar, Solar, Solar | 0 | , , , | , , , | , , , | Granted, Granted, Granted, Granted | STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA | NA, NA, NA, NA | NA, NA, NA, NA | NA, NA, NA, NA | 110/11 kV Farhatabad, 110/11 kV Bhagwat SS, 110/11kV Chittiguppa, 220/110/11kV Halbarg | , , , | NA, NA, NA, NA | 2018-03-16 | 40 | , , , , , , ,
[70 empty] | 2018-01-24 | 20
[70 empty] | 2018-01-22 | 20
[70 empty] | 2018-01-23 | 20
[70 empty] | 2018-03-14 | 20
[70 empty] | 2018-03-09 | 20
[70 empty] | 2018-03-15 | 20
[21 empty] | Talettutayi Solar Projects One Private Limited | 30 | -- | 02-07-2016 | 30 | 4.43 | Solar | 30 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 29-06-2016 | 30 | KARNATAKA | 25 | BESCOM | 4.5 | Talettutayi Solar Projects One Private Limited | Kirandeep Singh; | 9818807132 | 02-08-2016 | 30 | 4.43 | KARNATAKA | 25 |  | NA | 02-09-2017 | NA | Solar | 0 |  |  |  | Granted | STU : KARNATAKA | NA | NA | NA | 110/33/11 kV Yelburg |  | NA | 2018-01-05 | 30 | ,
[21 empty] | Parampujya Solar Energy Private Limited | 390 | -- | 02-07-2016 | 350 | 4.43 | Solar | 350 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 29-06-2016, 29-06-2016, 29-06-2019 | 350 | KARNATAKA, KARNATAKA, KARNATAKA | 75 | BESCOM, HESCOM, CSEC | 13.5 | Wardha Solar (Maharashtra) Private Limited, Wardha Solar (Maharashtra) Private Limited, Wardha Solar (Maharashtra) Private Limited, Wardha Solar (Maharashtra) Private Limited, Wardha Solar (Maharashtra) Private Limited, Wardha Solar (Maharashtra) Private Limited, Wardha Solar (Maharashtra) Private Limited, Wardha Solar (Maharashtra) Private Limited, Wardha Solar (Maharashtra) Private Limited | Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj | 77299854588 | 02-08-2016, 02-08-2016, 02-08-2016, 02-08-2016, 02-08-2016, 02-08-2016, 02-08-2016, 02-08-2016, 02-08-2016 | 350 | 39.87 | KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA | 224 | , , , , , , , , | NA, NA, NA, NA, NA, NA, NA, NA, NA | 02-09-2017, 02-09-2017, 02-09-2017, 02-09-2017, 02-09-2017, 02-09-2017, 02-09-2017, 02-09-2017, 02-09-2017 | NA, NA, NA, NA, NA, NA, NA, NA, NA | Solar, Solar, Solar, Solar, Solar, Solar, Solar, Solar, Solar | 0 | , , , , , , , , | , , , , , , , , | , , , , , , , , | Granted, Granted, Granted, Granted, Granted, Granted, Granted, Granted, Granted | STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA , STU : KARNATAKA | NA, NA, NA, NA, NA, NA, NA, NA, NA | NA, NA, NA, NA, NA, NA, NA, NA, NA | NA, NA, NA, NA, NA, NA, NA, NA, NA | 110/33 KV Rajeshwar, 110/33-11kV Santapur, 220/66Madhuvanahally, 220/66Madhuvanahally, 110/11 kV Nalwar s/s, 110/33/11kV Yelburga, 220/110/11kV Shahpur, 110/11kVTakkalaki Ss, 110/11kVTakkalaki SS | , , , , , , , , 110/11kVTakkalaki Ss | NA, NA, NA, NA, NA, NA, NA, NA, NA | 2018-01-29 | 50 | , , , , , , , , , , , , , , , , ,
[70 empty] | 2018-02-27 | 50
[70 empty] | 2018-02-12 | 50
[70 empty] | 2018-02-26 | 40
[70 empty] | 2018-03-08 | 10
[70 empty] | 2018-02-14 | 50
[70 empty] | 2018-03-13 | 30
[70 empty] | 2018-03-13 | 10
[70 empty] | 2018-02-12 | 50
[70 empty] | 2018-04-05 | 10
[24 empty] | 02-07-2016 | 40 | 4.43 | Solar | 40 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 29-06-2016 | 40 | KARNATAKA | 25 | HESCOM | 4.5 | Parampujya Solar Energy Private Limited | Prakhar Bhardwaj | 8588872732 | 02-08-2016 | 40 | 4.43 | KARNATAKA | 25 |  |  | 02-09-2017 | NA | Solar | 0 |  |  |  | Granted | STU:KARNATAKA | NA | NA | NA |  | 110/33/11kV Yelburga | NA | 2018-03-08 | 20 | ,
[70 empty] | 2018-04-30 | 20
[21 empty] | Karnataka Power Corporation Limited | 10 | -- | 02-07-2016 | 10 | 4.43 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 29-06-2016 | 10 | KARNATAKA | 25 | HESCOM | 4.5 | Karnataka Power Corporation Limited | Triveni | 9538053622 | 02-08-2016 | 10 | 4.43 | KARNATAKA | 25 |  | NA | 02-09-2017 | NA | Solar | 0 |  |  |  | Granted | STU : KARNATAKA | NA | NA | NA | 110/33/11kV Shiggaon |  | NA | 2017-11-07 | 10 | ,
6 |  | 50 MW, Maharashtra (P-II, B-III) | -- | SECI/JNNSM/P-2/B-3/RfS/MH/022016 | 50 | NA | 25-02-2016 | NA | 18-03-2016 | Solar | Without Storage | Without Greenshoe | -- | 19-03-2016 | 12-04-2016 | 50 | 0 | 3 | 90 | 0 | Tata Power Renewable Energy Limited | 30 | -- | 16-06-2016 | 30 | 4.43 | Solar | 30 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-04-2016 | 30 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Tata Power Renewable Energy Limited | Kirtipal Khobragade | 8879772352 | 16-07-2016 | 30 | 4.43 | MAHARASHTRA | 25 |  | NA | 16-08-2017 | NA | Solar | 0 |  |  |  | Granted | STU : NA | NA | NA | NA | kV Palaswadi |  | NA | 2017-10-28 | 30 | ,
[21 empty] | Adani Green Energy Limited | 20 | -- | 16-06-2016 | 20 | 4.43 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-04-2016 | 20 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Parampujya Solar Energy Private Limited | Prakhar Bhardwaj | 8588872732 | 16-07-2016 | 20 | 4.16 | MAHARASHTRA | 25 |  | NA | 16-08-2017 | NA | Solar | 0 |  |  |  | Granted | STU : NA | NA | NA | NA | 132/33kV Naldurg s/s |  | NA | 2018-02-22 | 20 | ,
7 |  | 100 MW, Chhattisgarh (P-II B-III) | -- | SECI/SOLAR/JNNSM/P-2/B-3/RfS/CG/032016 | 100 | NA | 17-03-2016 | NA | 20-05-2016 | Solar | Without Storage | Without Greenshoe | -- | 23-05-2016 | 02-06-2016 | 100 | 0 | 3 | 160 | 0 | Parampujya Solar Energy Private Limited | 100 | -- | 02-07-2016 | 100 | 4.43 | Solar | 100 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 29-06-2016 | 100 | CHHATTISGARH | 25 | CSPDCL | 4.5 | Parampujya Solar Energy Private Limited, Parampujya Solar Energy Private Limited | Prakhar Bhardwaj, Prakhar Bhardwaj | 17177745464 | 02-08-2016, 02-08-2016 | 100 | 8.85 | CHHATTISGARH, CHHATTISGARH | 50 | , | NA, NA | 02-09-2017, 02-09-2017 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : CHHATTISGARH , STU : CHHATTISGARH | NA, NA | NA, NA | NA, NA | , | , | NA, NA | -- | -- | --
8 |  | 315 MW, Uttar Pradesh (P-II B-III) | -- | SECI/JNNSM/P-2/B-3/RfS/UP/042016 | 315 | NA | 19-04-2016 | NA | 06-06-2016 | Solar | Without Storage | Without Greenshoe | -- | 16-06-2016 | 04-07-2016 | 40 | 275 | 2 | 80 | 0 | Azure Power Venus Private Limited | 40 | -- | 08-09-2016 | 40 | 4.43 | Solar | 40 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 04-01-2017 | 40 | UTTAR PRADESH | 25 | UPPCL | 4.5 | Azure Power Venus Private Limited | Vidya Dutt | 8800733708 | 08-10-2016 | 40 | 4.43 | UTTAR PRADESH | 25 |  | NA | 08-11-2017 | NA | Solar | 0 |  |  |  | Granted | STU : NA | NA | NA | NA | 132/220/400 kV Aata |  | NA | 2018-04-14 | 40 | ,
9 |  | 250 MW Gujarat (P-II B-IV) | -- | SECI/JNNSM/P-2/B-4/RfS/GJ/042016 | 250 | NA | 22-04-2016 | NA | 31-05-2016 | Solar | Without Storage | Without Greenshoe | Last Date of Bid Submission for 160 MW capacity was 31.05.2025. Last Date of Bid Submission for 65 MW capacity was 28.06.2016. Last Date of Bid Submission for 25 MW capacity was 14.09.2016. | 02-06-2016 | 20-06-2016 | 250 | 0 | 7 | 725 | 0 | Tata Power Renewable Energy Limited | 25 | -- | 18-11-2016 | 25 | 4.43 | Solar | 25 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-02-2017 | 25 | GUJARAT | 25 | GUVNL | 4.5 | Tata Power Renewable Energy Limited (P6) - DCR | Kirtipal | 8879772352 | 18-12-2016 | 25 | 4.43 |  | 25 |  | NA | 18-12-2016 | NA | Solar | 0 |  |  |  | Granted | STU : GUJARAT | NA | NA | NA | 400/220/66 kV Charan |  | NA | 2017-08-16 | 25 | ,
[21 empty] | Gujarat Industries Power Company Limited | 80 | -- | 04-07-2016 | 40 | 4.43 | Solar | 40 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-02-2017 | 40 | GUJARAT | 25 | GUVNL | 4.5 | Gujarat Industries Power Company Limited | psgoyal | 9909925801 | 04-08-2016 | 40 | 4.43 | GUJARAT | 25 |  | NA | 04-08-2017 | NA | Solar | 0 |  |  |  | Granted | STU : GUJARAT | NA | NA | NA | 400/220/66 kV Charan |  | NA | 2017-08-28 | 20 | ,
[70 empty] | 2017-09-14 | 20
[24 empty] | 04-07-2016 | 40 | 4.43 | Solar | 40 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-02-2017 | 40 | GUJARAT | 25 | GUVNL | 4.5 | Gujarat Industries Power Company Limited | P S Goyal | 9909925801 | 04-08-2016 | 40 | 4.43 | GUJARAT | 25 |  |  | 04-08-2017 | NA | Solar | 0 |  |  |  | Granted | STU:GUJARAT | NA | NA | NA | 400/220/66 kV Charan |  | NA | 2017-08-04 | 30 | ,
[70 empty] | 2017-08-28 | 10
[21 empty] | Mahindra Renewables Private Limited | 65 | -- | 04-07-2016 | 40 | 4.43 | Solar | 40 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-02-2017 | 40 | GUJARAT | 25 | GUVNL | 4.5 | Astra Solren Private Limited | Pankaj Vaidya | 8451041564 | 04-08-2016 | 40 | 4.43 | GUJARAT | 25 |  | NA | 04-08-2017 | NA | Solar | 0 |  |  |  | Granted | STU : GUJARAT | NA | NA | NA | 400/220/66 kV Charan |  | NA | 2017-03-31 | 40 | ,
[24 empty] | 29-07-2016 | 25 | 4.43 | Solar | 25 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-02-2017 | 25 | GUJARAT | 25 | GUVNL | 4.5 | Astra Solren Private Limited | Pankaj Vaidya | 8451041564 | 29-08-2016 | 25 | 4.43 | GUJARAT | 25 |  |  | 29-08-2017 | NA | Solar | 0 |  |  |  | Granted | STU:GUJARAT | NA | NA | NA | 400/220/66 kV Charan |  | NA | 2017-06-02 | 25 | ,
[21 empty] | Orange Renewable Power Private Limited | 40 | -- | 04-07-2016 | 40 | 4.43 | Solar | 40 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-02-2017 | 40 | GUJARAT | 25 | GUVNL | 4.5 | Greenko Charanka Solar Energy Private Limited (Formerly, Orange Charanka Solar Energy Private Limited) | Pratul Gupta | 9910408668 | 04-08-2016 | 40 | 4.43 |  | 25 |  | NA | 04-08-2017 | NA | Solar | 0 |  |  |  | Granted | STU : GUJARAT | NA | NA | NA | 400/220/66 kV Charan |  | NA | 2017-08-04 | 40 | ,
[21 empty] | ReNew Solar Power Private Limited | 40 | -- | 29-07-2016 | 40 | 4.43 | Solar | 40 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-02-2017 | 40 | GUJARAT | 25 | GUVNL | 4.5 | ReNew Solar Energy (Karnataka Two) Private Limited | Rohit Singh | 7389909907 | 29-08-2016 | 40 | 4.43 |  | 25 |  | NA | 29-08-2017 | NA | Solar | 0 |  |  |  | Granted | STU : GUJARAT | NA | NA | NA | 400/220/66 kV Charan |  | NA | 2017-03-31 | 40 | ,
10 |  | 160 MW, Uttar Pradesh (P-II, B-III) | -- | SECI/JNNSM/P-2/B-3/RfS/UP/04 2016 | 160 | NA | 29-04-2016 | NA | 14-07-2016 | Solar | Without Storage | Without Greenshoe | -- | 15-07-2016 | 08-08-2016 | 160 | 0 | 2 | 320 | 0 | Essel Green Energy Private Limited | 160 | -- | 16-08-2016 | 160 | 4.43 | Solar | 160 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-04-2017 | 160 | UTTAR PRADESH | 25 | UPPCL | 4.5 | UP Mehrauni - I Urja Private Limited, UP Mehrauni - II Urja Private Limited, UP Sarila Urja Private Limited, UP Koraun Urja Private Limited | Gaurav Gupta, Gaurav Gupta, Gaurav Gupta, Gaurav Gupta | 38240178264 | 16-09-2016, 16-09-2016, 16-09-2016, 16-09-2016 | 160 | 16.551 | UTTAR PRADESH, UTTAR PRADESH, UTTAR PRADESH, UTTAR PRADESH | 100 | , , , | NA, NA, NA, NA | 16-10-2017, 16-10-2017, 16-10-2017, 16-10-2017 | NA, NA, NA, NA | Solar, Solar, Solar, Solar | 0 | , , , | , , , | , , , | Granted, Granted, Granted, Granted | STU : UTTAR PRADESH , STU : UTTAR PRADESH , STU : UTTAR PRADESH , STU : UTTAR PRADESH | NA, NA, NA, NA | NA, NA, NA, NA | NA, NA, NA, NA | Shankargarh 132/33 k, Lalganj 132/33 kV SS, 132/33 kV Usawan S/S, 132/33 kV Koraun S/S | , , , | NA, NA, NA, NA | 2018-06-19 | 20 | , , , , , , ,
[70 empty] | 2018-10-14 | 40
[70 empty] | 2018-07-26 | 40
[70 empty] | 2018-07-23 | 20
[70 empty] | 2018-10-08 | 20
[70 empty] | 2018-10-08 | 20
11 |  | 300 MW, Odisha (P-II, B-IV) | -- | SECI/JNNSM/P-2/B-4/RfS/OD/052016/B | 300 | NA | 11-05-2016 | NA | 15-07-2016 | Solar | Without Storage | Without Greenshoe | -- | 18-07-2016 | 22-08-2016 | 270 | 30 | 4 | 340 | 0 | Jyoti Infrastructure Private Limited | 10 | -- | 22-11-2016 | 10 | 4.43 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 25-10-2016 | 10 | ODISHA | 25 | GRIDCO | 4.5 | Jyoti Solar Solutions Private Limited | Supravat Mohapatra | 9990751919 | 22-12-2016 | 10 | 4.43 | ODISHA | 25 |  | NA | 22-12-2017 | NA | Solar | 0 |  |  |  | Granted | STU : ODISHA | NA | NA | NA | 132/33 kV GSS, Patan |  | NA | 2018-04-04 | 10 | ,
[21 empty] | IBC Solar Ventures India B.V. | 20 | -- | 22-11-2016 | 20 | 4.43 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 25-10-2016 | 20 | ODISHA | 25 | GRIDCO | 4.5 | Sadipali Solar Private Limited | Ramachandra Reddy | 9848888388 | 22-12-2016 | 20 | 4.43 | ODISHA | 25 |  | NA | 22-12-2017 | NA | Solar | 0 |  |  |  | Granted | STU : ODISHA | NA | NA | NA | 132/33 kV Kesinga |  | NA | 2018-04-14 | 20 | ,
[21 empty] | Essel Green Energy Private Limited | 240 | -- | 22-11-2016 | 240 | 4.43 | Solar | 240 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 25-10-2016, 25-10-2016, 25-10-2016, 25-10-2016, 25-10-2016, 25-10-2016 | 240 | ODISHA, ODISHA, ODISHA, ODISHA, ODISHA, ODISHA | 150 | GRIDCO, GRIDCO, GRIDCO, GRIDCO, GRIDCO, GRIDCO | 27 | Vento Energy Infra Limited (Formerly, Vento Energy Infra Private Limited), Vento Power Private Limited, Dakshin Odisha Urja Private Limited, Vento Power Infra Private Limited, Vento Power Projects Private Limited, Vento Power & Energy Limited | Prakhar Bhardwaj, Gaurav Gupta, Gaurav Gupta, Sanjay Jain, Gaurav Gupta, Gaurav Gupta | 56547119863 | 22-12-2016, 22-12-2016, 22-12-2016, 22-12-2016, 22-12-2016, 22-12-2016 | 240 | 24.515 | ODISHA, , , , , | 150 | , , , , , | NA, NA, NA, NA, NA, NA | 22-12-2016, 22-12-2016, 22-12-2017, 22-12-2016, 22-12-2017, 22-12-2017 | NA, NA, NA, NA, NA, NA | Solar, Solar, Solar, Solar, Solar, Solar | 0 | , , , , , | , , , , , | , , , , , | Granted, Granted, Granted, Granted, Granted, Granted | STU : ODISHA , STU : NA , STU : ODISHA , STU : NA , STU : ODISHA , STU : ODISHA | NA, NA, NA, NA, NA, NA | NA, NA, NA, NA, NA, NA | NA, NA, NA, NA, NA, NA | 132/33 kV Tentulikhu, kV Tusra, 132/33 kV padampur, kV Tusra, 132/33 kV Kesinga, 132/33 kV Kesinga | , , , , , | NA, NA, NA, NA, NA, NA | 2018-12-22 | 40 | , , , , , ,
[70 empty] | 2018-12-19 | 40
[70 empty] | 2018-12-20 | 40
[70 empty] | 2018-08-27 | 40
[70 empty] | 2018-12-22 | 40
[70 empty] | 2018-08-06 | 40
12 |  | 450 MW, Maharashtra (P-II B-IV) | -- | SECI/NSM/P-2/B-4/RfS/MH/062016/B | 450 | NA | 14-06-2016 | NA | 05-08-2016 | Solar | Without Storage | Without Greenshoe | -- | 08-08-2016 | 20-09-2016 | 450 | 0 | 14 | 1460 | 0 | Vijay Printing Press Private Limited | 10 | -- | 23-11-2016 | 10 | 4.42 | Solar | 10 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-12-2016 | 10 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Vijay Printing Press Private Limited | Ravi Khanna | 9815165650 | 22-12-2016 | 10 | 4.42 | MAHARASHTRA | 25 |  | NA | 23-12-2017 | NA | Solar | 0 |  |  |  | Granted | STU : MAHARASHTRA | NA | NA | NA | 132/11 kV Wagdhari S |  | NA | 2018-01-24 | 10 | ,
[21 empty] | Solar Edge Power and Energy Private Limited | 130 | -- | 23-11-2016 | 130 | 4.43 | Solar | 130 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-12-2016, 01-12-2016, 01-12-2016 | 130 | MAHARASHTRA, MAHARASHTRA, MAHARASHTRA | 75 | MSEDCL, MSEDCL, MSEDCL | 13.5 | Solar Edge Power and Energy Private Limited, Solar Edge Power and Energy Private Limited, Solar Edge Power and Energy Private Limited | Lokendra Ranawat, Lokendra Ranawat, Lokendra Ranawat | 27933837549 | 23-12-2016, 23-12-2016, 23-12-2016 | 130 | 13.29 | MAHARASHTRA, MAHARASHTRA, MAHARASHTRA | 75 | , , | NA, NA, NA | 23-12-2017, 23-12-2017, 23-12-2017 | NA, NA, NA | Solar, Solar, Solar | 0 | , , | , , | , , | Granted, Granted, Granted | STU : MAHARASHTRA , STU : MAHARASHTRA , STU : MAHARASHTRA | NA, NA, NA | NA, NA, NA | NA, NA, NA | 132/33 kV Pangri S/S, 132/33 kV Muktai Nag, 132/33 kV Pangri S/S | , , | NA, NA, NA | 2018-03-09 | 50 | , , , , ,
[70 empty] | 2018-03-27 | 50
[70 empty] | 2018-03-23 | 30
[21 empty] | Lightsource Renewable Energy Holdings Ltd | 50 | -- | 23-11-2016 | 50 | 4.43 | Solar | 50 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-12-2016 | 50 | MAHARASHTRA | 25 | MSEDCL | 4.5 | Torrent Saurya Urja 6 Private Limited (Formerly, LREHL Renewable India SPV 1 Private Limited) | Jaydip Chudasoma | 9227410136 | 23-12-2016 | 50 | 4.43 |  | 25 |  | NA | 23-12-2017 | NA | Solar | 0 |  |  |  | Granted | STU : MAHARASHTRA | NA | NA | NA | 132/33 kV Wagdhari S |  | NA | 2018-02-26 | 30 | ,
[70 empty] | 2018-03-08 | 20
[21 empty] | Neel Metal Products Limited | 100 | -- | 23-11-2016 | 100 | 4.43 | Solar | 100 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-12-2016, 01-12-2016 | 100 | MAHARASHTRA, MAHARASHTRA | 50 | MSEDCL, MSEDCL | 9 | JBM Solar Energy Maharashtra Private Limited, JBM Solar Power Maharashtra Private Limited | "B D Sharma; Neeraj Kumar", B D Sharma Neeraj Kumar | 19799823782 | 23-12-2016, 23-12-2016 | 100 | 8.86 | MAHARASHTRA, MAHARASHTRA | 50 | , | NA, NA | 23-12-2017, 23-12-2017 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : MAHARASHTRA , STU : MAHARASHTRA | NA, NA | NA, NA | NA, NA | 220/132 kV Jalna S/S, 220/132 kV Jalna S/S | , | NA, NA | 2018-04-18 | 60 | , , ,
[70 empty] | 2018-04-18 | 40
[21 empty] | Sukhbir Agro Energy Limited | 20 | -- | 23-11-2016 | 20 | 4.43 | Solar | 20 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-12-2016, 01-12-2016 | 20 | MAHARASHTRA, MAHARASHTRA | 50 | MSEDCL, MSEDCL | 9 | SAEL Limited (Formerly, Sukhbir Agro Energy Limited), SAEL Limited (Formerly, Sukhbir Agro Energy Limited) | Ravi Khanna, Ravi Khanna | 18262404276 | 23-12-2016, 23-12-2016 | 20 | 8.86 | MAHARASHTRA, MAHARASHTRA | 50 | , | NA, NA | 23-12-2017, 23-12-2017 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : MAHARASHTRA , STU : MAHARASHTRA | NA, NA | NA, NA | NA, NA | 132/11 kV Wagdhari S, 132/11 kV Wagdhari S | , | NA, NA | 2018-01-24 | 10 | , , ,
[70 empty] | 2018-01-24 | 10
[21 empty] | Canadian Solar Energy Holding Singapore 2 Pte.Limited | 80 | -- | 23-11-2016 | 80 | 4.43 | Solar | 80 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-12-2016, 01-12-2016, 01-12-2016, 01-12-2016 | 80 | MAHARASHTRA, MAHARASHTRA, MAHARASHTRA, MAHARASHTRA | 100 | MSEDCL, MSEDCL, MSEDCL, MSEDCL | 18 | Fermi Solarfarms Private Limited, Fermi Solarfarms Private Limited, Fermi Solarfarms Private Limited, Fermi Solarfarms Private Limited | Angshuman Rudra, Angshuman Rudra, Angshuman Rudra, Angshuman Rudra | 31340018692 | 23-12-2016, 23-12-2016, 23-12-2016, 23-12-2016 | 80 | 17.72 | MAHARASHTRA, MAHARASHTRA, MAHARASHTRA, MAHARASHTRA | 100 | , , , | NA, NA, NA, NA | 23-12-2017, 23-12-2017, 23-12-2017, 23-12-2017 | NA, NA, NA, NA | Solar, Solar, Solar, Solar | 0 | , , , | , , , | , , , | Granted, Granted, Granted, Granted | STU : MAHARASHTRA , STU : MAHARASHTRA , STU : MAHARASHTRA , STU : MAHARASHTRA | NA, NA, NA, NA | NA, NA, NA, NA | NA, NA, NA, NA | 220/132 kV Chalisgao, 220/132 kV Chalisgao, 220/132 kV Chalisgao, 220/132 kV Chalisgao | , , , | NA, NA, NA, NA | 2018-04-14 | 20 | , , , , , , ,
[70 empty] | 2018-04-14 | 20
[70 empty] | 2018-04-14 | 20
[70 empty] | 2018-04-14 | 20
[21 empty] | Essel Green Energy Private Limited | 60 | -- | 23-11-2016 | 60 | 4.43 | Solar | 60 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-12-2016, 01-12-2016 | 60 | MAHARASHTRA, MAHARASHTRA | 50 | MSEDCL, MSEDCL | 9 | MH Parbhani Power Private Limited, Flexirural Urja Jalgaon Limited | Gaurav Gupta, Gaurav Gupta | 19120089132 | 23-12-2016, 23-12-2016 | 60 | 7.72 | , | 50 | , | NA, NA | 23-12-2017, 23-12-2017 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : MAHARASHTRA , STU : MAHARASHTRA | NA, NA | NA, NA | NA, NA | 132/33 kV Gangakhed, | , | NA, NA | 2018-12-22 | 40 | , ,
[70 empty] | 2018-12-22 | 20
13 |  | 500 MW Bhadla-III (Part-1) (P-II B-IV) | -- | SECI/NSM/P-2/B-4/RfS/RJ/112016/Bhadla-III | 500 | NA | 08-11-2016 | NA | 19-04-2017 | Solar | Without Storage | Without Greenshoe | -- | 20-04-2017 | 11-05-2017 | 500 | 0 | 24 | 5500 | 0 | ACME Solar Holdings Private Limited | 200 | -- | 16-08-2017 | 200 | 2.44 | Solar | 200 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-05-2017, 12-05-2017 | 200 | RAJASTHAN, RAJASTHAN | 50 | RUVNL, RUVNL | 5.02 | ACME Jodhpur Solar Power Private Limited, ACME Rewa Solar Energy Private Limited | Yogesh Kumar Sanklecha, Yogesh Kumar Sanklecha | 17488121202 | 16-09-2017, 16-09-2017 | 200 | 4.88 | , | 50 | , | NA, NA | 16-09-2018, 16-09-2018 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : RAJASTHAN , STU : RAJASTHAN | NA, NA | NA, NA | NA, NA | Bhadla Solar Park Po, Bhadla Solar Park Po | , | NA, NA | 2018-09-21 | 100 | , ,
[70 empty] | 2018-09-24 | 100
[21 empty] | SBG Cleantech One Limited | 300 | -- | 16-08-2017 | 300 | 2.45 | Solar | 300 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-05-2017, 12-05-2017, 12-05-2017, 12-05-2017 | 400 | RAJASTHAN, RAJASTHAN, RAJASTHAN, RAJASTHAN | 100 | RUVNL, RUVNL, RUVNL, RUVNL | 10.26 | Adani Solar Energy Jodhpur Three Private Limited (Formerly, SB Energy One Private Limited), Adani Solar Energy Jodhpur Three Private Limited (Formerly, SB Energy One Private Limited), Adani Solar Energy Jodhpur Three Private Limited (Formerly, SB Energy One Private Limited) | Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj | 25766618196 | 16-09-2017, 16-09-2017, 16-09-2017 | 300 | 7.35 | RAJASTHAN, RAJASTHAN, RAJASTHAN | 75 | , , | NA, NA, NA | 16-09-2018, 16-09-2018, 16-09-2018 | NA, NA, NA | Solar, Solar, Solar | 0 | , , | , , | , , | Granted, Granted, Granted | STU : RAJASTHAN , STU : RAJASTHAN , STU : RAJASTHAN | NA, NA, NA | NA, NA, NA | NA, NA, NA | Bhadla Solar Park Po, Bhadla Solar Park Po, Bhadla Solar Park Po | , , | NA, NA, NA | 2018-09-21 | 100 | , , , , ,
[70 empty] | 2018-09-24 | 100
[70 empty] | 2018-09-24 | 100
14 |  | 250 MW Bhadla-IV (Part-1) (P-II B-IV) | -- | SECI/NSM/P-2/B-4/RfS/RJ/112016/Bhadla-IV | 250 | NA | 08-11-2016 | NA | 19-04-2017 | Solar | Without Storage | Without Greenshoe | -- | 20-04-2017 | 09-05-2017 | 250 | 0 | 27 | 3520 | 0 | SBE Cleantech Three Limited | 100 | -- | 16-08-2017 | 100 | 2.63 | Solar | 100 | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-05-2017 | 100 | RAJASTHAN | 25 | RUVNL | 2.7 | Adani Solar Energy Jodhpur Four Private Limited (Formerly, SB Energy Three Private Limited), Adani Solar Energy Jodhpur Four Private Limited (Formerly, SB Energy Three Private Limited) | Prakhar Bhardwaj, Prakhar Bhardwaj | 17177745464 | 16-09-2017, 16-09-2017 | 100 | 5.26 | RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 16-09-2018, 16-09-2018 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : RAJASTHAN , STU : RAJASTHAN | NA, NA | NA, NA | NA, NA | Bhadla Solar Park Po, | , | NA, NA | 2018-09-18 | 30 | , , ,
[70 empty] | 2018-10-04 | 20
[70 empty] | 2018-09-18 | 30
[70 empty] | 2018-10-04 | 20
[21 empty] | Avaada Power Private Limited | 100 | -- | 16-08-2017 | 100 | 2.62 | Solar | 100 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-05-2017, 12-05-2017 | 100 | RAJASTHAN, RAJASTHAN | 50 | RUVNL, RUVNL | 5.38 | Clean Sustainable Energy Private Limited, Clean Sustainable Energy Private Limited | Angshuman, Angshuman | 15670009346 | 16-09-2017, 16-09-2017 | 100 | 5.24 | RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 16-09-2018, 16-09-2018 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : RAJASTHAN , STU : RAJASTHAN | NA, NA | NA, NA | NA, NA | Bhadla Solar Park Po, Bhadla Solar Park Po | , | NA, NA | 2018-09-16 | 30 | , , ,
[70 empty] | 2018-10-06 | 20
[70 empty] | 2018-09-16 | 30
[70 empty] | 2018-10-06 | 20
[21 empty] | Phelan Energy Group Limited | 50 | -- | 16-08-2017 | 50 | 2.62 | Solar | 50 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-05-2017 | 50 | RAJASTHAN | 25 | RUVNL | 2.69 | Bhadla Renewable Power Private Limited (Formerly, Phelan Energy India RJ Private Limited) | Laxmi B narayanan | 88005 5474 | 16-09-2017 | 50 | 2.62 | RAJASTHAN | 25 |  | NA | 16-09-2018 | NA | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA | Bhadla Solar Park Po |  | NA | 2018-11-06 | 30 | ,
[70 empty] | 2018-11-22 | 20
15 |  | 500 MW Bhadla-III (Part-2) (P-II B-IV) | -- | SECI/NSM/P2-B4-T11/RfS/RJ/062017/Bhadla-III | 500 | NA | 21-06-2017 | NA | 05-12-2017 | Solar | Without Storage | Without Greenshoe | -- | 06-12-2017 | 21-12-2017 | 500 | 0 | 16 | 4200 | 0 | Hero Solar Energy Private Limited | 300 | -- | 28-03-2018 | 300 | 2.47 | Solar | 300 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-03-2018, 28-03-2018, 28-03-2018 | 300 | UTTAR PRADESH, UTTAR PRADESH, UTTAR PRADESH | 75 | UPPCL, UPPCL, UPPCL | 7.62 | Clean Solar Power (Bhadla) Private Limited, Clean Solar Power (Bhadla) Private Limited, Clean Solar Power (Bhadla) Private Limited | Ashutosh Vyas, Ashutosh Vyas, Ashutosh Vyas | 29859944376 | 27-04-2018, 27-04-2018, 27-04-2018 | 300 | 7.41 | , , | 75 | , , | NA, NA, NA | 27-04-2019, 27-04-2019, 27-04-2019 | NA, NA, NA | Solar, Solar, Solar | 0 | , , | , , | , , | Granted, Granted, Granted | CTU , CTU , CTU | NA, NA, NA | NA, NA, NA | NA, NA, NA | 765/400/220 kV PGCIL, 765/400/220 kV PGCIL, 765/400/220 kV PGCIL | , , | NA, NA, NA | 2020-01-03 | 70 | , , ,
[70 empty] | 2020-02-15 | 30
[70 empty] | 2020-01-23 | 70
[70 empty] | 2020-02-28 | 30
[70 empty] | 2019-12-10 | 100
[21 empty] | SBE Four Limited | 200 | -- | 28-03-2018 | 200 | 2.48 | Solar | 200 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-03-2018, 28-03-2018 | 200 | UTTAR PRADESH, UTTAR PRADESH | 50 | UPPCL, UPPCL | 5.1 | Adani Solar Energy Jodhpur Five Private Limited (Formerly, SB Energy Four Private Limited), Adani Solar Energy Jodhpur Five Private Limited (Formerly, SB Energy Four Private Limited) | Prakhar Bhardwaj, Prakhar Bhardwaj | 17177745464 | 27-04-2018, 27-04-2018 | 200 | 4.96 | RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 27-04-2019, 27-04-2019 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | CTU , CTU | NA, NA | NA, NA | NA, NA | 765/400/220 kV PGCIL, 765/400/220 kV PGCIL | , | NA, NA | 2019-07-09 | 100 | , , ,
[70 empty] | 2019-05-03 | 100
16 |  | 250 MW Bhadla-IV (Part-2) (P-II B-IV) | -- | SECI/NSM/P2-B4-T12/RfS/RJ/062017/Bhadla-IV | 250 | NA | 21-06-2017 | NA | 05-12-2017 | Solar | Without Storage | Without Greenshoe | -- | 06-12-2017 | 21-12-2017 | 250 | 0 | 14 | 2150 | 0 | Azure Power India Private Limited | 200 | -- | 28-03-2018 | 200 | 2.48 | Solar | 200 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-03-2018, 28-03-2018, 28-03-2018, 28-05-2018 | 200 | UTTAR PRADESH, UTTAR PRADESH, UTTAR PRADESH, UTTAR PRADESH | 100 | UPPCL, UPPCL, UPPCL, UPPCL | 10.2 | Azure Power India Private Limited, Azure Power India Private Limited, Azure Power India Private Limited, Azure Power India Private Limited | Vidya Dutt, Vidya Dutt, Vidya Dutt, Vidya Dutt | 35202934832 | 27-04-2018, 27-04-2018, 27-04-2018, 27-04-2018 | 200 | 9.92 | , , , | 100 | , , , | NA, NA, NA, NA | 27-04-2019, 27-04-2019, 27-04-2019, 27-04-2019 | NA, NA, NA, NA | Solar, Solar, Solar, Solar | 0 | , , , | , , , | , , , | Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU | NA, NA, NA, NA | NA, NA, NA, NA | NA, NA, NA, NA | 765/400/220 kV PGCIL, 765/400/220 kV PGCIL, 765/400/220 kV PGCIL, 765/400/220 kV PGCIL | , , , | NA, NA, NA, NA | 2019-07-27 | 50 | , , , ,
[70 empty] | 2019-04-27 | 50
[70 empty] | 2019-04-27 | 50
[70 empty] | 2019-04-27 | 50
[21 empty] | Renew Solar Power Private Limited | 50 | -- | 28-03-2018 | 50 | 2.49 | Solar | 50 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-03-2018 | 50 | UTTAR PRADESH | 25 | UPPCL | 2.56 | ReNew Solar Power Private Limited | Rohit Singh | 7389909907 | 27-04-2018 | 50 | 2.49 |  | 25 |  | NA | 27-04-2019 | NA | Solar | 0 |  |  |  | Granted | CTU | NA | NA | NA | 765/400/220 kV PGCIL |  | NA | 2019-04-27 | 50 | ,
17 |  | 750 MW Kadapa, AP (Ph-II B-IV) | -- | SECI/NSM/P2-B4-T15/RfS/AP/012018 | 750 | NA | 05-01-2018 | NA | 22-06-2018 | Solar | Without Storage | Without Greenshoe | -- | 29-06-2018 | 06-07-2018 | 750 | 0 | 7 | 1750 | 0 | SB Energy Seven Pvt Ltd. | 250 | -- | 30-08-2018 | 250 | 2.7 | Solar | 250 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-07-2018 | 250 | ANDHRA PRADESH | 25 | AP Discoms | 2.77 | Adani Solar Energy AP Eight Private Limited | Prakhar Bhardwaj | 2147483647 | 29-06-2018 | 250 | 2.7 |  | 25 |  | NA | 29-06-2020 | 28-02-2026 | Solar | 0 |  |  |  | Granted | STU : ANDHRA PRADESH | NA | NA | NA | Jammalamadugu SS |  | NA | 2025-02-19 | 137.4 | ,
[70 empty] | 2025-03-08 | 112.6
[21 empty] | Sprng Soura Kiran Vidyut Pvt Ltd. | 250 | -- | 30-08-2018 | 250 | 2.7 | Solar | 250 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-07-2018 | 250 | ANDHRA PRADESH | 25 | AP Discoms | 2.77 | Sprng Soura Kiran Vidyut Private Limited | Poorva Pitke | 2147483647 | 29-09-2018 | 250 | 2.7 | ANDHRA PRADESH | 25 |  | NA | 29-06-2020 | 28-02-2026 | Solar | 0 |  |  |  | Granted | STU : NA | NA | 30-01-2018 | NA | Jammalamadugu SS | Kadapa | NA | 2025-11-03 | 105.6 | ,
[70 empty] | 2025-11-18 | 131.2
[70 empty] | 2025-11-20 | 13.2
[21 empty] | Ayana Renewable Power Pvt. Ltd. | 250 | -- | 30-08-2018 | 250 | 2.71 | Solar | 250 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-07-2018 | 250 | ANDHRA PRADESH | 25 | AP Discoms | 2.78 | Ayana Kadapa Renewable Power Private Limited | Laxmi B Narayanan | 2147483647 | 29-09-2018 | 250 | 2.71 | ANDHRA PRADESH | 25 |  | NA | 29-06-2020 | 28-02-2026 | Solar | 0 |  |  |  | Granted | STU : NA | NA | NA | NA | Jammalamadugu Ss |  | NA | 2026-02-14 | 158.4 | ,
[70 empty] | 2026-02-27 | 91.6
18 |  | 200 MW Pavagada, KA (P-II B-IV) | -- | SECI/NSM/P2-B4-T14/RfS/KA/012018 | 200 | NA | 05-01-2018 | NA | 10-05-2018 | Solar | Without Storage | Without Greenshoe | -- | 10-05-2018 | 18-05-2018 | 200 | 0 | 2 | 400 | 0 | SBE Five Limited | 200 | -- | 30-11-2018 | 200 | 2.82 | Solar | 200 |  | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 15-11-2018, 15-11-2018, 15-11-2018, 15-11-2018 | 200 | UTTAR PRADESH, UTTAR PRADESH, UTTAR PRADESH, UTTAR PRADESH | 100 | UPPCL, UPPCL, UPPCL, UPPCL | 11.56 | Adani Solar Energy KA Nine Private Limited (Formerly, SBG Cleantech Projectco Five Private Limited), Adani Solar Energy KA Nine Private Limited (Formerly, SBG Cleantech Projectco Five Private Limited), Adani Solar Energy KA Nine Private Limited (Formerly, SBG Cleantech Projectco Five Private Limited), Adani Solar Energy KA Nine Private Limited (Formerly, SBG Cleantech Projectco Five Private Limited) | Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj | 34355490928 | 30-12-2018, 30-12-2018, 30-12-2018, 30-12-2018 | 200 | 11.28 | KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA | 100 | , , , | NA, NA, NA, NA | 30-12-2019, 30-12-2019, 30-12-2019, 30-12-2019 | NA, NA, NA, NA | Solar, Solar, Solar, Solar | 0 | , , , | , , , | , , , | Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU | NA, NA, NA, NA | NA, NA, NA, NA | NA, NA, NA, NA | Pavagada Solar Park, Pavagada Solar Park, Pavagada Solar Park, Pavagada Solar Park | , , , | NA, NA, NA, NA | -- | -- | --
19 |  | Solar (ISTS-I) | -- | SECI/C&P/SPD/RfS/2000MW/012018 | 2000 | NA | 30-01-2018 | NA | 15-06-2018 | Solar | Without Storage | Without Greenshoe | -- | 18-06-2018 | 02-07-2018 | 2000 | 0 | 10 | 3800 | 0 | ACME Solar Holdings Limited | 600 | -- | 27-07-2018 | 600 | 2.44 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 06-09-2018, 29-10-2024 | 600 | DELHI, BIHAR | 50 | TPDDL, BSPHCL | 5.02 | ACME Raisar Solar Energy Private Limited, ACME Phalodi Solar Energy Private Limited | Yogesh Sanklecha, Yogesh Sanklecha | 17488121202 | 25-10-2018, 25-10-2018 | 600 | 4.88 | RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 25-10-2020, 25-10-2020 | 07-01-2025, 23-01-2025 | Solar, Solar | 0 | , | , | , | Granted, Granted | CTU , CTU | 2400003205 | 19-07-2018, 19-07-2018 | 17-09-2019, 17-01-2019 | Fatehgarh-I, Fatehgarh-I | Rajasthan, Rajasthan | 02-04-2022, 02-04-2022 | 2024-12-18 | 272 | , , ,
[70 empty] | 2025-01-07 | 28
[70 empty] | 2024-12-18 | 260.05
[70 empty] | 2025-01-23 | 39.95
[21 empty] | Shapoorji Pallonji Infrastructure Capital Company Private Limited | 250 | -- | 27-07-2018 | 250 | 2.52 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 07-08-2018 | 250 | JHARKHAND | 25 | JBVNL | 2.59 | Arina Solar Pvt Ltd | Sunil Kulkarni | 2267490019 | 25-10-2018 | 250 | 2.52 | TAMIL NADU | 25 |  | NA | 25-10-2020 | 31-01-2021 | Solar | 0 |  |  |  | Granted | CTU | 1200002127 | 25-10-2018 | 25-10-2020 | Tuticorin | Tuticorin | 25-10-2020 | -- | -- | --
[21 empty] | Hero Solar Energy Private Limited | 250 | -- | 27-07-2018 | 250 | 2.53 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 07-08-2018 | 250 | JHARKHAND | 25 | JBVNL | 2.6 | Clean Solar Power (Jodhpur) Private Limited | Sourya Choudhary | 9330930693 | 25-10-2018 | 250 | 2.53 | RAJASTHAN, RAJASTHAN, RAJASTHAN, RAJASTHAN, RAJASTHAN | 25 |  | NA | 25-10-2020 | 06-10-2022 | Solar | 0 |  |  |  | Granted | CTU | 1200001663 | 27-07-2018 | 17-01-2019 | Bhadla | Rajasthan | 06-10-2022 | 2022-03-14 | 115 | , , , , ,
[70 empty] | 2022-04-21 | 135
[21 empty] | Mahindra Susten Private Limited | 250 | -- | 27-07-2018 | 250 | 2.53 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 03-08-2018 | 250 | CHHATTISGARH | 25 | CSPDCL | 2.6 | Megasolis Renewables Private Limited (formerly known as Mahindra Renewables Private Limited) | Rakesh Khaitan | 8452845433 | 25-10-2018 | 250 | 2.53 | RAJASTHAN | 25 |  | NA | 25-10-2020 | 29-10-2021 | Solar | 0 |  |  |  | Granted | CTU | 1200001645 | 23-08-2018 | 17-01-2019 | Bhadla PGCIL | Rajasthan | 29-10-2021 | 2021-05-14 | 100 | ,
[70 empty] | 2021-06-07 | 60
[70 empty] | 2021-07-23 | 50
[70 empty] | 2021-08-17 | 40
[21 empty] | Azure Power India Private Limited | 600 | -- | 27-07-2018 | 600 | 2.53 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 07-08-2018, 27-11-2018, 21-08-2018 | 600 | JHARKHAND, HARYANA, ODISHA | 75 | JBVNL, HPPC, GRIDCO | 7.8 | Azure Power Forty Three Pvt. Ltd., Azure Power Forty Three Pvt Ltd | H S Wadhwa, H S Wadhwa | 229881960 | 25-10-2018, 25-10-2018 | 600 | 5.06 | RAJASTHAN, RAJASTHAN, RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 25-10-2020, 25-10-2020 | 25-09-2021, 31-12-2021 | Solar, Solar | 0 | , | , | , | Granted, Granted | CTU , CTU | 2400003305 | 22-08-2018, 22-08-2018 | 17-01-2019, 17-01-2019 | Bikaner PG, Bikaner | Rajasthan, Rajasthan | 20-11-2021, 25-09-2021 | 2020-12-15 | 150 | , , , , ,
[70 empty] | 2021-01-30 | 100
[70 empty] | 2021-02-08 | 50
[70 empty] | 2021-06-25 | 50
[70 empty] | 2021-08-08 | 50
[70 empty] | 2021-09-22 | 100
[70 empty] | 2021-12-31 | 100
[21 empty] | Mahoba Solar (UP) Private Limited | 50 | -- | 27-07-2018 | 50 | 2.54 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 02-08-2018 | 50 | DELHI | 25 | BYPL | 2.61 | Adani Solar Energy Four Pvt Ltd | Prakhar Bhardwaj Durgesh kumar Gupta | 7925557437 | 25-10-2018 | 50 | 2.54 | RAJASTHAN | 25 |  | NA | 25-10-2020 | 20-11-2021 | Solar | 0 |  |  |  | Granted | CTU | 1200001793 | 29-11-2018 | 04-02-2019 | Bhadla | Rajasthan | 20-11-2021 | 2020-04-17 | 50 | ,
20 |  | Solar (ISTS-II) | -- | SECI/C&P/SPD/RfS/3000MW/022018 | 3000 | NA | 27-02-2018 | NA | 26-06-2018 | Solar | Without Storage | Without Greenshoe | -- | 05-07-2018 | 13-07-2018 | 600 | 2400 | 12 | 5100 | 0 | ACME Solar Holdings Limited | 600 | -- | 10-08-2018 | 600 | 2.44 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 13-06-2019, 28-05-2019, 24-10-2019 | 600 | BIHAR, HARYANA, PUDUCHERRY | 75 | NBPDCL and SBPDCL, HPPC, Puducherry | 7.53 | ACME Deoghar Solar Power Pvt. Ltd., ACME Dhaulpur Powertech Pvt. Ltd. | Yogesh Sanklecha, Yogesh Sanklecha | 17488121202 | 08-11-2018, 08-11-2018 | 600 | 4.88 | RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 08-11-2020, 08-11-2020 | 23-01-2025, 07-01-2025 | Solar, Solar | 0 | , | , | , | Granted, Granted | CTU , CTU | 2400003285 | 11-08-2018, 11-08-2018 | 17-01-2019, 18-08-2021 | Fatehgarh-I, Fatehgarh-I | Rajasthan, Rajasthan | 02-04-2022, 11-05-2022 | 2024-12-18 | 253 | , , ,
[70 empty] | 2025-01-23 | 47
[70 empty] | 2024-12-18 | 238
[70 empty] | 2025-01-07 | 62
21 |  | Solar RJ (Tranche-I) | -- | SECI/C&P/SPD/RfS/RJ/082018 | 750 | NA | 03-08-2018 | NA | 19-02-2019 | Solar | Without Storage | Without Greenshoe | -- | 19-02-2019 | 01-03-2019 | 750 | 0 | 13 | 2370 | 0 | Fortum Solar Plus Private Limited | 250 | -- | 02-03-2019 | 250 | 2.48 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-06-2019 | 250 | RAJASTHAN | 25 | RUVITL | 2.55 | Sprng Solar Plus PL | Poorva Pitke | 9545659577 | 02-06-2019 | 250 | 2.48 | RAJASTHAN | 25 |  | NA | 02-12-2020 | 04-05-2021 | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA | Jaisalmer-II | Jaisalmer | NA | 2021-03-19 | 150 | ,
[70 empty] | 2021-05-01 | 100
[21 empty] | Palimarwar Solar House Private Limited | 40 | -- | 02-03-2019 | 40 | 2.48 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-06-2019 | 40 | RAJASTHAN | 25 | RUVITL | 2.55 | Palimarwar Solar Hou, Palimarwar Solar Hou | Rohan Jhawar, Rohan Jhawar | 19979562902 | 02-06-2019, 02-06-2019 | 40 | 4.96 | RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 02-12-2020, 02-12-2020 | 04-05-2021, 04-05-2021 | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : RAJASTHAN , STU : RAJASTHAN | NA, NA | NA, NA | NA, NA | Sheo GSS, Sheo GSS | Sheo, Sheo | NA, NA | 2021-04-19 | 20 | , , ,
[70 empty] | 2021-04-19 | 20
[21 empty] | ACME Solar Holdings Limited | 250 | -- | 02-03-2019 | 250 | 2.48 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-06-2019 | 250 | RAJASTHAN | 25 | RUVITL | 2.55 | ACME Aklera Power Te | Yogesh Kumar Sanklecha | 8744060601 | 02-06-2019 | 250 | 2.48 | RAJASTHAN | 25 |  | NA | 02-12-2020 | 06-01-2024 | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA | Jaisalmer-II | Jaisalmer | NA | 2023-07-20 | 200 | ,
[70 empty] | 2024-01-06 | 50
[21 empty] | Sitara Solar Energy Private Limited | 100 | -- | 02-03-2019 | 100 | 2.48 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-06-2019 | 100 | RAJASTHAN | 25 | RUVITL | 2.55 | Sitara Solar Energy | Fahim Alam | 7982419161 | 02-06-2019 | 100 | 2.48 | RAJASTHAN | 25 |  | NA | 02-12-2020 | 20-05-2021 | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA | Kanasar Ss | Kanasar | NA | 2021-05-20 | 100 | ,
[21 empty] | ReNew Solar Power Private Limited | 110 | -- | 02-03-2019 | 110 | 2.49 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 27-06-2019 | 110 | RAJASTHAN | 25 | RUVITL | 2.56 | ReNew Sol Jharkhand Five |  |  | 02-06-2019 | 110 | 2.49 | RAJASTHAN | 25 |  | NA | 02-12-2020 | 04-05-2021 | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA | Jaisalmer-II | Jaisalmer | NA | 2021-02-04 | 50 | ,
[70 empty] | 2021-03-11 | 60
23 |  | Solar (ISTS-III) | -- | SECI/C&P/SPD/ISTS-III/RfS/1200MW/012019 | 1200 | NA | 10-01-2019 | NA | 15-02-2019 | Solar | Without Storage | Without Greenshoe | -- | 18-02-2019 | 25-02-2019 | 1200 | 0 | 4 | 1500 | 150 | ReNew Solar Energy (Jharkhand Four) Private Limited | 300 | -- | 05-03-2019 | 300 | 2.55 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 13-06-2019 | 300 | BIHAR | 25 | NBPDCL and SBPDCL | 2.62 | Solzen Urja Private Limited (Previously known asReNew Sun Waves Pvt. Ltd.) | Neeraj Gupta | 7389909907 | 20-06-2019 | 300 | 2.55 | RAJASTHAN, RAJASTHAN, RAJASTHAN | 25 |  | NA | 20-12-2020 | 14-11-2021 | Solar | 0 |  |  |  | Granted | CTU | 1200001967 | 11-03-2019 | 18-12-2019 | Fatehgarh II | Rajasthan | 14-11-2021 | 2021-08-13 | 150 | , , ,
[70 empty] | 2021-08-17 | 50
[70 empty] | 2021-09-04 | 50
[70 empty] | 2021-10-04 | 50
[21 empty] | Azure Power India Private Limited | 300 | -- | 05-03-2019 | 300 | 2.58 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 22-08-2019, 17-06-2019 | 300 | ODISHA, DELHI | 50 | GRIDCO, BRPL | 5.3 | Azure Power Forty One Pvt. Ltd. | Gaurang Sethi | 114940980 | 29-08-2019 | 300 | 2.58 | RAJASTHAN, RAJASTHAN, RAJASTHAN, RAJASTHAN | 25 |  | NA | 01-03-2021 | 07-03-2022 | Solar | 0 |  |  |  | Granted | CTU | 1200001601 | 30-07-2018 | 10-08-2021 | Bikaner-1 | Rajasthan | 20-11-2021 | 2021-10-12 | 50 | , , , ,
[70 empty] | 2021-10-30 | 50
[70 empty] | 2021-11-30 | 50
[70 empty] | 2021-12-24 | 50
[70 empty] | 2022-01-31 | 50
[70 empty] | 2022-03-07 | 50
[21 empty] | Eden Renewable Cite Private Limited | 300 | -- | 05-03-2019 | 300 | 2.6 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 17-06-2019, 17-06-2019 | 300 | DELHI, DELHI | 50 | BRPL, BYPL | 5.34 | Eden Renewable Cite Private Limited | Vivek Kodesia | 9717031091 | 24-06-2019 | 300 | 2.6 | RAJASTHAN | 25 |  | NA | 24-12-2020 | 14-11-2021 | Solar | 0 |  |  |  | Granted | CTU | 1200002009 | 29-05-2019 | 02-08-2019 | Fatehgarh II | Rajasthan | 15-10-2022 | 2021-08-13 | 300 | ,
[21 empty] | SBSR Power Cleantech Eleven Private Limited | 300 | -- | 05-03-2019 | 300 | 2.61 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 17-06-2019, 16-06-2019 | 300 | DELHI, DELHI | 50 | BYPL, TPDDL | 5.36 | Adani Solar Energy Jaisalmer Two Pvt Ltd (earlier known as SBSR Power Cleantech Eleven Pvt. Ltd. ) | Prakhar Bhardwaj | 9873018527 | 03-07-2019 | 300 | 2.61 | RAJASTHAN | 25 |  | NA | 03-01-2021 | 20-11-2021 | Solar | 0 |  |  |  | Granted | CTU | 1200000271 | 14-08-2019 | 29-10-2019 | Bikaner I | Rajasthan | 01-06-2021 | 2021-08-15 | 50 | , PPA capacity reduced from 300 MW to 150 MW.
[70 empty] | 2022-04-04 | 50
[70 empty] | 2022-04-11 | 50
24 |  | Solar (ISTS-IV) | -- | SECI/C&P/SPD/ISTS-IV/RfS/1200MW/032019 | 1200 | NA | 13-03-2019 | NA | 30-05-2019 | Solar | Without Storage | Without Greenshoe | -- | 04-06-2019 | 12-06-2019 | 1150 | 50 | 7 | 2100 | 0 | Ayana Renewable Power Private Limited | 300 | -- | 25-07-2019 | 300 | 2.54 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 16-10-2019 | 300 | MADHYA PRADESH | 25 | MPPMCL | 2.61 | Ayana Renewable Power One Pvt. Ltd. | Lakshmi Narayanan Balasubramanian | 8800554749 | 23-10-2019 | 300 | 2.54 | RAJASTHAN | 25 |  | NA | 23-04-2021 | 23-12-2021 | Solar | 0 |  |  |  | Granted | CTU | 1200002274 | 30-09-2019 | 15-11-2019 | Bikaner | Rajasthan | 23-12-2021 | 2021-11-25 | 100 | ,
[70 empty] | 2021-12-07 | 50
[70 empty] | 2021-12-22 | 150
[21 empty] | ReNew Solar Power Private Limited | 300 | -- | 25-07-2019 | 300 | 2.54 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 16-10-2019 | 300 | MADHYA PRADESH | 25 | MPPMCL | 2.61 | Renew Solar Energy (Jharkhand Three) Pvt. Ltd. | Parul Agrawal | 1244896670 | 23-10-2019 | 300 | 2.54 | RAJASTHAN | 25 |  | NA | 23-04-2021 | 11-05-2022 | Solar | 0 |  |  |  | Granted | CTU | 1200002274 | 30-09-2019 | 20-12-2021 | Fatehgarh II | Rajasthan | 23-12-2021 | 2021-09-02 | 150 | ,
[70 empty] | 2021-09-27 | 50
[70 empty] | 2021-10-04 | 50
[70 empty] | 2021-12-09 | 50
[21 empty] | Azure Power Maple Private Limited | 300 | -- | 25-07-2019 | 300 | 2.54 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 16-10-2019 | 300 | MADHYA PRADESH | 25 | MPPMCL | 2.61 | Azure Power Maple Pvt. Ltd | Gaurang Sethi | 1149409800 | 23-10-2019 | 300 | 2.54 | RAJASTHAN, RAJASTHAN | 25 |  | NA | 23-04-2021 | 31-03-2023 | Solar | 0 |  |  |  | Granted | CTU | 1200001651 | 22-08-2018 | 17-01-2019 | Bhadla I | Rajasthan | 06-10-2022 | 2022-02-14 | 53 | , ,
[70 empty] | 2022-03-30 | 204
[70 empty] | 2023-03-31 | 43
[21 empty] | Mahindra Susten Private Limited | 250 | -- | 25-07-2019 | 250 | 2.54 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 19-03-2020 | 250 | HARYANA | 25 | HPPC | 2.61 | Mega SuryaUrja Pvt. Ltd. | Rakesh Khaitan | 7838568948 | 25-03-2020 | 250 | 2.54 | RAJASTHAN | 25 |  | NA | 25-09-2021 | 29-06-2022 | Solar | 0 |  |  |  | Granted | CTU | 1200002239 | 07-08-2019 | 27-06-2022 | Bhadla II | Rajasthan | 29-06-2022 | 2022-05-20 | 175 | ,
[70 empty] | 2022-06-17 | 75
25 |  | CPSU Scheme (Tranche-I) | -- | SECI/C&P/SPD/CPSU-I/RfS/2000MW/032019 | 2000 | NA | 15-03-2019 | 10-04-2019 | 24-07-2019 | Solar | Without Storage | Without Greenshoe | -- | 01-08-2019 | 20-08-2019 | 922 | 1078 | 6 | 1153 | 55 | NHDC Limited | 25 | -- | 28-09-2019 | 25 | 3.5 | Solar | 25 | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [6 empty] | NHDC Limited | XYZ | 1234567890 | 28-09-2019 | 25 | 3.5 |  | 0 |  | NA | 28-09-2021 | NA | Solar | 0 |  |  |  | Yet to Apply |  |  | NA | NA |  |  | NA | -- | -- | --
[21 empty] | The Singareni Collieries Company Limted | 90 | -- | 28-09-2019 | 90 | 3.5 | Solar | 90 | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [6 empty] | SCCL, SCCL, SCCL, SCCL | Appa Rao, Appa Rao, Appa Rao, Appa Rao | 33331898492 | 28-09-2019, 28-09-2019, 28-09-2019, 28-09-2019 | 90 | 14 | TELANGANA, TELANGANA, TELANGANA, TELANGANA | 0 | , , , | NA, NA, NA, NA | 28-09-2021, 28-09-2021, 28-09-2021, 28-09-2021 | 28-08-2022, 28-08-2022, 28-08-2022, 28-08-2022 | Solar, Solar, Solar, Solar | 0 | , , , | , , , | , , , | Captive, Captive, Captive, Captive | , , , | 0 | NA, NA, NA, NA | NA, NA, NA, NA | , , , | , , , | NA, NA, NA, NA | -- | -- | --
[21 empty] | Assam Power Distribution Company Limited | 30 | -- | 28-09-2019 | 30 | 3.5 | Solar | 30 | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [6 empty] | APDCL, APDCL | Baishali, Baishali | 17277797008 | 28-09-2021, 28-09-2021 | 30 | 7 | , | 0 | , | NA, NA | 28-09-2021, 28-09-2021 | 30-09-2024, 30-09-2024 | Solar, Solar | 0 | , | , | , | Yet to Apply, Yet to Apply | , | , | NA, NA | NA, NA | , | , | NA, NA | -- | -- | --
[21 empty] | Delhi Metro Rail Corporation Limited | 3 | -- | 28-09-2019 | 3 | 3.5 | Solar | 3 | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [6 empty] | DMRC | Surendra Singh | 7705004563 | 28-09-2019 | 3 | 3.5 | DELHI | 0 |  | NA | 28-09-2021 | 28-08-2022 | Solar | 0 |  |  |  | Captive |  | 0 | NA | NA |  |  | NA | 2021-11-06 | 3 | Rooftop ,
[21 empty] | Nalanda University | 5 | -- | 28-09-2019 | 5 | 3.5 | Solar | 5 | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [6 empty] | Nalanda University | Manoj Kumar | 7033698507 | 28-09-2019 | 5 | 3.5 | BIHAR | 0 |  | NA | 28-09-2021 | 30-09-2023 | Solar | 0 |  |  |  | Captive |  | 0 | NA | NA |  |  | NA | 2023-06-19 | 5 | ,
[21 empty] | NTPC Limited | 769 | -- | 28-09-2019 | 769 | 3.5 | Solar | 769 | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | [6 empty] | NTPC Limited, NTPC Limited, NTPC Limited, NTPC Limited | Anupam Gupta, Anupam Gupta, Anupam Gupta, Anupam Gupta | 31998585928 | 28-09-2019, 28-09-2019, 28-09-2019, 28-09-2019 | 769 | 14 | RAJASTHAN, RAJASTHAN, RAJASTHAN, TAMIL NADU | 0 | , , , | NA, NA, NA, NA | 28-09-2021, 28-09-2021, 28-09-2021, 28-09-2021 | 13-12-2022, 06-08-2022, 30-12-2022, 15-12-2022 | Solar, Solar, Solar, Solar | 0 | , , , | , , , | , , , | Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU | 0 | NA, NA, NA, NA | NA, NA, NA, NA | , , , | , , , | NA, NA, NA, NA | 2022-12-13 | 150 | , , , , , , ,
[70 empty] | 2022-08-06 | 250
[70 empty] | 2022-12-30 | 139
[70 empty] | 2022-12-15 | 230
26 |  | Solar RJ (Tranche-II) | -- | SECI/C&P/SPD/RfS/RJ-II/032019 | 750 | NA | 22-03-2019 | NA | 04-06-2019 | Solar | Without Storage | Without Greenshoe | -- | 04-06-2019 | 19-06-2019 | 680 | 70 | 5 | 850 | 70 | NTPC Limited | 160 | -- | 16-09-2019 | 160 | 2.5 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-09-2019 | 160 | RAJASTHAN | 25 | RUVITL | 2.57 | NTPC GEL | Ajay Kumar Shukla | 9650991589 | 16-10-2019 | 160 | 2.5 | RAJASTHAN | 25 |  | NA | 16-04-2021 | 25-03-2022 | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA | Raisingh&Vijay Nagar | Jetsar | NA | 2021-10-22 | 80 | ,
[70 empty] | 2022-03-25 | 80
[21 empty] | Mahindra Susten Private Limited | 200 | -- | 16-09-2019 | 200 | 2.5 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-09-2019 | 200 | RAJASTHAN | 25 | RUVITL | 2.57 | Emergent Solren PL | Pankaj Vaidya | 8451041564 | 16-10-2019 | 200 | 2.5 | RAJASTHAN | 25 |  | NA | 16-04-2021 | 01-12-2021 | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA | Gajner SS 220 kV | Gajner | NA | 2021-10-14 | 200 | ,
[21 empty] | Hero Solar Energy Private Limited | 250 | -- | 16-09-2019 | 250 | 2.5 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-09-2019 | 250 | RAJASTHAN | 25 | RUVITL | 2.57 | Clean Solar (O2) | Rohit Joshi | 9717012055 | 16-10-2019 | 250 | 2.5 | RAJASTHAN | 25 |  | NA | 16-04-2021 | 05-05-2022 | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA | Jaisalmer-II | Jaisalmer | NA | 2022-04-05 | 150 | ,
[70 empty] | 2022-05-05 | 100
[21 empty] | Azure Power Maple Private Limited | 70 | -- | 16-09-2019 | 70 | 2.5 | Solar | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
27 |  | Solar Manufacture (Ph-II) | -- | SECI/C&P/RfS/2GW MANUFACTURING/P-3/R1/062019 | 7000 | NA | 25-06-2019 | NA | 13-11-2019 | Solar | Without Storage | Without Greenshoe | -- | 14-11-2019 | 22-11-2019 | 12000 | 0 | 3 | 8000 | 0 | ADANI GREEN ENERGY FOUR LIMITED | 10333 | -- | 10-12-2019 | 500 | 2.54 | Solar | 500 |  |  | Granted | -- | -- | NA | NA | -- | -- | NA | 16-09-2021 | 500 | TAMIL NADU | 25 | TANGEDCO | 2.61 | Adani Green Energy Twenty Five B Limited A1P3, Adani Green Energy Twenty Five B Limited A1P4 | Rakesh Kr Jha, Rakesh Kumar Jha | 19423179138 | 13-10-2021, 13-10-2021 | 500 | 5.08 | RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 13-10-2023, 13-10-2023 | 25-12-2025, 25-12-2025 | Solar, Solar | 362.5 | , | , | , | Granted, Granted | CTU , CTU | 2400004864 | 08-01-2020, 08-01-2020 | 29-04-2020, 29-04-2020 | Ramgarh PS, Ramgarh PS | Rajasthan, Rajasthan | 30-06-2026, 30-06-2026 | 2026-03-28 | 137.5 | , , ,
[24 empty] | 08-06-2020 | 500 | 2.54 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 16-09-2021, 22-07-2021 | 500 | TAMIL NADU, GUJARAT | 50 | TANGEDCO, Odisha | 5.22 | Adani Green Energy Twenty Six A Limited A1P2, Adani Green Energy Twenty Six A Limited A1P5 | Rakesh Kumar Jha, Rakesh Kumar Jha | 19423179138 | 31-10-2021, 17-11-2021 | 500 | 5.08 | GUJARAT, GUJARAT | 50 | Yes, Yes | 2022-08-17, 2022-08-17 | 13-10-2023, 17-11-2023 | 12-01-2026, 12-01-2026 | Solar, Solar | 0 | , | , | , | Granted, Granted | CTU , CTU | 2400005356 | 22-01-2020, 22-01-2020 | 30-04-2020, 30-04-2020 | KPS-1, KPS-1 | Gujarat, Gujarat | 25-02-2024, 25-02-2024 | 2026-02-23 | 50 | , , as per latest JCC minutes , as per latest JCC minutes
[70 empty] | 2026-03-06 | 50
[70 empty] | 2026-03-11 | 50
[70 empty] | 2026-03-27 | 50
[70 empty] | 2026-03-28 | 58
[70 empty] | 2026-04-20 | 67
[70 empty] | 2026-04-15 | 50
[70 empty] | 2026-04-20 | 125
[24 empty] | 10-12-2019 | 1500 | 2.42 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-12-2021 | 1500 | ANDHRA PRADESH | 25 | APCDPCL | 2.49 | Adani Green Energy Twenty Four Limited A2P1, Adani Green Energy Twenty Four Limited A2P2, Adani Green Energy Twenty Five Limited A2P3, Adani Green Energy Twenty Five Limited A2P4, Adani Green Energy Twenty Four A Limited A2P5, Adani Green Energy Twenty Four A Limited A2P6 | Rakesh Kumar Jha, Rakesh Kumar Jha, Rakesh Kumar Jha, Rakesh Kumar Jha, Rakesh Kumar Jha, Rakesh Kumar Jha | 58269537414 | 01-12-2021, 01-12-2021, 01-12-2021, 01-12-2021, 01-12-2021, 01-12-2021 | 1500 | 14.52 | RAJASTHAN, RAJASTHAN, RAJASTHAN, RAJASTHAN, GUJARAT, GUJARAT | 150 | , , , , , | , , , , , | 01-10-2024, 01-10-2024, 01-10-2024, 01-10-2024, 01-10-2024, 01-10-2024 | 18-01-2026, 18-01-2026, 18-01-2026, 18-01-2026, 26-12-2026, 26-12-2026 | Solar, Solar, Solar, Solar, Solar, Solar | 0 | , , , , , | , , , , , | , , , , , | Granted, Granted, Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU , CTU , CTU | 7200015074 | 08-01-2020, 08-01-2020, 08-01-2020, 08-01-2020, 16-07-2020, 16-07-2020 | 22-06-2020, 22-06-2020, 29-04-2020, 29-04-2020, 24-12-2020, 24-12-2020 | Fatehgarh-II, Fatehgarh-II, Bhadla-II, Bhadla-II, KPS-1, KPS-1 | Rajasthan, Rajasthan, Rajasthan, Rajasthan, Gujarat, Gujarat | 18-01-2026, 18-01-2026, 18-01-2026, 18-01-2026, 26-12-2025, 26-12-2025 | 2025-01-02 | 59.46 | , , , , , , , , , , ,
[70 empty] | 2025-02-19 | 95.54
[70 empty] | 2025-03-19 | 95
[70 empty] | 2025-01-02 | 178.54
[70 empty] | 2025-02-19 | 71.46
[70 empty] | 2024-12-11 | 250
[70 empty] | 2025-03-03 | 107
[70 empty] | 2025-03-12 | 72
[70 empty] | 2025-03-21 | 71
[70 empty] | 2024-12-11 | 250
[70 empty] | 2024-12-11 | 250
[24 empty] | 08-06-2020 | 1000 | 2.54 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 12-08-2021, 10-02-2022, 20-07-2022, 09-12-2022 | 534 | CHHATTISGARH, JAMMU AND KASHMIR, TRIPURA, MAHARASHTRA | 100 | CSPDCL, JKPCL, TSECL, BEST Undertaking | 10.44 | Adani Green Energy Twenty Six A Limited A1P1, Adani Green Energy Twenty Six A Limited A1P6, Adani Green Energy Twenty Six A Limited A1 P7, Adani Green Energy Twenty Six A Limited A1P8 | Rakesh k Jha, Rakesh k Jha, Rakesh K Jha, Rakesh Kumar Jha | 38846358276 | 01-10-2021, 10-02-2022, 20-07-2022, 09-12-2022 | 534 | 10.16 | GUJARAT, GUJARAT, GUJARAT, | 100 | , , , | , , , | 01-10-2023, 10-02-2024, 20-07-2024, 09-12-2024 | 12-01-2026, 12-01-2026, 13-02-2026, 25-02-2027 | Solar, Solar, Solar, Solar | 234 | , , , | , , , | , , , | Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU | 2861405376 | 27-03-2021, 27-03-2021, 11-11-2022, 11-11-2022 | 30-05-2021, 05-03-2021, 12-01-2023, 12-01-2023 | KPS-1, KPS-1, KPS -1, KPS-1 | Gujarat, Gujarat, Gujarat, Gujarat | 25-02-2024, 25-02-2024, 08-03-2026, 31-12-2026 | 2025-10-10 | 50 | , , , , , ,
[70 empty] | 2026-01-21 | 50
[70 empty] | 2026-01-23 | 50
[70 empty] | 2026-02-10 | 50
[70 empty] | 2026-03-17 | 50
[70 empty] | 2026-04-20 | 50
[24 empty] | 08-06-2020 | 3000 | 2.42 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-12-2021 | 3000 | ANDHRA PRADESH | 25 | APCPDCL | 2.49 | Adani Green Energy Twenty Four B Limited A2P7, Adani Green Energy Twenty Four B Limited A2P8, Adani Renewable Energy Fifty Six Limited A3P1, Adani Renewable Energy Fifty Six Limited A3P2, Adani Green Energy Twenty Five A Limited A3P3, Adani Green Energy Twenty Five A Limited A3P4, Adani Green Energy Twenty Five B Limited A3P5, Adani Green Energy Twenty Five B Limited A3P6, Adani Green Energy Twenty Five C Limited A3P7, Adani Green Energy Twenty Five C Limited A3P8, Adani Green Energy Twenty Six B Limited A3P9, Adani Green Energy Twenty Seven A Limited A4P1 | Rakesh K Jha, Rakesh K Jha, Rakesh K Jha, Rakesh K Jha, Rakesh K Jha, Rakesh K Jha, Rakesh k Jha, Rakesh K Jha, Prakhar Bhardwaj, Prakhar Bhardwaj, Rakesh K Jha, Rakesh K Jha | 116861932744 | 01-12-2021, 01-12-2021, 01-12-2021, 01-12-2021, 01-12-2021, 01-12-2021, 01-12-2021, 01-12-2021, 01-12-2021, 01-12-2021, 13-03-2024, 01-12-2021 | 3000 | 29.04 | GUJARAT, GUJARAT, GUJARAT, GUJARAT, GUJARAT, GUJARAT, , , GUJARAT, GUJARAT, , | 300 | , , , , , , , , Yes, Yes, , | , , , , , , , , 2024-10-26, 2024-10-26, , | 01-10-2024, 01-10-2024, 01-10-2025, 01-10-2025, 01-10-2025, 01-10-2025, 01-10-2025, 01-10-2025, 01-10-2025, 01-10-2025, 01-10-2025, 01-10-2026 | 26-12-2026, 26-12-2026, 31-12-2026, 31-12-2026, 31-12-2026, 31-12-2026, 31-12-2026, 31-12-2026, 29-11-2025, 29-11-2025, NA, 29-11-2026 | Solar, Solar, Solar, Solar, Solar, Solar, Solar, Solar, Solar, Solar, Solar, Solar | 500 | , , , , , , , , , , , | , , , , , , , , , , , | , , , , , , , , , , , | Granted, Granted, Granted, Granted, Granted, Granted, Granted, Granted, Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU , CTU , CTU , CTU , CTU , CTU , CTU , CTU , CTU | 11522819451 | 28-03-2024, 16-07-2020, 16-07-2020, 12-01-2023, 12-01-2023, 16-07-2020, 16-07-2020, 16-07-2020, 16-07-2020, 11-11-2022, 11-11-2022, 22-01-2020 | 27-08-2024, 24-12-2020, 24-12-2020, 03-04-2023, 03-04-2023, 24-12-2020, 24-12-2020, 24-12-2020, 24-12-2020, 12-01-2023, 12-01-2023, 30-04-2020 | Ramgarh PS, KPS-1, KPS-1, KPS-3, KPS-3, KPS-1, KPS-1, KPS-1, KPS-1, KPS-III, KPS-III, KPS-I | Rajasthan, Gujarat, Gujarat, Gujarat, Gujarat, Gujarat, Gujarat, Gujarat, Gujarat, Gujarat, Gujarat, Gujarat | 31-12-2028, 26-12-2025, 26-12-2025, 26-12-2025, 26-12-2025, 31-12-2026, 31-12-2026, 31-12-2026, 31-12-2026, 08-03-2026, 08-03-2026, 25-02-2024 | 2025-04-23 | 100 | , , , , , , , , In principle connectivity granted. , , , , , , , , , Connectivity under GNA is operationalized. , Connectivity under GNA is operationalized. ,
[70 empty] | 2025-06-09 | 62.5
[70 empty] | 2025-06-25 | 75
[70 empty] | 2025-09-01 | 12.5
[70 empty] | 2025-08-06 | 87.5
[70 empty] | 2025-09-30 | 87.5
[70 empty] | 2025-01-08 | 137.5
[70 empty] | 2025-02-25 | 112.5
[70 empty] | 2024-12-11 | 237.87
[70 empty] | 2025-01-08 | 12.13
[70 empty] | 2024-12-11 | 250
[70 empty] | 2024-12-12 | 249.975
[70 empty] | 2025-03-07 | 0.025
[70 empty] | 2024-12-11 | 250
[70 empty] | 2024-12-11 | 250
[70 empty] | 2025-12-02 | 75
[70 empty] | 2025-11-27 | 75
[70 empty] | 2026-02-06 | 50
[70 empty] | 2026-02-23 | 75
[70 empty] | 2026-03-23 | 100
[70 empty] | 2026-05-07 | 50
[70 empty] | 2026-03-30 | 50
[70 empty] | 2026-05-07 | 100
[24 empty] | 23-02-2024 | 2333 | 2.42 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-12-2021 | 1000 | ANDHRA PRADESH | 25 | APCPDCL | 2.49 | Adani Green Energy Twenty Seven A Limited A4P2, Adani Green Energy Twenty Six B Limited A4P3, Adani Renewable Energy Fifty Five Limited A4P4, Adani Green Energy Twenty Five B Limited A4P5A, Adani Renewable Energy Fifty Seven Limited A4P7 | Rakesh Kumar Jha, Rakesh K Jha, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj | 49042234719 | 01-12-2021, 01-12-2021, 26-12-2023, 26-12-2023, 26-12-2023 | 1000 | 12.1 | , GUJARAT, , , GUJARAT | 125 | , , , , | , , , , | 01-10-2026, 01-10-2026, 01-10-2026, 01-10-2026, 01-10-2026 | 29-11-2026, 05-11-2026, 15-09-2029, NA, 19-05-2029 | Solar, Solar, Solar, Solar, Solar | 500 | , , , , | , , , , | , , , , | Granted, Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU , CTU | 8000008988 | 10-01-2024, 16-07-2020, 10-01-2024, 16-07-2020, 16-07-2020 | 25-09-2024, 31-10-2023, 25-09-2024, 24-12-2020, 24-12-2020 | KPS I, KPS I, KPS III, KPS-1, KPS-I | Gujarat, Gujarat, Gujarat, Gujarat, Gujarat | 31-08-2029, 31-12-2026, 31-08-2029, 01-10-2026, 01-10-2026 | 2024-12-11 | 87.72 | , , , , , ,
[70 empty] | 2025-02-21 | 67
[70 empty] | 2025-02-25 | 12.28
[70 empty] | 2025-02-27 | 83
[70 empty] | 2025-02-17 | 100
[70 empty] | 2025-03-27 | 112.5
[70 empty] | 2025-03-28 | 37.5
[24 empty] | 08-06-2020 | 1500 | 2.42 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 01-12-2021 | 1500 | ANDHRA PRADESH | 25 | APCPDCL | 2.49 | Adani Renewable Energy Fifty Five Limited A4P5, Adani Renewable Energy Fifty Five Limited A4P6, Adani Renewable Energy Fifty Seven Limited A4P8, Adani Renewable Energy Fifty Seven Limited A4P9, Adani Renewable Energy Fifty Seven Limited A4P10, Adani Renewable Energy Fifty Seven Limited A4P11, Adani Renewable Energy Fifty Seven Limited A4P12, Adani Renewable Energy Fifty Seven Limited A4P13, Adani Renewable Energy Fifty Five Limited A4P14, Adani Green Energy Twenty Six B Limited A4P15, Adani Green Energy Twenty Six B Limited A4P16 | Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj, Prakhar Bhardwaj | 108605220372 | 26-12-2023, 26-12-2023, 26-12-2023, 26-12-2023, 26-12-2023, 26-12-2023, 26-12-2023, 26-12-2023, 26-12-2023, 13-03-2024, 13-03-2024 | 1500 | 26.62 | , , GUJARAT, GUJARAT, GUJARAT, GUJARAT, GUJARAT, GUJARAT, , , | 275 | , , , , , , , , , , | , , , , , , , , , , | 01-10-2026, 01-10-2026, 01-10-2026, 01-10-2026, 01-10-2026, 01-10-2026, 01-10-2026, 01-10-2026, 01-10-2026, 01-10-2026, 01-10-2026 | 15-09-2029, 15-09-2029, 19-05-2029, 19-05-2029, 19-05-2029, 15-09-2029, 19-05-2029, 15-09-2029, 15-09-2029, 15-09-2029, 15-09-2029 | Solar, Solar, Solar, Solar, Solar, Solar, Solar, Solar, Solar, Solar, Solar | 900 | , , , , , , , , , , | , , , , , , , , , , | , , , , , , , , , , | Granted, Granted, Granted, Granted, Granted, Granted, Granted, Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU , CTU , CTU , CTU , CTU , CTU , CTU , CTU | 12320005614 | 10-01-2024, 10-01-2024, 10-01-2024, 10-01-2024, 10-01-2024, 10-01-2024, 10-01-2024, 10-01-2024, 10-01-2024, 28-03-2024, 28-03-2024 | 25-09-2024, 25-09-2024, 25-09-2024, 25-09-2024, 25-09-2024, 25-09-2024, 25-09-2024, 25-09-2024, 25-09-2024, 27-08-2024, 27-08-2024 | KPS I, KPS I, KPS III, KPS III, KPS III, KPS III, KPS III, KPS III, KPS I, Ramgarh PS, Ramgarh PS | Gujarat, Gujarat, Gujarat, Gujarat, Gujarat, Gujarat, Gujarat, Gujarat, Gujarat, Rajasthan, Rajasthan | 31-08-2029, 31-08-2029, 19-05-2029, 19-05-2029, 19-05-2029, 19-05-2029, 19-05-2029, 19-05-2029, 31-08-2029, 31-03-2030, 31-03-2030 | 2025-04-25 | 87.5 | , , , , , , , , , , , , , , , In principle connectivity granted. , In principle connectivity granted.
[70 empty] | 2025-05-16 | 62.5
[70 empty] | 2025-03-29 | 50
[70 empty] | 2025-05-16 | 50
[70 empty] | 2025-05-01 | 50
[70 empty] | 2025-06-20 | 75
[70 empty] | 2025-06-26 | 50
[70 empty] | 2025-06-30 | 50
[70 empty] | 2025-11-26 | 100
[70 empty] | 2025-11-26 | 25
[21 empty] | Azure Power India Pvt. Ltd. | 1667 | -- | 10-12-2019 | 1000 | 2.54 | Solar | 1000 |  |  | Granted | -- | -- | NA | NA | -- | -- | NA | 12-08-2021, 16-09-2021, 22-07-2021, 10-01-2022, 20-07-2022, 17-10-2025 | 750 | CHHATTISGARH, TAMIL NADU, ODISHA, JAMMU AND KASHMIR, TRIPURA, JHARKHAND | 150 | CSPDCL, TANGEDCO, GRIDCO, JKPCL, TSECL, TATA Steel Limited | 15.66 | Azure Power Fifty one Pvt. Ltd., Azure Power Fifty Two Pvt. Ltd., Azure Power Fifty Two Pvt. Ltd., Azure Power Fifty One Private Limited, Azure Power Fifty One Private Limited, Azure Solar Private Limited | Nikhil Mathews, Nikhil Mathews, Nikhil Mathews, Nikhil Mathews, Nikhil Mathews, Kritika Balaria | 9102329566 | 11-11-2021, 11-11-2021, 17-11-2021, 10-02-2022, 20-07-2022, 04-11-2025 | 750 | 15.24 | , , , , , | 150 | , , , , , | NA, NA, NA, NA, NA, NA | 11-11-2023, 11-11-2023, 17-11-2023, 10-02-2024, 20-07-2024, 04-11-2027 | NA, NA, NA, NA, NA, NA | Solar, Solar, Solar, Solar, Solar | 0 | , , , , | , , , , | , , , , | Granted, Granted, Granted, Granted, Granted | CTU , CTU , CTU , CTU , CTU | NA, NA, NA, NA, NA | NA, NA, NA, NA, NA | NA, NA, NA, NA, NA | , , , , | , , , , | NA, NA, NA, NA, NA | -- | -- | --
[24 empty] | NA | -- | -- | -- | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[24 empty] | 23-07-2020 | 667 | 2.42 | Solar | 667 | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 09-01-2026 | 350 | WEST BENGAL | 25 | WBSEDCL | 2.49 | [25 empty] | -- | -- | --
28 |  | Solar (ISTS-V) | -- | SECI/C&P/SPD/ISTS-V/RfS/1200MW/062019 | 1200 | NA | 28-06-2019 | NA | 09-08-2019 | Solar | Without Storage | Without Greenshoe | -- | 20-08-2019 | 28-08-2019 | 480 | 720 | 2 | 600 | 0 | GRT Jewellers (India) Private Limited | 150 | -- | 28-09-2019 | 150 | 2.53 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-02-2020 | 150 | BIHAR | 25 | BSPHCL | 2.6 | GRT JEWELLERES (INDIA) PVT. LTD. | Veeramani Marimuthu | 9566100888 | 11-02-2020 | 150 | 2.53 | TAMIL NADU | 25 |  | NA | 11-08-2021 | 17-06-2022 | Solar | 0 |  |  |  | Granted | CTU | 1200002950 | 09-12-2020 | 04-06-2021 | Tuticorin II GIS | Tamilnadu | 01-06-2022 | 2022-03-30 | 50 | ,
[70 empty] | 2022-04-13 | 50
[70 empty] | 2022-06-17 | 50
[21 empty] | SBE Renewables Sixteen Private Limited | 330 | -- | 28-09-2019 | 330 | 2.65 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-02-2020, 05-02-2020 | 330 | BIHAR, BIHAR | 50 | BSPHCL, BSPHCL | 5.44 | Adani Solar Energy RJ Two Private Limited (earlier known as SBE Renewables Sixteen Projects Private Limited), Adani Solar Energy RJ Two Private Limited (earlier known as SBE Renewables Sixteen Projects Private Limited) | Prakhar Bhardwaj, Prakhar Bhardwaj | 19746037054 | 11-02-2020, 11-02-2020 | 330 | 5.3 | RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 11-08-2021, 11-08-2021 | NA, 28-06-2024 | Solar, Solar | 0 | , | , | , | Granted, Granted | CTU , CTU | 2400002720 | 30-06-2020, 04-12-2015 | 18-08-2021, 12-10-2017 | Fatehgarh II, Bhadla | Rajasthan, Rajasthan | 22-01-2025, 01-06-2021 | 2024-02-23 | 59.95 | , , ,
[70 empty] | 2024-03-21 | 105.05
[70 empty] | 2024-09-30 | 15
[70 empty] | 2024-06-28 | 150
29 |  | SOlar (ISTS-VI) | -- | SECI/C&P/SPD/ISTS-VI/MP/RfS/1200MW/062019 | 1200 | NA | 28-06-2019 | NA | 10-10-2019 | Solar | Without Storage | Without Greenshoe | -- | 21-10-2019 | 30-10-2019 | 900 | 300 | 4 | 1200 | 0 | ReNew Solar Power Private Limited | 300 | -- | 25-11-2019 | 300 | 2.71 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-05-2020, 21-01-2020 | 300 | TAMIL NADU, TELANGANA | 50 | TANGEDCO, TSPCC | 5.56 | ReNew Solar Urja Private Limited | Neeraj Gupta | 7389909907 | 11-05-2020 | 300 | 2.71 | RAJASTHAN | 25 |  | NA | 11-11-2021 | 11-05-2022 | Solar | 0 |  |  |  | Granted | CTU | 1200002370 | 27-11-2019 | 10-08-2021 | Fatehgarh II | Rajasthan | 11-05-2022 | 2021-12-01 | 150 | ,
[70 empty] | 2021-12-07 | 50
[70 empty] | 2021-12-13 | 50
[70 empty] | 2021-12-16 | 50
[21 empty] | Avaada Energy Private Limited | 300 | -- | 25-11-2019 | 300 | 2.71 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-05-2020, 21-01-2020 | 300 | TAMIL NADU, TELANGANA | 50 | TANGECCO, TSPCC | 5.56 | Avaada Sustainable RJ Project Private Limited | Angshuman Rudra | 7835004673 | 11-05-2020 | 300 | 2.71 | RAJASTHAN | 25 |  | NA | 11-11-2021 | 12-11-2022 | Solar | 0 |  |  |  | Granted | CTU | 1200002391 | 09-12-2019 | 18-03-2020 | Bikaner | Rajasthan | 23-04-2022 | 2022-01-14 | 100 | ,
[70 empty] | 2022-02-07 | 50
[70 empty] | 2022-04-12 | 50
[70 empty] | 2022-05-11 | 100
[21 empty] | Masaya Solar Energy Private Limited | 300 | -- | 25-11-2019 | 300 | 2.71 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 05-05-2020, 21-01-2020 | 300 | TAMIL NADU, TELANGANA | 50 | TANGEDCO, TSPCC | 5.56 | Masaya Solar Energy Private Limited | Vikash Kumar | 9717786478 | 11-05-2020 | 300 | 2.71 | MADHYA PRADESH | 25 |  | NA | 11-11-2021 | 31-12-2023 | Solar | 0 |  |  |  | Granted | CTU | 1200002397 | 11-12-2019 | 24-03-2022 | Khandwa | Khandwa | 25-03-2022 | 2023-06-21 | 150 | ,
[70 empty] | 2023-09-08 | 100
[70 empty] | 2024-03-18 | 50
30 |  | CPSU Scheme (Tranche-II) | -- | SECI/C&P/SPD/CPSU-II/RfS/1500MW/082019 | 1500 | NA | 01-08-2019 | NA | 17-09-2019 | Solar | Without Storage | Without Greenshoe | -- | 18-09-2019 | 08-11-2019 | 1104 | 396 | 4 | 1481 | 40 | The Singareni Collieries Company Limited | 81 | -- | 25-11-2019 | 81 | 3.5 | Solar | 81 | -- | -- | Granted | STUTELANGANA | -- | NA | NA | -- | -- | NA | [6 empty] | The Singareni Collieries Company Limited, The Singareni Collieries Company Limited, The Singareni Collieries Company Limited, The Singareni Collieries Company Limited, The Singareni Collieries Company Limited, The Singareni Collieries Company Limited | Appa Rao, Appa Rao, Appa Rao, Appa Rao, Appa Rao, Appa Rao | 49997847738 | 24-11-2019, 24-11-2019, 24-11-2019, 24-11-2019, 24-11-2018, 24-11-2019 | 81 | 21 | TELANGANA, TELANGANA, TELANGANA, TELANGANA, TELANGANA, TELANGANA | 0 | , , , , , | NA, NA, NA, NA, NA, NA | 25-11-2021, 25-11-2021, 25-11-2021, 25-11-2021, 25-11-2021, 25-11-2021 | 30-09-2024, 30-09-2024, 31-12-2025, 31-12-2025, 31-12-2025, 30-12-2025 | Solar, Solar, Solar, Solar, Solar, Solar | 54.5 | , , , , , | , , , , , | , , , , , | Captive, Captive, Captive, Captive, Captive, Granted | , , , , , CTU | , , , , 0, 0 | NA, NA, NA, NA, NA, NA | NA, NA, NA, NA, NA, NA | , , , , , | , , , , , | NA, NA, NA, NA, NA, NA | 2023-01-22 | 5 | , , , , , , , , , , ,
[70 empty] | 2024-08-30 | 11
[70 empty] | 2024-04-26 | 10.5
[21 empty] | Indore Municipal Corporation | 100 | -- | 25-11-2019 | 100 | 3.5 | Solar | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [6 empty] | Indore Municipal Corporation, Indore Municipal Corporation | Kapil, Kapil | 14495521406 | 25-11-2019, 25-11-2019 | 100 | 7 | MADHYA PRADESH, MADHYA PRADESH | 0 | , | NA, NA | 25-11-2021, 25-11-2021 | 31-12-2025, 30-09-2024 | Solar, Solar | 60 | , | , | , | Captive, Captive | STU : NA , STU : NA | NA, | NA, NA | NA, NA | , | , | NA, NA | 2026-03-03 | 60 | , , No ,
[70 empty] | 2026-03-03 | 60
[70 empty] | 2026-03-03 | 60
[70 empty] | 2026-03-03 | 60
[21 empty] | NTPC Limited | 923 | -- | 25-11-2019 | 923 | 3.5 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | [6 empty] | NTPC Limited, NTPC Limited, NTPC Limited, NTPC Limited, NTPC Limited, NTPC Limited | Anupam Gupta, Anupam Gupta, Anupam Gupta, Anupam Gupta, Anupam Gupta, Anupam Gupta | 47997878892 | 25-11-2019, 25-11-2019, 25-11-2019, 25-11-2019, 25-11-2019, 25-11-2019 | 923 | 21000010.5 | RAJASTHAN, RAJASTHAN, RAJASTHAN, RAJASTHAN, GUJARAT, GUJARAT | 0 | , , , , , | NA, NA, NA, NA, NA, NA | 25-11-2021, 25-11-2021, 25-11-2021, 25-11-2021, 25-11-2021, 25-11-2021 | 30-09-2023, 09-01-2023, 09-01-2023, 31-03-2025, 30-09-2023, 09-01-2023 | Solar, Solar, Solar, Solar, Solar, Solar | 0 | , , , , , | , , , , , | , , , , , | Granted, Granted, Granted, Granted, Captive, Captive | CTU , CTU , CTU , CTU , , | 0 | NA, NA, NA, NA, NA, NA | NA, NA, NA, NA, NA, NA | , , , , , | , , , , , | NA, NA, NA, NA, NA, NA | 2023-06-03 | 161 | , , , , , , , , , , ,
[70 empty] | 2022-12-13 | 90
[70 empty] | 2022-08-05 | 296
[70 empty] | 2023-06-07 | 20
[70 empty] | 2022-08-15 | 56
[70 empty] | 2025-03-01 | 300
31 |  | Solar (ISTS-VIII) | -- | SECI/C&P/SPD/ISTS-VIII/RfS/1200MW/012020 | 1200 | NA | 03-01-2020 | NA | 17-02-2020 | Solar | Without Storage | Without Greenshoe | -- | 20-02-2020 | 27-02-2020 | 1200 | 0 | 11 | 4000 | 0 | SBE Renewables Fifteen Private Limited | 600 | -- | 06-04-2020 | 600 | 2.5 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 13-01-2023 | 600 | BIHAR | 25 | BSPHCL | 2.57 | Adani Solar Energy Jodhpur Six Pvt Ltd (earlier known as SBE Renewables Twenty Four Projects Pvt. Ltd.), Adani Solar Energy Jodhpur Six Pvt Ltd (earlier known as SBE Renewables Twenty Four Projects Pvt. Ltd.) | Prakhar Bhardwaj, Prakhar Bhardwaj | 19746037054 | 20-01-2023, 20-01-2023 | 600 | 5 | GUJARAT, GUJARAT | 50 | , | NA, NA | 20-07-2024, 20-07-2024 | 30-01-2027, 30-01-2027 | Solar, Solar | 600 | , | , | , | Granted, Granted | CTU , CTU | 461400022 | 12-01-2023, 12-01-2023 | 31-10-2023, 31-10-2023 | Khavda KPS One, Khavda KPS-1 | Gujarat, Gujarat | 28-02-2026, 28-02-2026 | -- | -- | --
[21 empty] | AMP Energy Green Private Limited | 100 | -- | 06-04-2020 | 100 | 2.5 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 26-06-2025 | 100 | WEST BENGAL | 25 | WBSEDCL | 2.57 | AMPIN Energy Green Four Private Limited | Sourya Choudhary | 9320930693 | 03-07-2025 | 100 | 2.5 | RAJASTHAN, RAJASTHAN | 25 |  | NA | 03-01-2027 | NA | Solar | 100 |  |  |  | Granted | CTU | 1200002559 | 13-04-2020 | 03-05-2024 | Bhadla II | Rajasthan | 31-12-2026 | 2025-08-21 | 100 | , , As per 36 JCC minutes for NR
[21 empty] | Eden Renewable Alma Private Limited | 300 | -- | 06-04-2020 | 300 | 2.5 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 13-01-2023 | 300 | TAMIL NADU | 25 | TANGEDCO | 2.57 | Eden Renewable Alma Private Limited | Vivek kodesia | 9717031091 | 20-10-2023 | 300 | 2.5 | RAJASTHAN | 25 |  | NA | 20-04-2025 | 31-12-2026 | Solar | 0 |  |  |  | Granted | CTU | 1200002554 | 06-04-2020 | 19-09-2024 | Bhadla II | Rajasthan | 31-12-2026 | 2025-06-23 | 100 | ,
[70 empty] | 2025-07-16 | 55.55
[70 empty] | 2025-08-01 | 144.45
[21 empty] | ReNew Solar Power Private Limited | 200 | -- | 06-04-2020 | 200 | 2.51 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 13-01-2023 | 200 | TAMIL NADU | 25 | TANGEDCO | 2.58 | ReNew Surya Vihaan Pvt Ltd | Rohit Singh | 9542388443 | 20-10-2023 | 200 | 2.51 | RAJASTHAN | 25 |  | NA | 20-04-2025 | 11-02-2027 | Solar | 0 |  |  |  | Granted | CTU | 1200002778 | 30-07-2020 | 15-03-2024 | Fatehgarh III | Rajasthan | 19-09-2025 | 2025-05-02 | 158.3 | ,
[70 empty] | 2025-05-19 | 41.7
32 |  | Solar (ISTS-IX) | -- | SECI/C&P/SPD/ISTS-IX/RfS/2000MW/032020 | 2000 | NA | 20-03-2020 | 20-05-2020 | 22-06-2020 | Solar | Without Storage | Without Greenshoe | -- | 23-06-2020 | 30-06-2020 | 2000 | 0 | 11 | 5280 | 0 | Solarpack Corporacion Technologica SA | 300 | -- | 15-07-2020 | 300 | 2.36 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 30-12-2023 | 300 | PUNJAB | 25 | PSPCL | 2.43 | Gorbea Solar Private LTd |  |  | 30-12-2023 | 300 | 2.36 | RAJASTHAN, RAJASTHAN, RAJASTHAN | 25 |  | NA | 30-06-2025 | NA | Solar | 0 |  |  |  | Granted | CTU | 1200002742 | 27-07-2020 | 03-05-2024 | Bhadla II | Rajasthan | 31-12-2026 | 2025-04-13 | 100 | , , ,
[70 empty] | 2025-05-08 | 100
[70 empty] | 2025-06-06 | 100
[21 empty] | Avikiran Surya India Private Limited | 300 | -- | 15-07-2020 | 300 | 2.37 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 20-07-2021, 20-07-2021 | 300 | DELHI, DELHI | 50 | BRPL, BYPL | 4.88 | Thar Surya 1 Pvt Ltd | Balakishore Kollabathula | 9810279841 | 27-07-2021 | 300 | 2.37 | RAJASTHAN, RAJASTHAN | 25 |  | NA | 27-01-2021 | 26-07-2023 | Solar | 0 |  |  |  | Granted | CTU | 1200002642 | 16-06-2020 | 06-01-2021 | Bikaner | Rajasthan | 26-07-2023 | 2022-03-23 | 54 | , ,
[70 empty] | 2022-06-23 | 54
[70 empty] | 2022-08-09 | 54
[70 empty] | 2022-10-11 | 74
[70 empty] | 2022-11-24 | 64
[21 empty] | AMP Energy Green Private Limited | 100 | -- | 15-07-2020 | 100 | 2.37 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 17-02-2022 | 100 | TELANGANA | 25 | TSDISCOM | 2.44 | AMPIN Energy Green Five Pvt. Ltd. | Sourya Choudhary | 9320930693 | 11-04-2022 | 100 | 2.37 | RAJASTHAN, RAJASTHAN | 25 |  | NA | 11-10-2023 | NA | Solar | 0 |  |  |  | Granted | CTU | 1200003882 | 21-04-2022 | 15-07-2022 | Bhadla II | Rajasthan | 12-12-2025 | 2024-06-07 | 100 | , ,
[21 empty] | Eden Renewable Bercy Private Limited | 300 | -- | 15-07-2020 | 300 | 2.37 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 17-02-2022 | 300 | TELANGANA | 25 | TSDISCOM | 2.44 | Eden Renewable Bercy Pvt. Ltd. | Vivek Kodesia | 9717031091 | 11-04-2022 | 300 | 2.37 | RAJASTHAN | 25 |  | NA | 11-10-2023 | 08-04-2027 | Solar | 300 |  |  |  | Granted | CTU | 1200002688 | 07-07-2020 | 06-06-2024 | Fatehgarh-II PS | Rajasthan | 18-01-2026 | -- | -- | --
[21 empty] | IB Vogt Singapore Pte Ltd | 300 | -- | 15-07-2020 | 300 | 2.37 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 17-02-2022 | 300 | TELANGANA | 25 | TSDISCOM | 2.44 | IB Vogt Solar Seven |  |  | 11-04-2022 | 300 | 2.37 | RAJASTHAN, RAJASTHAN | 25 |  | NA | 11-10-2023 | NA | Solar | 100 |  |  |  | Granted | CTU | 1200002700 | 16-07-2020 | 25-09-2023 | Fatehgarh-III | Rajasthan | 30-06-2026 | 2026-03-28 | 150 | , ,
[70 empty] | 2026-03-31 | 50
[21 empty] | Ayana Renewable Power Private Limited | 300 | -- | 15-07-2020 | 300 | 2.38 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 17-02-2022 | 300 | TELANGANA | 25 | TSDISCOM | 2.45 | Ayana Ren. Power3 PL | Laxmi Narayanan Balasubramanian | 8800554749 | 11-04-2022 | 300 | 2.38 | RAJASTHAN | 25 |  | NA | 11-10-2023 | 12-12-2025 | Solar | 0 |  |  |  | Granted | CTU | 1200003933 | 24-07-2020 | 18-08-2022 | Bikaner | Rajasthan | 12-12-2025 | 2024-06-13 | 97.16 | ,
[70 empty] | 2024-08-08 | 97.16
[70 empty] | 2025-01-30 | 101.68
[70 empty] | 2025-02-06 | 4
[21 empty] | ReNew Solar Power Private Limited | 400 | -- | 15-07-2020 | 400 | 2.38 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 21-04-2022, 12-10-2021 | 400 | KERALA, UTTARAKHAND | 50 | KSEB, UPCL | 4.88 | ReNew Surya Aayan Pvt Ltd, ReNew Surya Vihaan Pvt Ltd | Rohit Singh, Rohit Singh | 19084776886 | 28-04-2011, 28-04-2022 | 400 | 4.74 | RAJASTHAN, RAJASTHAN, RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 28-10-2023, 28-10-2023 | 22-01-2025, 22-01-2025 | Solar, Solar | 0 | , | , | , | Granted, Granted | CTU , CTU | 2400005565 | 15-07-2020, 15-07-2020 | 27-10-2020, 27-10-2020 | Fatehgarh III, Fatehgarh III | Rajasthan, Rajasthan | 22-01-2025, 22-01-2025 | 2024-03-28 | 290 | , , , , ,
[70 empty] | 2024-06-05 | 10
[70 empty] | 2024-03-29 | 98
[70 empty] | 2024-05-20 | 2
33 |  | Solar RJ (Tranche-III) | -- | SECI/C&P/SPD/RfS/RJ-III/072020 | 1070 | NA | 16-07-2020 | 31-07-2020 | 28-10-2020 | Solar | Without Storage | Without Greenshoe | -- | 03-11-2020 | 23-11-2020 | 1070 | 0 | 24 | 5790 | 200 | Aljomaih Energy and Water Co. | 200 | -- | 28-12-2020 | 200 | 2 | Solar | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 13-01-2021 | 200 | RAJASTHAN | 25 | RUVITL | 2.07 | Pavni (Raj) Solar PL |  |  | 27-01-2021 | 200 | 2 | RAJASTHAN | 25 |  | NA | 27-07-2022 | 05-05-2025 | Solar | 0 |  |  |  | Applied | STU : RAJASTHAN | NA | NA | NA | Jaisalmer-II | Jaisalmer | NA | -- | -- | --
[21 empty] | Green Infra Wind Energy Limited | 400 | -- | 28-12-2020 | 400 | 2 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 13-01-2021 | 400 | RAJASTHAN | 25 | RUVITL | 2.07 | Sembcorp Green Infra | Rajesh Zoldeo | 8008700714 | 27-01-2021 | 400 | 2 | RAJASTHAN | 25 |  | NA | 27-07-2022 | 05-05-2025 | Solar | 0 |  |  |  | Granted | STU : NA | NA | NA | 09-06-2021 | Jaisalmer-II | Jaisalmer | 31-03-2025 | 2025-02-07 | 102.3 | ,
[70 empty] | 2025-05-05 | 201.3
[70 empty] | 2025-06-30 | 96.4
[21 empty] | NTPC Limited | 470 | -- | 28-12-2020 | 470 | 2.01 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 13-01-2021 | 470 | RAJASTHAN | 25 | RUVITL | 2.08 | NTPC REL, NTPC REL | Saurabh Khare, Saurabh Khare | 19300067694 | 27-01-2021, 27-01-2021 | 470 | 4.02 | RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 27-07-2022, 27-07-2022 | 20-03-2025, 31-03-2024 | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : RAJASTHAN , STU : RAJASTHAN | NA, NA | NA, NA | NA, NA | Jaisalmer-II, Chattargarh | Jaisalmer, Chattargarh | NA, NA | 2024-08-28 | 160 | , , ,
[70 empty] | 2025-01-07 | 60
[70 empty] | 2025-03-20 | 100
[70 empty] | 2024-02-21 | 70
[70 empty] | 2024-03-29 | 80
34 |  | Solar RJ (Tranche-IV) | -- | SECI/C&P/SPD/RfS/RJ-IV/032021 | 1785 | NA | 04-03-2021 | 23-03-2021 | 01-07-2021 | Solar | Without Storage | Without Greenshoe | -- | 06-07-2021 | 24-11-2021 | 1785 | 0 | 22 | 8175 | 160 | Calpine Subsico Solar Energy Private Limited | 90 | -- | 15-02-2022 | 90 | 2.17 | Solar | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 11-02-2022 | 90 | RAJASTHAN | 25 | RUVITL | 2.24 | Calpine Subsico SEPL |  |  | 16-04-2022 | 90 | 2.17 |  | 25 |  | NA | 16-10-2023 | 31-03-2024 | Solar | 0 |  |  |  | Yet to Apply |  |  | NA | NA |  |  | NA | -- | -- | --
[21 empty] | NTPC Renewable Energy Limited | 500 | -- | 15-02-2022 | 500 | 2.17 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-02-2022 | 500 | RAJASTHAN | 25 | RUVITL | 2.24 | NTPC REL | Saurabh Khare | 9650033847 | 16-04-2022 | 500 | 2.17 | RAJASTHAN | 25 |  | NA | 16-10-2023 | 30-09-2025 | Solar | 0 |  |  |  | Granted | STU : NA | NA | 20-07-2022 | NA | Bhadla | Bhadla, Rajasthan | NA | 2026-01-13 | 300 | ,
[70 empty] | 2026-01-31 | 125
[70 empty] | 2026-03-25 | 75
[21 empty] | Sprng Natural Power Source Private Limited | 200 | -- | 15-02-2022 | 200 | 2.17 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-02-2022 | 200 | RAJASTHAN | 25 | RUVITL | 2.24 | Sprng Natural Power | Poorva Pitke | 9545659577 | 16-04-2022 | 200 | 2.17 | RAJASTHAN | 25 |  | NA | 16-10-2023 | 28-08-2024 | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | NA | 400 kV Barmer | Barmer | NA | 2024-08-28 | 150 | ,
[21 empty] | Metka EGN Singapore Holdings 3 Pte. Ltd. | 20 | -- | 15-02-2022 | 20 | 2.17 | Solar | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 11-02-2022 | 20 | RAJASTHAN | 25 | RUVITL | 2.24 | Hera Sun Power PL |  |  | 16-04-2022 | 20 | 2.17 |  | 25 |  | NA | 16-10-2023 | 29-11-2023 | Solar | 0 |  |  |  | Yet to Apply |  |  | NA | NA |  |  | NA | -- | -- | --
[21 empty] | ReNew Solar Power Private Limited | 600 | -- | 15-02-2022 | 600 | 2.18 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-02-2022 | 600 | RAJASTHAN | 25 | RUVITL | 2.25 | ReNew Hans Urja PL, ReNew Hans Urja PL | , | , | 16-04-2022, 16-04-2022 | 600 | 4.36 | RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 16-10-2023, 16-10-2023 | 28-07-2024, 23-08-2024 | Solar, Solar | 0 | , | , | , | Granted, Granted | STU : RAJASTHAN , STU : RAJASTHAN | NA, NA | NA, NA | 04-03-2022, 04-03-2022 | Jaisalmer-II, Jaisalmer-II | Jaisalmer, Jaisalmer | NA, NA | 2024-07-28 | 300 | , , ,
[70 empty] | 2024-07-28 | 100
[70 empty] | 2024-08-29 | 100
[70 empty] | 2024-10-29 | 50
[70 empty] | 2024-12-23 | 50
[21 empty] | ACME Solar Holdings Private Limited | 375 | -- | 15-02-2022 | 375 | 2.18 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-02-2022 | 375 | RAJASTHAN | 25 | RUVITL | 2.25 | ReNew Solar Photovol |  |  | 16-04-2022 | 375 | 2.18 | RAJASTHAN | 25 |  | NA | 16-10-2023 | 09-11-2024 | Solar | 0 |  |  |  | Granted | STU : RAJASTHAN | NA | NA | 04-03-2022 | Jaisalmer-II | Jaisalmer | NA | 2024-10-16 | 200 | ,
[70 empty] | 2024-12-16 | 100
[70 empty] | 2025-03-25 | 75
35 |  | Solar (ISTS-X) | -- | SECI/C&P/SPD/ISTS-X/RfS/1200 MW/072021 | 1200 | NA | 14-07-2021 | 26-07-2021 | 30-11-2021 | Solar | Without Storage | Without Greenshoe | -- | 03-12-2021 | 02-02-2022 | 1200 | 0 | 12 | 7210 | 1200 | Project Eight Renewable Power Private Limited | 600 | -- | 10-03-2022 | 300 | 2.36 | Solar | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[24 empty] | 10-03-2022 | 300 | 2.35 | Solar | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | SolarOne Energy Private Limited | 600 | -- | 10-03-2022 | 300 | 2.37 | Solar | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[24 empty] | 10-03-2022 | 300 | 2.36 | Solar | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
36 |  | Solar (ISTS-XI) | -- | SECI/C&P/IPP/11/0009/22-23 | 2000 | NA | 31-03-2023 | 13-04-2023 | 28-06-2023 | Solar | Without Storage | Without Greenshoe | -- | 03-07-2023 | 21-07-2023 | 2000 | 0 | 14 | 5050 | 0 | Eden Renewable Cadet Private Limited | 300 | -- | 28-07-2023 | 300 | 2.6 | Solar | 300 | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-08-2025 | 300 | PUNJAB | 25 | PSPCL | 2.67 | Eden Renewable Cadet Private Limited | Vivek Kodesia | 9717031091 | 25-08-2025 | 300 | 2.6 |  | 25 |  | NA | 25-02-2027 | NA | Solar | 300 |  |  |  | Granted | CTU | 2200000181 | 11-08-2023 | 31-12-2023 | Barmer I | Rajasthan | 30-06-2027 | -- | -- | --
[21 empty] | SAEL Industries Limited | 600 | -- | 28-07-2023 | 600 | 2.6 | Solar | 600 | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 30-12-2023 | 600 | GUJARAT | 25 | GUVNL | 2.67 | SAEL SOLAR MHP1 Pvt. Ltd., SAEL SOLAR MHP2 Pvt Ltd | Pankaj Kumar, Pankaj Kumar | 14030040726 | 30-12-2023, 30-12-2023 | 600 | 5.34 | ANDHRA PRADESH, ANDHRA PRADESH, ANDHRA PRADESH | 50 | , | NA, NA | 30-06-2025, 30-06-2025 | 30-06-2026, 30-06-2026 | Solar, Solar | 0 | , | , | , | Granted, Granted | CTU , CTU | 4400000659 | 20-10-2023, 20-10-2023 | 18-06-2024, 14-06-2024 | Kurnool III, Kurnool III | Andhra Pradesh, Andhra Pradesh | 30-06-2026, 30-06-2026 | 2025-12-01 | 200.9 | , , , ,
[70 empty] | 2025-12-30 | 55.05
[70 empty] | 2026-01-09 | 156.88
[70 empty] | 2026-01-30 | 44.05
[70 empty] | 2026-02-23 | 66.06
[70 empty] | 2026-03-13 | 77.06
[21 empty] | Jakson Limited | 200 | -- | 28-07-2023 | 200 | 2.6 | Solar | 200 | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-12-2023, 14-10-2024, 11-08-2025 | 200 | UTTAR PRADESH, GUJARAT, PUNJAB | 75 | UPPCL, ASL, PSPCL | 8.01 | JGRJ One Solar Private Limited, JGRJ One Solar Private Limited, JGRJ One Solar Private Limited | Krishnan Kannan, Sh Krishnan Kannan, Sh Krishnan Kannan | 445163120 | 21-02-2024, 24-10-2024, 25-08-2025 | 200 | 7.94 | RAJASTHAN, RAJASTHAN, RAJASTHAN | 75 | , , | NA, NA, NA | 21-08-2025, 24-04-2026, 25-02-2027 | 11-02-2027, NA, NA | Solar, Solar, Solar | 200 | , , | , , | , , | Granted, Granted, Granted | CTU , CTU , CTU | 6600000294 | 14-06-2023, 14-06-2023, 14-06-2023 | 25-10-2024, 25-10-2024, 25-10-2024 | Bikaner III, Bikaner III, Bikaner III | Rajasthan, Rajasthan, Rajasthan | 31-12-2026, 31-12-2026, 31-12-2026 | -- | -- | --
[21 empty] | Shiva Corporation India Limited | 100 | -- | 28-07-2023 | 100 | 2.6 | Solar | 100 | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-12-2023 | 100 | UTTAR PRADESH | 25 | UPPCL | 2.67 | MRS Green Energy P L | Raghavendra Singh | 8168744844 | 09-01-2024 | 100 | 2.67 | RAJASTHAN | 25 |  | NA | 09-07-2025 | 11-02-2027 | Solar | 100 |  |  |  | Granted | CTU | 2200000098 | 14-06-2023 | 25-10-2024 | Bikaner III | Rajasthan | 31-12-2026 | -- | -- | --
[21 empty] | ReNew Solar Power Private Limited | 600 | -- | 28-07-2023 | 600 | 2.6 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 28-12-2023, 14-10-2024, 11-08-2025 | 600 | UTTAR PRADESH, GUJARAT, PUNJAB | 75 | UPPCL, AEML, PSPCL | 8.01 | Renew Solar Piyush Private Limited, Renew Ushma Energy Private Limited, Renew Ushma Energy Private Limited | Rohit Singh, Rohit Singh, Rohit Singh | 29876848782 | 21-02-2024, 24-10-2024, 25-08-2025 | 600 | 7.94 | RAJASTHAN, RAJASTHAN, RAJASTHAN | 75 | , , | NA, NA, NA | 21-08-2025, 24-04-2026, 25-02-2027 | 06-01-2027, 06-01-2027, NA | Solar, Solar, Solar | 600 | , , | , , | , , | Granted, Granted, Granted | CTU , CTU , CTU | 6600000560 | 02-08-2023, 02-08-2023, 02-08-2023 | 05-03-2025, 05-03-2025, 05-03-2025 | Fatehgarh IV, Fatehgarh IV, Fatehgarh-IV | Rajasthan, Rajasthan, Rajasthan | 30-06-2027, 30-06-2027, 30-06-2027 | -- | -- | --
[21 empty] | Avaada Energy Private Limited | 200 | -- | 28-07-2023 | 200 | 2.61 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 17-09-2024 | 200 | DELHI | 25 | NDMC | 2.68 | Avaada GJ Sustainable Private Limited | Sumit Sood | 9560078282 | 24-09-2024 | 200 | 2.68 | GUJARAT, GUJARAT | 25 |  | NA | 24-03-2026 | 17-04-2026 | Solar | 0 |  |  |  | Granted | CTU | 2200000200 | 21-08-2023 | 20-08-2024 | Lakadia PS | Gujarat | 28-03-2026 | 2026-02-04 | 108.33 | , ,
[70 empty] | 2026-04-07 | 91.67
37 |  | Solar (ISTS-XII) | -- | SECI/C&P/IPP/11/0007/23-24 | 1000 | NA | 13-10-2023 | 19-10-2023 | 30-11-2023 | Solar | Without Storage | Without Greenshoe | -- | 05-12-2023 | 20-12-2023 | 1000 | 0 | 9 | 2300 | 0 | Avaada Energy Private Limited | 300 | -- | 01-01-2024 | 300 | 2.52 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 07-02-2024 | 300 | UTTAR PRADESH | 25 | UPPCL | 2.59 | Avaada GJ Green Private Limited | Sumit Sood | 9560078282 | 31-03-2024 | 300 | 2.59 | GUJARAT, GUJARAT, GUJARAT | 25 |  | NA | 31-03-2026 | 30-05-2027 | Solar | 300 |  |  |  | Granted | CTU | 2200000537 2200 | 30-01-2024 | 06-06-2025 | Bhuj-II | Gujarat | 31-03-2027 | -- | -- | --
[21 empty] | Sprng Energy Private Limited | 250 | -- | 01-01-2024 | 250 | 2.52 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 07-02-2024 | 250 | UTTAR PRADESH | 25 | UPPCL | 2.59 | Sprng Power Earth Private Limited | Poorva Pitke | 9545659577 | 31-03-2024 | 250 | 2.59 | GUJARAT | 25 |  | NA | 31-03-2026 | NA | Solar | 250 |  |  |  | Granted | CTU | 2200000247 | 11-09-2023 | 29-01-2024 | Radhaneshda | Gujarat | 30-06-2026 | -- | -- | --
[21 empty] | ReNew Solar Power Private Limited | 300 | -- | 01-01-2024 | 300 | 2.52 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 07-02-2024 | 300 | UTTAR PRADESH | 25 | UPPCL | 2.59 | Renew Solar Stellar Private Limited | Rohit Singh | 8511114255 | 31-03-2024 | 300 | 2.59 | RAJASTHAN | 25 |  | NA | 31-03-2026 | 30-05-2030 | Solar | 300 |  |  |  | Granted | CTU | 2200000516 | 25-01-2024 | 27-08-2024 | Bhadla IV | Rajasthan | 31-03-2030 | -- | -- | --
[21 empty] | Solarcraft Power India 8 Private Limited | 150 | -- | 01-01-2024 | 150 | 2.53 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 07-02-2024 | 150 | UTTAR PRADESH | 25 | UPPCL | 2.6 | Solarcraft Power India 17 Private Limited | Pankaj Tyagi | 1124666229 | 31-03-2024 | 150 | 2.6 | RAJASTHAN | 25 |  | NA | 31-03-2026 | 01-10-2027 | Solar | 150 |  |  |  | Granted | CTU | 2200000210 | 05-09-2023 | 31-12-2023 | Bikaner IV | Rajasthan | 31-03-2027 | -- | -- | --
38 |  | Solar (ISTS-XIII) | -- | SECI/C&P/IPP/11/0016/23-24 | 1500 | NA | 29-12-2023 | 05-01-2024 | 15-02-2024 | Solar | Without Storage | Without Greenshoe | -- | 21-02-2024 | 07-03-2024 | 1500 | 0 | 12 | 4230 | 0 | JSW Neo Energy Limited | 700 | -- | 10-03-2024 | 700 | 2.56 | Solar | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | 08-10-2024 | 700 | MAHARASHTRA | 25 | MSEDCL | 2.63 | JSW Renew Energy Eleven Limited | Rakesh Rathore | 7738091123 | 18-10-2024 | 700 | 2.63 | MAHARASHTRA, MAHARASHTRA | 25 |  | NA | 18-10-2026 | NA | Solar | 700 |  |  |  | Applied | STU : NA | 20707000000921 | 19-03-2025 | NA | Ektuni SS | Maharashtra | NA | -- | -- | --
[21 empty] | Sunsure Solarpark Fourteen Private Limited | 300 | -- | 13-03-2024 | 300 | 2.56 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 09-01-2025 | 300 | HIMACHAL PRADESH | 25 | HPSEBL | 2.63 | Sunsure Solarpark Fourteen Pvt. Ltd. | Aakash Singh | 9560003515 | 23-01-2025 | 300 | 2.63 | RAJASTHAN | 25 |  | NA | 23-01-2027 | NA | Solar | 300 |  |  |  | Granted | CTU | 2200000285 | 30-09-2023 | 16-01-2025 | Bikaner IV | Rajasthan | 31-03-2027 | -- | -- | --
[21 empty] | Tejorupa Renewables India Project Private Limited | 250 | -- | 13-03-2024 | 250 | 2.56 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 09-01-2025 | 250 | HIMACHAL PRADESH | 25 | HPSECL | 2.63 | Tejorupa Renewables India Project Pvt. Ltd. | Alok Kumar Nigam | 9717855521 | 25-01-2025 | 250 | 2.63 | RAJASTHAN | 25 |  | NA | 25-01-2027 | NA | Solar | 250 |  |  |  | Granted | CTU | 2200000067 | 26-05-2023 | 20-12-2024 | Fatehgarh IV | Rajasthan | 30-06-2027 | -- | -- | --
[21 empty] | NTPC Renewable Energy Limited | 250 | -- | 13-03-2024 | 250 | 2.57 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-08-2025 | 250 | PUNJAB | 25 | PSPCL | 2.64 | NTPC Renewable Energy Limited | Sh. Rajiv Kumar | 9650990167 | 30-06-2025 | 250 | 2.57 | GUJARAT | 25 |  | NA | 30-06-2027 | NA | Solar | 250 |  |  |  | Granted | CTU | 2200000093 | 14-06-2023 | 03-11-2023 | KPS -2 | Gujarat | 31-03-2027 | -- | -- | --
39 |  | Solar (ISTS-XIV) | -- | SECI/C&P/IPP/11/0017/23-24 | 1500 | NA | 18-01-2024 | 29-01-2024 | 23-02-2024 | Solar | Without Storage | Without Greenshoe | -- | 28-02-2024 | 15-03-2024 | 1500 | 0 | 9 | 2950 | 0 | Avaada Energy Private Limited | 300 | -- | 23-04-2024 | 300 | 2.57 | Solar | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | ReNew Solar Power Private Limited | 300 | -- | 23-04-2024 | 300 | 2.57 | Solar | 300 | -- | -- | Applied | CTU | 2200000778 | 30-04-2024 | NA | Barmer II | Rajasthan | NA | [31 empty] | -- | -- | --
[21 empty] | Engie Energy India Private Limited | 100 | -- | 23-04-2024 | 100 | 2.57 | Solar | 100 | -- | -- | Granted | CTU | 12000003893 | 29-04-2024 | 16-11-2023 | Bikaner II | Rajasthan | 27-12-2025 | 11-08-2025 | 100 | PUNJAB | 25 | PSPCL | 2.64 | ENREN-I Energy Private Limited | Saurabh Gupta | 9223349273 | 30-06-2025 | 100 | 2.57 |  | 25 |  | NA | 30-06-2027 | NA | Solar | 100 |  |  |  | Granted | CTU | 2200000286 | 30-09-2023 | 13-12-2023 | Barmer | Rajasthan | 07-11-2026 | -- | -- | --
[21 empty] | SAEL Industries Limited | 600 | -- | 23-04-2024 | 300 | 2.57 | Solar | 300 | -- | -- | Granted | CTU | 2200000948 | 20-06-2024 | 15-10-2024 | Tumkur II PS | Karnataka | 04-09-2026 | 11-08-2025 | 300 | PUNJAB | 25 | PSPCL | 2.64 | SAEL Solar P7 Private Limited | Khalid Nadeem | 9650599663 | 30-06-2025 | 300 | 2.57 |  | 25 |  | NA | 30-06-2027 | NA | Solar | 300 |  |  |  | Granted | CTU | 2200000948 | 20-06-2024 | 19-03-2025 | Tumkur-II | Karnataka | 04-09-2026 | -- | -- | --
[24 empty] | 23-04-2024 | 300 | 2.57 | Solar | 300 | -- | -- | Granted | CTU | 2200000759 | 25-04-2024 | 22-07-2024 | Bidar PS | Karnataka | 22-04-2026 | 11-08-2025 | 300 | PUNJAB | 25 | PSPCL | 2.64 | SAEL Solar P8 Private Limited | Khalid Nadeem | 9650599663 | 30-06-2025 | 300 | 2.57 |  | 25 |  |  | 30-06-2027 | NA | Solar | 300 |  |  |  | Granted | CTU | 2200000759 | 25-04-2024 | 03-03-2025 | Bidar | Karnataka | 30-06-2026 | -- | -- | --
[21 empty] | NTPC Renewable Energy Limited | 200 | -- | 23-04-2024 | 200 | 2.58 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-08-2025 | 200 | PUNJAB | 25 | PSPCL | 2.65 | NTPC Renewable Energy Limited | Sh. Rajiv Kumar | 9650990167 | 20-06-2025 | 200 | 2.58 |  | 25 |  | NA | 30-06-2027 | NA | Solar | 200 |  |  |  | Granted | CTU | 2200000093 | 17-11-2023 | 16-01-2025 | KPS II | Rajasthan | 31-03-2027 | -- | -- | --
40 |  | Solar (ISTS-XV) | -- | SECI/C&P/IPP/11/0023/23-24 | 1200 | NA | 16-03-2024 | 16-05-2024 | 26-06-2024 | Solar | With Storage | Without Greenshoe | -- | 28-06-2024 | 16-07-2024 | 1200 | 0 | 10 | 2650 | 0 | Pace Digitek Infra Private Limited | 100 | -- | 19-07-2024 | 100 | 3.41 | Solar | 100 | -- | 100 | -- | -- | -- | NA | NA | -- | -- | NA | 12-09-2024 | 100 | KERALA | 25 | KSEB | 3.48 | Pace Digitek Private | Alok Singhal | 7503689170 | 27-09-2024 | 100 | 3.48 | ANDHRA PRADESH | 25 |  | NA | 27-09-2026 | 07-11-2026 | Solar | 100 |  |  | 50 | Applied | CTU | 2200001607 | 24-12-2024 | NA | NP Kunta SS | Andhra Pradesh | NA | -- | -- | --
[21 empty] | Hero Solar Energy Private Limited | 250 | -- | 19-07-2024 | 250 | 3.42 | Solar | 250 | -- | 250 | Granted | -- | -- | NA | NA | -- | -- | NA | 12-09-2024 | 250 | KERALA | 25 | KSEB | 3.49 | Clean Renewable Ener | Ashutosh Vyas | 9953314792 | 27-09-2024 | 250 | 3.49 | KARNATAKA, KARNATAKA | 25 |  | NA | 27-09-2026 | 29-04-2027 | Solar | 250 |  |  |  | Granted | CTU | 2200001072 | 19-07-2024 | 30-12-2024 | Bidar | Karnataka | 19-02-2027 | -- | -- | --
[21 empty] | ACME Solar Holdings Limited | 350 | -- | 19-07-2024 | 350 | 3.42 | Solar | 350 | -- | 550 | Granted | CTU | 2200001082 | 26-07-2024 | 07-03-2025 | Tumkur Pavagada PS | Karnataka | 01-01-2027 | 12-09-2024, 20-11-2025 | 350 | KERALA, BIHAR | 50 | KSEB, NBPDCL & SBPDCL (BSPHCL) | 6.98 | ACME Platinum Urja Private Limited (A-150 MW), ACME Platinum Urja Private Limited (B-200 MW) | Yogesh Sanklecha, Yogesh Kumar Sanklecha | 17488121202 | 27-09-2024, 01-07-2025 | 350 | 6.91 | KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA, KARNATAKA | 50 | , | NA, NA | 27-09-2026, 30-06-2027 | 02-03-2027, NA | Solar, Solar | 350 | , | , | , 400 | Granted, Granted | CTU , CTU | 4400002164 | 26-07-2024, 26-07-2024 | 07-03-2025, 07-03-2025 | Tumkur (Pavagada PS), Tumkur (Pavagada PS) | Karnataka, Karnataka | 01-01-2027, 01-01-2027 | -- | -- | --
[21 empty] | JSW Neo Energy Limited | 500 | -- | 19-07-2024 | 500 | 3.42 | Solar | 500 | -- | 500 | Applied | CTU | 2200001074 | 22-07-2024 | NA | Anantapur II PS | Andhra Pradesh | NA | [31 empty] | -- | -- | --
41 |  | Solar (ISTS-XVI) | -- | SECI/C&P/IPP/11/0004/24-25 | 500 | NA | 29-05-2024 | 06-06-2024 | 12-07-2024 | Solar | Without Storage | Without Greenshoe | -- | 18-07-2024 | 12-08-2024 | 450 | 50 | 5 | 940 | 0 | SAEL Industries Limited | 250 | -- | 20-08-2024 | 250 | 2.48 | Solar | 250 | -- | -- | Granted | CTU | 2200000843 | 25-05-2024 | 24-12-2024 | Kunrool IV PS | Andhra Pradesh | 25-03-2027 | 11-08-2025 | 250 | PUNJAB | 25 | PSPCL | 2.55 | SAEL Solar P12 Private Limited | Khalil Nadeem | 9650599663 | 30-06-2025 | 250 | 2.55 |  | 25 |  | NA | 30-06-2027 | NA | Solar | 250 |  |  |  | Granted | CTU | 2200000843 | 25-05-2024 | 19-06-2025 | Kurnool-IV | Karnataka | 25-03-2027 | -- | -- | --
[21 empty] | NTPC Renewable Energy Limited | 200 | -- | 20-08-2024 | 200 | 2.48 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 11-08-2025 | 200 | PUNJAB | 25 | PSPCL | 2.55 | NTPC Renewable Energy Limited | Sh. Rajiv Kumar | 9650990167 | 30-06-2025 | 200 | 2.48 |  | 25 |  | NA | 30-06-2027 | NA | Solar | 200 |  |  |  | Granted | CTU | 2200000373 | 17-11-2023 | 16-01-2025 | Bikaner IV | Rajasthan | 31-03-2027 | -- | -- | --
42 |  | Solar (ISTS-XVII) | -- | SECI/C&P/IPP/11/0011/24-25 | 2000 | NA | 31-07-2024 | 12-08-2024 | 30-09-2024 | Solar | With Storage | Without Greenshoe | -- | 04-10-2024 | 09-12-2024 | 2000 | 0 | 14 | 4820 | 0 | NTPC Renewable Energy Limited | 500 | -- | 16-12-2024 | 500 | 3.52 | Solar | 500 | -- | 1000 | Granted | CTU | 2200000308 | 21-10-2023 | 15-02-2024 | Bikaner IV | Rajasthan | 31-03-2027 | 13-03-2025 | 500 | DELHI | 25 | BRPL | 3.59 | NTPC Renewable Energy Limited | Sh Rajiv Kumar | 9650990167 | 18-04-2025 | 500 | 3.52 | RAJASTHAN | 25 |  | NA | 18-04-2027 | 24-06-2025 | Solar | 500 |  |  |  | Granted | CTU | 2200000308 | 21-10-2023 | 16-01-2025 | Bikaner IV | Bikaner, Rajasthan | 31-03-2027 | -- | -- | --
[21 empty] | Sembcorp Green Infra Private Limited | 150 | -- | 16-12-2024 | 150 | 3.52 | Solar | 150 | -- | 300 | Granted | -- | -- | 14-05-2024 | 30-08-2024 | Merta II PS | Rajasthan | NA | 13-03-2025 | 150 | DELHI | 25 | BRPL | 3.59 | Sembcorp Green Infra |  |  | 02-04-2025 | 150 | 3.52 | RAJASTHAN | 25 |  | NA | 02-04-2027 | NA | Solar | 150 |  |  |  | Granted | CTU | 2200000410 | 19-12-2023 | 23-01-2025 | Barmer I PS | Rajasthan | 30-12-2026 | -- | -- | --
[21 empty] | Solarcraft Power India 8 Private Limited | 150 | -- | 16-12-2024 | 150 | 3.52 | Solar | 150 | -- | 300 | Granted | CTU | 2200000210 | 05-09-2023 | 13-12-2023 | Bikaner IV | Rajasthan | 11-11-2026 | 13-03-2025 | 150 | DELHI | 25 | BRPL | 3.59 | Solarcraft Power India 17 Private Limited | Pankaj Tyagi | 9599967147 | 02-04-2025 | 150 | 3.52 | RAJASTHAN | 25 |  | NA | 02-04-2027 | NA | Solar | 150 |  |  |  | Granted | CTU | 2200000210 | 05-09-2023 | 16-01-2025 | Bikaner-IV | Bikaner, Rajasthan | 11-11-2026 | -- | -- | --
[21 empty] | Hero Solar Energy Private Limited | 270 | -- | 16-12-2024 | 270 | 3.52 | Solar | 270 | -- | 540 | Granted | CTU | 2200000978 | 26-06-2024 | 24-03-2025 | Lakadia II | Gujarat | NA | 13-03-2025 | 270 | DELHI | 25 | BYPL | 3.59 | Clean Renewable Energy Hybrid Eleven Private Limited | Ashutosh Vyas | 9111495980 | 31-03-2025 | 270 | 3.52 | GUJARAT, GUJARAT | 25 |  | NA | 31-03-2027 | NA | Solar | 270 |  |  |  | Granted | CTU | 2200000978 | 26-06-2024 | 24-03-2025 | Lakadia-II | Gujarat | NA | -- | -- | --
[21 empty] | Reliance NU Suntech Private Limited | 930 | -- | 16-12-2024 | 930 | 3.53 | Solar | 930 | -- | 1860 | Applied | CTU | 2200001686 | 25-01-2025 | NA | Kurnool IV | Andhra Pradesh | NA | 13-03-2025, 13-03-2025 | 930 | DELHI, DELHI | 50 | BYPL, BRPL | 7.2 | Reliance NU Suntech Private Limited | Sameer Kumar Gupta | 224303100 | 18-04-2025 | 930 | 3.53 |  | 25 |  | NA | 18-04-2027 | NA | Solar | 930 |  |  | 1860 | Applied | CTU | 2200001686 | 23-01-2025 | NA | Kurnool-IV | Andhra Pradesh | NA | -- | -- | --
43 |  | Solar (ISTS-XVIII) | -- | SECI/C&P/IPP/11/0014/24-25 | 1000 | NA | 12-09-2024 | 18-09-2024 | 14-11-2024 | Solar | Without Storage | Without Greenshoe | Green shoe capacity not awarded | 20-11-2024 | 24-12-2024 | 550 | 450 | 4 | 800 | 0.4 | ReNew Solar Power Private Limited | 250 | -- | 09-01-2025 | 250 | 3.04 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 21-02-2025 | 250 | HIMACHAL PRADESH | 25 | HPSEBL | 3.11 | Renew Green TN 3 P L, Renew Surya Ravi Pvt Ltd | , | , | 07-04-2025, 07-04-2025 | 250 | 6.08 | MAHARASHTRA, RAJASTHAN, RAJASTHAN | 50 | , | NA, NA | 30-06-2025, 30-06-2025 | NA, NA | Solar, Solar | 0 | , | , | , | Granted, Granted | CTU , CTU | , 1200003301 | 08-03-2023, 07-06-2021 | 02-02-2024, 02-09-2021 | Solapur, Bikaner | Maharashtra, Rajasthan | 31-03-2025, 15-05-2024 | 2025-06-30 | 99.6 | , , , 0.4 MW capacity is cancelled as per SPD request and PPA amendment is executed for 99.6 MW capacity. , Intimation for 300 MW GNA grant was w.e.f. 15.05.2024 vide intimation dated 13.10.2023.
[70 empty] | 2025-06-30 | 150
[24 empty] | NA | -- | -- | -- | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | ACME Solar Holdings Limited | 300 | -- | 09-01-2025 | 300 | 3.05 | Solar | -- | -- | -- | Granted | -- | -- | NA | NA | -- | -- | NA | 21-02-2025 | 300 | HIMACHAL PRADESH | 25 | HPSEBL | 3.12 | Acme Sikar Solar Private Limited | Yogesh Sanklecha | 8744060601 | 12-03-2025 | 300 | 3.05 | RAJASTHAN | 25 |  | NA | 30-06-2025 | NA | Solar | 0 |  |  |  | Granted | CTU |  | 01-02-2022 | 10-05-2022 | Bikaner II | Rajasthan | 31-05-2025 | 2025-05-09 | 52.5 | ,
[70 empty] | 2025-05-19 | 112.5
[70 empty] | 2025-06-09 | 75
[70 empty] | 2025-06-23 | 60
[24 empty] | NA | -- | -- | -- | -- | -- | -- | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
45 |  | Solar (ISTS-XX) | -- | SECI/C&P/IPP/11/0004/25-26 | 2000 | NA | 12-06-2025 | 20-06-2025 | 29-08-2025 | Solar | With Storage | Without Greenshoe | -- | 03-09-2025 | 15-10-2025 | 2000 | 0 | 27 | 7220 | 0 | Welspun Renewable Energy Private Limited | 200 | -- | 27-10-2025 | 200 | 2.86 | Solar | 200 |  | 400 | -- | -- | -- | NA | NA | -- | -- | NA | 13-03-2026 | 200 | KERALA | 25 | KSEB | 2.93 | Satpura Renewable Private Limited | Nishant Thakkar | 226613600 | 01-04-2026 | 200 | 2.86 |  | 25 |  | NA | 01-04-2028 | NA | [13 empty] | -- | -- | --
[21 empty] | MB Power (Madhya Pradesh) Limited | 100 | -- | 27-10-2025 | 150 | 2.86 | Solar | 150 |  | 300 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Shivalaya Constructions Limited | 600 | -- | 27-10-2025 | 600 | 2.86 | Solar | 600 |  | 1200 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Oswal Cables Limited | 50 | -- | 27-10-2025 | 50 | 2.86 | Solar | 50 |  | 100 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Purvah Green Power Private Limited | 300 | -- | 27-10-2025 | 300 | 2.86 | Solar | 300 |  | 600 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Banyan Insolation Private Limited | 100 | -- | 27-10-2025 | 100 | 2.86 | Solar | 100 |  | 200 | -- | -- | -- | NA | NA | -- | -- | NA | 26-05-2026 | 100 | DADRA AND NAGAR HAVELI AND DAMAN AND DIU | 25 | DNHPDCL | 2.93 | [25 empty] | -- | -- | --
[21 empty] | LC Infra Projects Private Limited | 50 | -- | 27-10-2025 | 50 | 2.86 | Solar | 50 |  | 100 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Stockwell Solar Services Private Limited | 80 | -- | 27-10-2025 | 80 | 2.86 | Solar | 80 |  | 160 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | SAEL Industries Limited | 300 | -- | 27-10-2025 | 300 | 2.87 | Solar | 300 |  | 600 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | GH2 Solar Limited | 50 | -- | 27-10-2025 | 50 | 2.87 | Solar | 50 |  | 100 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
[21 empty] | Navayuga Green Energy Private Limited | 120 | -- | 27-10-2025 | 120 | 2.87 | Solar | 120 |  | 240 | -- | -- | -- | NA | NA | -- | -- | NA | [31 empty] | -- | -- | --
1 | SECI Hybrid | ESS (ESS-I) | -- | SECI/C&P/IPP/15/0001/22-23 | 500 | NA | 13-04-2022 | 06-05-2022 | 29-07-2022 | Hybrid | With Storage | Without Greenshoe | NA | NA |  |  |  |  | 0 | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | --
1 | SECI Solar | FSPV Rihand dam | -- | SECI/C&P/SPD/RfS/150MW FLOATING/UP/R1/092018 | 150 | NA | 06-09-2018 | NA | 25-10-2018 | Solar | Without Storage | Without Greenshoe | NA | NA |  |  |  |  | 0 | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | --
2 |  | Solar (ISTS-XIX) | -- | SECI/C&P/IPP/11/0024/24-25 | 500 | NA | 13-02-2025 | 18-02-2025 | 30-09-2025 | Solar | Without Storage | With Greenshoe | NA | NA |  |  |  |  | 0 | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | --
3 |  | Solar (ISTS-XXI) | -- | SECI/C&P/IPP/11/0006/25-26 | 1200 | NA | 19-06-2025 | 10-07-2025 | 30-09-2025 | Solar | With Storage | Without Greenshoe | NA | NA |  |  |  |  | 0 | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | -- | --